## Program
Pioneer Group Windows & doors 24/25 | [28 empty] | Program Overview
[6 empty] | Quarter 4 | [12 empty] | Quarter 1 | [12 empty] | Quarter 2 | [12 empty] | Quarter 3 | [12 empty] | Quarter 4
2024-07-18 | [5 empty] | January |  |  |  | February |  |  |  | March |  |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  | AUGUST |  |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  |  | JANUARY |  |  |  | FEBRUARY |  |  |  | MARCH
| Activity |  |  | Responsibility | WK Ending | [66 empty] | Original Program Summary | time axis 2024-01-06 to 2025-03-29
MOBILISATION | kickstart meeting |  |  | Client & NWW | [67 empty] | properties list | 2017 | excel counts this from data collection which looks up tracker UPRN | bar: 2024-03-30
| Internal Handover Meeting |  |  | NWW (KC) | [67 empty] | Targeted Start on Site | 2024-06-13 | excel takes this from this from Mile stone dates (so any change must be made on the milestone tab) | bar: 2024-04-06
| Summary Spec & door choice form issued |  |  | NWW (KC) | [67 empty] | Targeted completion | 2025-07-31 | excel takes this from this from Mile stone dates (so any change must be made on the milestone tab) | bar: 2024-04-06
| Specification & door choice approved |  |  | Client | [67 empty] | Duration | 59 | excel calculates the No of weeks between the start & finish date | bar: 2024-04-06
| Contract / order issued |  |  | Client | [67 empty] | Holiday shutdown | 3 | you should enter the number of shut down weeks between the start and finish dates and enter it here | bar: 2024-04-06
| Property list & resident contact details issued |  |  | Client | [67 empty] | Available weeks | 56 | excel calculates the available install weeks by removing the shutdown period indicated above | bar: 2024-04-13
| Provisional Programme issued |  |  | NWW (PM) | [67 empty] | required Installs Per week | 36.0179 | excel calculates how many properties are required per week by dividing the property Qty over the available weeks | bar: 2024-04-13
| Provisional Programme agreed |  |  | Client | bar: 2024-04-20
| Contract / order executed / Accepted (Signed) |  |  | Client & NWW | [68 empty] | 45491 | bar: 2024-04-13
| Vulnerable & high risk resident list issued |  |  | Client | bar: 2024-04-20
| Resident advised of NWW appointment |  |  | Client | [67 empty] | Revised Program Summary | bar: 2024-04-20
| Pre construction info provided |  |  | Client | [67 empty] | Program modification Date | 2024-07-18 | this date will automatically populate when the original date has elapsed | bar: 2024-04-20
| Asbestos information provided |  |  | NWW (PM & Compliance) | [68 empty] | 378 | bar: 2024-04-20
| construction phase plan issued |  |  | Client | [67 empty] | Available weeks remaining | 54 | standard calc | bar: 2024-04-27
| construction phase plan agreed |  |  | NWW (PM) | [67 empty] | Holiday shutdown (Wks.) | 3 | Linked to the holiday period shown in the original above | bar: 2024-04-27
| start survey mobilisation |  |  | Client | [67 empty] | Available weeks | 51 | standard calc | bar: 2024-04-27
Delivery | Surveying period |  |  | NWW (PM) | [67 empty] | installs completed to date | 0 | this will come directly from the program / tracker
| submission of price surveys |  |  | NWW (PM) | [67 empty] | Less removed Properties | 5 | this comes from the data collection tab
| Surveys available for manufacture |  |  | NWW (PM) | [68 empty] | 0
| product available for installation |  |  | NWW (PM) | [67 empty] | balance to-do | 2012 | standard calc
| Installs Planned ( Frequency) |  |  | NWW (PM) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 |  |  |  | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 36.0179 | 1404.6964 | Installs Per week | 39.451 | this is yet to be established
| Installs Handed over ( Frequency) |  |  | NWW (PM) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Installs revised plan ( Frequency) |  |  | NWW (PM) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.451 | 39.451 | 39.451 | 39.451 | 39.451 | 39.451 | 39.451 | 39.451 | 39.451 | 39.451 | 39.451 | 39.451 | 39.451 | 39.451 | 39.451 | 39.451 | 39.451 | 39.451 | 39.451 | 39.451 | 39.451 | 39.451 |  |  |  | 39.451 | 39.451 | 39.451 | 39.451 | 39.451 | 39.451 | 39.451 | 39.451 | 39.451 | 39.451 | 39.451 | 39.451 | 1341.3333 | 1341.3333
| Targeted completion |  |  | NWW (PM)
Pioneer Group Windows & doors 24/25 | [5 empty] | 2024-06-15: Route March
|  |  |  | call off |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.451 | 78.902 | 118.3529 | 157.8039 | 197.2549 | 236.7059 | 276.1569 | 315.6078 | 355.0588 | 394.5098 | 433.9608 | 473.4118 | 512.8627 | 552.3137 | 591.7647 | 631.2157 | 670.6667 | 710.1176 | 749.5686 | 789.0196 | 828.4706 | 867.9216 | 867.9216 | 867.9216 | 867.9216 | 907.3725 | 946.8235 | 986.2745 | 1025.7255 | 1065.1765 | 1104.6275 | 1144.0784 | 1183.5294 | 1222.9804 | 1262.4314 | 1301.8824 | 1341.3333 | 0 | 0 | 0 | 0
|  |  |  | delivery |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.451 | 78.902 | 118.3529 | 157.8039 | 197.2549 | 236.7059 | 276.1569 | 315.6078 | 355.0588 | 394.5098 | 433.9608 | 473.4118 | 512.8627 | 552.3137 | 591.7647 | 631.2157 | 670.6667 | 710.1176 | 749.5686 | 789.0196 | 828.4706 | 867.9216 | 867.9216 | 867.9216 | 867.9216 | 907.3725 | 946.8235 | 986.2745 | 1025.7255 | 1065.1765 | 1104.6275 | 1144.0784 | 1183.5294 | 1222.9804 | 1262.4314 | 1301.8824 | 1341.3333 | 0
|  |  |  | install |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.451 | 78.902 | 118.3529 | 157.8039 | 197.2549 | 236.7059 | 276.1569 | 315.6078 | 355.0588 | 394.5098 | 433.9608 | 473.4118 | 512.8627 | 552.3137 | 591.7647 | 631.2157 | 670.6667 | 710.1176 | 749.5686 | 789.0196 | 828.4706 | 867.9216 | 867.9216 | 867.9216 | 867.9216 | 907.3725 | 946.8235 | 986.2745 | 1025.7255 | 1065.1765 | 1104.6275 | 1144.0784 | 1183.5294 | 1222.9804 | 1262.4314 | 1301.8824 | 1341.3333
key | call off | delivery | install |  |  | 2024-01-06: Quarter 4; 2024-04-06: Quarter 1; 2024-07-06: Quarter 2; 2024-10-05: Quarter 3; 2025-01-04: Quarter 4
No | Address |  |  | Post code / area |  | 2024-01-06: January; 2024-02-03: February; 2024-03-02: March; 2024-04-06: APRIL; 2024-05-04: MAY; 2024-06-08: JUNE; 2024-07-06: JULY; 2024-08-03: AUGUST; 2024-09-07: SEPTEMBER; 2024-10-05: OCTOBER; 2024-11-02: NOVEMBER; 2024-11-30: DECEMBER; 2025-01-04: JANUARY; 2025-02-01: FEBRUARY; 2025-03-01: MARCH
 | time axis 2024-01-06 to 2025-03-29
14 | Javelin Avenue |  |  | B35 7LW | 1
50 | Heyford Way |  |  | B35 6HU | 2
19 | Heyford Way |  |  | B35 6HY | 3
25 | Heyford Way |  |  | B35 6HY | 4
40 | Heyford Way |  |  | B35 6HU | 5
78 | Heyford Way |  |  | B35 6HU | 6
9 | Heyford Way |  |  | B35 6HY | 7
89 | Heyford Way |  |  | B35 6JB | 8
18 | Heyford Way |  |  | B35 6JH | 9
80 | Javelin Avenue |  |  | B35 7LW | 10
9 | Northolt Drive |  |  | B35 6QX | 11
74 | Heyford Way |  |  | B35 6HU | 12
FLAT 10 | Northolt Drive |  |  | B35 6QX | 13
39 | Heyford Way |  |  | B35 6HY | 14
45 | Heyford Way |  |  | B35 6HZ | 15
47 | Heyford Way |  |  | B35 6HZ | 16
93 | Heyford Way |  |  | B35 6JB | 17
101 | Heyford Way |  |  | B35 6JB | 18
14 | Northolt Drive |  |  | B35 6QX | 19
16 | Northolt Drive |  |  | B35 6QX | 20
17 | Northolt Drive |  |  | B35 6QX | 21
21 | Northolt Drive |  |  | B35 6QX | 22
26 | Northolt Drive |  |  | B35 6QX | 23
77 | Blenheim Way |  |  | B35 7JF | 24
11 | Northolt Drive |  |  | B35 6QX | 25
18 | Northolt Drive |  |  | B35 6QX | 26
22 | Northolt Drive |  |  | B35 6QX | 27
25 | Northolt Drive |  |  | B35 6QX | 28
FLAT 5 | Northolt Drive |  |  | B35 6QX | 29
FLAT 7 | Northolt Drive |  |  | B35 6QX | 30
12 | Northolt Drive |  |  | B35 6QX | 31
15 | Northolt Drive |  |  | B35 6QX | 32
23 | Northolt Drive |  |  | B35 6QX | 33
24 | Northolt Drive |  |  | B35 6QX | 34
28 | Northolt Drive |  |  | B35 6QX | 35
19 | Northolt Drive |  |  | B35 6QX | 36
82 | Heyford Way |  |  | B35 6HU | 37
66 | Javelin Avenue |  |  | B35 7LW | 38
FLAT 1 | Northolt Drive |  |  | B35 6QX | 39
FLAT 27 | Northolt Drive |  |  | B35 6QX | 40
FLAT 29 | Northolt Drive |  |  | B35 6QX | 41
FLAT 3 | Northolt Drive |  |  | B35 6QX | 42
FLAT 34 | Northolt Drive |  |  | B35 6QX | 43
FLAT 38 | Northolt Drive |  |  | B35 6QX | 44
FLAT 4 | Northolt Drive |  |  | B35 6QX | 45
FLAT 6 | Northolt Drive |  |  | B35 6QX | 46
130 | Watton Green |  |  | B35 7JT | 47
140 | Watton Green |  |  | B35 7JT | 48
142 | Watton Green |  |  | B35 7JT | 49
10 | Baginton Road |  |  | B35 6HN | 50
38 | Baginton Road |  |  | B35 6JE | 51
40 | Baginton Road |  |  | B35 6JE | 52
31 | Baginton Road |  |  | B35 6JS | 53
35 | Baginton Road |  |  | B35 6JS | 54
37 | Baginton Road |  |  | B35 6JS | 55
2 | Baginton Road |  |  | B35 6HN | 56
60 | Watton Green |  |  | B35 7JP | 57
12 | Coltishall Close |  |  | B35 7EF | 58
31 | Concorde Drive |  |  | B35 7EE | 59
9 | Concorde Drive |  |  | B35 7EE | 60
17 | Concorde Drive |  |  | B35 7EE | 61
19 | Concorde Drive |  |  | B35 7EE | 62
27 | Concorde Drive |  |  | B35 7EE | 63
14 | Coltishall Close |  |  | B35 7EF | 64
4 | De Havilland Drive |  |  | B35 7FP | 65
10 | De Havilland Drive |  |  | B35 7FP | 66
57E | Heyford Way |  |  | B35 6HZ | 67
28 | Montrose Drive |  |  | B35 6DH | 68
30 | Montrose Drive |  |  | B35 6DH | 69
32 | Montrose Drive |  |  | B35 6DH | 70
8 | School Close |  |  | B35 7NU | 71
1 | Bicester Square |  |  | B35 6HR | 72
3 | Bicester Square |  |  | B35 6HR | 73
5 | Bicester Square |  |  | B35 6HR | 74
20 | Bicester Square |  |  | B35 6HR | 75
24 | Bicester Square |  |  | B35 6HR | 76
26 | Bicester Square |  |  | B35 6HR | 77
FLAT 2 Block 14 | Bicester Square |  |  | B35 6HR | 78
FLAT 3 Block 14 | Bicester Square |  |  | B35 6HR | 79
FLAT 4 Block 14 | Bicester Square |  |  | B35 6HR | 80
FLAT 5 Block 14 | Bicester Square |  |  | B35 6HR | 81
FLAT 6 Block 14 | Bicester Square |  |  | B35 6HR | 82
FLAT 1 Block 14 | Bicester Square |  |  | B35 6HR | 83
3 | Biggin Close |  |  | B35 6BU | 84
4 | Biggin Close |  |  | B35 6BU | 85
6 | Biggin Close |  |  | B35 6BU | 86
7 | Biggin Close |  |  | B35 6BU | 87
8 | Biggin Close |  |  | B35 6BU | 88
9 | Biggin Close |  |  | B35 6BU | 89
10 | Biggin Close |  |  | B35 6BU | 90
17 | Biggin Close |  |  | B35 6BU | 91
1 | Biggin Close |  |  | B35 6BU | 92
12 | Biggin Close |  |  | B35 6BU | 93
68 | Brabazon Grove |  |  | B35 6DT | 94
27 | Brabazon Grove |  |  | B35 6DT | 95
31 | Brabazon Grove |  |  | B35 6DT | 96
34 | Brabazon Grove |  |  | B35 6DT | 97
36 | Brabazon Grove |  |  | B35 6DT | 98
37 | Brabazon Grove |  |  | B35 6DT | 99
38 | Brabazon Grove |  |  | B35 6DT | 100
61 | Brabazon Grove |  |  | B35 6DT | 101
FLAT 54 | Brabazon Grove |  |  | B35 6DT | 102
FLAT 56 | Brabazon Grove |  |  | B35 6DT | 103
FLAT 60 | Brabazon Grove |  |  | B35 6DT | 104
FLAT 64 | Brabazon Grove |  |  | B35 6DT | 105
72 | Brabazon Grove |  |  | B35 6DT | 106
74 | Brabazon Grove |  |  | B35 6DT | 107
76 | Brabazon Grove |  |  | B35 6DT | 108
FLAT 62 | Brabazon Grove |  |  | B35 6DT | 109
57A | Heyford Way |  |  | B35 6HZ | 110
57B | Heyford Way |  |  | B35 6HZ | 111
57F | Heyford Way |  |  | B35 6HZ | 112
97 | Watton Green |  |  | B35 7GA | 113
90 | Watton Green |  |  | B35 7JR | 114
33 | Watton Green |  |  | B35 7JS | 115
21 | Cranwell Way |  |  | B35 6QH | 116
4 | Cranwell Way |  |  | B35 6QH | 117
30 | Cosford Crescent |  |  | B35 6QE | 118
46 | Cosford Crescent |  |  | B35 6QE | 119
FLAT 32 | Cosford Crescent |  |  | B35 6QE | 120
FLAT 34 | Cosford Crescent |  |  | B35 6QE | 121
FLAT 36 | Cosford Crescent |  |  | B35 6QE | 122
6 | Drem Croft |  |  | B35 7HW | 123
8 | Drem Croft |  |  | B35 7HW | 124
FLAT 2 | Kemble Drive |  |  | B35 6QS | 125
FLAT 4 | Kemble Drive |  |  | B35 6QS | 126
FLAT 6 | Kemble Drive |  |  | B35 6QS | 127
21 | Watton Green |  |  | B35 7JS | 128
25 | Watton Green |  |  | B35 7JS | 129
33 | Baginton Road |  |  | B35 6JS | 130
FLAT 3 Block 16 | Bicester Square |  |  | B35 6HR | 131
FLAT 58 | Brabazon Grove |  |  | B35 6DT | 132
23 | Concorde Drive |  |  | B35 7EE | 133
2 | Cosford Crescent |  |  | B35 6QE | 134
FLAT 12 | Cosford Crescent |  |  | B35 6QE | 135
1 | Donibristle Croft |  |  | B35 6BL | 136
5 | Donibristle Croft |  |  | B35 6BL | 137
6 | Donibristle Croft |  |  | B35 6BL | 138
8 | Donibristle Croft |  |  | B35 6BL | 139
12 | Donibristle Croft |  |  | B35 6BL | 140
18 | Donibristle Croft |  |  | B35 6BL | 141
23 | Donibristle Croft |  |  | B35 6BL | 142
26 | Donibristle Croft |  |  | B35 6BL | 143
28 | Donibristle Croft |  |  | B35 6BL | 144
29 | Donibristle Croft |  |  | B35 6BL | 145
31 | Donibristle Croft |  |  | B35 6BL | 146
33 | Donibristle Croft |  |  | B35 6BL | 147
22 | Donibristle Croft |  |  | B35 6BL | 148
19 | Donibristle Croft |  |  | B35 6BL | 149
107 | Hawker Drive |  |  | B35 7EA | 150
1 | Merlin Close |  |  | B35 7JW | 151
3 | Merlin Close |  |  | B35 7JW | 152
5 | Merlin Close |  |  | B35 7JW | 153
7 | Merlin Close |  |  |  | 154
9 | Merlin Close |  |  | B35 7JW | 155
10 | Merlin Close |  |  | B35 7JW | 156
11 | Merlin Close |  |  | B35 7JW | 157
3 | Montrose Drive |  |  | B35 7JW | 158
5 | Montrose Drive |  |  | B35 6DH | 159
12 | Montrose Drive |  |  | B35 6DH | 160
15 | Montrose Drive |  |  | B35 6DH | 161
FLAT 2 Block 1 | Montrose Drive |  |  | B35 6DH | 162
FLAT 6 Block 1 | Montrose Drive |  |  | B35 6DH | 163
Communals 1 - 7 | Northolt Drive |  |  | B35 6DH | 164
Communals 2 - 8 | Northolt Drive |  |  | B35 6QX | 165
Communal 34 - 40 | Northolt Drive |  |  | B35 6QX | 166
Communals 27 - 33 | Northolt Drive |  |  | B35 6QX | 167
FLAT 33 | Northolt Drive |  |  | B35 6QX | 168
FLAT 31 | Northolt Drive |  |  | B35 6QX | 169
20 | Northolt Drive |  |  | B35 6QX | 170
FLAT 36 | Northolt Drive |  |  | B35 6QX | 171
6 | School Close |  |  | B35 6QX | 172
12 | School Close |  |  | B35 7NU | 173
14 | School Close |  |  | B35 7NU | 174
2 | St Athan Croft |  |  | B35 7NU | 175
86 | Watton Green |  |  | B35 7LS | 176
88 | Watton Green |  |  | B35 7JR | 177
92 | Watton Green |  |  | B35 7JR | 178
132 | Watton Green |  |  | B35 7JR | 179
134 | Watton Green |  |  | B35 7JT | 180
27 | Watton Green |  |  | B35 7JT | 181
42 | Watton Green |  |  | B35 7JS | 182
44 | Watton Green |  |  | B35 7JP | 183
68 | Watton Green |  |  | B35 7JP | 184
80 | Watton Green |  |  | B35 7JP | 185
35 | Watton Green |  |  | B35 7JR | 186
136 | Watton Green |  |  | B35 7JS | 187
349 | Yatesbury Avenue |  |  | B35 7JT | 188
FLAT 339 | Yatesbury Avenue |  |  | B35 6QP | 189
FLAT 341 | Yatesbury Avenue |  |  | B35 6QP | 190
327 | Yatesbury Avenue |  |  | B35 6QP | 191
FLAT 329 | Yatesbury Avenue |  |  | B35 6QP | 192
FLAT 333 | Yatesbury Avenue |  |  | B35 6QP | 193
64 | Cosford Crescent |  |  | B35 6QP | 194
FLAT 44 | Cosford Crescent |  |  | B35 6QE | 195
FLAT 66 | Cosford Crescent |  |  | B35 6QE | 196
FLAT 76 | Cosford Crescent |  |  | B35 6QE | 197
2 | Cranwell Way |  |  | B35 6QE | 198
2 | Drem Croft |  |  | B35 6QH | 199
4 | Drem Croft |  |  | B35 7HW | 200
381 | Yatesbury Avenue |  |  | B35 7HW | 201
FLAT 365 | Yatesbury Avenue |  |  | B35 6QP | 202
FLAT 367 | Yatesbury Avenue |  |  | B35 6QP | 203
FLAT 369 | Yatesbury Avenue |  |  | B35 6QP | 204
FLAT 373 | Yatesbury Avenue |  |  | B35 6QP | 205
FLAT 377 | Yatesbury Avenue |  |  | B35 6QP | 206
FLAT 379 | Yatesbury Avenue |  |  | B35 6QP | 207
FLAT 2 Block 33 | Concorde Drive |  |  | B35 6QP | 208
FLAT 4 Block 33 | Concorde Drive |  |  | B35 7EE | 209
FLAT 5 Block 33 | Concorde Drive |  |  | B35 7EE | 210
FLAT 6 Block 33 | Concorde Drive |  |  | B35 7EE | 211
11 | Concorde Drive |  |  | B35 7EE | 212
FLAT 1 Block 64 | Heyford Way |  |  | B35 7EE | 213
FLAT 2 Block 64 | Heyford Way |  |  | B35 6HU | 214
FLAT 5 Block 64 | Heyford Way |  |  | B35 6HU | 215
FLAT 6 Block 64 | Heyford Way |  |  | B35 6HU | 216
FLAT 68 | Heyford Way |  |  | B35 6HU | 217
FLAT 70 | Cosford Crescent |  |  | B35 6QE | 218
FLAT 74 | Cosford Crescent |  |  | B35 6QE | 219
1 | Cosford Crescent |  |  | B35 6QE | 220
5 | Cranwell Way |  |  | B35 6QH | 221
363 | Cranwell Way |  |  | B35 6QH | 222
1 | Yatesbury Avenue |  |  | B35 6QP | 223
3 | Coltishall Close |  |  | B35 7EF | 224
5 | Coltishall Close |  |  | B35 7EF | 225
7 | Coltishall Close |  |  | B35 7EF | 226
9 | Coltishall Close |  |  | B35 7EF | 227
11 | Coltishall Close |  |  | B35 7EF | 228
15 | Coltishall Close |  |  | B35 7EF | 229
6 | Coltishall Close |  |  | B35 7EF | 230
8 | Mere Avenue |  |  | B35 6QT | 231
12 | Mere Avenue |  |  | B35 6QT | 232
14 | Mere Avenue |  |  | B35 6QT | 233
16 | Mere Avenue |  |  | B35 6QT | 234
24 | Mere Avenue |  |  | B35 6QT | 235
28 | Mere Avenue |  |  | B35 6QT | 236
30 | Mere Avenue |  |  | B35 6QT | 237
32 | Mere Avenue |  |  | B35 6QT | 238
38 | Mere Avenue |  |  | B35 6QT | 239
40 | Mere Avenue |  |  | B35 6QT | 240
34 | Mere Avenue |  |  | B35 6QT | 241
36 | Mere Avenue |  |  | B35 6QT | 242
FLAT 1 Block 16 | Mere Avenue |  |  | B35 6QT | 243
FLAT 2 Block 16 | Bicester Square |  |  | B35 6HR | 244
1 | Bicester Square |  |  | B35 6HR | 245
2 | Bond Drive |  |  | B35 7QQ | 246
3 | Bond Drive |  |  | B35 7QQ | 247
6 | Bond Drive |  |  | B35 7QQ | 248
8 | Bond Drive |  |  | B35 7QQ | 249
10 | Bond Drive |  |  | B35 7QQ | 250
12 | Bond Drive |  |  | B35 7QQ | 251
16 | Bond Drive |  |  | B35 7QQ | 252
14 | Bond Drive |  |  | B35 7QQ | 253
8 | Bond Drive |  |  | B35 7QQ | 254
FLAT 14 | Cosford Crescent |  |  | B35 6QE | 255
FLAT 14 | Cosford Crescent |  |  | B35 6QE | 256
FLAT 16 | Cosford Crescent |  |  | B35 6QE | 257
FLAT 18 | Cosford Crescent |  |  | B35 6QE | 258
24 | Donibristle Croft |  |  | B35 6BL | 259
8 | Merlin Close |  |  | B35 7JW | 260
32 | Northolt Drive |  |  | B35 6QX | 261
FLAT 40 | Northolt Drive |  |  | B35 6QX | 262
10 | School Close |  |  | B35 7NU | 263
138 | Watton Green |  |  | B35 7JT | 264
FLAT 343 | Yatesbury Avenue |  |  | B35 6QP | 265
FLAT 345 | Yatesbury Avenue |  |  | B35 6QP | 266
10 | Kemble Drive |  |  | B35 6QS | 267
12 | Kemble Drive |  |  | B35 6QS | 268
18 | Kemble Drive |  |  | B35 6QS | 269
20 | Kemble Drive |  |  | B35 6QS | 270
24 | Kemble Drive |  |  | B35 6QS | 271
FLAT 8 | Kemble Drive |  |  | B35 6QS | 272
26 | Mere Avenue |  |  | B35 6QT | 273
8 | Watton Green |  |  | B35 7JS | 274
12 | Watton Green |  |  | B35 7JS | 275
14 | Watton Green |  |  | B35 7JS | 276
16 | Watton Green |  |  | B35 7JS | 277
10 | Watton Green |  |  | B35 7JS | 278
18 | Watton Green |  |  | B35 7JS | 279
20 | Watton Green |  |  | B35 7JS | 280
24 | Watton Green |  |  | B35 7JS | 281
28 | Watton Green |  |  | B35 7JS | 282
15 | Javelin Avenue |  |  | B35 7LH | 283
17 | Javelin Avenue |  |  | B35 7LH | 284
19 | Javelin Avenue |  |  | B35 7LH | 285
26 | Javelin Avenue |  |  | B35 7LW | 286
28 | Javelin Avenue |  |  | B35 7LW | 287
30 | Javelin Avenue |  |  | B35 7LW | 288
38 | Javelin Avenue |  |  | B35 7LW | 289
40 | Javelin Avenue |  |  | B35 7LW | 290
42 | Javelin Avenue |  |  | B35 7LW | 291
72 | Javelin Avenue |  |  | B35 7LW | 292
74 | Javelin Avenue |  |  | B35 7LW | 293
32 | Javelin Avenue |  |  | B35 7LW | 294
36 | Javelin Avenue |  |  | B35 7LW | 295
44 | Javelin Avenue |  |  | B35 7LW | 296
14 | Trident Boulevard |  |  | B35 7LZ | 297
19 | Trident Boulevard |  |  | B35 7LZ | 298
22 | Trident Boulevard |  |  | B35 7LZ | 299
22 | Watton Green |  |  | B35 7JS | 300
14 | Drem Croft |  |  | B35 7HW | 301
16 | Drem Croft |  |  | B35 7HW | 302
FLAT 127A | Farnborough Road |  |  | B35 7LQ | 303
FLAT 127B | Farnborough Road |  |  | B35 7LQ | 304
FLAT 127D | Farnborough Road |  |  | B35 7LQ | 305
FLAT 127E | Farnborough Road |  |  | B35 7LQ | 306
FLAT 129A | Farnborough Road |  |  | B35 7LQ | 307
FLAT 129B | Farnborough Road |  |  | B35 7LQ | 308
FLAT 129F | Farnborough Road |  |  | B35 7LQ | 309
FLAT 131A | Farnborough Road |  |  | B35 7LQ | 310
5 | Javelin Avenue |  |  | B35 7LH | 311
7 | Javelin Avenue |  |  | B35 7LH | 312
9 | Javelin Avenue |  |  | B35 7LH | 313
6 | Javelin Avenue |  |  | B35 7LW | 314
8 | Javelin Avenue |  |  | B35 7LW | 315
76 | Javelin Avenue |  |  | B35 7LW | 316
84 | Javelin Avenue |  |  | B35 7LW | 317
124 | Javelin Avenue |  |  | B35 7LW | 318
126 | Javelin Avenue |  |  | B35 7LW | 319
86 | Javelin Avenue |  |  | B35 7LW | 320
6 | Lysander Way |  |  | B35 7JY | 321
8 | Lysander Way |  |  | B35 7JY | 322
10 | Lysander Way |  |  | B35 7JY | 323
6 | Trident Boulevard |  |  | B35 7LZ | 324
21 | Trident Boulevard |  |  | B35 7LZ | 325
23 | Trident Boulevard |  |  | B35 7LZ | 326
5 | Concorde Drive |  |  | B35 7EE | 327
8 | De Havilland Drive |  |  | B35 7FP | 328
10 | Drem Croft |  |  | B35 7HW | 329
FLAT 131B | Farnborough Road |  |  | B35 7LQ | 330
FLAT 131C | Farnborough Road |  |  | B35 7LQ | 331
FLAT 131D | Farnborough Road |  |  | B35 7LQ | 332
FLAT 131E | Farnborough Road |  |  | B35 7LQ | 333
FLAT 131G | Farnborough Road |  |  | B35 7LQ | 334
FLAT 133B | Farnborough Road |  |  | B35 7LQ | 335
FLAT 133D | Farnborough Road |  |  | B35 7LQ | 336
12 | Merlin Close |  |  | B35 7JW | 337
25 | Trident Boulevard |  |  | B35 7LZ | 338
28 | Trident Boulevard |  |  | B35 7LZ | 339
12 | Drem Croft |  |  | B35 7HW | 340
4 | Abingdon Way |  |  | B35 6QF | 341
6 | Abingdon Way |  |  | B35 6QF | 342
8 | Abingdon Way |  |  | B35 6QF | 343
FLAT 3 | Abingdon Way |  |  | B35 6QF | 344
FLAT 5 | Abingdon Way |  |  | B35 6QF | 345
FLAT 7 | Abingdon Way |  |  | B35 6QF | 346
49 | Abingdon Way |  |  | B35 6QF | 347
10 | Abingdon Way |  |  | B35 6QF | 348
12 | Abingdon Way |  |  | B35 6QF | 349
14 | Abingdon Way |  |  | B35 6QF | 350
16 | Abingdon Way |  |  | B35 6QF | 351
17 | Abingdon Way |  |  | B35 6QF | 352
18 | Abingdon Way |  |  | B35 6QF | 353
19 | Abingdon Way |  |  | B35 6QF | 354
20 | Abingdon Way |  |  | B35 6QF | 355
21 | Abingdon Way |  |  | B35 6QF | 356
23 | Abingdon Way |  |  | B35 6QF | 357
24 | Abingdon Way |  |  | B35 6QF | 358
25 | Abingdon Way |  |  | B35 6QF | 359
27 | Abingdon Way |  |  | B35 6QF | 360
29 | Abingdon Way |  |  | B35 6QF | 361
30 | Abingdon Way |  |  | B35 6QF | 362
31 | Abingdon Way |  |  | B35 6QF | 363
32 | Abingdon Way |  |  | B35 6QF | 364
33 | Abingdon Way |  |  | B35 6QF | 365
34 | Abingdon Way |  |  | B35 6QF | 366
37 | Abingdon Way |  |  | B35 6QF | 367
41 | Abingdon Way |  |  | B35 6QF | 368
45 | Abingdon Way |  |  | B35 6QF | 369
47 | Abingdon Way |  |  | B35 6QF | 370
FLAT 1 | Abingdon Way |  |  | B35 6QF | 371
FLAT 11 | Abingdon Way |  |  | B35 6QF | 372
FLAT 9 | Abingdon Way |  |  | B35 6QF | 373
29 | Abingdon Way |  |  | B35 6QF | 374
30 | Abingdon Way |  |  | B35 6QF | 375
31 | Abingdon Way |  |  | B35 6QF | 376
32 | Abingdon Way |  |  | B35 6QF | 377
33 | Abingdon Way |  |  | B35 6QF | 378
34 | Abingdon Way |  |  | B35 6QF | 379
37 | Abingdon Way |  |  | B35 6QF | 380
41 | Abingdon Way |  |  | B35 6QF | 381
45 | Abingdon Way |  |  | B35 6QF | 382
47 | Abingdon Way |  |  | B35 6QF | 383
FLAT 1 | Abingdon Way |  |  | B35 6QF | 384
FLAT 11 | Abingdon Way |  |  | B35 6QF | 385
FLAT 9 | Abingdon Way |  |  | B35 6QF | 386
5 | Avro Way |  |  | B35 7NW | 387
6 | Avro Way |  |  | B35 7NW | 388
7 | Avro Way |  |  | B35 7NW | 389
8 | Avro Way |  |  | B35 7NW | 390
2 | Bovingdon Road |  |  | B35 6QD | 391
4 | Bovingdon Road |  |  | B35 6QD | 392
6 | Bovingdon Road |  |  | B35 6QD | 393
8 | Bovingdon Road |  |  | B35 6QD | 394
10 | Bovingdon Road |  |  | B35 6QD | 395
12 | Bovingdon Road |  |  | B35 6QD | 396
34 | Bovingdon Road |  |  | B35 6QD | 397
36 | Bovingdon Road |  |  | B35 6QD | 398
38 | Bovingdon Road |  |  | B35 6QD | 399
40 | Bovingdon Road |  |  | B35 6QD | 400
FLAT 20 | Bovingdon Road |  |  | B35 6QD | 401
FLAT 22 | Bovingdon Road |  |  | B35 6QD | 402
FLAT 26 | Bovingdon Road |  |  | B35 6QD | 403
FLAT 28 | Bovingdon Road |  |  | B35 6QD | 404
FLAT 30 | Bovingdon Road |  |  | B35 6QD | 405
26 | Brabazon Grove |  |  | B35 6DT | 406
44 | Brabazon Grove |  |  | B35 6DT | 407
2 | Chigwell Close |  |  | B35 7HH | 408
6 | Chigwell Close |  |  | B35 7HH | 409
14 | Chigwell Close |  |  | B35 7HH | 410
16 | Chigwell Close |  |  | B35 7HH | 411
3 | Concorde Drive |  |  | B35 7EE | 412
35 | Donibristle Croft |  |  | B35 6BL | 413
FLAT 133E | Farnborough Road |  |  | B35 7LQ | 414
FLAT 133F | Farnborough Road |  |  | B35 7LQ | 415
FLAT 133G | Farnborough Road |  |  | B35 7LQ | 416
FLAT 135A | Farnborough Road |  |  | B35 7LQ | 417
FLAT 135B | Farnborough Road |  |  | B35 7LQ | 418
FLAT 135C | Farnborough Road |  |  | B35 7LQ | 419
FLAT 135D | Farnborough Road |  |  | B35 7LQ | 420
FLAT 135E | Farnborough Road |  |  | B35 7LQ | 421
FLAT 135F | Farnborough Road |  |  | B35 7LQ | 422
FLAT 137A | Farnborough Road |  |  | B35 7LQ | 423
FLAT 137B | Farnborough Road |  |  | B35 7LQ | 424
FLAT 141F | Farnborough Road |  |  | B35 7LQ | 425
FLAT 127F | Farnborough Road |  |  | B35 7LQ | 426
FLAT 143A | Farnborough Road |  |  | B35 7LQ | 427
FLAT 143B | Farnborough Road |  |  | B35 7LQ | 428
FLAT 143C | Farnborough Road |  |  | B35 7LQ | 429
FLAT 143D | Farnborough Road |  |  | B35 7LQ | 430
FLAT 143E | Farnborough Road |  |  | B35 7LQ | 431
FLAT 143F | Farnborough Road |  |  | B35 7LQ | 432
FLAT 141A | Farnborough Road |  |  | B35 7LQ | 433
FLAT 141B | Farnborough Road |  |  | B35 7LQ | 434
FLAT 141D | Farnborough Road |  |  | B35 7LQ | 435
FLAT 141E | Farnborough Road |  |  | B35 7LQ | 436
48 | Heyford Way |  |  | B35 6HU | 437
FLAT 4 Block 64 | Heyford Way |  |  | B35 6HU | 438
8 | Heyford Way |  |  | B35 6JH | 439
16 | Heyford Way |  |  | B35 6JH | 440
72 | Heyford Way |  |  | B35 6HU | 441
31 | Heyford Way |  |  | B35 6HY | 442
37 | Heyford Way |  |  | B35 6HY | 443
57C | Heyford Way |  |  | B35 6HZ | 444
80 | Heyford Way |  |  | B35 6HU | 445
57D | Heyford Way |  |  | B35 6HZ | 446
21 | Javelin Avenue |  |  | B35 7LH | 447
35 | Javelin Avenue |  |  | B35 7LH | 448
37 | Javelin Avenue |  |  | B35 7LH | 449
39 | Javelin Avenue |  |  | B35 7LH | 450
41 | Javelin Avenue |  |  | B35 7LH | 451
10 | Javelin Avenue |  |  | B35 7LW | 452
12 | Javelin Avenue |  |  | B35 7LW | 453
16 | Javelin Avenue |  |  | B35 7LW | 454
18 | Javelin Avenue |  |  | B35 7LW | 455
54 | Javelin Avenue |  |  | B35 7LW | 456
56 | Javelin Avenue |  |  | B35 7LW | 457
58 | Javelin Avenue |  |  | B35 7LW | 458
60 | Javelin Avenue |  |  | B35 7LW | 459
68 | Javelin Avenue |  |  | B35 7LW | 460
70 | Javelin Avenue |  |  | B35 7LW | 461
46 | Javelin Avenue |  |  | B35 7LW | 462
52 | Javelin Avenue |  |  | B35 7LW | 463
88 | Javelin Avenue |  |  | B35 7LW | 464
120 | Javelin Avenue |  |  | B35 7LW | 465
50 | Javelin Avenue |  |  | B35 7LW | 466
122 | Javelin Avenue |  |  | B35 7LW | 467
16 | Kemble Drive |  |  | B35 6QS | 468
14 | Kemble Drive |  |  | B35 6QS | 469
26 | Kemble Drive |  |  | B35 6QS | 470
28 | Kemble Drive |  |  | B35 6QS | 471
FLAT 34 | Kemble Drive |  |  | B35 6QS | 472
FLAT 36 | Kemble Drive |  |  | B35 6QS | 473
4 | Lysander Way |  |  | B35 7JY | 474
7 | Lysander Way |  |  | B35 7JY | 475
9 | Lysander Way |  |  | B35 7JY | 476
11 | Lysander Way |  |  | B35 7JY | 477
12 | Lysander Way |  |  | B35 7JY | 478
14 | Lysander Way |  |  | B35 7JY | 479
15 | Lysander Way |  |  | B35 7JY | 480
16 | Lysander Way |  |  | B35 7JY | 481
21 | Lysander Way |  |  | B35 7JY | 482
22 | Lysander Way |  |  | B35 7JY | 483
23 | Lysander Way |  |  | B35 7JY | 484
24 | Lysander Way |  |  | B35 7JY | 485
25 | Lysander Way |  |  | B35 7JY | 486
26 | Lysander Way |  |  | B35 7JY | 487
27 | Lysander Way |  |  | B35 7JY | 488
30 | Lysander Way |  |  | B35 7JY | 489
5 | Lysander Way |  |  | B35 7JY | 490
2 | Mere Avenue |  |  | B35 6QT | 491
42 | Mere Avenue |  |  | B35 6QT | 492
52 | Mere Avenue |  |  | B35 6QT | 493
4 | Mere Avenue |  |  | B35 6QT | 494
18 | Mere Avenue |  |  | B35 6QT | 495
20 | Mere Avenue |  |  | B35 6QT | 496
56 | Mere Avenue |  |  | B35 6QT | 497
58 | Mere Avenue |  |  | B35 6QT | 498
76 | Mere Avenue |  |  | B35 6QT | 499
78 | Mere Avenue |  |  | B35 6QT | 500
80 | Mere Avenue |  |  | B35 6QT | 501
82 | Mere Avenue |  |  | B35 6QT | 502
FLAT 44 | Mere Avenue |  |  | B35 6QT | 503
FLAT 48 | Mere Avenue |  |  | B35 6QT | 504
FLAT 50 | Mere Avenue |  |  | B35 6QT | 505
FLAT 70 | Mere Avenue |  |  | B35 6QT | 506
FLAT 72 | Mere Avenue |  |  | B35 6QT | 507
FLAT 74 | Mere Avenue |  |  | B35 6QT | 508
10 | Mere Avenue |  |  | B35 6QT | 509
FLAT 64 | Mere Avenue |  |  | B35 6QT | 510
FLAT 66 | Mere Avenue |  |  | B35 6QT | 511
24 | Montrose Drive |  |  | B35 6DH | 512
FLAT 1 Block 1 | Montrose Drive |  |  | B35 6DH | 513
3 | Trident Boulevard |  |  | B35 7LZ | 514
5 | Trident Boulevard |  |  | B35 7LZ | 515
8 | Trident Boulevard |  |  | B35 7LZ | 516
12 | Trident Boulevard |  |  | B35 7LZ | 517
15 | Trident Boulevard |  |  | B35 7LZ | 518
16 | Trident Boulevard |  |  | B35 7LZ | 519
18 | Trident Boulevard |  |  | B35 7LZ | 520
24 | Trident Boulevard |  |  | B35 7LZ | 521
76 | Watton Green |  |  | B35 7JR | 522
14 | Avro Way |  |  | B35 7NW | 523
16 | Avro Way |  |  | B35 7NW | 524
17 | Avro Way |  |  | B35 7NW | 525
18 | Avro Way |  |  | B35 7NW | 526
20 | Avro Way |  |  | B35 7NW | 527
FLAT 6 Block 16 | Bicester Square |  |  | B35 6HR | 528
5 | Bond Drive |  |  | B35 7QQ | 529
16 | Bovingdon Road |  |  | B35 6QD | 530
18 | Bovingdon Road |  |  | B35 6QD | 531
15 | Chigwell Close |  |  | B35 7HG | 532
55 | Chigwell Close |  |  | B35 7HG | 533
61 | Chigwell Close |  |  | B35 7HG | 534
63 | Chigwell Close |  |  | B35 7HG | 535
4 | Chigwell Close |  |  | B35 7HH | 536
10 | Chigwell Close |  |  | B35 7HH | 537
20 | Chigwell Close |  |  | B35 7HH | 538
21 | Concorde Drive |  |  | B35 7EE | 539
FLAT 1 Block 33 | Concorde Drive |  |  | B35 7EE | 540
FLAT 3 Block 33 | Concorde Drive |  |  | B35 7EE | 541
FLAT 10 | Cosford Crescent |  |  | B35 6QE | 542
3 | Cranwell Way |  |  | B35 6QH | 543
FLAT 133A | Farnborough Road |  |  | B35 7LQ | 544
1 | Hawker Drive |  |  | B35 7DX | 545
35 | Hawker Drive |  |  | B35 7DY | 546
37 | Hawker Drive |  |  | B35 7DY | 547
39 | Hawker Drive |  |  | B35 7DY | 548
43 | Hawker Drive |  |  | B35 7DY | 549
45 | Hawker Drive |  |  | B35 7DY | 550
10 | Hawker Drive |  |  | B35 7EG | 551
38 | Hawker Drive |  |  | B35 7EG | 552
10A | Hawker Drive |  |  | B35 7EG | 553
4B | Hawker Drive |  |  | B35 7EG | 554
6 | Hawker Drive |  |  | B35 7EG | 555
6A | Hawker Drive |  |  | B35 7EG | 556
8 | Hawker Drive |  |  | B35 7EG | 557
8A | Hawker Drive |  |  | B35 7EG | 558
8B | Hawker Drive |  |  | B35 7EG | 559
FLAT 2A | Hawker Drive |  |  | B35 7EG | 560
FLAT 2B | Hawker Drive |  |  | B35 7EG | 561
FLAT 4 | Hawker Drive |  |  | B35 7EG | 562
76 | Heyford Way |  |  | B35 6HU | 563
34 | Javelin Avenue |  |  | B35 7LW | 564
11 | Javelin Avenue |  |  | B35 7LH | 565
48 | Javelin Avenue |  |  | B35 7LW | 566
22 | Mere Avenue |  |  | B35 6QT | 567
FLAT 60 | Mere Avenue |  |  | B35 6QT | 568
FLAT 62 | Mere Avenue |  |  | B35 6QT | 569
FLAT 68 | Mere Avenue |  |  | B35 6QT | 570
FLAT 5 Block 1 | Montrose Drive |  |  | B35 6DH | 571
9 | Montrose Drive |  |  | B35 6DH | 572
17 | Montrose Drive |  |  | B35 6DH | 573
19 | Montrose Drive |  |  | B35 6DH | 574
30 | Northolt Drive |  |  | B35 6QX | 575
3 | Pioneer Way |  |  | B35 7LA | 576
5 | Pioneer Way |  |  | B35 7LA | 577
7 | Pioneer Way |  |  | B35 7LA | 578
14 | Pioneer Way |  |  | B35 7LA | 579
18 | Pioneer Way |  |  | B35 7LA | 580
FLAT 6 | Pioneer Way |  |  | B35 7LA | 581
4 | Sopwith Croft |  |  | B35 7QH | 582
6 | Sopwith Croft |  |  | B35 7QH | 583
10 | Sopwith Croft |  |  | B35 7QH | 584
14 | Sopwith Croft |  |  | B35 7QH | 585
7 | Trident Boulevard |  |  | B35 7LZ | 586
27 | Trident Boulevard |  |  | B35 7LZ | 587
29 | Trident Boulevard |  |  | B35 7LZ | 588
30 | Trident Boulevard |  |  | B35 7LZ | 589
FLAT 129D | Farnborough Road |  |  | B35 7LQ | 590
2 | Abingdon Way |  |  | B35 6QF | 591
35 | Abingdon Way |  |  | B35 6QF | 592
3 | Avro Way |  |  | B35 7NW | 593
4 | Avro Way |  |  | B35 7NW | 594
10 | Coltishall Close |  |  | B35 7EF | 595
FLAT 139A | Farnborough Road |  |  | B35 7LQ | 596
FLAT 139B | Farnborough Road |  |  | B35 7LQ | 597
FLAT 139C | Farnborough Road |  |  | B35 7LQ | 598
FLAT 139D | Farnborough Road |  |  | B35 7LQ | 599
FLAT 139E | Farnborough Road |  |  | B35 7LQ | 600
FLAT 139F | Farnborough Road |  |  | B35 7LQ | 601
FLAT 145A | Farnborough Road |  |  | B35 7LQ | 602
FLAT 145B | Farnborough Road |  |  | B35 7LQ | 603
FLAT 145C | Farnborough Road |  |  | B35 7LQ | 604
FLAT 145E | Farnborough Road |  |  | B35 7LQ | 605
FLAT 145F | Farnborough Road |  |  | B35 7LQ | 606
FLAT 145G | Farnborough Road |  |  | B35 7LQ | 607
FLAT 147A | Farnborough Road |  |  | B35 7LQ | 608
FLAT 147B | Farnborough Road |  |  | B35 7LQ | 609
FLAT 147C | Farnborough Road |  |  | B35 7LQ | 610
FLAT 147D | Farnborough Road |  |  | B35 7LQ | 611
FLAT 147E | Farnborough Road |  |  | B35 7LQ | 612
FLAT 147F | Farnborough Road |  |  | B35 7LQ | 613
FLAT 4 Block 214 | Farnborough Road |  |  | B35 7NH | 614
FLAT 1 Flats 214 1-6 Farnborough Road | Farnborough Road |  |  | B35 7NH | 615
FLAT 3 Flats 214 1-6 Farnborough Road | Farnborough Road |  |  | B35 7NH | 616
FLAT 5 Flats 214 1-6 Farnborough Road | Farnborough Road |  |  | B35 7NH | 617
FLAT 6 Flats 214 1-6 Farnborough Road | Farnborough Road |  |  | B35 7NH | 618
97 | Hawker Drive |  |  | B35 7EA | 619
101 | Hawker Drive |  |  | B35 7EA | 620
60 | Hawker Drive |  |  | B35 7EG | 621
8 | Montrose Drive |  |  | B35 6DH | 622
4 | Shawberry Avenue |  |  | B35 6QU | 623
1 | Shawberry Avenue |  |  | B35 6QU | 624
2 | Shawberry Avenue |  |  | B35 6QU | 625
3 | Shawberry Avenue |  |  | B35 6QU | 626
18 | Sopwith Croft |  |  | B35 7QH | 627
20 | Sopwith Croft |  |  | B35 7QH | 628
26 | Sopwith Croft |  |  | B35 7QH | 629
10 | Trident Boulevard |  |  | B35 7LZ | 630
26 | Hawker Drive |  |  | B35 7EG | 631
8 | Sopwith Croft |  |  | B35 7QH | 632
FLAT 331 | Yatesbury Avenue |  |  | B35 6QP | 633
FLAT 335 | Yatesbury Avenue |  |  | B35 6QP | 634
FLAT 337 | Yatesbury Avenue |  |  | B35 6QP | 635
FLAT 127C | Farnborough Road |  |  | B35 7LQ | 636
FLAT 129C | Farnborough Road |  |  | B35 7LQ | 637
FLAT 129E | Farnborough Road |  |  | B35 7LQ | 638
7 | Bond Drive |  |  | B35 7QQ | 639
14 | Bovingdon Road |  |  | B35 6QD | 640
FLAT 24 | Bovingdon Road |  |  | B35 6QD | 641
FLAT 42 | Cosford Crescent |  |  | B35 6QE | 642
FLAT 131F | Farnborough Road |  |  | B35 7LQ | 643
FLAT 141C | Farnborough Road |  |  | B35 7LQ | 644
57 | Chigwell Close |  |  | B35 7HG | 645
4A | Hawker Drive |  |  | B35 7EG | 646
12 | Pioneer Way |  |  | B35 7LA | 647
16 | Pioneer Way |  |  | B35 7LA | 648
FLAT 10 | Pioneer Way |  |  | B35 7LA | 649
FLAT 4 | Pioneer Way |  |  | B35 7LA | 650
FLAT 8 | Pioneer Way |  |  | B35 7LA | 651
16 | Sopwith Croft |  |  | B35 7QH | 652
29 | A St Athan Croft |  |  | B35 7LR | 653
65 | Abbey Road |  |  | B23 7QQ | 654
67 | Abbey Road |  |  | B23 7QQ | 655
81 | Abbey Road |  |  | B23 7QQ | 656
FLAT 133C | Farnborough Road |  |  | B35 7LQ | 657
42 | Brabazon Grove |  |  | B35 6DT | 658
58 | Cosford Crescent |  |  | B35 6QE | 659
FLAT 78 | Cosford Crescent |  |  | B35 6QE | 660
1 | Cosford Crescent |  |  | B35 6QE | 661
24 | Cosford Crescent |  |  | B35 6QE | 662
28 | Cosford Crescent |  |  | B35 6QE | 663
50 | Hermitage Road |  |  | B23 6AS | 664
29 | Lysander Way |  |  | B35 7JY | 665
FLAT 4 Block 1 | Montrose Drive |  |  | B35 6DH | 666
FLAT 1 | Reservoir Road |  |  | B23 6DJ | 667
FLAT 2 | Reservoir Road |  |  | B23 6DJ | 668
50 | Watton Green |  |  | B35 7JP | 669
22 | Abingdon Way |  |  | B35 6QF | 670
43 | Abingdon Way |  |  | B35 6QF | 671
FLAT 15 | Abingdon Way |  |  | B35 6QF | 672
560 | Auckland Drive |  |  | B36 0DB | 673
25 | Avery Croft |  |  | B35 7DG | 674
31 | Avery Croft |  |  | B35 7DG | 675
16 | Avery Croft |  |  | B35 7DH | 676
18 | Avery Croft |  |  | B35 7DH | 677
FLAT 12 | Avery Croft |  |  | B35 7DH | 678
FLAT 14 | Avery Croft |  |  | B35 7DH | 679
FLAT 8 | Avery Croft |  |  | B35 7DH | 680
52 | Avery Croft |  |  | B35 7DQ | 681
29 | B St Athan Croft |  |  | B35 7LR | 682
15 | Bader Walk |  |  | B35 7HA | 683
17 | Bader Walk |  |  | B35 7HA | 684
19 | Bader Walk |  |  | B35 7HA | 685
21 | Bader Walk |  |  | B35 7HA | 686
23 | Bader Walk |  |  | B35 7HA | 687
25 | Bader Walk |  |  | B35 7HA | 688
31 | Bader Walk |  |  | B35 7HA | 689
33 | Bader Walk |  |  | B35 7HA | 690
FLAT 20 | Barra Croft |  |  | B35 6NF | 691
14 | Beale Close |  |  | B35 7DA | 692
15 | Beale Close |  |  | B35 7DA | 693
22 | Beale Close |  |  | B35 7DA | 694
31 | Beale Close |  |  | B35 7DA | 695
FLAT 5 | Beale Close |  |  | B35 7DA | 696
FLAT 7 | Beale Close |  |  | B35 7DA | 697
FLAT 9 | Beale Close |  |  | B35 7DA | 698
35 | Blenheim Way |  |  | B35 7JF | 699
37 | Blenheim Way |  |  | B35 7JF | 700
39 | Blenheim Way |  |  | B35 7JF | 701
45 | Blenheim Way |  |  | B35 7JF | 702
47 | Blenheim Way |  |  | B35 7JF | 703
49 | Blenheim Way |  |  | B35 7JF | 704
50 | Blenheim Way |  |  | B35 7JF | 705
51 | Blenheim Way |  |  | B35 7JF | 706
53 | Blenheim Way |  |  | B35 7JF | 707
55 | Blenheim Way |  |  | B35 7JF | 708
56 | Blenheim Way |  |  | B35 7JF | 709
58 | Blenheim Way |  |  | B35 7JF | 710
59 | Blenheim Way |  |  | B35 7JF | 711
60 | Blenheim Way |  |  | B35 7JF | 712
61 | Blenheim Way |  |  | B35 7JF | 713
62 | Blenheim Way |  |  | B35 7JF | 714
63 | Blenheim Way |  |  | B35 7JF | 715
64 | Blenheim Way |  |  | B35 7JF | 716
65 | Blenheim Way |  |  | B35 7JF | 717
66 | Blenheim Way |  |  | B35 7JF | 718
67 | Blenheim Way |  |  | B35 7JF | 719
68 | Blenheim Way |  |  | B35 7JF | 720
70 | Blenheim Way |  |  | B35 7JF | 721
73 | Blenheim Way |  |  | B35 7JF | 722
79 | Blenheim Way |  |  | B35 7JF | 723
81 | Blenheim Way |  |  | B35 7JF | 724
85 | Blenheim Way |  |  | B35 7JF | 725
87 | Blenheim Way |  |  | B35 7JF | 726
89 | Blenheim Way |  |  | B35 7JF | 727
91 | Blenheim Way |  |  | B35 7JF | 728
93 | Blenheim Way |  |  | B35 7JF | 729
95 | Blenheim Way |  |  | B35 7JF | 730
97 | Blenheim Way |  |  | B35 7JF | 731
57 | Blenheim Way |  |  | B35 7JF | 732
69 | Blenheim Way |  |  | B35 7JF | 733
71 | Blenheim Way |  |  | B35 7JF | 734
75 | Blenheim Way |  |  | B35 7JF | 735
18 | Bond Drive |  |  | B35 7QQ | 736
FLAT 32 | Bovingdon Road |  |  | B35 6QD | 737
70 | Brabazon Grove |  |  | B35 6DT | 738
20 | Brookpiece Walk |  |  | B35 7LG | 739
3 | Brookpiece Walk |  |  | B35 7LG | 740
5 | Brookpiece Walk |  |  | B35 7LG | 741
9 | Brookpiece Walk |  |  | B35 7LG | 742
24 | Brookpiece Walk |  |  | B35 7LJ | 743
38 | Brookpiece Walk |  |  | B35 7LJ | 744
40 | Brookpiece Walk |  |  | B35 7LJ | 745
44 | Brookpiece Walk |  |  | B35 7LJ | 746
46 | Brookpiece Walk |  |  | B35 7LJ | 747
48 | Brookpiece Walk |  |  | B35 7LJ | 748
50 | Brookpiece Walk |  |  | B35 7LJ | 749
50A | Brookpiece Walk |  |  | B35 7LS | 750
22 | Brooks Croft |  |  | B35 7BX | 751
19 | Brooks Croft |  |  | B35 7BY | 752
31 | Brooks Croft |  |  | B35 7BY | 753
33 | Brooks Croft |  |  | B35 7BY | 754
63 | Brooks Croft |  |  | B35 7BY | 755
67 | Brooks Croft |  |  | B35 7BY | 756
35A | Brooks Croft |  |  | B35 7BY | 757
FLAT 11 | Brooks Croft |  |  | B35 7BY | 758
FLAT 15 | Brooks Croft |  |  | B35 7BY | 759
FLAT 35 | Brooks Croft |  |  | B35 7BY | 760
FLAT 37 | Brooks Croft |  |  | B35 7BY | 761
FLAT 39 | Brooks Croft |  |  | B35 7BY | 762
FLAT 43 | Brooks Croft |  |  | B35 7BY | 763
FLAT 45 | Brooks Croft |  |  | B35 7BY | 764
FLAT 47 | Brooks Croft |  |  | B35 7BY | 765
FLAT 49 | Brooks Croft |  |  | B35 7BY | 766
FLAT 51 | Brooks Croft |  |  | B35 7BY | 767
FLAT 7 | Brooks Croft |  |  | B35 7BY | 768
FLAT 9 | Brooks Croft |  |  | B35 7BY | 769
FLAT 11 | Cadbury Drive |  |  | B35 7EJ | 770
FLAT 15 | Cadbury Drive |  |  | B35 7EJ | 771
FLAT 17 | Cadbury Drive |  |  | B35 7EJ | 772
FLAT 19 | Cadbury Drive |  |  | B35 7EJ | 773
FLAT 21 | Cadbury Drive |  |  | B35 7EJ | 774
FLAT 23 | Cadbury Drive |  |  | B35 7EJ | 775
FLAT 29 | Cadbury Drive |  |  | B35 7EJ | 776
FLAT 31 | Cadbury Drive |  |  | B35 7EJ | 777
FLAT 33 | Cadbury Drive |  |  | B35 7EJ | 778
FLAT 35 | Cadbury Drive |  |  | B35 7EJ | 779
FLAT 37 | Cadbury Drive |  |  | B35 7EJ | 780
FLAT 41 | Cadbury Drive |  |  | B35 7EJ | 781
FLAT 9 | Cadbury Drive |  |  | B35 7EJ | 782
63 | Cadbury Drive |  |  | B35 7EP | 783
65 | Cadbury Drive |  |  | B35 7EP | 784
73 | Cadbury Drive |  |  | B35 7EP | 785
77 | Cadbury Drive |  |  | B35 7EP | 786
89 | Cadbury Drive |  |  | B35 7EP | 787
93 | Cadbury Drive |  |  | B35 7EP | 788
51 | Cadbury Drive |  |  | B35 7EP | 789
FLAT 55 | Cadbury Drive |  |  | B35 7EP | 790
FLAT 57 | Cadbury Drive |  |  | B35 7EP | 791
FLAT 61 | Cadbury Drive |  |  | B35 7EP | 792
24 | Cadbury Drive |  |  | B35 7EW | 793
26 | Cadbury Drive |  |  | B35 7EW | 794
28 | Cadbury Drive |  |  | B35 7EW | 795
30 | Cadbury Drive |  |  | B35 7EW | 796
22 | Cadbury Drive |  |  | B35 7EW | 797
121 | Cadbury Drive |  |  | B35 7EX | 798
127 | Cadbury Drive |  |  | B35 7EX | 799
131 | Cadbury Drive |  |  | B35 7EX | 800
133 | Cadbury Drive |  |  | B35 7EX | 801
135 | Cadbury Drive |  |  | B35 7EX | 802
137 | Cadbury Drive |  |  | B35 7EX | 803
147 | Cadbury Drive |  |  | B35 7EY | 804
157 | Cadbury Drive |  |  | B35 7EY | 805
165 | Cadbury Drive |  |  | B35 7EY | 806
169 | Cadbury Drive |  |  | B35 7EY | 807
171 | Cadbury Drive |  |  | B35 7EY | 808
145 | Cadbury Drive |  |  | B35 7EY | 809
FLAT 149 | Cadbury Drive |  |  | B35 7EY | 810
FLAT 151 | Cadbury Drive |  |  | B35 7EY | 811
FLAT 153 | Cadbury Drive |  |  | B35 7EY | 812
34 | Canterbury Close |  |  | B23 7QL | 813
No.3, Air Ministry Houses | Chester Road |  |  | B35 7AA | 814
No.5, Air Ministry Houses | Chester Road |  |  | B35 7AA | 815
1301 | Chester Road |  |  | B35 7ED | 816
1303 | Chester Road |  |  | B35 7ED | 817
1305 | Chester Road |  |  | B35 7ED | 818
1307 | Chester Road |  |  | B35 7ED | 819
17 | Chigwell Close |  |  | B35 7HG | 820
19 | Chigwell Close |  |  | B35 7HG | 821
21 | Chigwell Close |  |  | B35 7HG | 822
27 | Chigwell Close |  |  | B35 7HG | 823
59 | Chigwell Close |  |  | B35 7HG | 824
23 | Chigwell Close |  |  | B35 7HG | 825
8 | Chigwell Close |  |  | B35 7HH | 826
25 | Chigwell Close |  |  | B35 7HH | 827
1 | Clayton Walk |  |  | B35 7DB | 828
3 | Clayton Walk |  |  | B35 7DB | 829
7 | Clayton Walk |  |  | B35 7DB | 830
11 | Clayton Walk |  |  | B35 7DB | 831
25 | Clayton Walk |  |  | B35 7DB | 832
27 | Clayton Walk |  |  | B35 7DB | 833
29 | Clayton Walk |  |  | B35 7DB | 834
31 | Clayton Walk |  |  | B35 7DB | 835
33 | Clayton Walk |  |  | B35 7DB | 836
35 | Clayton Walk |  |  | B35 7DB | 837
40 | Clayton Walk |  |  | B35 7DD | 838
42 | Clayton Walk |  |  | B35 7DD | 839
44 | Clayton Walk |  |  | B35 7DD | 840
46 | Clayton Walk |  |  | B35 7DD | 841
28 | Clayton Walk |  |  | B35 7DD | 842
30 | Clayton Walk |  |  | B35 7DD | 843
48 | Clayton Walk |  |  | B35 7DD | 844
50 | Clayton Walk |  |  | B35 7DD | 845
FLAT 18 | Clayton Walk |  |  | B35 7DD | 846
FLAT 24 | Clayton Walk |  |  | B35 7DD | 847
FLAT 32 | Clayton Walk |  |  | B35 7DD | 848
FLAT 34 | Clayton Walk |  |  | B35 7DD | 849
FLAT 36 | Clayton Walk |  |  | B35 7DD | 850
FLAT 38 | Clayton Walk |  |  | B35 7DD | 851
FLAT 47 | Clayton Walk |  |  | B35 7DE | 852
FLAT 49 | Clayton Walk |  |  | B35 7DE | 853
FLAT 51 | Clayton Walk |  |  | B35 7DE | 854
FLAT 52 | Clayton Walk |  |  | B35 7DF | 855
FLAT 54 | Clayton Walk |  |  | B35 7DF | 856
FLAT 56 | Clayton Walk |  |  | B35 7DF | 857
FLAT 58 | Clayton Walk |  |  | B35 7DF | 858
20 | Cobham Close |  |  | B35 6EA | 859
22 | Cobham Close |  |  | B35 6EA | 860
24 | Cobham Close |  |  | B35 6EA | 861
16 | Coltishall Close |  |  | B35 7EF | 862
17 | Coltishall Close |  |  | B35 7EF | 863
19 | Coltishall Close |  |  | B35 7EF | 864
15A | Coltishall Close |  |  | B35 7EF | 865
25 | Concorde Drive |  |  | B35 7EE | 866
29 | Concorde Drive |  |  | B35 7EE | 867
15 | Concorde Drive |  |  | B35 7EE | 868
3 | Cosford Crescent |  |  | B35 6QE | 869
4 | Cosford Crescent |  |  | B35 6QE | 870
5 | Cosford Crescent |  |  | B35 6QE | 871
6 | Cosford Crescent |  |  | B35 6QE | 872
7 | Cosford Crescent |  |  | B35 6QE | 873
9 | Cosford Crescent |  |  | B35 6QE | 874
11 | Cosford Crescent |  |  | B35 6QE | 875
26 | Cosford Crescent |  |  | B35 6QE | 876
48 | Cosford Crescent |  |  | B35 6QE | 877
50 | Cosford Crescent |  |  | B35 6QE | 878
52 | Cosford Crescent |  |  | B35 6QE | 879
54 | Cosford Crescent |  |  | B35 6QE | 880
56 | Cosford Crescent |  |  | B35 6QE | 881
60 | Cosford Crescent |  |  | B35 6QE | 882
62 | Cosford Crescent |  |  | B35 6QE | 883
88 | Cosford Crescent |  |  | B35 6QE | 884
90 | Cosford Crescent |  |  | B35 6QE | 885
94 | Cosford Crescent |  |  | B35 6QE | 886
96 | Cosford Crescent |  |  | B35 6QE | 887
98 | Cosford Crescent |  |  | B35 6QE | 888
106 | Cosford Crescent |  |  | B35 6QE | 889
118 | Cosford Crescent |  |  | B35 6QE | 890
120 | Cosford Crescent |  |  | B35 6QE | 891
122 | Cosford Crescent |  |  | B35 6QE | 892
124 | Cosford Crescent |  |  | B35 6QE | 893
126 | Cosford Crescent |  |  | B35 6QE | 894
130 | Cosford Crescent |  |  | B35 6QE | 895
132 | Cosford Crescent |  |  | B35 6QE | 896
134 | Cosford Crescent |  |  | B35 6QE | 897
138 | Cosford Crescent |  |  | B35 6QE | 898
100 | Cosford Crescent |  |  | B35 6QE | 899
102 | Cosford Crescent |  |  | B35 6QE | 900
116 | Cosford Crescent |  |  | B35 6QE | 901
128 | Cosford Crescent |  |  | B35 6QE | 902
FLAT 108 | Cosford Crescent |  |  | B35 6QE | 903
FLAT 110 | Cosford Crescent |  |  | B35 6QE | 904
FLAT 112 | Cosford Crescent |  |  | B35 6QE | 905
FLAT 114 | Cosford Crescent |  |  | B35 6QE | 906
FLAT 15 | Cosford Crescent |  |  | B35 6QE | 907
FLAT 17 | Cosford Crescent |  |  | B35 6QE | 908
FLAT 19 | Cosford Crescent |  |  | B35 6QE | 909
FLAT 2 | Cosford Crescent |  |  | B35 6QE | 910
FLAT 20 | Cosford Crescent |  |  | B35 6QE | 911
FLAT 21 | Cosford Crescent |  |  | B35 6QE | 912
FLAT 22 | Cosford Crescent |  |  | B35 6QE | 913
FLAT 23 | Cosford Crescent |  |  | B35 6QE | 914
FLAT 27 | Cosford Crescent |  |  | B35 6QE | 915
FLAT 38 | Cosford Crescent |  |  | B35 6QE | 916
FLAT 40 | Cosford Crescent |  |  | B35 6QE | 917
FLAT 72 | Cosford Crescent |  |  | B35 6QE | 918
FLAT 80 | Cosford Crescent |  |  | B35 6QE | 919
FLAT 82 | Cosford Crescent |  |  | B35 6QE | 920
FLAT 84 | Cosford Crescent |  |  | B35 6QE | 921
FLAT 86 | Cosford Crescent |  |  | B35 6QE | 922
6 | Cranwell Way |  |  | B35 6QH | 923
10 | Cranwell Way |  |  | B35 6QH | 924
12 | Cranwell Way |  |  | B35 6QH | 925
14 | Cranwell Way |  |  | B35 6QH | 926
16 | Cranwell Way |  |  | B35 6QH | 927
17 | Cranwell Way |  |  | B35 6QH | 928
19 | Cranwell Way |  |  | B35 6QH | 929
7 | Cranwell Way |  |  | B35 6QH | 930
9 | Cranwell Way |  |  | B35 6QH | 931
FLAT 11 | Cranwell Way |  |  | B35 6QH | 932
3 | Davenport Drive |  |  | B35 7NT | 933
4 | Davenport Drive |  |  | B35 7NT | 934
5 | Davenport Drive |  |  | B35 7NT | 935
7 | Davenport Drive |  |  | B35 7NT | 936
11 | Davenport Drive |  |  | B35 7NT | 937
12 | Davenport Drive |  |  | B35 7NT | 938
14 | Davenport Drive |  |  | B35 7NT | 939
17 | Davenport Drive |  |  | B35 7NT | 940
18 | Davenport Drive |  |  | B35 7NT | 941
19 | Davenport Drive |  |  | B35 7NT | 942
20 | Davenport Drive |  |  | B35 7NT | 943
21 | Davenport Drive |  |  | B35 7NT | 944
25 | Davenport Drive |  |  | B35 7NT | 945
29 | Davenport Drive |  |  | B35 7NT | 946
31 | Davenport Drive |  |  | B35 7NT | 947
33 | Davenport Drive |  |  | B35 7NT | 948
37 | Davenport Drive |  |  | B35 7NT | 949
43 | Davenport Drive |  |  | B35 7NT | 950
12 | Dixon Close |  |  | B35 7EN | 951
22 | Dixon Close |  |  | B35 7EN | 952
26 | Dixon Close |  |  | B35 7EN | 953
28 | Dixon Close |  |  | B35 7EN | 954
30 | Dixon Close |  |  | B35 7EN | 955
32 | Dixon Close |  |  | B35 7EN | 956
34 | Dixon Close |  |  | B35 7EN | 957
36 | Dixon Close |  |  | B35 7EN | 958
38 | Dixon Close |  |  | B35 7EN | 959
40 | Dixon Close |  |  | B35 7EN | 960
42 | Dixon Close |  |  | B35 7EN | 961
44 | Dixon Close |  |  | B35 7EN | 962
46 | Dixon Close |  |  | B35 7EN | 963
48 | Dixon Close |  |  | B35 7EN | 964
89 | Doidge Road |  |  | B23 7SQ | 965
40 | Doncaster Way |  |  | B36 8UD | 966
16 | Donibristle Croft |  |  | B35 6BL | 967
21 | Donibristle Croft |  |  | B35 6BL | 968
20 | Donibristle Croft |  |  | B35 6BL | 969
1 | Farnborough Road |  |  | B35 7EH | 970
3 | Farnborough Road |  |  | B35 7EH | 971
5 | Farnborough Road |  |  | B35 7EH | 972
9 | Farnborough Road |  |  | B35 7EH | 973
11 | Farnborough Road |  |  | B35 7EH | 974
15 | Farnborough Road |  |  | B35 7EH | 975
17 | Farnborough Road |  |  | B35 7EH | 976
27 | Farnborough Road |  |  | B35 7EH | 977
FLAT 101 | Farnborough Road |  |  | B35 7EH | 978
FLAT 103 | Farnborough Road |  |  | B35 7EH | 979
FLAT 105 | Farnborough Road |  |  | B35 7EH | 980
FLAT 107 | Farnborough Road |  |  | B35 7EH | 981
FLAT 109 | Farnborough Road |  |  | B35 7EH | 982
FLAT 111 | Farnborough Road |  |  | B35 7EH | 983
FLAT 113 | Farnborough Road |  |  | B35 7EH | 984
FLAT 115 | Farnborough Road |  |  | B35 7EH | 985
FLAT 117 | Farnborough Road |  |  | B35 7EH | 986
FLAT 119 | Farnborough Road |  |  | B35 7EH | 987
FLAT 121 | Farnborough Road |  |  | B35 7EH | 988
FLAT 123 | Farnborough Road |  |  | B35 7EH | 989
FLAT 31 | Farnborough Road |  |  | B35 7EH | 990
100 | Farnborough Road |  |  | B35 7JG | 991
98 | Farnborough Road |  |  | B35 7JG | 992
FLAT 145D | Farnborough Road |  |  | B35 7LQ | 993
FLAT 147G | Farnborough Road |  |  | B35 7LQ | 994
172 | Farnborough Road |  |  | B35 7NE | 995
FLAT 1 Flats 216 1-6 Farnborough Road | Farnborough Road |  |  | B35 7NH | 996
FLAT 2 Flats 216 1-6 Farnborough Road | Farnborough Road |  |  | B35 7NH | 997
| Farnborough Road |  |  |  | 998
FLAT 3 Flats 216 1-6 Farnborough Road | Farnborough Road |  |  | B35 7NH | 999
FLAT 4 Flats 216 1-6 Farnborough Road | Farnborough Road |  |  | B35 7NH | 1000
0
Note on U26: Kevin Caveney: this figures will come from the tracker Automaticly and will reflect the install date and hand over status

## Financial Summary
FINANCIAL YEAR END | 2024-03-31
ANNUAL CONTRACT BUDGET | 7000000
2024-07-18 | CASE | TILT TURN | FULLY REVERSE | VERT SLIDER | FIRE | CAVITY CLOSER | SINGLE | DOUBLE | BI-FOLD | IN-LINE SLIDER | FRONT SOLID GRP | FRONT GLAZED GRP | REAR SOLID GRP | REAR GLAZED GRP | SOLID FIRE | GLAZED FIRE | BASIC SHED | INT TOP LIGHT | SEPARATE TOP LIGHT | SIDE LIGHT | Communal Door | TOTAL
TOTAL NO OF UNITS | 2590 | 1 | 0 | 0 | 0 | 0 | 48 | 41 | 0 | 7 | 1 | 212 | 3 | 255 | 0 | 0 | 0 | 0 | 3 | 76 | 0 | 3237
AVERAGE RATE | 400 | 400 | 400 | 400 | 400 |  | 750 | 1000 | 1000 | 1000 | 800 | 850 | 800 | 850 | 885.14 | 885.14 | 600 | 120 | 97.82 | 220 | 850
TOTAL VALUE (ON TRACKER) | 1036000 | 400 | 0 | 0 | 0 | 0 | 36000 | 41000 | 0 | 7000 | 800 | 180200 | 2400 | 216750 | 0 | 0 | 0 | 0 | 293.46 | 16720 | 0 | 1537563.46
FITTED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HANDED OVER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RECALL REQUIRED | 32800 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 6800 | 0 | 6800 | 0 | 0 | 0 | 0 | 0 | 1540 | 0 | 51940
PART FITTED | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1700 | 0 | 2550 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 15070
SUBTOTAL "COMPLETE" VALUE | 42400 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 1000 | 0 | 8500 | 0 | 9350 | 0 | 0 | 0 | 0 | 0 | 1760 | 0 | 67010
NO OF UNITS "COMPLETE" TRACKER | 106 | 0 | n/a | n/a | n/a | n/a | 0 | 4 | n/a | 1 | 0 | 10 | 0 | 11 | n/a | n/a | n/a | n/a | 0 | 8 | n/a | 140
COMMENCEMENT PENDING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ON HOLD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SURVEY BOOKED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCOPE SURVEY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SURVEY RECEIVED | 48400 | 400 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 1700 | 0 | 2550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54050
PM TO CLEANSE | 214800 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 800 | 39950 | 2400 | 76500 | 0 | 0 | 0 | 0 | 0 | 5500 | 0 | 342950
CLEANSED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SENT FOR PRICING | 346400 | 0 | 0 | 0 | 0 | 0 | 13500 | 16000 | 0 | 2000 | 0 | 56100 | 0 | 60350 | 0 | 0 | 0 | 0 | 195.64 | 2640 | 0 | 497185.64
PRICED | 5600 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 1700 | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000
AWAIT CLIENT APPROVAL | 228800 | 0 | 0 | 0 | 0 | 0 | 15750 | 11000 | 0 | 4000 | 0 | 45050 | 0 | 34850 | 0 | 0 | 0 | 0 | 0 | 3080 | 0 | 342530
CALLED OFF | 46000 | 0 | 0 | 0 | 0 | 0 | 750 | 1000 | 0 | 0 | 0 | 7650 | 0 | 6800 | 0 | 0 | 0 | 0 | 97.82 | 880 | 0 | 63177.82
DELIVERED TO DEPOT/CONTAINER | 15600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400 | 0 | 3400 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 22620
BOOKED TO FIT | 88000 | 0 | 0 | 0 | 0 | 0 | 6000 | 3000 | 0 | 0 | 0 | 16150 | 0 | 21250 | 0 | 0 | 0 | 0 | 0 | 2640 | 0 | 137040
CANCELLED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NWR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NO ACCESS SURVEY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NO ACCESS INSTALL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REFUSAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HANDED BACK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DUPLICATE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUPPLY ONLY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUBTOTAL "TO COMPLETE" VALUE | 993600 | 400 | 0 | 0 | 0 | 0 | 36000 | 37000 | 0 | 6000 | 800 | 171700 | 2400 | 207400 | 0 | 0 | 0 | 0 | 293.46 | 14960 | 0 | 1470553.46
NO OF UNITS "TO COMPLETE" TRACKER | 2484 | 1 | n/a | n/a | n/a | n/a | 48 | 37 | n/a | 6 | 1 | 202 | 3 | 244 | n/a | n/a | n/a | n/a | 3 | 68 | n/a | 3097
MONTHS REMAINING IN FIN YEAR | -3.5832 | -3.5832 | -3.5832 | -3.5832 | -3.5832 | -3.5832 | -3.5832 | -3.5832 | -3.5832 | -3.5832 | -3.5832 | -3.5832 | -3.5832 | -3.5832 | -3.5832 | -3.5832 | -3.5832 | -3.5832 | -3.5832 | -3.5832 | -3.5832 | -3.5832
AVERAGE UNITS P/MTH TO INSTALL | -694 | -1 | 0 | 0 | 0 | 0 | -14 | -11 | 0 | -2 | -1 | -57 | -1 | -69 | 0 | 0 | 0 | 0 | -1 | -19 | 0 | -865
REMAINING BUDGET TO BE ALLOCATED | [21 empty] | 5462436.54
CHECK VALUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CHECK UNITS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Summary Report
[Client Name] Windows & doors 23/24
Progress Report
|  | Date | 2024-07-18
Project Overview
| Start | Finish
Project Constraints | 2024-06-13 | 2025-07-31
Time Elapsed | 8.475% | 25
Time Left | 378 | 12
Handovers | Targeted | Achieved
| 170.1695 | 0
Handover Status Against Target | 0%
project summary
Qty
Programme (issued) | 2017
Properties Omitted as NWR | 3 | 0.1487%
Further properties identified as "Cancelled" | 1 | 0.04958%
Further properties identified as "Duplicate" | 0 | 0%
Survey no access | 4 | 0.1983%
Handed Back to client | 0 | 0%
Survey refused | 1 | 0.04958%
Balance | 2008 | 99.55%
Project Status
active properties |  | % of active project
2008
on hold | 2 | 0.0996%
surveys scheduled | 108 | 5.378%
Properties scope surveyed | 0 | 0%
surveys completed | 512 | 25.5%
awaiting client instruction to proceed | 81 | 4.034%
issued to manufacture | 58 | 2.888%
installation scheduled | 31 | 1.544%
Properties fitted but not handed over | 11 | 0.5478%
Completed properties handed over to client | 0 | 0%
properties in WIP | 11 | 0.5478%
Properties supply only /no access install | 0 | 0%
Commencement pending | 1388 | 69.12%
of the properties on hold these are awaiting client action |  | 1
No Access History
Subtotal | 71 | 3.536%
Survey Access failures stage 1 | 50 | 2.49%
Survey Access failures stage 2 | 17 | 0.8466%
Survey Access failures stage 3 | 4 | 0.1992%
Install Access failures stage 1 | 0 | 0%
Install Access failures stage 2 | 0 | 0%
Install Access failures stage 3 | 0 | 0%
Project Product Split
Product | Qty | % of project
Total Products | 3237
windows | 2591 | 80.04%
PVCu-u doors | 48 | 1.483%
patios / French doors | 48 | 1.483%
composite doors | 471 | 14.55%
fire doors | 0 | 0%
top light & side lights | 79 | 2.441%
Cavity Closer | 0 | 0%
Communal Door | 0 | 0%
Health & Safety
Health & Safety Executive Site Visits | 0
In House Health & Safety Visits | 0
Accident and Near Misses | None
Site Issues | None
BUDGET SPEND GUIDANCE
SPEND | 7000000
Windows | 725480
PVC-U Doors | 19056
Patios/French doors | 35187.36
Composite Doors | 235500
Fire Doors | 0
Top Light & Side Lights | 9480
PLUS SCAFFOLD
PLUS LINTELS
SPEND SO FAR (if all surveys received back according to the tracker, was fitted) | 1537563.46
REMAINING SPEND | 5462436.54
% COMPLETE | 21.97%
COMPLETION DATE

## Mile Stones
Kick start item Ref | owner |  | Task |  |  |  | mile stone date | from acceptance of order | week ending
|  |  |  | linked task | linked time period
| Client & NWW | Mile stone (1) | kickstart meeting |  |  | 70 | 2024-04-04 |  | 2024-04-05
| NWW | Mile stone (4) | Internal Handover Meeting | Mile stone (1) |  | 7 | 2024-04-11 |  | 2024-04-12
8.1 | NWW | Mile stone (2) | Summary Spec & door choice form issued | Mile stone (1) |  | 4 | 2024-04-08 |  | 2024-04-12
8.2 | Client | Mile stone (3) | Specification & door choice approved | Mile stone (2) |  | 2 | 2024-04-10 |  | 2024-04-12
3.4 | Client | Mile stone (5) | Contract / order issued | Mile stone (1) | 1 | 7 | 2024-04-11 |  | 2024-04-12
11.5 | Client | Mile stone (6) | Property list & resident contact details issued | Mile stone (5) |  | 2 | 2024-04-13 |  | 2024-04-12
5.4 | NWW | Mile stone (7) | Provisional Programme issued | Mile stone (4) |  | 7 | 2024-04-18 |  | 2024-04-19
5.4 | Client & NWW | Mile stone (8) | Provisional Programme agreed | Mile stone (7) |  | 2 | 2024-04-20 |  | 2024-04-19
3.5 | Client & NWW | Mile stone (9) | Contract / order executed / Accepted (Signed) | Mile stone (5) | 2 | 14 | 2024-04-18 |  | 2024-04-19 | Issued by KC 26.05.23
11.6 | Client | Mile stone (10) | Vulnerable & high risk resident list issued | Mile stone (9) |  | 4 | 2024-04-22 |  | 2024-04-26
11.4 | Client | Mile stone (11) | Resident advised of NWW appointment | Mile stone (10) |  | 4 | 2024-04-22 |  | 2024-04-26
6.3 | Client | Mile stone (12) | Pre construction info provided | Mile stone (9) |  | 4 | 2024-04-22 |  | 2024-04-26
5.1 | NWW | Mile stone (13) | start survey mobilisation | Mile stone (9) | 3 | 21 | 2024-04-25 | 1 | 2024-04-26 | 2024-05-03 | 2024-05-10
6.6 | Client | Mile stone (14) | Asbestos information provided | Mile stone (9) |  | 2 | 2024-04-27 |  | 2024-04-26
6.4 | NWW | Mile stone (15) | construction phase plan issued | Mile stone (6) |  | 2 | 2024-04-27 |  | 2024-04-26
6.4 | Client & NWW | Mile stone (16) | construction phase plan agreed | Mile stone (13) |  | 4 | 2024-05-01 |  | 2024-05-03
5.2 | NWW | Mile stone (17) | Surveys available for pricing | Mile stone (13) | 5 | 35 | 2024-05-09 | 3 | 2024-05-10 | 2024-05-10 | 2025-06-20
5.3 | NWW | Mile stone (18) | Surveys available for manufacture | Mile stone (17) | 6 | 42 | 2024-05-16 | 4 | 2024-05-17 | 2024-05-17 | 2025-07-04
| NWW | Mile stone (19) | product available for installation | Mile stone (18) |  | 21 | 2024-06-06 |  | 2024-06-07 | 2024-06-07 | 2025-07-17
|  | Mile stone (20) | Targeted Start on Site | Mile stone (1) | 8 |  | 2024-06-13 | 8 | 2024-06-14 |  |  | These dates are to be adjusted by the PM and shall be reflected on the Program Automaticly
|  | Mile stone (21) | Targeted completion |  |  |  | 2025-07-31 |  | 2025-08-01
[7 empty] | 3 |  |  |  |  | Holiday shutdown period within program time line
Formulas:
mile stone date = [mile stone date, row above]+G23
week ending = [mile stone date]+6-WEEKDAY([mile stone date])

## UPRN Fix
Don’t edit this colomn | UPRN | New UPRN
If the program is not populating - follow these steps
1. copy uprn coloumn from tracker page and paste into colomn B on this page
2. Coloumn D should auto populate with the UPRNS
3. Copy all UPRNS from coloumn D and past into the UPRN coloumn on the tracker page.
4. Remember to paste as text only

## Tracker
| Contract No |  |  | Version 7.5 | Vision Version 5 | [22 empty] | WINDOWS | [5 empty] | DOORS |  |  |  | GRP COMPOSITE
0 | Date Property Instruction Received From Client | UPRN or Client Instruction Number | Priority Order | Status |  | House Number | Street | Town | County | Postcode | Property Archetype | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Tenant Disability | Scope of Work | Surveyor | Initial Programmed Survey Date | AM / PM Appointment | Route march order | Survey Access Attempts Made | Comments | Survey Access Comments | Asbestos Information Available | Job No. | Sq's | CASE | TILT TURN | FULLY REVERSE | VERT SLIDER | FIRE | CAVITY CLOSER | SINGLE | DOUBLE | BI-FOLD | IN-LINE SLIDER | FRONT SOLID GRP | FRONT GLAZED GRP | REAR SOLID GRP | REAR GLAZED GRP | SOLID FIRE | GLAZED FIRE | BASIC SHED | INT TOP LIGHT | SEPARATE TOP LIGHT | SIDE LIGHT | Communal Door | Lintel Works Required | Access Equipment Required | Property Construction Type | Survey Identified Comment(s) | Call Off Number | Called Off Date | Delivery Date | Delivery Point | Delivery Note Received | Scheduled Fitting Date | AM / PM Appointment | Route march order | Install Access Attempts Made | Installation (Primary) | Installation (Secondary) | Installation Related Comments | Installation Sheet Received | Variation Details | Variation Order Number | Date Handed Over | Inspected by | Install Wages Applied For | Lease Holder House Number | Lease Holder Street | Lease Holder Town | Lease Holder County | Lease Holder Postcode | Lease Holder Name | Lease Holder Telephone Number (Primary) | Lease Holder Telephone Number (Secondary) | L+A3:CD3ease Holder Email Address
3 |  | 61388 |  | PART FITTED | POST 2000 | 14 | Javelin Avenue | Birmingham |  | B35 7LW | House | Miss A Dean |  | 07930 656 107 | mandyjdean@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-04-22 | 8am to 2pm |  |  | TS-12/04/24 Text sent for 22/04/24. TS-15/04/24 Survey CONFIRMED for 22/04/24. TS-26/04/24 Survey received waiting for photos. TS-30/04/24 Photos received passed to DA to cleanse. TS-01/05/24 Survey cleansed and sent for pricing. Post 2000 no asbestos report needed. |  |  |  |  | 16 | [10 empty] | 1 |  | 2 | [7 empty] | No |  | Brick |  | PG02(W) | 2024-06-10 | 2024-07-04 | Container |  | 08.07, 09.07, 10.07.24 | 8am to 2pm |  |  | Eric |  | 3 DAY FITTING - 02.07.24 SF Tenant works nights, her son will be at home for the installation. Tenant CONFIRMED we can attend 8th - 10th July 2024. 09.07.24 SF Neil emailed broken glass units, broken on installation by Eric, remake unit Win No6 441 x 936, Win No9 461 x 826, delivery to Coleshill Depot on the 15.07.24. 12/7; REMAKE FRAME REORDERED DUE TO SURVEYOR ERROR DELIVERY DUE 18/7.
3 |  | 67102 |  | RECALL REQUIRED |  | 50 | Heyford Way | Birmingham |  | B35 6HU | House | Mr J E Bramwell | 0121 748 1936 | 07848 932 573 | johnbramwell45@yahoo.co.uk |  | Windows & Doors | P Beahan | 2024-04-15 | 8am to 12 noon |  |  | TS-04/04/24 Text sent for 15/04/24. TS-08/04/24 Called tenant survey CONFIRMED for 15/04/24. TS-26/04/24 Survey cleansed sent for pricing. |  |  |  |  | 8 | [6 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 1 |  | No | Jammer System | Brick | Blinds fixed to windows | [5 empty] | 12.07 & 15.07.24 | 8am to 2pm |  |  | Eric |  | 1.5 day fit. 02/07 SMS text sent for 12th & 15th July. 03/07 SMS called left voicemail. 04/07 SMS called N/A Lttr sent. 15/07 SMS 1 x re-make unit 654 x 1803 req deliv 23/07
3 |  | 55902 |  | RECALL REQUIRED |  | 19 | Heyford Way | Birmingham |  | B35 6HY | House | Mr A Hughes |  | 07984 536 982 |  |  | Windows & Doors | P Beahan | 2024-04-11 | 8am to 12 noon |  |  | TS-02/04/24 Text sent for 11/04/24. TS-03/04/24 Tenant CONFIRMED for the 11/04/24. TS16/04/24 Tenant called with her door choice - she text it in she wants THIRSK in white. TS-26/04/24 Survey cleansed sent for pricing. |  |  |  |  | 8 | [6 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 1 |  | No | Jammer System | Brick | Asthma No Solvents | PG03(W) | 2024-06-18 | 2024-07-08 | Depot |  | 11.07 & 12.07.24 | 8am to 2pm |  |  | Eric |  | 1.5 day fit. 02/07 SMS text sent for 11 &12th July. CONFIRMED. 15/07 SMS 1 x remake unit 481 x 241 & 256 x 661 req deliv 23/07
3 |  | 66717 |  | RECALL REQUIRED | SCAFFOLD | 25 | Heyford Way | Birmingham |  | B35 6HY | House | Miss D Newbold | 07854 247 764 |  |  |  | Windows & Doors | P Beahan | 2024-04-11 | 8am to 12 noon |  |  | TS-02/04/24 Text sent for 11/04/24. TS-02/04/24 Tenant CONFIRMED for the 11/04/24. TS-26/04/24 Survey cleansed sent for pricing. |  |  |  |  | 8 | [6 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 1 |  | No | Independent Scaffold | Brick | SCAFFOLD pitched roof & conservatory | [5 empty] | 11.07 & 12.07.24 | 8am to 2pm |  |  | Adrian |  | SCAFFOLD REQUIRED :- Erect 08.07.24 - 1.5 DAY FITTING - 02.07.24 SF Tenant CONFIRMED we can attend 11th - 12th July 2024. 12/7; 2 remake unit ordered for delivery 18/7.
4 |  | 67740 |  | BOOKED TO FIT |  | 40 | Heyford Way | Birmingham |  | B35 6HU | House | Miss K Clarke | 07947 832 739 |  |  |  | Windows & Doors | P Beahan | 2024-04-11 | 11am to 3pm |  |  | TS-02/04/24 Text sent for 11/04/24. TS-04/04/24 Called tenant and she confirmed for 11/04/24. 23.05.24 SF attached photos to surveys, given to Darren to cleanse. |  |  |  |  | 10 | [10 empty] | 1 | [7 empty] | 1 |  | No | Jammer System | Brick |  | PG05(W) | 2024-06-18 | 2024-07-11 | Container |  | 25/07/2024 & 26/07/2024 | 8am to 2pm |  |  | Jim McDonald |  | 3/7; AC rang and booked install for 11th and 12th July, confirmed. Cancelled due to overbooking. 12/07 SMS text sent for 25 & 26 July. 15/07 SMS left voicemail. 15/07 SMS re-make glass unit 552 x 606 req deliv 23/07. CONFIRMED for 25/07 & 26/07
3 |  | 59777 |  | RECALL REQUIRED |  | 78 | Heyford Way | Birmingham |  | B35 6HU | House | Mrs A Youssef | 07760 550 633 | 07366459329 |  |  | Windows & Doors | P Beahan | 2024-04-10 | 8am to 12 noon |  |  | TS-02/04/24 Text sent for 10/04/24. TS-03/04/24 Called left vm, txt & ltr sent. TS-03/04/24 Tenant CONFIRMED survey for 10/04/24. 23.05.24 SF attached photos to surveys, given to Darren to cleanse. 30/05 SMS sent to Dominie to get missing front door choice from tenant before i can scan to commercial for pricing, paperwork in queries tray/box behind my desk until received. |  |  |  |  | 10 | [10 empty] | 1 |  | 1 | [7 empty] | No | Jammer System | Brick | No Solvents, Door Jammer | [5 empty] | 15.07 & 16.07.24 | 8am to 2pm |  |  | Eric |  | No Solvents, Door Jammer. 1.5 day fit. 02/07 SMS text sent for 15th & 16th July. 03/07 SMS called no NIS Lttr sent. 08/07 SMS tenant CONFIRMED with TLO on 08/07. 15/07 SMS 4 x glass re-makes 518 x 961 & 516 x 961 & 441 x 961 & 516 x 816 req deliv 23/07
3 |  | 56957 |  | RECALL REQUIRED |  | 9 | Heyford Way | Birmingham |  | B35 6HY | Flat | Mr T Woodward | 0121 749 2825 | 07572983481 |  |  | Windows & Doors | P Beahan | 2024-04-10 | 11am to 3pm |  |  | TS-02/04/24 Text sent for 10/04/24. TS-03/04/24 Called tenant survey CONFIRMED for 10/04/24 - ltr sent. 23.05.24 SF attached photos to surveys, given to Darren to cleanse. |  |  |  |  | 11 | [10 empty] | 1 |  | 1 | [5 empty] | 1 |  | No | Jammer System | Brick | Jammer | PG03(W) | 2024-06-18 | 2024-07-08 | Container |  | 15.07 & 16.07.24 | 8am to 2pm |  |  | Adrian |  | Jammer. 1.5 day fit. 02/07 SMS text sent for 15th & 16th July. 03/07 SMS called N/A. 04/07 SMS called N/A Lttr sent. 10.07.24 SF Tenant called to CONFIRM installation on the 15.07 & 16.07.24 over two days.16/07 SMS re-make 441 x 886 req deliv 23/07
4 |  | 55925 |  | PART FITTED |  | 89 | Heyford Way | Birmingham |  | B35 6JB | House | Mr R J Hughes | 07704 255 990 |  |  |  | Windows & Doors | P Beahan | 2024-04-15 | 8am to 12 noon |  |  | TS-04/04/24 Letter sent to the tenant as no contact number for 15/04/24. ts-26/04/24 Survey cleansed and sent for pricing. |  |  |  |  | 8 | [8 empty] | 1 |  | 1 |  | 1 | [5 empty] | 1 |  | No | Jammer System | Brick | Blinds fixed to 8 windows | [5 empty] | 12.07 & 15.07.24 | 8am to 2pm |  |  | Adrian |  | 1.5 day fit. 02/07 SMS text sent for 12th & 15th July. CONFIRMED. 15/07 SMS revised Dims for Lounge flag and ordered for req deliv 23/07
3 |  | 55901 |  | RECALL REQUIRED |  | 18 | Heyford Way | Birmingham |  | B35 6JH |  | Mr S B Brown | 01217494098 | 07956 658 295 |  | Mobility Issues | Windows & Doors | P Beahan | 2024-04-10 | 11am to 3pm |  |  | TS-02/04/24 Text sent for 10/04/24. TS-03/04/24 Called tenant survey CONFIRMED for 10/04/24. 23.05.24 SF attached photos to surveys, given to Darren to cleanse. |  |  |  |  | 10 | [6 empty] | 1 |  |  |  | 1 | [7 empty] | 1 |  | No | Jammer System | Brick | [6 empty] | 10.07 & 11.07.24 | 8am to 2pm |  |  | Jim McDonald |  | 3/7; AC rang and booked install for 10th and 11th July, confirmed. 15/07 SMS re-make glass units 546 x 1783 & 295 x 741 req deliv 23/07
4 |  | 66058 |  | BOOKED TO FIT | POST 2000 | 80 | Javelin Avenue | Birmingham |  | B35 7LW | House | Miss A Grant | 07947 201 836 |  | Ashagrant@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-04-23 | 8am to 2pm |  |  | TS-17/04/24 Called tenant left vm, text & ltr sent for 23/04/24. TS-17/04/24 Tenant called to CONFIRMED for 23/04/24. TS-26/04/24 Survey rec'd waiting for photos. TS-30/04/24 Photos received passed to DA to cleanse. TS-01/05/24 Survey cleansed and sent for pricing. Post 2000 no asbestos report needed. |  |  |  |  | 18 | [10 empty] | 1 |  | 3 | [7 empty] | No |  | Brick |  | PG02(W) | 2024-06-10 | 2024-07-04 | Container |  | 08.07, 09.07, 10.07.24 | 8am to 2pm |  |  | Adrian |  | 3 Day fit - Tenant CONFRIMED the installation over 3 days. 05/07 SMS re-make glass unit 481 x 226 ordered, req deliv 11/07. 11.07.24 SF Neil emailed, GF Lounge welded sills required, survey error, new survey attached on Vision, delivery for 15.07.24, urgent delivery, this is a PILOT Property.
4 |  | 59965 |  | BOOKED TO FIT |  | 9 | Northolt Drive | Birmingham |  | B35 6QX | Flat | Mrs A Fletcher | 0121 7487 110 | 07511 467 413 |  |  | Windows & Doors | S Burgess | 2024-04-17 | 8am to 12 noon |  |  | TS-04/04/24 Text sent for 17/04/24. TS-04/04/24 Survey CONFIRMED for 17/04/24. TS-22/04/24 Survey and photos given to DA to cleanse. Rear Door is NWR. TS-24/04/24 Survey sent for pricing. TS-24/04/24 Emailed client to advise of the rear door NWR. 28/05 SMS Neil amended survey, scanned through for pricing. our code isp......l |  | Yes |  |  | 6 | [10 empty] | 1 | [9 empty] | No |  | Brick | No Solvent - Blinds fixed to 6 windows | PG04(W) | 2024-06-18 | 2024-07-09 | Container |  | 2024-07-24 | 8am to 2pm |  |  | Eric |  | 04/07 SMS text sent for 15/07. 08/07 SMS left voicemail. CONFIRMED for 15/07. CNCELLED. Re-scheduled from Monday 15/07 to 24/07. CONFIRMED
4 |  | 59773 |  | BOOKED TO FIT |  | 74 | Heyford Way | Birmingham |  | B35 6HU | Bungalow | Miss A O'toole | 07787804787 |  | ange-71@hotmail.co.uk |  | Windows & Doors | P Beahan | 2024-04-09 | 11am to 3pm |  |  | TS-02/04/24 Text sent for 09/04/24. TS-02/04/24 Tenant CONFIRMED for 09/04/24. TS-15/04/24 Tenant called she wants to change the glass choice in the back door advised her to text her choice in. 23.05.24 SF attached photos to surveys, given to Darren to cleanse. |  |  |  |  | 10 | [10 empty] | 1 |  | 1 | [7 empty] | No |  | Brick |  | PG04(W) | 2024-06-18 | 2024-07-09 | Container |  | 16.07 & 17.07.24 | 8am to 2pm |  |  | Adrian |  | 2 day fit. 04/07 SMS text sent for 16 & 17th. CONFIRMED
3 |  | 59938 |  | RECALL REQUIRED |  | FLAT 10 | Northolt Drive | Birmingham |  | B35 6QX | Flat | Mr H Cadby | 07950 391 607 |  |  |  | Windows & Doors | S Burgess | 2024-04-17 | 8am to 12 noon |  |  | TS-04/04/24 Text sent for 17/04/24. TS08/04/24 Survey CONFIRMED for 17/04/24. TS-22/04/24 Survey and photos given to DA to cleanse. Tenant's own doors NWR. TS-24/04/24 Survey sent for pricing. TS-24/04/24 Emailed client to advise of both doors being NWR. 28/05 SMS Neil amended survey, scanned through for pricing. |  | Yes |  |  | 6 | [20 empty] | No |  | Brick | COPD No Solvent | PG04(W) | 2024-06-18 | 2024-07-09 | Container |  | 2024-07-16 | 8am to 2pm |  |  | Jim McDonald |  | 04/07 SMS text sent for 16/07. 08/07 SMS called N/A. 11/07 SMS called N/A Lttr sent. 11.07.24 SF Tenants partner Miss Burt from 3 Bicester Street called & CONFIRMED the 16.07.24 for the installation of the windows.16.07.24 SF Neil reported surveyor erro, remake full frame including glass for the bathroom window, delivery to Coleshill Depot on the 30.07.24,
4 |  | 55907 |  | BOOKED TO FIT |  | 39 | Heyford Way | Birmingham |  | B35 6HY | House | Mrs J Kilday | 0121 730 1217 | 07775 423 054 | jackiekilday@yahoo.co.uk |  | Windows & Doors | P Beahan | 2024-04-11 | 11am to 3pm |  |  | TS-02/04/24 Text sent for 11/04/24. TS-02/04/24 Tenant CONFIRMED for the 11/04/24. TS-12/04/24 Tenant emailed her door choice over she would like a Stratford in black with clear glass - furnture in Chrome. TS-26/04/24 Survey cleansed and sent for pricing. |  |  |  |  | 8 | [6 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 1 |  | No | Jammer System | Brick |  | PG05(W) | 2024-06-18 | 2024-07-11 | Container |  | 17/07/2024 & 18/07/2024 | 8am to 2pm |  |  | Eric |  | 1.5 day fit. 08/07 SMS text sent for 17 & 18. CONFIRMED
4 |  | 55910 |  | BOOKED TO FIT |  | 45 | Heyford Way | Birmingham |  | B35 6HZ | House | Mrs E Hales | 0121747 9889 | 07473 520346 - Daughter |  |  | Windows & Doors | P Beahan | 2024-04-15 | 8am to 12 noon |  |  | TS-08/04/24 Called tenant to book in for survey on the 15/04/24 CONFIRMED after 11am. TS-26/04/24 Survey cleansed and sent for pricing. |  |  |  |  | 8 | [6 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 1 |  | No | Jammer System | Brick | Asthma/heart condition No Solvents | PG05(W) | 2024-06-18 | 2024-07-11 | Container |  | 2024-07-17 | 8am to 2pm |  |  | Adrian |  | 08/07 SMS text sent for 17/07. CONFIRMED for 17/07. CONFIRMED. 15/07 SMS re-make glass unit 320 x 1,141
3 |  | 61164 |  | RECALL REQUIRED |  | 47 | Heyford Way | Birmingham |  | B35 6HZ | House | Mrs D M Phillips |  | 07511 960 048 |  |  | Windows & Doors | P Beahan | 2024-04-15 | 8am to 12 noon |  |  | TS-04/04/24 Text sent for 15/04/24. TS-04/04/24 Survey CONFIRMED for 15/04/24. TS-26/04/24 Survey cleansed and sent for pricing. |  |  |  |  | 9 | [10 empty] | 1 |  | 1 | [5 empty] | 1 |  | No | Jammer System | Brick |  | PG05(W) | 2024-06-18 | 2024-07-11 | Container |  | 16/07/2024 & 17/07/2024 | 8am to 2pm |  |  | Eric |  | 1.5 day fit. 08/07 SMS left voicemail with tenants daughter who is mobile contact. CONFIRMED. 18/07 SMS re-make 441 x 886 req deliv 30/07
4 |  | 64271 |  | BOOKED TO FIT |  | 93 | Heyford Way | Birmingham |  | B35 6JB | House | Miss J Leach | 01217482328 | 07359 032 693 |  |  | Windows & Doors | P Beahan | 2024-04-18 | 11am to 3pm |  |  | TS-04/04/24 Text sent for 15/04/24. TS-04/04/24 Survey CONFIRMED for 15/04/24. TS-26/04/24 Survey cleansed and sent for pricing. |  |  |  |  | 8 | [10 empty] | 1 |  | 1 | [5 empty] | 1 |  | No | Jammer System | Brick | Blinds fixed to 2 windows | PG05(W) | 2024-06-18 | 2024-07-11 | Container |  | 2024-07-18 | 8am to 2pm |  |  | Adrian |  | 10/07 SMS text sent for 18/07. CONFIRMED
4 |  | 64741 |  | BOOKED TO FIT |  | 101 | Heyford Way | Birmingham |  | B35 6JB | House | Miss N Campbell | 0121 748 3964 | 07306 617 934 |  |  | Windows & Doors | P Beahan | 2024-04-17 | 8am to 12 noon |  |  | TS-08/04/24 Called to offer survey for the 15/04/24 no answer or vm, ltr sent. TS-15/04/24 Tenant called as PB has not arrived yet, advised that he is not going as she hadn't confirmed the appointment, apologised and advised that we would rebook her - updated tracker with her mobile number. TS*26/04/24 Survey cleansed and sent for pricing. |  |  |  |  | 8 | [6 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 1 |  | No | Jammer System | Brick | Asthma No Solvents | PG05(W) | 2024-06-18 | 2024-07-11 | Container |  | 19/07/2024 & 22/07/2024 | 8am to 2pm |  |  | Eric |  | 1.5 day install. 10/07 text sent for 19th & 22nd. CONFIRMED
4 |  | 68663 |  | BOOKED TO FIT |  | 14 | Northolt Drive | Birmingham |  | B35 6QX | Flat | Mrs H Evans | 07472 266 832 |  | hayley_chamberlain@hotmail.co.uk |  | Windows & Doors | S Burgess | 2024-04-17 | 8am to 12 noon |  |  | TS-04/04/24 Text sent for 17/04/24. TS-09/04/24 Called tenant left vm, txt & ltr sent. TS-10/04/24 Survey CONFIRMED for 17/04/24. TS-15/04/24 Door choice emailed to tenant. TS-22/04/24 Survey and photos given to DA to cleanse. TS-24/04/24 Survey sent for pricing. 28/05 SMS Neil amended survey, scanned through for pricing. |  | Yes |  |  | 5 | [10 empty] | 1 |  | 1 | [5 empty] | 1 |  | No |  | Brick | Epileptic - No Solvent | PG04(W) | 2024-06-18 | 2024-07-09 | Container |  | 2024-07-22 | 8am to 2pm |  |  | Adrian |  | Scaffold Req. (Req Scaff Fri 19th) 09/07 SMS text for Scaff 19/7 and install 22/07. CONFIRMED
4 |  | 59943 |  | BOOKED TO FIT |  | 16 | Northolt Drive | Birmingham |  | B35 6QX | Flat | Mr J Leek | 07384 277 336 | 07548541014 | jonathanleek66@live.com |  | Windows & Doors | S Burgess | 2024-04-17 | 11am to 3pm |  |  | TS-04/04/24 Text sent for 17/04/24. Ts-09/04/24 Called left vm, text & ltr sent. TS-15/04/24 Door choice emailed to tenant. TS--22/04/24 Survey and photos given to DA to cleanse. No rear door NWR. TS-24/4/24 Survey sent for pricing. TS-24/04/24 Emailed client to advise of the rear door NWR. 28/05 SMS Neil amended survey, scanned through for pricing. |  | Yes |  |  | 6 | [10 empty] | 1 | [11 empty] | Brick |  | PG06(W) | 2024-06-18 | 2024-07-15 | Container |  | 2024-07-22 | 8am to 2pm |  |  | Adrian |  | 10/07 SMS text sent for 22/07. CONFIRMED
3 |  | 63198 |  | RECALL REQUIRED |  | 17 | Northolt Drive | Birmingham |  | B35 6QX | House | Mrs A O'regan | 07877 826 615 |  |  |  | Windows & Doors | S Burgess | 2024-04-17 | 11am to 3pm |  |  | TS-04/04/24 Text sent for 17/04/24. TS-09/04/24 Called tenant survey CONFIRMED for 17/04/24. TS-22/04/24 Survey and photos given to DA to cleanse. TS-24/04/24 Survey sent for pricing. 28/05 SMS Neil amended survey, scanned through for pricing. |  | Yes |  |  | 12 | [10 empty] | 1 |  | 2 | [5 empty] | 1 |  | No |  | Brick | Disabled property | PG06(W) | 2024-06-18 | 2024-07-15 | Container |  | 16/07/2024 & 17/07/2024 | 8am to 2pm |  |  | Jim McDonald |  | 1.5 day fit. 08/07 SMS text sent for 16 & 17. 16/07 SMS re-make 461 x 871 req deliv 23/07/24
4 |  | 70536 |  | BOOKED TO FIT |  | 21 | Northolt Drive | Birmingham |  | B35 6QX |  | Miss E McLean |  | 07764 707 718 | elliemaymclean@icloud.com |  | Windows & Doors | S Burgess | 2024-06-07 | 11am to 3pm |  |  | TS-04/04/24 Text sent for 19/04/24. TS-08/04/24 Date changed to 18/04/24 - text sent advising. TS-08/04/24 Tenant text back no, she needs May. 23.05.24 SF Sent text for 07.07 to survey.29/05 SMS called N/A. 30/05 SMS called N/A lttr sent. 04/06 SMS Dominie visited address and they confirmed for 07/0610/06 SMS surveyor reported NWR on Doors. 21/6/2024; AC sent for pricing. |  | Yes |  |  | 10 | [20 empty] | No |  | Brick | NO SOLVENT TO BE USED. | PG08(W) | 2024-06-28 | 2024-07-18 | Depot |  | 19/07/2024 & 23/07/2024 | 8am to 2pm |  |  | Eric |  | 11/07 text sent for 19th & 23rd. 15/07 SMS left voicemail.
4 |  | 70003 |  | BOOKED TO FIT |  | 26 | Northolt Drive | Birmingham |  | B35 6QX | Flat | Miss M O'Loughlin | 07736 941 862 | 07710651416 | Megz_christina@hotmail.com |  | Windows & Doors | S Burgess | 2024-04-23 | 8am to 12 noon |  |  | TS-12/04/24 Text sent for 23/04/24. TS-17/04/24 Called tenant survey CONFIRMED for 23/04/24. TS-30/04/24 Survey received and given to DA to cleanse. Front door & Lounge combi NWR.28/05 SMS Neil amended survey, scanned through for pricing. |  | Yes |  |  | 6 | [22 empty] | Brick | No Solvent - Access flat below garden 28. | PG07(W) | 2024-06-18 | 2024-07-16 | Container |  | 2024-08-09 | 8am to 2pm |  |  | Jim McDonald |  | 10/07 SMS text sent for 18/07. CONFIRMED. 15/07 SMS TLO cancelled as no fitter available, re-scheduled to 09/08/2024
5 |  | 66205 |  | DELIVERED TO DEPOT/CONTAINER | SEE COMMENTS | 77 | Blenheim Way | Birmingham |  | B35 7JF | House | VOID PROPERTY |  |  |  |  | Windows & Doors | D Ansell | 2024-04-20 | 8am to 2pm |  |  | 05.07.24 SF (No information originally put on the tracker) Darren attended the property and completed the survey. Cleansed, priced, approved, called off |  |  |  |  | 5 | [10 empty] | 1 |  | 1 | [7 empty] | No |  | Brick | Void Property contact Leonie Hammond for access, some clutter, internal access issues, soffits abutting head or window or door? Fire damage property | PG01(W) | 2024-04-03 | 2024-04-17 | Container | [7 empty] | Void Property contact Leonie Hammond for access, some clutter, internal access issues, soffits abutting head or window or door? Fire damage property. 12/07 SMS emailed Leionie to req access on 31/07, awaiting reply. On hold until client advises is available.
4 |  | 59939 |  | BOOKED TO FIT |  | 11 | Northolt Drive | Birmingham |  | B35 6QX | House | Miss T Scrivens | 07307 000 453 |  |  |  | Windows & Doors | S Burgess | 2024-04-17 | 8am to 12 noon |  |  | TS-04/04/24 Text sent for 17/04/24. TS-0404/24 Survey CONFIRMED for 17/04/24. TS-22/04/24 Survey and photos given to DA to cleanse. Rear door is NWR. TS-24/04/24 Survey sent for pricing. TS-24/04/24 Emailed client to advise of the rear door NWR. 28/05 SMS Neil amended survey, scanned through for pricing.- the replye bewooen |  | Yes |  |  | 10 | [10 empty] | 1 | [9 empty] | No |  | Brick |  | PG04(W) | 2024-06-18 | 2024-07-09 | Container |  | 25/07/2024 & 26/07/2024 | 8am to 2pm |  |  | Eric |  | DA advised no Scaffold Req. 12/07 SMS text sent for 25 & 26 July. 15/07 SMS called no NIS Lttr sent
4 |  | 70121 |  | BOOKED TO FIT |  | 18 | Northolt Drive | Birmingham |  | B35 6QX | Flat | Mr C Lee | 07572 168 119 |  | cameronlee03@live.co.uk |  | Windows & Doors | S Burgess | 2024-04-18 | 8am to 12 noon |  |  | TS-04/04/24 Text sent for 19/04/24. TS-04/04/24 Survey CONFIRMED for 19/04/24. TS-08/04/24 Date changed to 18/04/24 - text sent advising. TS-09/04/24 Called left vm txt & ltr sent. TS-11/04/24 Survey CONFIRMED for 18/04/24. TS-15/04/24 Door choice emailed to Tenant. TS-22/04/24 Survey and photos given to DA to cleanse. TS-26/24/24 Survey cleansed sent for pricing.28/05 SMS Neil amended survey, scanned through for pricing. |  | Yes |  |  | 9 | [10 empty] | 1 |  | 2 | [7 empty] | No | Independent Scaffold | Brick | SCAFFOLD - F/bed pitch roof - 1st floor flat - access via Flat 20 for 1st Floor windows. | PG06(W) | 2024-06-18 | 2024-07-15 | Container |  | 2024-07-24 | 8am to 2pm |  |  | Adrian |  | Scaffold quoted . SCAFFOLD REQUIRED. 12/07 SMS text for 24/07. CONFIRMED
4 |  | 63463 |  | BOOKED TO FIT |  | 22 | Northolt Drive | Birmingham |  | B35 6QX | Flat | Miss S Sterling | 07507 642 265 |  | sabrinasterling83@gmail.com |  | Windows & Doors | S Burgess | 2024-04-18 | 8am to 12 noon |  |  | TS-04/04/24 Text sent for 19/04/24. TS-08/04/24 Date changed to 18/04/24 - text sent advising. TS-08/04/24 Survey CONFIRMED for 18/04/24. TS-15/04/24 Door choice emailed to tenant. TS-22/04/24 Survey and photos given to DA to cleanse. TS-26/04/24 Survey cleansed sent for pricing.28/05 SMS Neil amended survey, scanned through for pricing. |  | Yes |  |  | 9 | [10 empty] | 1 |  | 2 | [7 empty] | No | Independent Scaffold | Brick | SCAFFOLD - Ded/cupboard pitch roof. Access via flat 24 to 1st floor | PG06(W) | 2024-06-18 | 2024-07-15 | Container |  | 2024-07-25 | 8am to 2pm |  |  | Adrian |  | Scaffold req 23/07 COPY DOM IN. Ded/cupboard pitch roof. Access via flat 24 to 1st floor (18 & 22 need doing together due to Scaffolding) 12/07 SMS text for 25/07. CONFIRMED
4 |  | 59950 |  | BOOKED TO FIT |  | 25 | Northolt Drive | Birmingham |  | B35 6QX | Flat | Mrs B Wardell |  | 07384 626 802 |  |  | Windows & Doors | S Burgess | 2024-04-18 | 11am to 3pm |  |  | TS-04/04/24 Text sent for 19/04/24. TS-04/04/24 Survey CONFIRMED for 19/04/24. TS-08/04/24 Date changed to 18/04/24 - text sent advising. TS-08/04/24 Tenant CONFIRMED for 18/04/24. TS-22/04/24 Survey and photos given to DA to cleanse. TS-26/04/24 Survey cleansed and sent for pricing. 28/05 SMS Neil amended survey, scanned through for pricing. |  | Yes |  |  | 6 | [10 empty] | 1 |  | 1 | [7 empty] | No |  | Brick | No Solvent - Grd floor flat | PG07(W) | 2024-06-18 | 2024-07-16 | Container |  | 2024-07-22 | 8am to 2pm |  |  | Jim McDonald |  | DA advised no scaff req. 12/07 SMS text sent for 22/07. CONFIRMED
4 |  | 70500 |  | BOOKED TO FIT |  | FLAT 5 | Northolt Drive | Birmingham |  | B35 6QX | Flat | Miss A Holder | 07404 868 654 | 07424 790 036 | mandiejh1973@gmail.com |  | Windows & Doors | S Burgess | 2024-04-16 | 8am to 12 noon |  |  | TS-04/04/24 Text sent for 16/04/24. TS-04/04/24 Tenant called survey is CONFIRMED for 16/04/24. TS-15/04/24 Door choice emailed to tenant. TS-22/04/24 Survey and photos given to DA to cleanse. TS-29/04/24 Survey cleansed and sent for pricing. 28/05 SMS Neil amended survey, scanned through for pricing. |  | Yes |  |  | 5 | [12 empty] | 1 | [5 empty] | 1 |  | No | Independent Scaffold | Brick | SCAFFOLD required under flat 7. Acess via 9 Northolt & 2 Mere Avenue | PG07(W) | 2024-06-18 | 2024-07-16 | Container |  | 2024-07-24 | 8am to 2pm |  |  | Jim McDonald |  | SCAFFOLD Ordered Mon 22/07 COPY DOM IN required under flat 7. Acess via 9 Northolt & 2 Mere Avenue (Flat 5 & 7 are under same Scaffold quote so need to be done together)12/07 SMS text tenant for Scaff on 22/07 & install 24/07. 15/07 SMS left voicemail. 16.07.24 SF Tenant called and CONFIRMED he'll be home on the 22.07.24 for the scaffold to be erected and CONFIRMED the 24.07.24 for the installation.
4 |  | 61640 |  | BOOKED TO FIT |  | FLAT 7 | Northolt Drive | Birmingham |  | B35 6QX | Flat | Mrs Adobor | 07947 625 350 |  | evelyn_mens@yahoo.com |  | Windows & Doors | S Burgess | 2024-04-16 | 11am to 3pm |  |  | TS-04/04/24 Text sent for 16/04/24. TS-08/04/24 Called left vm, txt & ltr sent. TS-11/04/24 Survey CONFIRMED for 16/04/24. TS-15/04/24 Door choice emailed to Tenant. TS-22/04/24 Survey and photos given to DA to cleanse. TS-29/04/24 Survey cleasnsed sent for pricing. 28/05 SMS Neil amended survey, scanned through for pricing. |  | Yes |  |  | 5 | [12 empty] | 1 | [5 empty] | 1 |  | No | Independent Scaffold | Brick | SCAFFOLD REQUIRED. Acess via 9 Northolt & 2 Mere Avenue | PG07(W) | 2024-06-18 | 2024-07-16 | Container |  | 2024-07-23 | 8am to 2pm |  |  | Jim McDonald |  | SCAFFOLD Ordered Mon 22/07 COPY DOM IN. Acess via 9 Northolt & 2 Mere Avenue. (Flat 5 & 7 are under same Scaffold quote so need to be done together) 12/07 SMS text tenant for Scaff on 22/07 & install 23/07. CONFIRMED
4 |  | 65978 |  | BOOKED TO FIT |  | 12 | Northolt Drive | Birmingham |  | B35 6QX | House | Miss J Flanagan | 07972 262 8256 | 07972 262850 | flanners07@hotmail.co.uk |  | Windows & Doors | S Burgess | 2024-04-17 | 8am to 12 noon |  |  | TS-04/04/24 Text sent for 17/04/24. TS-04/04/24 Survey CONFIRMED for 17/04/24. TS-15/04/24 Door choice emailed to tenant. TS-22/04/24 Survey and photos given to DA to cleanse. TS-24/04/24 Survey sent for pricing. |  | Yes |  |  | 10 | [10 empty] | 1 |  | 1 | [7 empty] | No |  | Brick |  | PG04(W) | 2024-06-18 | 2024-07-09 | Container |  | 29/07/2024 & 30/07/2024 | 8am to 2pm |  |  | Jim McDonald |  | DA advised no Scaffold Req. 17/07 SMS text for 29/07 & 30/07
4 |  | 59942 |  | BOOKED TO FIT |  | 15 | Northolt Drive | Birmingham |  | B35 6QX | House | Mrs S Cattell | 07498 590 107 |  |  |  | Windows & Doors | S Burgess | 2024-04-17 | 11am to 3pm |  |  | TS-04/04/24 Text sent for 17/04/24. TS-09/04/24 Called tenant no ans/vm text & ltr sent. TS-09/04/24 Survey CONFIRMED for 17/04/24. TS-22/04/24 Survey and photos given to DA to cleanse. TS-24/04/24 Survey sent for pricing. TS-30/04/24 Client confirmed that the Front Door is to be replaced. 28/05 SMS Neil amended survey, scanned through for pricing. |  | Yes |  |  | 10 | [10 empty] | 1 |  | 1 | [7 empty] | No |  | Brick |  | PG06(W) | 2024-06-18 | 2024-07-15 | Container |  | 29/07/2024 & 30/07/2024 | 8am to 2pm |  |  | Eric |  | DA advised no Scaffold Req. 17/07 SMS text for 29/07 & 30/07. CONFIRMED
4 |  | 60446 |  | BOOKED TO FIT |  | 23 | Northolt Drive | Birmingham |  | B35 6QX | House | Miss C Ansell |  | 07542 011 929 | clara_bell@hotmail.co.uk |  | Windows & Doors | S Burgess | 2024-04-24 | 8am to 12 noon |  |  | TS-04/04/24 Text sent for 19/04/24. TS-04/04/24 Tenant txt back no, text tenant asking for days that are better. TS-15/04/24 Text sent for 24/04/24. TS-15/04/24 Survey CONFIRMED for 24/04/24. TS-30/04/24 Survey received and passed to DA to cleanse.28/05 SMS Neil amended survey, scanned through for pricing. |  | Yes |  |  | 10 | [10 empty] | 1 |  | 1 | [9 empty] | Brick | tenant has birds, & 2 dogs - NEEDS PLENTY OF NOTICE | PG07(W) | 2024-06-18 | 2024-07-16 | Container |  | 31/07/2024& 01/08/2024 | 8am to 2pm |  |  | Jim McDonald |  | DA advised no scaff req. 17/07 SMS text sent for 31/07 & 01/08
4 |  | 68742 |  | BOOKED TO FIT |  | 24 | Northolt Drive | Birmingham |  | B35 6QX | Flat | Mr D Holmes | 01213111804 | 07534 737 626 |  |  | Windows & Doors | S Burgess | 2024-04-18 | 11am to 3pm |  |  | TS-04/04/24 Text sent for 19/04/24. TS-04/04/24 Survey CONFIRMED for 19/04/24. TS-08/04/24 Date changed to 18/04/24 - text sent advising. TS-08/04/24 Survey CONFIRMED for 18/04/24. TS-22/04/24 Survey and photos given to DA to cleanse. Front door NWR. TS-26/04/24 Survey cleansed sent for pricing. 28/05 SMS Neil amended survey, scanned through for pricing. |  | Yes |  |  | 4 | [12 empty] | 1 | [7 empty] | No |  | Brick | Grd floor flat | PG06(W) | 2024-06-18 | 2024-07-15 | Container |  | 2024-07-26 | 8am to 2pm |  |  | Eric |  | 17/07 SMS text for 26/07
4 |  | 70247 |  | BOOKED TO FIT |  | 28 | Northolt Drive | Birmingham |  | B35 6QX | Flat | Miss C Butlin |  | 07508 400 061 | clairapeterButlin17@gmail.com |  | Windows & Doors | S Burgess | 2024-04-23 | 8am to 12 noon |  |  | TS-12/04/24 Text sent for 23/04/24. TS-15/04/24 Survey CONFIRMED for 23/04/24. TS-30/04/24 Survey received and passed to DA to cleanse. Rear door NWR.28/05 SMS Neil amended survey, scanned through for pricing. |  | Yes |  |  | 5 | [10 empty] | 1 | [11 empty] | Brick |  | PG07(W) | 2024-06-18 | 2024-07-16 | Container |  | 2024-07-26 | 8am to 2pm |  |  | Jim McDonald |  | 17/07 SMS text for 26/07
5 |  | 64853 |  | DELIVERED TO DEPOT/CONTAINER |  | 19 | Northolt Drive | Birmingham |  | B35 6QX | House | Miss H O'Coy | 07462 777 770 |  | hailz_ocoy@yahoo.com |  | Windows & Doors | S Burgess | 2024-04-18 | 8am to 12 noon |  |  | TS-04/04/24 Text sent for 19/04/24. TS-04/04/24 Survey CONFIRMED for 19/04/24. TS-08/04/24 Date changed to 18/04/24 - text sent advising. TS-08/04/24 Survey CONFIRMED for 18/04/24. TS-15/04/24 Door choice emailed to tenant. TS-22/04/24 Survey and photos given to DA to cleanse. TS-26/04/24 Survey cleansed and sent for pricing.28/05 SMS Neil amended survey, scanned through for pricing. |  | Yes |  |  | 12 | [10 empty] | 1 |  | 1 | [7 empty] | No |  | Brick | Blinds fitted to 11 windows | PG06(W) | 2024-06-18 | 2024-07-15 | Container | [7 empty] | 1.5 day fit. 08/07 SMS text sent for 17 & 18. 11/07 SMS called N/A lttr sent. CONFIRMED. 17/07 SMS tenant cancelled
5 |  | 59780 |  | DELIVERED TO DEPOT/CONTAINER |  | 82 | Heyford Way | Birmingham |  | B35 6HU | Terrace | Miss N Clarke | 0121 747 9892 | 07530 588 432 |  |  | Windows & Doors | P Beahan | 2024-04-10 | 8am to 12 noon |  |  | TS-02/04/24 Text sent for 10/04/24. TS-02/04/24 Tenant CONFIRMED for 10/04/24. |  |  |  |  | 11 | [10 empty] | 1 |  | 1 | [7 empty] | No |  | Brick | No Solvents, Door Jammer | PG04(W) | 2024-06-18 | 2024-07-09 | Container | [7 empty] | No Solvents, Door Jammer. 1st day of 1.5 day fit. 04/07 SMS text sent for 16 & 17. 08/07 SMS spoke to tenant on phone who declined these dates due to a riverboat cruise
5 |  | 69698 |  | DELIVERED TO DEPOT/CONTAINER | POST 2000 | 66 | Javelin Avenue | Birmingham |  | B35 7LW | Bungalow | Mrs A Rogers | 07776 286 239 |  | zeb_A_Dee@hotmail.com |  | Windows & Doors | M Turpin | 2024-04-25 | 8am to 2pm |  |  | TS-15/04/24 Text sent for 25/04/24. TS-15/04/24 Survey CONFIRMED for 25/04/24. TS-26/04/24 Survey received waiting for photos. TS-30/04/24 Photos received passed to DA to cleanse. TS-01/05/24 Survey cleansed and sent for pricing. Post 2000 no asbestos report needed. |  |  |  |  | 11 | [10 empty] | 1 |  | 1 | [5 empty] | 1 |  | No |  | Brick |  | PG02(W) | 2024-06-10 | 2024-07-04 | Container | [5 empty] | Jim McDonald |  | 3 Day fit. 02/07 SMS text sent for 10,11 &12th July. 03/07 SMS called and spoke to tenant who declined these dates, is on holiday until 5th August. 05/07 SMS re-make glass unit 240 x 1305 req deliv 11/07
4 |  | 60440 |  | BOOKED TO FIT |  | FLAT 1 | Northolt Drive | Birmingham |  | B35 6QX |  | Mr M Brookes |  | 07984 225 726 |  |  | Windows & Doors | S Burgess | 2024-06-07 | 8am to 12 noon |  | 1 | TS-04/04/24 Text sent for 16/04/24. TS-08/04/24 Called tenant left vm, txt & ltr sent for 16/04/24. TS-17/04/24 No access for 16/04/24, carded @ 8.40am - sent to client. 23.05.24 SF Sent text for 07.07 to survey. 23.05.24 SF Sent text for 07.07. 29/05 SMS called N/A. 30/05 SMS called N/A lttr sent. 21/6/2024; AC sent for pricing. |  | Yes |  |  | 5 | [5 empty] | 2 | [14 empty] | No | Independent Scaffold | Brick | Acess via 9 Northolt & 2 Mere Avenue. NO SOLVENT CLEANER ALLOWED. SCAFFOLD. | PG08(W) | 2024-06-18 | 2024-07-18 | Depot |  | 2024-07-30 | 8am to 2pm |  |  | Jim McDonald |  | Acess via 9 Northolt & 2 Mere Avenue. NO SOLVENT CLEANER ALLOWED. SCAFFOLD quote BSL 12/07-3
4 |  | 68709 |  | BOOKED TO FIT |  | FLAT 27 | Northolt Drive | Birmingham |  | B35 6QX |  | Miss Q Mapp |  | 07903 811 842 | queshia-teann.mapp@hotmail.co.uk |  | Windows & Doors | S Burgess | 2024-06-07 | 11am to 3pm |  |  | TS-12/04/24 Text sent for 23/04/24. TS-15/04/24 Tenant text back declining the 23/04/24 and asking for 25/04/24 SB is not in the area that day replied back to the tenant advising this and said that we would be back in touch when we have a new date. 23.05.24 SF Sent text for 07.07 to survey. |  | Yes |  |  | 5 | [5 empty] | 2 | [14 empty] | No | Independent Scaffold | Brick | Acess via 18 Mere Avenue & 25 Northolt Drive. SCAFFOLD. | PG08(W) | 2024-06-18 | 2024-07-18 | Depot |  | 2024-08-02 | 8am to 2pm |  |  | Jim McDonald |  | Acess via 18 Mere Avenue & 25 Northolt Drive. SCAFFOLD. Quote BSL 12/07-5. Scaff req 29/07. 17/07 SMS text sent for 02/08. CONFIRMED
4 |  | 62545 |  | BOOKED TO FIT |  | FLAT 29 | Northolt Drive | Birmingham |  | B35 6QX | Flat | Mr D Kelleher |  | 07543 339 344 | dkelleher26@gmail.com |  | Windows & Doors | S Burgess | 2024-04-23 | 11am to 3pm |  |  | TS-12/04/24 Text sent for 23/04/24. TS-15/04/24 Tenant text back No - replied asking what days would be better. TS-15/04/24 Tenant advised that the afternoons would be better, text back offering the same day but the afternoon. TS-17/04/24 Survey CONFIRMED for 17/04/24 (PM). TS-30/04/24 Survey received and passed to DA to cleanse. Lounge combi NWR. 28/05 SMS Neil amended survey, scanned through for pricing. 21/6/2024 AC sent for pricing. |  | Yes |  |  | 3 | [5 empty] | 1 | [12 empty] | 1 |  | No | Independent Scaffold | Brick | COPD No Solvent - Acess via 18 Mere Avenue & 25 Northolt Drive. SCAFFOLD. | PG08(W) | 2024-06-18 | 2024-07-18 | Depot |  | 2024-08-08 | 8am to 2pm |  |  | Jim McDonald |  | COPD No Solvent - Acess via 18 Mere Avenue & 25 Northolt Drive. SCAFFOLD quote BSL 12/07-6. SCAFFOLD REQ 29/07. 17/07 SMS text sent for 01/08. Tenant declined 01/08 as away until 07/08 so text for 08/08. CONFIRMED
4 |  | 59932 |  | BOOKED TO FIT |  | FLAT 3 | Northolt Drive | Birmingham |  | B35 6QX | Flat | Mr P Mulholland |  | 07756 059 115 |  |  | Windows & Doors | S Burgess | 2024-04-16 | 8am to 12 noon |  |  | TS-04/04/24 Text sent for 16/04/24. TS-08/04/24 Called tenant survey CONFIRMED for 16/04/24. TS-22/04/24 Survey and photos given to DA to cleanse. TS-29/04/24 Survey cleansed sent for pricing. 28/05 SMS Neil amended survey, scanned through for pricing. 21/6/2024; AC sent for pricing. |  | Yes |  |  | 3 | [5 empty] | 1 | [14 empty] | No | Independent Scaffold | Brick | SCAFFOLD - Bath/lounge combi pitch roof. Acess to rear through flat 469 Yatesbury Avenue. Acess via 9 Northolt & 2 Mere Avenue | PG08(W) | 2024-06-18 | 2024-07-18 | Depot |  | 2024-07-30 | 8am to 2pm |  |  | Eric |  | SCAFFOLD - Bath/lounge combi pitch roof. Acess to rear through flat 469 Yatesbury Avenue. Acess via 9 Northolt & 2 Mere Avenue. Scaffold quote BSL 12/07-4. CONFIRMED
4 |  | 65010 |  | BOOKED TO FIT |  | FLAT 34 | Northolt Drive | Birmingham |  | B35 6QX | Flat | Miss S Southcombe | 07773 354453 | 07368 455 874 | southylee@yahoo.co.uk |  | Windows & Doors | S Burgess | 2024-04-24 | 8am to 12 noon |  |  | TS-15/04/24 Text sent for 24/04/24. TS-18/04/24 Called left vm, text & ltr sent. TS-30/04/24 Survey received and passed to DA to cleanse.28/05 SMS Neil amended survey, scanned through for pricing. 21/6/2024 AC sent for pricing. |  | Yes |  |  | 4 | [5 empty] | 2 | [12 empty] | 1 |  | No | Independent Scaffold | Brick | SCAFFOLD - Lounge balcony - Access via 32 Northolt Drive & 20 Mere Avenue. *Tenant will need RLO support during fitting. NO SOLVENT TO BE USED. | PG08(W) | 2024-06-18 | 2024-07-18 | Depot |  | 2024-08-02 | 8am to 2pm |  |  | Jim McDonald |  | SCAFFOLD quote BSL 12/07-7 - Lounge balcony - Access via 32 Northolt Drive & 20 Mere Avenue. *Tenant will need RLO support during fitting. NO SOLVENT TO BE USED. Scaff req 29/07. 17/07 SMS text sent for 02/08
6 |  | 59963 |  | CALLED OFF |  | FLAT 38 | Northolt Drive | Birmingham |  | B35 6QX |  | Mr B Boyle |  | 07719 866 234 |  |  | Windows & Doors | S Burgess | 2024-04-24 | 8am to 12 noon |  |  | TS-15/04/24 Text sent for 24/04/24. TS-17/04/24 Survey CONFIRMED for 24/04/24. TS-30/04/24 Survey received and passed to DA to cleanse. 28/05 SMS Neil amended survey, scanned through for pricing. 21/6/2024 AC sent for re-pricing. |  | Yes |  |  | 6 | [5 empty] | 1 | [14 empty] | No |  | Brick | Tenant has epilepsy. Access via 32 Northolt Drive & 20 Mere Avenue. SCAFFOLD. | PG08(W) | 2024-06-18 | 2024-07-18 | Depot | [7 empty] | Flat 38 & 40 need Scaff & install together
4 |  | 67959 |  | BOOKED TO FIT |  | FLAT 4 | Northolt Drive | Birmingham |  | B35 6QX | Flat | Miss O Shahbazi |  | 07463 894 102 | n.shahbazi82@yahoo.com |  | Windows & Doors | S Burgess | 2024-04-16 | 8am to 12 noon |  |  | TS-04/04/24 Text sent for 16/04/24. TS-0804/24 Called tenant survey is CONFIRMED for 16/04/24. TS-15/04/24 Door choice emailed to client. TS-22/04/24 Survey and photos givent to DA to cleanse. TS-29/04/24 Survey cleansed sent for pricing. 28/05 SMS Neil amended survey, scanned through for pricing. |  | Yes |  |  | 4 | [12 empty] | 2 | [5 empty] | 1 |  | No | Independent Scaffold | Brick | SCAFFOLD - bath/lounge combi - NO SOLVENT - 1st floor - Acess to rear through 471 Yatesbury Avenue. Access via 10 Northolt & 471 Yatesbury Avenue | PG07(W) | 2024-06-18 | 2024-07-16 | Container |  | 2024-08-01 | 8am to 2pm |  |  | Eric |  | SCAFFOLD REQ 29/07. Ref :- BSL 12/07-2 (same as no. Flat 4 & 6 as need to be done together)1st floor - Acess to rear through 471 Yatesbury Avenue. Access via 10 Northolt & 471 Yatesbury Avenue. 17/07 SMS text sent for 01/08
4 |  | 60441 |  | BOOKED TO FIT |  | FLAT 6 | Northolt Drive | Birmingham |  | B35 6QX | Flat | Mr T Gould | 07835 472 041 |  |  |  | Windows & Doors | S Burgess | 2024-04-16 | 11am to 3pm |  |  | TS-04/04/24 Text sent for 16/04/24. TS-05/04/24 Survey CONFIRMED for 16/04/24. TS-22/04/24 Survey and photos given to DA to cleanse. TS-29/024/24 Survey received and sent for pricing. 28/05 SMS Neil amended survey, scanned through for pricing. |  | Yes |  |  | 4 | [12 empty] | 2 | [5 empty] | 1 |  | No | Independent Scaffold | Brick | SCAFFOLD -Bath/lounge pitch roof/flat roof - NO SOLVENT COPD - Access to rear through flat 10. Tenant has lung & stomach cancer is happy to proceed - FITTERS DO NOT ATTEND IF YOU HAVE ANY BUGS. Access via 10 Northolt & 471 Yatesbury Avenue | PG07(W) | 2024-06-18 | 2024-07-16 | Container |  | 2024-08-01 | 8am to 2pm |  |  | Jim McDonald |  | SCAFFOLD REQ 29/07. Ref :- BSL 12/07-2 (same as no. Flat 4 & 6 as need to be done together)NO SOLVENT COPD - Access to rear through flat 10. Tenant has lung & stomach cancer is happy to proceed - FITTERS DO NOT ATTEND IF YOU HAVE ANY BUGS. Access via 10 Northolt & 471 Yatesbury Avenue. 17/07 SMS text sent for 01/08. CONFIRMED
6 |  | 60111 |  | CALLED OFF |  | 130 | Watton Green | Birmingham |  | B35 7JT |  | Miss B Bonner | 07818650367 | 0121 574 2835 |  |  | Windows & Doors | M Turpin | 2024-05-24 | 8am to 2pm |  |  | 13/05 SMS text sent for 24/05. 15/05 SMS mob no NIS landlane N/A. 16/05 SMS lttr sent. 24.05.24 SF CANCELLED via phone, LM, no answer, sent text. 24.05.24 SF Martin Turpin did actually attend, his van probably got fixed quicker than he thought, he attended the proper and surveyed the doors & windows. 20/6/2024; AC sent to pricing. 11.07.24 SF Handed to Darren to check the Asbestos Reports before we can "call off". 10.07.27 SF Eleanor advised this has been approved. 11.07.24 SF Handed to Darren to check the Asbestos Reports before we can "call off". |  |  |  |  | 11 | [10 empty] | 1 |  | 1 | [11 empty] | PG10(W) | 2024-07-12 | 2024-08-02 | Container
6 |  | 65736 |  | CALLED OFF |  | 140 | Watton Green | Birmingham |  | B35 7JT |  | Mrs L Round | 07368 589 897 | 0121 572-0644 | lainey-01@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-05-24 | 8am to 2pm |  |  | 13/05 SMS text sent for 24/05. CONFIRMED for 24/05. 24.05.24 SF CANCELLED via phone, LM and sent text. 24.05.24 SF Martin Turpin did actually attend, his van probably got fixed quicker than he thought, he attended the proper and surveyed the doors & windows. 20/6/2024; AC sent to pricing. 11.07.24 SF Handed to Darren to check the Asbestos Reports before we can "call off". 10.07.27 SF Eleanor advised this has been approved. 11.07.24 SF Handed to Darren to check the Asbestos Reports before we can "call off". |  |  |  |  | 11 | [10 empty] | 1 |  | 1 | [11 empty] | PG10(W) | 2024-07-12 | 2024-08-02 | Container
6 |  | 60117 |  | CALLED OFF |  | 142 | Watton Green | Birmingham |  | B35 7JT |  | Miss G Powell |  | 07496 569 312 | spiderladyuk07@hotmail.com OR gaynapowell@outlook.com |  | Windows & Doors | M Turpin | 2024-05-24 | 8am to 2pm |  |  | 13/05 SMS text sent for 24/05. 15/05 SMS called N/A. 16/05 SMS lttr sent. 24.05.24 SF CANCELLED via phone, LM and sent text. 24.05.24 SF Martin Turpin did actually attend, his van probably got fixed quicker than he thought, he attended the proper and surveyed the doors & windows. 20/6/2024; AC sent to pricing. 11.07.24 SF Handed to Darren to check the Asbestos Reports before we can "call off". 10.07.27 SF Eleanor advised this has been approved. 11.07.24 SF Handed to Darren to check the Asbestos Reports before we can "call off". |  |  |  |  | 11 | [10 empty] | 1 |  | 1 | [11 empty] | PG10(W) | 2024-07-12 | 2024-08-02 | Container
6 |  | 64789 |  | CALLED OFF | SEE COMMENTS | 10 | Baginton Road | Birmingham |  | B35 6HN | House | Mrs S Mobbs | 01217491274 | 07521 031 740 | moobssally@yahoo.co.uk |  | Windows & Doors | S Burgess | 2024-04-10 | 8am to 12 noon |  |  | TS-02/04/24 Text sent for 10/04/24. TS-02/04/24 Tenant CONFIRMED for 10/04/24. TS-22/04/24 Survey and photos received passed to DA to cleanse. TS-24/04/24 Survey sent for pricing. 28/05 SMS put in query box as not stamped to say cleansed. 10.07.27 SF Eleanor advised this has been approved. 11.07.24 SF Handed to Darren to check the Asbestos Reports before we can "call off". |  |  |  |  | 11 | [10 empty] | 1 |  | 1 | [5 empty] | 1 |  | No |  | Brick | No Solvent - Blinds fitted to 2 x kitchen windows | PG09(W) | 2024-07-11 | 2024-08-01 | Depot |  | After 9th Aug | [5 empty] | TLO - 10 Bagington, tenant is lady who has multiple health issues as well as brittle bones, the property has a lot of ‘stuff’ in two of the bedrooms which will make this hard for fitters. After speaking to Darren, I am happy to support this tenant, move the stuff for her, and stay present whilst fitting is taking place., I will make housing officer aware but if we could update to tracker to ensure I am present for fitting that would be great. (see attached image 3 and 4). No Solvent Blinds fitted to 2 x kitchen windows. (Schedule after 10th August...tenant on hols & copy TLO in)
6 |  | 63170 |  | CALLED OFF |  | 38 | Baginton Road | Birmingham |  | B35 6JE | House | Miss S Blackburn | 07958642315 | 07865 349 608 |  |  | Windows & Doors | S Burgess | 2024-04-10 | 8am to 12 noon |  |  | TS-02/04/24 Text sent for 10/04/24. TS-03/04/24 Called left vm, text and letter sent for 10/04/24. TS-22/04/24 Survey and photos given to DA. Front Door NWR. TS-24/04/24 Survey sent for pricing. TS-24/04/24 Emailed client to advise of the front door NWR. 28/05 SMS put in query box as not stamped to say cleansed. 10.07.27 SF Eleanor advised this has been approved. 11.07.24 SF Handed to Darren to check the Asbestos Reports before we can "call off". |  |  |  |  | 12 | [12 empty] | 1 | [7 empty] | No |  | Brick | Son has ADHA & Autism - No Sovlent | PG09(W) | 2024-07-11 | 2024-08-01 | Depot | [7 empty] | Son has ADHA & Autism - No Sovlent
6 |  | 60675 |  | CALLED OFF |  | 40 | Baginton Road | Birmingham |  | B35 6JE | House | Mr N S Mustafa | 01217497673 | 07305 545 492 |  |  | Windows & Doors | S Burgess | 2024-04-10 | 8am to 12 noon |  |  | TS-02/04/24 Text sent for 10/04/24. TS-03/04/24 Called no vm on mobile and landline nis, text and letter sent. TS-09/04/24 Survey CONFIRMED for 10/4/24 - tenant's friend called to cancel asking for next Monday or Tuesday advised that the diary has already been booked and we are not in the area, they decided to keep the appointment. TS-22/04/24 Survey and photos given to DA to cleanse. Back door is NWR. TS-24/04/24 Survey sent for pricing. TS-24/04/24 Emailed client to advise of the rear door NWR. 28/05 SMS put in query box as not stamped to say cleansed. 10.07.27 SF Eleanor advised this has been approved. 11.07.24 SF Handed to Darren to check the Asbestos Reports before we can "call off". |  |  |  |  | 10 | [10 empty] | 1 | [7 empty] | 1 |  | No |  | Brick |  | PG09(W) | 2024-07-11 | 2024-08-01 | Depot
6 |  | 67567 |  | CALLED OFF |  | 31 | Baginton Road | Birmingham |  | B35 6JS | Bungalow | Mrs M Cullen | 0121 747 7986 | 07971715764 |  |  | Windows & Doors | S Burgess | 2024-04-09 | 8am to 12 noon |  |  | TS-02/04/24 Text sent for 09/04/24. TS-03/04/24 Called tenant survey CONFIRMED for 09/04/24. TS-22/04/24 Survey and photos received and passed to DA to cleanse. Front door NWR. TS-24/04/24 Survey sent for pricing. TS-24/04/24 Emailed client to advise of the front door NWR. 10.07.27 SF Eleanor advised this has been approved. 11.07.24 SF Handed to Darren to check the Asbestos Reports before we can "call off". |  |  |  |  | 5 | [12 empty] | 1 | [7 empty] | No |  | Brick | Blinds fixed to front bedroom window | PG09(W) | 2024-07-11 | 2024-08-01 | Depot
4 |  | 69030 |  | BOOKED TO FIT |  | 35 | Baginton Road | Birmingham |  | B35 6JS | Bungalow | Miss L P Tye | 07985 376 516 |  |  |  | Windows & Doors | S Burgess | 2024-04-09 | 11am to 3pm |  |  | TS-02/04/24 Text sent for 09/04/24. TS-03/04/24 Called no answer/vm txt & ltr sent. TS-04/04/24 Survey CONFIRMED for 09/04/24. TS-22/04/24 Survey and photos received passed to DA to cleanse. TS-24/04/24 Survey sent for pricing. 10.07.27 SF Eleanor advised this has been approved. 11.07.24 SF Handed to Darren to check the Asbestos Reports before we can "call off". |  |  |  |  | 6 | [10 empty] | 1 |  | 1 | [7 empty] | No |  | Brick | Blinds fixed to 5 windows | PG09(W) | 2024-07-11 | 2024-08-01 | Depot |  | 2024-08-05 | 8am to 2pm |  |  | Jim McDonald |  | 17/07 SMS text sent for 02/08. CONFIRMED. 18/07 SMS tenant called to cancel 02/08, text sent to offer 05/08. CONFIRMED
6 |  | 67542 |  | CALLED OFF |  | 37 | Baginton Road | Birmingham |  | B35 6JS | Bungalow | Mrs P Bermingham | 07757 383 294 | 0121 408 2804 |  |  | Windows & Doors | S Burgess | 2024-04-09 | 11am to 3pm |  |  | TS-02/04/24 Text sent for 09/04/24. TS-02/04/24 Tenant CONFIRMED for 09/04/24. TS-22/04/24 Survey and photos received passed to DA to cleanse. Rear door NWR. TS-24/04/24 Survey sent for pricing. TS-24/04/24 Emailed client to advise of the rear door NWR. 10.07.27 SF Eleanor advised this has been approved. 11.07.24 SF Handed to Darren to check the Asbestos Reports before we can "call off". |  |  |  |  | 5 | [10 empty] | 1 | [9 empty] | No |  | Brick | Permanent wheelchair user - No Solvent - Please set the lock loose | PG09(W) | 2024-07-11 | 2024-08-01 | Depot
6 |  | 55426 |  | CALLED OFF |  | 2 | Baginton Road | Birmingham |  | B35 6HN | House | Mrs D Woolaston |  | 07940411081 |  |  | Windows & Doors | S Burgess | 2024-04-23 | 8am to 12 noon |  |  | TS-02/04/24 Text sent for 09/04/24. TS-02/04/24 Tenant CONFIRMED for 09/04/24. TS-09/04/24 SB called he is unable to attend today - called tenant apologised and advised we will be back in touch to offer her a new date. TS-15/04/24 Called tenant and booked in for survey on 23/04/24 - CONFIRMED. TS-30/04/24 Survey received and passed to DA to cleanse. 10.07.27 SF Eleanor advised this has been approved. 11.07.24 SF Handed to Darren to check the Asbestos Reports before we can "call off". |  |  |  |  | 10 | [10 empty] | 1 |  | 1 |  |  |  |  | 1 | 2 |  |  | Independent Scaffold | Brick | SCAFFOLD - R/bed above pitched roof | PG09(W) | 2024-07-11 | 2024-08-01 | Depot
6 |  | 62238 |  | CALLED OFF |  | 60 | Watton Green | Birmingham |  | B35 7JP |  | Mr & Mrs David Nelson | 0121 682 5256 | 07961 096 673 | Davienelson68@gmail.com |  | Windows & Doors | M Turpin | 2024-05-07 | 8am to 2pm |  |  | TS-26/04/24 Letter sent to tenant offering 07/05/24 as no contact number held for tenant. 23.05.24 SF Sent to Dawn for pricing. 28/05 SMS Neil amended survey, scanned through for pricing. 20/6/2024 AC sent to re-pricing. 11.07.24 SF Handed to Darren to check the Asbestos Reports before we can "call off". 10.07.27 SF Eleanor advised this has been approved. 11.07.24 SF Handed to Darren to check the Asbestos Reports before we can "call off". |  |  |  |  | 10 | [10 empty] | 1 |  | 1 | [11 empty] | PG10(W) | 2024-07-12 | 2024-08-02 | Container
7 |  | 63952 |  | AWAIT CLIENT APPROVAL |  | 12 | Coltishall Close | Birmingham |  | B35 7EF |  | Mrs N Cheal |  | 07933 940 511 | n.cheal@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-06-17 | 8am to 2pm |  |  | 03/06 SMS text sent for 17/06. CONFIRMED for 17/06. 20.06.24 SF Received top sheet from Martin, survey received, no photos yet. 3/7; AC SENT TO PRICING. 04.07.24 SF Dawn sent to client for approval. |  |  |  |  | 11 | [10 empty] | 1 |  | 1
7 |  | 62463 |  | AWAIT CLIENT APPROVAL |  | 31 | Concorde Drive | Birmingham |  | B35 7EE | House | Mrs R V Shakespeare |  | 07972 147 963 | RitaShakespeare@yahoo.co.uk |  | Windows & Doors | M Turpin | 2024-06-19 | 8am to 2pm |  |  | 05/06 SMS text sent for 19/06. CONFIRMED for 19/06. 21.06.24 SF Received top sheet from Martin, survey received, photos waiting for. 3/7; AC SENT TO PRICING. 04.07.24 SF Dawn sent to client for approval. |  |  |  |  | 11 | [10 empty] | 1 |  | 1 | [8 empty] | Jammer System | Brick | DOOR JAMMER REQUIRED.
7 |  | 64722 |  | AWAIT CLIENT APPROVAL |  | 9 | Concorde Drive | Birmingham |  | B35 7EE |  | Miss Z Newell |  | 07948 505 771 | Zenanewall73@gmail.com |  | Windows & Doors | M Turpin | 2024-06-18 | 8am to 2pm |  |  | 04/06 SMS text sent for 18/06. 11/06 SMS called N/A. 13/06 SMS called N/A lttr sent. CONFIRMED for 18/06. 20.06.24 SF Received top sheet from Martin, survey received, not photos received. 3/7; AC SENT TO PRICING. 04.07.24 SF Dawn sent to client for approval. |  |  |  |  | 11 | [10 empty] | 1 |  | 1 | [8 empty] | Jammer System |  | DOOR JAMMER REQUIRED.
7 |  | 61361 |  | AWAIT CLIENT APPROVAL |  | 17 | Concorde Drive | Birmingham |  | B35 7EE |  | Mrs V Green | 07724 272 856 |  |  |  | Windows & Doors | M Turpin | 2024-06-18 | 8am to 2pm |  |  | 04/06 SMS text sent for 18/06. CONFIRMED for 18/06. 20.06.24 SF Received top sheet from Martin, survey received, not photos received. 3/7; AC SENT TO PRICING. 04.07.24 SF Dawn sent to client for approval. |  |  |  |  | 7 | [10 empty] | 1 | [10 empty] | Jammer System |  | DOOR JAMMER REQUIRED.
7 |  | 61362 |  | AWAIT CLIENT APPROVAL |  | 19 | Concorde Drive | Birmingham |  | B35 7EE |  | Mrs M Bowcott | SEND LETTER AS PREFERENCE. | 07904 122 836 |  |  | Windows & Doors | M Turpin | 2024-06-18 | 8am to 2pm |  | 1 | 04/06 SMS text sent for 18/06. CONFIRMED for 18/06. 20.06.24 SF Received top sheet from Martin, survey received, not photos received. 3/7; AC SENT TO PRICING. 04.07.24 SF Dawn sent to client for approval. |  |  |  |  | 7 | [10 empty] | 1 | [10 empty] | Jammer System |  | DOOR JAMMER REQUIRED. TENANT USES SCOOTER.
7 |  | 67951 |  | AWAIT CLIENT APPROVAL |  | 27 | Concorde Drive | Birmingham |  | B35 7EE |  | Mrs K Gillett | 07800 773 113 |  | KarlyKimble@msn.com |  | Windows & Doors | M Turpin | 2024-06-18 | 8am to 2pm |  |  | 04/06 SMS text sent for 18/06. CONFIRMED for 18/06. 20.06.24 SF Received top sheet from Martin, survey received, not photos received. 3/7; AC SENT TO PRICING. 04.07.24 SF Dawn sent to client for approval. |  |  |  |  | 10 | [10 empty] | 1 | [10 empty] | Jammer System |  | DOOR JAMMER REQUIRED.
7 |  | 65755 |  | AWAIT CLIENT APPROVAL |  | 14 | Coltishall Close | Birmingham |  | B35 7EF |  | Miss L McBride | 07588 323 233 |  | laura_mcbride@live.co.uk |  | Windows & Doors | M Turpin | 2024-06-17 | 8am to 2pm |  |  | 03/06 SMS text sent for 17/06. 06/06 SMS called N/A. CONFIRMED for 17/06. 20.06.24 SF Received top sheet from Martin, survey received, no photos yet. 1/7/2024; AC SENT TO PRICING. 3/7; DS Priced. |  |  |  |  | 11 | [10 empty] | 1 |  | 1
7 |  | 57194 |  | AWAIT CLIENT APPROVAL |  | 4 | De Havilland Drive | Birmingham |  | B35 7FP | House | Miss M Morahan | 0121 439 7477 | 07913206896 |  |  | Windows & Doors | M Turpin | 2024-06-19 | 8am to 2pm |  |  | 05/06 SMS text sent for 19/06. 11/06 SMS called N/A Lttr sent. 21.06.24 SF Received top sheet from Martin, survey received waiting for photos. 1/7/2024; AC SENT TO PRICING. 3/7; DS Priced. |  |  |  |  | 10 | [6 empty] | 1 |  |  |  | 1 |  | 1 | [9 empty] | Brick | Tenant been advised to isolate pets
7 |  | 67867 |  | AWAIT CLIENT APPROVAL |  | 10 | De Havilland Drive | Birmingham |  | B35 7FP | House | Mrs J Shakespeare-Hines |  | 07903 776 620 | hinestony@AOI.com |  | Windows & Doors | M Turpin | 2024-06-19 | 8am to 2pm |  |  | 05/06 SMS text sent for 19/06. CONFIRMED for 19/06 after 12pm pls. 21.06.24 SF Received top sheet from Martin, survey received waiting for photos. 1/7/2024; AC SENT TO PRICING. 3/7; DS Priced. |  |  |  |  | 11 | [10 empty] | 1 |  | 1 | [9 empty] | Brick
7 |  | 64087 |  | AWAIT CLIENT APPROVAL |  | 57E | Heyford Way | Birmingham |  | B35 6HZ |  | Miss L Scott | 07377 440 937 |  |  |  | Windows & Doors | P Beahan | 2024-06-18 | 11am to 3pm |  | 2 | TS-02/04/24 Text sent for 09/04/24. TS-03/04/24 Called tenant and left vm, txt & ltr sent. TS-15/04/24 No acess for 09/04/24 carded @ 12.45pm. TS-15/04/24 Text sent offering 25/04/24. TS-18/04/24 Called left vm, text & ltr sent. TS-26/04/24no access for 25/04/23 carded @ 11.5am card to follow. TS-03/05/24 Text sent for 14/05/24. TS-07/05/24 Ltr sent for 14/05/24. 08/05 SMS left voicemail for 14/05. 14/06 SMS Dominie arranged directly with tenant neice for 18/06, text sent also and surveyor updated with new date. 20.06.24 SF Received top sheet from Martin, survey received, not photos received. 1/7/2024; AC SENT TO PRICING. 3/7; DS Priced. |  |  |  |  | 6 | [10 empty] | 1 |  | 1
7 |  | 57988 |  | AWAIT CLIENT APPROVAL |  | 28 | Montrose Drive | Birmingham |  | B35 6DH | House | Mr J Belliss | 0121 747 1760 |  | jimbellis@talktalk.net |  | Windows & Doors | M Turpin | 2024-06-20 | 8am to 2pm |  |  | 13/06 SMS called N/A. 14/06 SMS called N/A Lttr sent. 24.06.24 SF Received top sheet from Martin, survey received waiting for photos. 1/7/2024; AC SENT TO PRICING. 3/7; DS Priced. |  |  |  |  | 10 | [6 empty] | 1 |  |  |  | 1 | [9 empty] | No |  | Brick
7 |  | 56202 |  | AWAIT CLIENT APPROVAL |  | 30 | Montrose Drive | Birmingham |  | B35 6DH | House | Mrs J Belliss | 0121 748 1898 | 07515 426 279 |  |  | Windows & Doors | M Turpin | 2024-06-20 | 8am to 2pm |  |  | CONFIRMED for 20/06. 24.06.24 SF Received top sheet from Martin, survey received waiting for photos. 1/7/2024; AC SENT TO PRICING. 3/7; DS Priced. |  |  |  |  | 10 | [6 empty] | 1 |  |  |  | 1 | [9 empty] | No |  | Brick
7 |  | 56203 |  | AWAIT CLIENT APPROVAL |  | 32 | Montrose Drive | Birmingham |  | B35 6DH | House | Miss W Jesson | 01214489328 | 07960 771 767 | wendyjesson@hotmail.co.uk | Breathing Difficulties | Windows & Doors | M Turpin | 2024-06-20 | First Call |  |  | Confirmed for 20/06, first call pls. 24.06.24 SF Received top sheet from Martin, survey received waiting for photos. 1/7/2024; AC SENT TO PRICING. 3/7; DS Priced. |  |  |  |  | 10 | [6 empty] | 1 |  |  |  | 1 | [9 empty] | No | Jammer System | Brick | COPD - Breathing difficulties | [11 empty] | COPD - Breathing difficulties
7 |  | 61451 |  | AWAIT CLIENT APPROVAL |  | 8 | School Close | Birmingham |  | B35 7NU |  | Mr H Malone |  | 07949 843 403 |  |  | Windows & Doors | M Turpin | 2024-06-17 | 8am to 2pm |  |  | 20/05 SMS sent email for 06/06 / 23.05.24 SF Sent another text. 29/05 SMS spoke to tenant & lttr sent. 06/06 SMS surveyor logged as tenant refusal, I spoke to tenants wife who said this is not correct so emailed MT, Dominie & DA to get this clarified before report to the client as a refusal. 12/06 SMS Dominie to liase and attend survey appointment and fitting appointment. *PLEASE CONTACT DOMINIE WITH AN ARRIVAL TIME AS SHE WILL ATTEND ALSO* 13/06 SMS text sent for 17/06. CONFIRMED for 17/06. 20.06.24 SF Received top sheet from Martin, survey received, no photos yet. 1/7/2024; AC SENT TO PRICING. 3/7; DS Priced. |  |  |  |  | 5 | [10 empty] | 1 |  | 1 | [22 empty] | (*Need to advise Dominie what fitting date allocated as she will liase directly with the tenants)
7 |  | 67835 |  | AWAIT CLIENT APPROVAL | Asbestos Report Required | 1 | Bicester Square | Birmingham |  | B35 6HR | Bungalow | Ms G Farbrother |  | 07723 067 036 |  |  | Windows & Doors | S Burgess | 2024-04-09 | 8am to 12 noon |  |  | TS-02/04/24 Text sent for 09/04/24. TS-02/04/24 Tenant CONFIMRED for 09/04/24. TS-22/04/24 Survey and photos given to DA to cleanse. TS-24/04/24 Survey sent for pricing. 05.07.24 SF Eleanor chased Jack at Pioneer for approval on the pricing costs. |  |  |  |  | 7 | [10 empty] | 1 |  | 1 | [7 empty] | No |  | Brick | No Solvent - scooter pushed through door to get outside not used in the property.
7 |  | 70054 |  | AWAIT CLIENT APPROVAL | Asbestos Report Required | 3 | Bicester Square | Birmingham |  | B35 6HR | Bungalow | Miss K Burt | 07454 317 261 | 07454 317 261 | kayburt1965@gmail.com |  | Windows & Doors | S Burgess | 2024-04-09 | 8am to 12 noon |  |  | TS-02/04/24 Text sent for 09/04/24. TS-02/04/24 Tenant text back no and that they can only do Thursday's AM. TS-04/04/24 Tenant called asking what Thursday she could have explained that we have allocated upto the 29th April and that we do not have a surveyor in the area on the day that wants, she then asked to be put back on to the 09/04/24 CONFIRMED. TS-15/04/24 Tenant called she has changed her mind about her door choice - sent over on email the door choice form. TS-15/04/24 Door choice received YORK in BLUE with OBSCURE Glass. TS-22/04/24 Survey and photos received passed to DA to cleanse. TS-24/04/24 Survey sent for pricing. 05.07.24 SF Eleanor chased Jack at Pioneer for approval on the pricing costs. 10.07.24 SF Tenant email the client requesting an installation timeframe, I've left a message for the tenant to call me back, but advised we don't have a date, but will let her know as soon as we do. |  |  |  |  | 7 | [10 empty] | 1 |  | 1 | [7 empty] | No |  | Brick | Blinds fixed to windows
7 |  | 70476 |  | AWAIT CLIENT APPROVAL |  | 5 | Bicester Square | Birmingham |  | B35 6HR | Bungalow | Mrs S Collins |  | 07428 113 447 | p.collins015@sky.com |  | Windows & Doors | S Burgess | 2024-04-09 | 8am to 12 noon |  |  | TS-02/04/24 Text sent for 09/04/24. TS-03/04/24 Called tenant and left vm, txt and ltr sent. TS-03/04/24 Tenant CONFIRMED for 09/04/24. TS-22/04/24 Survey and photos received passed to DA to cleanse. TS-24/04/24 Survey sent for pricing. 05.07.24 SF Eleanor chased Jack from Pioneer to approve the pricing costs. |  | Yes |  |  | 9 | [10 empty] | 1 |  | 1 | [7 empty] | No |  | Brick | No Solvent - Blinds fixed to the windows
7 |  | 55459 |  | AWAIT CLIENT APPROVAL | Asbestos Report Required | 20 | Bicester Square | Birmingham |  | B35 6HR | House | Mr J Powell | 0121 747 1197 |  |  |  | Windows & Doors | S Burgess | 2024-04-10 | 8am to 12 noon |  |  | TS-02/04/24 Called tenant and survey CONFIRMED for 10/04/24. TS-22/04/24 Survey and photos received passed to DA to cleanse. TS-24/04/24 Survey sent for pricing. 05.07.24 SF Eleanor chased Jack at Pioneer for approval on the pricing costs. |  |  |  |  | 4 | [8 empty] | 1 |  | 1 |  | 1 | [5 empty] | 1 |  | No |  | Brick | No Solvent COPD - Blinds to kitchen window
7 |  | 55460 |  | AWAIT CLIENT APPROVAL |  | 24 | Bicester Square | Birmingham |  | B35 6HR | House | Miss P A Mooney |  | 07761 898 550 | pamelamooney@live.co.uk |  | Windows & Doors | S Burgess | 2024-04-10 | 8am to 12 noon |  |  | TS-02/04/24 Text sent for 10/04/24. TS-02/04/24 Tenant CONFIRMED for 10/04/24. TS-22/04/24 Survey and photos received passed to DA to cleanse. TS-24/04/24 Survey and asbestos cleansed sent for pricing. 05.07.24 SF Eleanor chased Jack from Pioneer to approve the pricing costs. |  | Yes |  |  | 9 | [10 empty] | 1 |  | 1 | [5 empty] | 1 |  | No | Independent Scaffold | Brick | SCAFFOLD f/bed pitch roof - blinds being replaced after window installation.
7 |  | 55461 |  | AWAIT CLIENT APPROVAL |  | 26 | Bicester Square | Birmingham |  | B35 6HR | Bungalow | Mrs J Hughes | 0121 749 2668 |  |  |  | Windows & Doors | S Burgess | 2024-04-09 | 8am to 12 noon |  |  | TS-02/04/24 Letter sent for 09/04/24 as no contact number. TS-224/04/24 Survey and photos given to DA to cleanse. TS-24/04/24 Survey sent for pricing. 05.07.24 SF Eleanor chased Jack from Pioneer to approve the pricing costs. |  | Yes |  |  | 9 | [10 empty] | 1 |  | 1 | [5 empty] | 1 |  | No | Independent Scaffold | Brick | Son lives at the property is mum's carer - blinds fixed to kitchen & bathroom windows - SCAFFOLD FOR REAR BED WINDOW
7 |  | 58575 |  | AWAIT CLIENT APPROVAL | Asbestos Report Required | FLAT 2 Block 14 | Bicester Square | Castle Vale |  | B35 6HR | Flat | Mrs N W Griffiths | 07502 712 150 - text only tenant is deaf | 07751 745 796 |  |  | Windows & Doors | S Burgess | 2024-04-10 | 11am to 3pm |  |  | TS-02/04/24 Text sent for 10/04/24. TS-03/04/24 Called tenant spoke to son and he has CONFIRMED for 10/04/24 after 12pm (nurses leave by 12pm).] TS-22/04/24 Survey and photos given to DA to cleanse. TS-30/04/24 Survey cleansed and sent for pricing. 05.07.24 SF Eleanor chased Jack at Pioneer for approval on the pricing costs. |  |  |  |  | 6 | [6 empty] | 1 | [13 empty] | No | Independent Scaffold | Brick & Cladding | No Solvent - tenant is deaf text only & ltr. Grd Floor.
7 |  | 58464 |  | AWAIT CLIENT APPROVAL | Asbestos Report Required | FLAT 3 Block 14 | Bicester Square | Castle Vale |  | B35 6HR | Flat | Mr D Hobbs |  | 07368 395 454 |  |  | Windows & Doors | S Burgess | 2024-04-10 | 11am to 3pm |  |  | TS-02/04/24 Text sent for 10/04/24. TS-03/04/24 Called tenant left vm, txt & ltr sent. TS-22/04/24 Survey and photos received passed to DA to cleanse. TS-30/04/24 Survey cleansed and sent for pricing. 05.07.24 SF Eleanor chased Jack at Pioneer for approval on the pricing costs. |  |  |  |  | 7 | [20 empty] | No | Independent Scaffold | Brick & Cladding | COPD No solvent - block will have/need scaffold wheel/pully system. 1st Floor.
7 |  | 65086 |  | AWAIT CLIENT APPROVAL |  | FLAT 4 Block 14 | Bicester Square | Castle Vale |  | B35 6HR | Flat | Mr D Hilton | 07745 835 497 |  |  |  | Windows & Doors | S Burgess | 2024-04-12 | 8am to 12 noon |  |  | TS-02/04/24 Text sent for 12/04/24. TS-04/04/24 Called tenant survey CONFIRMED for 12/04/24. TS-22/04/24 Survey & photos receoived passed to DA to cleanse. Ts-30/04/24 Survey cleansed and sent for pricing. 05.07.24 SF Eleanor chased Jack from Pioneer to approve the pricing costs. |  | Yes |  |  | 6 | [20 empty] | No | Independent Scaffold | Brick & Cladding | SCAFFOLD - Block will have scaffold with wheel/pully system. 1st Floor.
7 |  | 70761 |  | AWAIT CLIENT APPROVAL | Asbestos Report Required | FLAT 5 Block 14 | Bicester Square | Castle Vale |  | B35 6HR | Flat | Mrs Tariq | 07361 213 383 |  |  |  | Windows & Doors | S Burgess | 2024-04-12 | 8am to 12 noon |  |  | TS-02/04/24 Letter sent for 12/04/24 as no contact number. TS-04/04/24 Ltr sent to the property. TS-22/04/24 Survey & photos receoived passed to DA to cleanse. TS-30/04/24 Survey cleansed and sent for pricing. 05.07.24 SF Eleanor chased Jack at Pioneer for approval on the pricing costs. |  |  |  |  | 7 | [20 empty] | No | Independent Scaffold | Brick & Cladding | SCAFFOLD - 2nd floor pulley for scaffold big frames
7 |  | 67508 |  | AWAIT CLIENT APPROVAL | Asbestos Report Required | FLAT 6 Block 14 | Bicester Square | Castle Vale |  | B35 6HR | Flat | Mr L Dilloway | 07779 765 081 | 07592758857 | luke.dilloway@yahoo.co.uk |  | Windows & Doors | S Burgess | 2024-04-12 | 8am to 12 noon |  |  | TS-02/04/24 Text sent for 12/04/24. TS-02/04/24 Tenant CONFIRMED for 12/04/24. TS-22/04/24 Survey received passed to DA to cleanse - photo to follow. TS-30/040/24 Survey cleansed sent for pricing. 05.07.24 SF Eleanor chased Jack at Pioneer for approval on the pricing costs. |  |  |  |  | 6 | [20 empty] | No | Independent Scaffold | Brick & Cladding | SCAFFOLD - Block will have scaffold - 2nd floor pulley on rear for large frames
7 |  | 69229 |  | AWAIT CLIENT APPROVAL |  | FLAT 1 Block 14 | Bicester Square | Castle Vale |  | B35 6HR |  | Miss C Mullen | 7415508478 |  |  |  | Windows & Doors | S Burgess | 2024-05-14 | First Call |  |  | TS-02/04/24 Text sent for 10/04/24. TS-03/04/24 Tenant text back no, text them asking which days are better. TS--23/04/24 Text sent offering 14/05/24 as the first call. TS-23/04/24 CONFIRMED as first call for 14/05/24. 05.07.24 SF Eleanor chased Jack at Pioneer for approval on the pricing costs. | [26 empty] | Independent Scaffold
7 |  | 68409 |  | AWAIT CLIENT APPROVAL |  | 3 | Biggin Close | Birmingham |  | B35 6BU | House | Mr M Waheed | 07480 515 723 | 07480515723 |  |  | Windows & Doors | S Burgess | 2024-04-24 | 11am to 3pm |  |  | TS-15/04/24 Text sent for 24/04/24. TS-15/04/24 Survey CONFIRMED for 24/04/24. TS-30/04/24 Survey received and passed to DA to cleanse. 05.07.24 SF Eleanor chased Jack at Pioneer for approval on the pricing costs. |  |  |  |  | 11 | [10 empty] | 1 |  | 1 | [5 empty] | 1 |  |  | Independent Scaffold | Brick | SCAFFOLD F/bed x 2 pitch roof - blinds fixed to windows
7 |  | 68957 |  | AWAIT CLIENT APPROVAL |  | 4 | Biggin Close | Birmingham |  | B35 6BU | Bungalow | Mr J Hagans | 07879 262 197 | 07790 624 520 |  |  | Windows & Doors | S Burgess | 2024-04-24 | 11am to 3pm |  |  | TS-15/04/24 Text sent for 24/04/24. TS-15/004/24 Survey CONFIRMED for 24/04/24. TS-30/04/24 Survey received and passed to DA to cleanse. 05.07.24 SF Eleanor chased Jack at Pioneer for approval on the pricing costs. |  |  |  |  | 6 | [10 empty] | 1 |  | 1 | [9 empty] | Brick | blinds fixed to windows tenant's son said he will refix them - Remove big motar beds
7 |  | 65528 |  | AWAIT CLIENT APPROVAL |  | 6 | Biggin Close | Birmingham |  | B35 6BU |  | Miss S Spicer | 0121 748 4193 | 07970 847 644 | spicersusan@hotmail.com |  | Windows & Doors | S Burgess | 2024-04-26 | 11am to 3pm |  |  | TS-15/04/24 Text sent for 26/04/24. TS-16/04/24 Tenant asked for the afternoon changed the time to 11am-3pm CONFIRMED for 26/04/24. TS-30/04/24 Survey received and passed to DA to cleanse. 05.07.24 SF Eleanor chased Jack at Pioneer for approval on the pricing costs. |  |  |  |  | 5 | [10 empty] | 1 |  | 1 | [9 empty] | Brick
7 |  | 66166 |  | AWAIT CLIENT APPROVAL |  | 7 | Biggin Close | Birmingham |  | B35 6BU |  | Mrs D Johnson |  | 07955 013 317 | debbie.johnson65@me.com |  | Windows & Doors | S Burgess | 2024-04-26 | 8am to 12 noon |  |  | TS-15/04/24 Text sent for 26/04/24. TS-15/04/24 Survey CONFIRMED for 26/04/24. TS-302/04/24 Survey received and passed to DA to cleanse. 05.07.24 SF Eleanor chased Jack at Pioneer for approval on the pricing costs. |  |  |  |  | 11 | [6 empty] | 1 |  |  |  | 1 | [7 empty] | 1 |  |  |  | Brick | No Solvent
7 |  | 67416 |  | AWAIT CLIENT APPROVAL |  | 8 | Biggin Close | Birmingham |  | B35 6BU |  | Mr A Spriggs | 01217497374 | 07376 359 568 | roy29949@live.co.uk |  | Windows & Doors | S Burgess | 2024-04-26 | 8am to 12 noon |  |  | TS-15/04/24 Text sent for 26/04/24. TS-30/04/24 Survey received and given to DA to cleanse. 05.07.24 SF Eleanor chased Jack at Pioneer for approval on the pricing costs. |  |  |  |  | 5 | [10 empty] | 1 |  | 1 | [8 empty] | Independent Scaffold | Brick | SCAFFOLD - 2 x F/bed pitch roof
7 |  | 65252 |  | AWAIT CLIENT APPROVAL |  | 9 | Biggin Close | Birmingham |  | B35 6BU |  | Miss A-M Wilson-Clarke | 07943 100 812 |  | annmarie_clrk@yahoo.co.uk |  | Windows & Doors | S Burgess | 2024-04-26 | 8am to 12 noon |  |  | TS-18/04/24 Sent letter offering 26/04/24. TS-30/04/24 Survey reveived and passed to DA to cleanse. 05.07.24 SF Eleanor chased Jack at Pioneer for approval on the pricing costs. |  |  |  |  | 11 | [8 empty] | 1 |  | 1 | [7 empty] | 1 |  |  | Independent Scaffold | Brick | SCAFFOLD - 2x F/Bed pitch roof - No Solvent
7 |  | 69337 |  | AWAIT CLIENT APPROVAL |  | 10 | Biggin Close | Birmingham |  | B35 6BU |  | Miss E Hemming | 07368257842 | 07368 257 884 | elaine.hemming1955@googlemail.com |  | Windows & Doors | S Burgess | 2024-04-26 | 11am to 3pm |  |  | TS-15/04/24 Text sent for 26/04/24. TS-15/04/24 Survey CONFIRMED for 26/04/24. TS-30/04/24 Survey received and passed to DA to cleanse. 05.07.24 SF Eleanor chased Jack at Pioneer for approval on the pricing costs. |  |  |  |  | 5 | [10 empty] | 1 | [11 empty] | Brick | No Solvent - on holiday 10/07 to 17/07
7 |  | 68633 |  | AWAIT CLIENT APPROVAL |  | 17 | Biggin Close | Birmingham |  | B35 6BU |  | Miss K Wesley | 07517 469 381 |  | katie_cienna@hotmail.co.uk |  | Windows & Doors | S Burgess | 2024-04-26 | 11am to 3pm |  |  | TS-15/04/24 Text sent for 26/04/24. TS-15/054/24 Survey CONFIRMED for 26/04/24. TS-30/04/24 Survey received and given to DA to cleanse. 05.07.24 SF Eleanor chased Jack at Pioneer for approval on the pricing costs. |  |  |  |  | 10 | [8 empty] | 1 |  | 1
7 |  | 67249 |  | AWAIT CLIENT APPROVAL |  | 1 | Biggin Close | Birmingham |  | B35 6BU |  | Miss J Nash |  | 07854 351518 |  |  | Windows & Doors | S Burgess | 2024-05-14 | 11am to 3pm |  |  | TS-15/04/24 Text sent for 24/04/24. TS-15/04/24 Survey CONFIRMED for 24/04/24. TS-18/04/24 Text sent cancelling 24/04 and offering 14/05/24. TS-24/04/24 Survey CONFIRMED for 14/05/24. 05.07.24 SF Eleanor chased Jack at Pioneer for approval on the pricing costs.
7 |  | 60237 |  | AWAIT CLIENT APPROVAL |  | 12 | Biggin Close | Birmingham |  | B35 6BU |  | Mr J Larkin |  |  |  |  | Windows & Doors | S Burgess | 2024-05-14 |  |  |  | TS-07/05/24 Ltr sent for 14/05/24. 05.07.24 SF Eleanor chased Jack at Pioneer for approval on the pricing costs.
7 |  | 65327 |  | AWAIT CLIENT APPROVAL |  | 68 | Brabazon Grove | Birmingham |  | B35 6DT |  | Miss T Pointon |  | 07557 398 593 | tracy-1979@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-05-24 | 8am to 2pm |  |  | TS-07/05/24 Ltr sent for 14/05/24. 13/05 SMS tenant cancelled. 14/05 SMS emailed tenant to offer 24/05. CONFIRMED. No survey so awaiting photos to see if was a no access.23/05 SMS tenant emailed to cancel. 24.05.24 SF Martin Turpin did actually attend, his van probably got fixed quicker than he thought, he attended the proper and surveyed the doors & windows. 20/6/2024; AC sent to pricing. 05.07.24 SF Eleanor chased Jack at Pioneer for approval on the pricing costs. |  |  |  |  | 12 | [10 empty] | 1 |  | 1 | [10 empty] | PETS.
7 |  | 65778 |  | AWAIT CLIENT APPROVAL |  | 27 | Brabazon Grove | Birmingham |  | B35 6DT |  | Miss A Witts | 07588 060 297 |  |  |  | Windows & Doors | M Turpin | 2024-05-13 | 8am to 2pm |  |  | TS-03/05/24 Text sent for 13/05/24. TS-07/05/24 Ltr sent. 08/05 SMS called no. NIS. 27.06.24 SF Tenant called and she needs at least 1 week notice when we are ready to install so she can arrange with work. 05.07.24 SF Eleanor chased Jack from Pioneer to approve the pricing costs. |  | Yes |  |  | 11 | [10 empty] | 1 |  | 1 | [5 empty] | 1
7 |  | 55484 |  | AWAIT CLIENT APPROVAL |  | 31 | Brabazon Grove | Birmingham |  | B35 6DT |  | Mr K Massey |  | 07534247544 |  |  | Windows & Doors | M Turpin | 2024-05-13 | PM |  |  | TS-03/05/24 Text sent for 13/05/24. TS-07/05/24 Ltr sent. 08/05 SMS tenant CONFIRMED after 12 pls. 05.07.24 SF Eleanor chased Jack at Pioneer for approval on the pricing costs. |  | Yes
7 |  | 64850 |  | AWAIT CLIENT APPROVAL |  | 34 | Brabazon Grove | Birmingham |  | B35 6DT |  | Mrs D Rivers | 01212411506 | 07969 870822 | dawnrivers169@yahoo.com |  | Windows & Doors | M Turpin | 2024-05-13 | 8am to 2pm |  |  | TS-03/05/24 Text sent for 13/05/24. TS-07/05/24 Ltr sent. 08/05 SMS Called engaged. 05.07.24 SF Eleanor chased Jack from Pioneer to approve the pricing costs. |  | Yes |  |  | 11 | [10 empty] | 1 |  | 1 | [5 empty] | 1
7 |  | 57609 |  | AWAIT CLIENT APPROVAL | DOOR CHOICE | 36 | Brabazon Grove | Birmingham |  | B35 6DT |  | Miss T Butler | 07956475367 | 07956475367 |  |  | Windows & Doors | M Turpin | 2024-05-13 | 8am to 2pm |  |  | TS-03/05/24 Text sent for 13/05/24. TS-07/05/24 Ltr sent. 08/05 SMS left voicemail. 14/06 SMS tenant called to advise does now want front door replaced, emailed her to request her door choice and will then re-scan to commercial for pricing. 14/06 SMS re-scanned to pricing 05.07.24 SF Eleanor chased Jack from Pioneer to approve the pricing costs. |  | Yes |  |  | 11 | [10 empty] | 1 |  | 1
7 |  | 55487 |  | AWAIT CLIENT APPROVAL |  | 37 | Brabazon Grove | Birmingham |  | B35 6DT |  | Mr J Meenan | 0121 730 1037 | 07846 480 995 | johnmeenan@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-05-13 | 8am to 2pm |  |  | TS-03/05/24 Text sent for 13/05/24. TS-03/05/24 Survey CONFIRMED for 13/05/24. 05.07.24 SF Eleanor chased Jack from Pioneer to approve the pricing costs. |  | Yes |  |  | 11 | [10 empty] | 1 |  | 1 | [5 empty] | 1
7 |  | 55488 |  | AWAIT CLIENT APPROVAL |  | 38 | Brabazon Grove | Birmingham |  | B35 6DT |  | Mrs M Sergeant |  | 07913 666 673 |  |  | Windows & Doors | M Turpin | 2024-05-13 | 8am to 2pm |  |  | TS-03/05/24 Text sent for 13/05/24. TS-07/05/24 Ltr sent. 08/05 SMS left voicemail. 05.07.24 SF Eleanor chased Jack from Pioneer to approve the pricing costs. |  | Yes |  |  | 11 | [10 empty] | 1 |  | 1
7 |  | 70734 |  | AWAIT CLIENT APPROVAL |  | 61 | Brabazon Grove | Birmingham |  | B35 6DT |  | Miss R Russell |  | 07908 063 136 | remirussell@icloud.com> |  | Windows & Doors | M Turpin | 2024-05-14 | 8am to 2pm |  |  | TS-03/05/24 Text sent for 14/05/24. TS-03/05/24 Survey CONFIRMED for 14/05/24. 05.07.24 SF Eleanor chased Jack from Pioneer to approve the pricing costs. |  | Yes |  |  | 10 | [6 empty] | 1 |  |  |  | 1 |  | 1
7 |  | 69274 |  | AWAIT CLIENT APPROVAL |  | FLAT 54 | Brabazon Grove | Birmingham |  | B35 6DT |  | Miss S Moore |  | 07887963343 | suemoore35@yahoo.co.uk |  | Windows & Doors | M Turpin | 2024-05-16 | 8am to 2pm |  |  | TS-03/05/24 Text sent for 13/05/24. TS-07/05/24 Ltr sent. 14/05 SMS text sent for 16/05. CONFIRMED for 16/05/24. 05.07.24 SF Eleanor chased Jack at Pioneer for approval on the pricing costs. |  |  |  |  | 3 | [8 empty] | 1
7 |  | 70364 |  | AWAIT CLIENT APPROVAL |  | FLAT 56 | Brabazon Grove | Birmingham |  | B35 6DT |  | Mr D Wallace |  | 07719750799 |  |  | Windows & Doors | M Turpin | 2024-05-14 | 8am to 2pm |  |  | TS-03/05/24 Text sent for 14/05/24. TS-07/05/24 Ltr sent. 08/05 SMS called N/A. 05.07.24 SF Eleanor chased Jack from Pioneer to approve the pricing costs. |  | Yes |  |  | 5
7 |  | 65237 |  | AWAIT CLIENT APPROVAL |  | FLAT 60 | Brabazon Grove | Birmingham |  | B35 6DT |  | Mr N Flynn |  | 07947975847 |  |  | Windows & Doors | M Turpin | 2024-05-14 | 8am to 2pm |  |  | TS-03/05/24 Text sent for 14/05/24. TS-07/05/24 Ltr sent. 08/05 SMS called & tenant CONFIRMED for 14/05/24. 05.07.24 SF Eleanor chased Jack from Pioneer to approve the pricing costs. |  | Yes |  |  | 5 | [10 empty] | 1
7 |  | 65463 |  | AWAIT CLIENT APPROVAL |  | FLAT 64 | Brabazon Grove | Birmingham |  | B35 6DT |  | Ms B A Hinsley | 07891806772 | 07891 806772 |  |  | Windows & Doors | M Turpin | 2024-05-14 | 8am to 2pm |  |  | TS-03/05/24 Text sent for 14/05/24. TS-07/05/24 Ltr sent. 08/05 SMS called tenant CONFIRMED for 14/05/24. 05.07.24 SF Eleanor chased Jack from Pioneer to approve the pricing costs. |  | Yes |  |  | 3 | [6 empty] | 1
7 |  | 67319 |  | AWAIT CLIENT APPROVAL |  | 72 | Brabazon Grove | Birmingham |  | B35 6DT |  | Miss H Fanning |  |  |  |  | Windows & Doors | M Turpin | 2024-05-14 | 8am to 2pm |  |  | TS-07/05/24 Ltr sent for 14/05. 05.07.24 SF Eleanor chased Jack from Pioneer to approve the pricing costs. |  | Yes |  |  | 10 | [6 empty] | 1 |  |  |  | 1 | [7 empty] | 1
7 |  | 55504 |  | AWAIT CLIENT APPROVAL |  | 74 | Brabazon Grove | Birmingham |  | B35 6DT |  | Mr M Coleing | 0121 749 6902 |  |  |  | Windows & Doors | M Turpin | 2024-05-14 | 8am to 2pm |  |  | TS-07/05/24 Ltr sent for 14/05. 08/05 SMS called tenant CONFIRMED for 14/05/24. 05.07.24 SF Eleanor chased Jack from Pioneer to approve the pricing costs. |  | Yes |  |  | 11 | [10 empty] | 1 |  | 1 | [5 empty] | 1
7 |  | 55505 |  | AWAIT CLIENT APPROVAL |  | 76 | Brabazon Grove | Birmingham |  | B35 6DT |  | Mrs D Hughes | 0121 748 6129 |  |  |  | Windows & Doors | M Turpin | 2024-05-15 | 8am to 2pm |  |  | TS-07/05/24 Ltr sent for 15/05. 08/05 SMS called but got a silent line.*19/06 SMS tenant called in to see if could amend her door choice, emailed Dominie to ask if she can attend to get paperwork filled out, awaiting reply. Door Choice recvd and paperwork amended. 05.07.24 SF Eleanor chased Jack from Pioneer to approve the pricing costs. |  | Yes |  |  | 9 | [10 empty] | 1 |  | 1 | [5 empty] | 1
7 |  | 65495 |  | AWAIT CLIENT APPROVAL |  | FLAT 62 | Brabazon Grove | Birmingham |  | B35 6DT |  | Mr ML Powers | 0121 748 7923 |  | mickpowers64@gmail.com |  | Windows & Doors | M Turpin | 2024-05-14 | 8am to 2pm |  |  | TS-07/05/24 Ltr sent. 08/05 SMS left voicemail for 14/05. CONFIRMED for 14/05/24. 05.07.24 SF Eleanor chased Jack from Pioneer to approve the pricing costs. |  | Yes |  |  | 5 | [10 empty] | 1
7 |  | 64946 |  | AWAIT CLIENT APPROVAL |  | 57A | Heyford Way | Birmingham |  | B35 6HZ |  | Miss S Trevis | 0121 747 1622 | 07966545174 |  |  | Windows & Doors | P Beahan | 2024-04-09 | 8am to 12 noon |  |  | TS-02/04/24 Text sent for 09/04/24. TS-02/04/24 Tenant CONFIRMED for 09/04/24. 23.05.24 SF attached photos to surveys, given to Darren to cleanse. 05.07.24 SF Eleanor chased Jack from Pioneer to approve the pricing costs. |  | Yes |  |  | 7 | [10 empty] | 1 |  | 1 | [10 empty] | *Remove blinds ect, Mobility Scooter, COPD no solvents* Front door wires through frame | [11 empty] | *Remove blinds ect, Mobility Scooter, COPD no solvents* Front door wires through frame
7 |  | 67577 |  | AWAIT CLIENT APPROVAL |  | 57B | Heyford Way | Birmingham |  | B35 6HZ |  | Miss R E Anderson | 0121 747 3136 | 07711956370 | rosebeth54@gmail.com |  | Windows & Doors | P Beahan | 2024-04-09 | 8am to 12 noon |  |  | TS-02/04/24 Text sent for 09/04/24. TS-03/04/24 Tenant CONFIRMED for 09/04/24. 23.05.24 SF attached photos to surveys, given to Darren to cleanse. 05.07.24 SF Eleanor chased Jack from Pioneer to approve the pricing costs. |  | Yes |  |  | 6 | [10 empty] | 1 |  | 1
7 |  | 61798 |  | AWAIT CLIENT APPROVAL |  | 57F | Heyford Way | Birmingham |  | B35 6HZ |  | Miss S Cooke | 0121 406 5559 |  |  |  | Windows & Doors | P Beahan | 2024-04-09 | 11am to 3pm |  |  | TS-02/04/24 Called tenant survey is booked for 09/04/24, tenant asked for us to call her 20 mins before arrival. She did advise that she has just received the news that she is terminal did offer her to decline the appointment but she said no. 23.05.24 SF attached photos to surveys, given to Darren to cleanse. | Tenant is terminal | Yes |  |  | 7 | [10 empty] | 1 |  | 1
7 |  | 68966 |  | AWAIT CLIENT APPROVAL |  | 97 | Watton Green | Birmingham |  | B35 7GA |  | Miss J Atterbury | 07970 331 259 |  |  |  | Windows & Doors | M Turpin | 2024-05-23 | 8am to 2pm |  |  | 13/05 SMS text sent for 23/05. CONFIRMED for 23/05. 24.05.24 SF Martin Turpin attended, received top sheet, survey sent for cleansing, doors & windows, surveyed awaiting photos. * Door Choice in tray*. 1/7/2024; AC SENT TO PRICING. 3/7; DS Priced. |  |  |  |  | 11 | [10 empty] | 1 |  | 1 | [8 empty] | Independent Scaffold |  | SCAFFOLD. 70MM CAPPIT X 2 LENGTHS REQUIRED.Scaffolding quote is in sharepoint file | [11 empty] | *Scaffolding req, Scaffolding quote is in sharepoint file
7 |  | 56839 |  | AWAIT CLIENT APPROVAL | Electrician Required | 90 | Watton Green | Birmingham |  | B35 7JR |  | Mr M Mooney | 0121 749 3839 |  | mooney.90wg@hotmail.com |  | Windows & Doors | M Turpin | 2024-05-23 | 8am to 2pm |  |  | 13/05 SMS lttr sent for 23/05. 24.05.24 SF Martin Turpin attended, received top sheet, survey sent for cleansing, doors & windows, surveyed awaiting photos. 20/6/2024; AC sent to pricing but passed back to DA to check if electrician is actually required. If so, he needs to find one and get a quote. 3/7; DS Priced. |  |  |  |  | 11 | [6 empty] | 1 |  |  |  | 1 |  | 1 | [10 empty] | Electrician Required
7 |  | 68247 |  | AWAIT CLIENT APPROVAL |  | 33 | Watton Green | Birmingham |  | B35 7JS | House | Miss L Craddock |  | 07712 139 229 | l_craddock1988@outlook.com |  | Windows & Doors | M Turpin | 2024-06-19 | 8am to 2pm |  |  | TS-25/04/24 Text sent for 07/05/24. TS-26/04/24 Survey CONFIRMED for 07/05/24. TS-07/05/24 Tenant called they have a family emergency and need to cancel - text MT. 13/05 SMS text sent for 23/05. CONFIRMED for 23/05. 22/05 SMS tenant called to cancel. 29/05 SMS text sent for 05/06. CONFIRMED for 05/06 between 9am and 2pm please. 04/06 SMS tenant called to cancel due to child being ill.11/06 text sent for 19/06. CONFIRMED for 19/06. 21.06.24 SF Received top sheet from Martin, survey received waiting for photos. 1/7/2024; AC SENT TO PRICING. 3/7; DS Priced. |  |  |  |  | 7 | [10 empty] | 1 |  | 1 | [9 empty] | Brick | 2 x CATS.
7 |  | 64808 |  | AWAIT CLIENT APPROVAL |  | 21 | Cranwell Way | Birmingham |  | B35 6QH |  | Miss P Davidson |  | 07920 420 656 | paulinepatricia@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-06-25 | 8am to 2pm |  |  | 14/06 SMS text sent for 25/06. CONFIRMED for 25/06. 28.06.24 SF Surveys received from Martin, still waiting photos.10/7/2034; AC sent to pricing. 12.07.24 SF Eleanor sent to client for approval. |  |  |  |  | 6 | [10 empty] | 1 |  | 1
7 |  | 65336 |  | AWAIT CLIENT APPROVAL |  | 4 | Cranwell Way | Birmingham |  | B35 6QH |  | Mrs CS Gould | 07354 229 124 |  |  |  | Windows & Doors | M Turpin | 2024-06-25 | 8am to 2pm |  |  | 14/06 SMS text sent for 25/06. 18/6; AC emailed. 19/6; letter sent. 28.06.24 SF Surveys received from Martin, still waiting photos. 12.07.24 SF Eleanor sent to client for approval. |  |  |  |  | 10 | [10 empty] | 1 |  | 1 | [8 empty] | Jammer System |  | Uses mobility scooter. Asthma.
7 |  | 69246 |  | AWAIT CLIENT APPROVAL |  | 30 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss F Bah | 07478 263 967 |  | Fatoubah@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-06-24 | 8am to 2pm |  |  | (Access via 30 & 46 Cosford Crescent). 13.06.24 SF sent text for survey on the 24.06.24, waiting confirmation. 18.06.24 SF Number NIS sent letter. 3/7; Ac sent to PM to cleanse. . 10/7/2034; AC sent to pricing. 10/7/2034; AC sent to pricing. 12/7/.2024; EG priced. |  |  |  |  | 6 | [10 empty] | 1 |  | 1
7 |  | 70690 |  | AWAIT CLIENT APPROVAL |  | 46 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss N Altaf | 07397 098 767 |  | Nafizah9@gmail.com |  | Windows & Doors | M Turpin | 2024-06-24 | 8am to 2pm |  |  | (Access via 30 & 46 Cosford Crescent). 13.06.24 SF sent text for survey on the 24.06.24, tenant text back & CONFIRMED the survey date.18.06.24 SF Tenant CONFIRMED by return text. 3/7; AC sent to PM to cleanse. 10/7/2034; AC sent to pricing. 12/7/.2024; EG priced. |  |  |  |  | 7 | [10 empty] | 1 |  | 1 | [10 empty] | Tenant has mobility issues.
7 |  | 63764 |  | AWAIT CLIENT APPROVAL |  | FLAT 32 | Cosford Crescent | Birmingham |  | B35 6QE |  | Eva Bor | 07551 907 865 |  | ewici@outlook.com |  | Windows & Doors | M Turpin | 2024-06-24 | 8am to 2pm |  |  | (Access via 30 & 46 Cosford Crescent). 13.06.24 SF sent text for survey on the 24.06.24, waiting confirmation. 18.06.24 SF LM again & sent letter. 3/7; Ac sent to PM to cleanse. 10/7/2034; AC sent to pricing. 12/7/.2024; EG priced. |  |  |  |  | 5 | [5 empty] | 2 | [17 empty] | Access via 30 & 46 Cosford Crescent
7 |  | 69460 |  | AWAIT CLIENT APPROVAL |  | FLAT 34 | Cosford Crescent | Birmingham |  | B35 6QE |  | Ms S Phelan | 07468 602 288 |  |  |  | Windows & Doors | M Turpin | 2024-06-24 | 8am to 2pm |  |  | (Access via 30 & 46 Cosford Crescent). 13.06.24 SF sent text for survey on the 24.06.24, waiting confirmation. 18.06.24 SF Tenant CONFIRMED by return text message for the survey to be done. 3/7; AC sent to PM to cleanse. 10/7/2034; AC sent to pricing. 12/7/.2024; EG priced. |  |  |  |  | 5 | [6 empty] | 1 | [16 empty] | Access via 30 & 46 Cosford Crescent
7 |  | 66105 |  | AWAIT CLIENT APPROVAL |  | FLAT 36 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mr K Nzumba | 07826 497 918 |  |  |  | Windows & Doors | M Turpin | 2024-06-24 | 8am to 2pm |  |  | (Access via 30 & 46 Cosford Crescent). 13.06.24 SF sent text for survey on the 24.06.24, waiting confirmation. 18.06.24 SF Tenant CONFIRMED by phone call, between 8am - 9pm. 3/7; Ac sent to PM to cleanse. 10/7/2034; AC sent to pricing. 12/7/.2024; EG priced. |  |  |  |  | 3 | [5 empty] | 1 | [17 empty] | Access via 30 & 46 Cosford Crescent
7 |  | 62885 |  | AWAIT CLIENT APPROVAL |  | 6 | Drem Croft | Birmingham |  | B35 7HW |  | Mr D W Henry | 0121 241 4086 | 07986 013 017 | suehenry145@hotmail.com |  | Windows & Doors | M Turpin | 2024-06-27 | 8am to 2pm |  |  | 14/06 SMS text sent for 27/06. CONFIRMED for 27/06. 10/7/2034; AC sent to pricing. 16.07.24 SF Eleanor sent to client for approval. |  |  |  |  | 5 | [10 empty] | 1 |  | 1 | [10 empty] | Uses walking frame and COPD.
7 |  | 65980 |  | AWAIT CLIENT APPROVAL |  | 8 | Drem Croft | Birmingham |  | B35 7HW |  | Mrs A Bricknell | 0121 250 6476 | 27488 340 815 | brickanne7@gmail.com |  | Windows & Doors | M Turpin | 2024-06-27 | 8am to 2pm |  |  | 14/06 SMS text sent for 27/06. 19/6 AC rang but number is incorrect, letter sent. 10/7/2034; AC sent to pricing. 16.07.24 SF Eleanor sent to client for approval. |  |  |  |  | 5 | [10 empty] | 1 |  | 1 | [10 empty] | MOBILE SCOOTER.
7 |  | 59785 |  | AWAIT CLIENT APPROVAL |  | FLAT 2 | Kemble Drive | Birmingham |  | B35 6QS |  | Mr B Riley | 01217 484 548 |  |  |  | Windows & Doors | P Beahan | 2024-04-16 | 11am to 3pm |  |  | TS-08/04/24 Called tenant survey is CONFIRMED for 16/04/24.. 10/7/2034; AC sent to pricing. 16.07.24 SF Eleanor sent to client for approval. |  |  |  |  | 5 | [5 empty] | 2 | [17 empty] | Access Via 10 Kemble & 469 Yatesbury Avenue
7 |  | 70048 |  | AWAIT CLIENT APPROVAL |  | FLAT 4 | Kemble Drive | Birmingham |  | B35 6QS |  | Mr J G Carter | 07305 295 274 |  | jordancarter@hotmail.co.uk |  | Windows & Doors | P Beahan | 2024-04-16 | 11am to 3pm |  |  | TS-04/04/24 Text sent for 16/04/24. TS-08/04/24 Called line rang once then cut off, sent txt & ltr. TS-11/04/24 Tenant txt back no, replied back asking which days are better. TS-11/04/24 Tenant txt back to advise that they need after 1.30pm - CONFIRMED for 16/04/24 after 1.30pm. TS-15/04/24 Door choice emailed to client.. 10/7/2034; AC sent to pricing. 16.07.24 SF Eleanor sent to client for approval. |  |  |  |  | 5 | [5 empty] | 2 | [17 empty] | Access Via 10 Kemble & 469 Yatesbury Avenue
7 |  | 66013 |  | AWAIT CLIENT APPROVAL |  | FLAT 6 | Kemble Drive | Birmingham |  | B35 6QS |  | Miss S Davies | 07845 628 491 | 07845628491 |  | Breathing Difficulties | Windows & Doors | P Beahan | 2024-04-16 | 11am to 3pm |  |  | TS-04/04/24 Text sent for 16/04/24. TS-05/04/24 Survey CONFIRMED for 16/04/24.. 10/7/2034; AC sent to pricing. 16.07.24 SF Eleanor sent to client for approval. |  |  |  |  | 6 | [5 empty] | 1 | [17 empty] | Access Via 10 Kemble & 469 Yatesbury Avenue | [11 empty] | Astma no Solvents. Access Via 10 Kemble & 469 Yatesbury Avenue.
8 |  | 67404 |  | PRICED |  | 21 | Watton Green | Birmingham |  | B35 7JS | House | Miss KL Batchelor | 07493 984 344 |  | keelybatch@gmail.com |  | Windows & Doors | M Turpin | 2024-05-02 | 8am to 2pm |  |  | TS-24/04/24 Letter sent for 02/05/24 as no contact number for tenant. TS-30/04/24 Tenant called to CONFIRM survey tracker updated with number. TS-03/05/24 Survey received photos to follow. 20/6/2024 AC sent to pricing. 11.07.24 SF Handed to Darren to check the Asbestos Reports before we can "call off". 10.07.27 SF Eleanor advised this has been approved. 11.07.24 SF Handed to Darren to check the Asbestos Reports before we can "call off". |  |  |  |  | 7 | [6 empty] | 1 |  |  |  | 1 |  | 1 | [7 empty] | No | Jammer System |  | Possible asbestos removal to LH bed jamb.
8 |  | 56824 |  | PRICED |  | 25 | Watton Green | Birmingham |  | B35 7JS | House | Mrs B A Cooke | 0121 748 3529 | 07837951264 |  |  | Windows & Doors | M Turpin | 2024-05-02 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 02/05/24. TS-01/05/24 DM did a site visit and tenant has CONFIRMED for 02/05/24. TS-03/05/24 Survey received photos to follow. 20/6/2024 AC sent to pricing. 11.07.24 SF Handed to Darren to check the Asbestos Reports before we can "call off". 10.07.27 SF Eleanor advised this has been approved. 11.07.24 SF Handed to Darren to check the Asbestos Reports before we can "call off". |  |  |  |  | 7 | [6 empty] | 1 |  |  |  | 1 |  | 1 | [7 empty] | No | Jammer System |  | Possible asbestos removal to panel in small bed.
9 |  | 63131 |  | SENT FOR PRICING | Asbestos Report Required | 33 | Baginton Road | Birmingham |  | B35 6JS | Bungalow | Mr I Turner | 0121 748 3216 |  |  |  | Windows & Doors | S Burgess | 2024-04-23 | 8am to 12 noon |  | 1 | TS-02/04/24 Called no answer or vm ltr to be sent. TS-03/04/24 Called tenant no answer/vm ltr sent. TS-10/804/24 No access for survey 09/04/24 carded @ 13.01. TS-10/04/24 Tenant called he is only available in the mornings before 12pm. TS-17/04/24 Called tenant survey CONFIRMED for 23/04/24. TS-30/04/24 Survey received given to DA to cleanse. 10.07.27 SF Eleanor advised this has not yet been costed or sent to the client. 11.07.24 SF Handed to Darren to check the Asbestos Reports before we can "call off". |  |  |  |  | 6 | [10 empty] | 1 |  | 1 | [9 empty] | Brick
9 |  | 66252 |  | SENT FOR PRICING |  | FLAT 3 Block 16 | Bicester Square | Castle Vale |  | B35 6HR |  | Mr A Chinn |  | 07384 342 527 |  |  | Windows & Doors | S Burgess | 2024-06-18 |  |  |  | TS-02/04/24 Text sent for 12/04/24. TS-02/004/24 Tenant CONFIRMED survey for 12/04/24. TS-15/04/24 Marked on SB diary tenant works nights needs rebooking.04/06 SMS text sent for 18/06. CONFIRMED for 18/06. 1/7/2024; AC SENT TO PRICING. |  |  |  |  | 7 | [21 empty] | Independent Scaffold |  | SCAFFOLD 1ST AND 2ND FLOOR.
9 |  | 69922 |  | SENT FOR PRICING |  | FLAT 58 | Brabazon Grove | Birmingham |  | B35 6DT |  | Miss L Harding | 07491880111 |  | harding63@hotmail.com |  | Windows & Doors | M Turpin | 2024-05-14 | 8am to 2pm |  |  | TS-03/05/24 Text sent for 14/05/24. TS-03/05/24 Survey CONFIRMED for 14/05/24. |  | Yes
9 |  | 65714 |  | SENT FOR PRICING |  | 23 | Concorde Drive | Birmingham |  | B35 7EE |  | Miss S Lewis | 0121 779 2571 | 07887 745 870 | Sarah190580@live.co.uk |  | Windows & Doors | M Turpin | 2024-06-18 | 8am to 2pm |  |  | 04/06 SMS text sent for 18/06. CONFIRMED for 18/06. 20.06.24 SF Received top sheet from Martin, survey received, not photos received. 3/7; AC SENT TO PRICING. |  |  |  |  | 9 | [10 empty] | 1 | [10 empty] | Jammer System |  | DOOR JAMMER REQUIRED.
9 |  | 65373 |  | SENT FOR PRICING |  | 2 | Cosford Crescent | Birmingham |  | B35 6QE |  | Ms S Bills | 01215725293 | 07519 750 875 | SamanthaBills755@gmail.com |  | Windows & Doors | M Turpin | 2024-06-10 | 8am to 2pm |  |  | 31/05 SMS called N/A. 03/06 SMS called N/A Lttr sent. 17/6; AC chased photos. 21/6/2024 AC SENT FOR PRICING. |  |  |  |  | 6 | [10 empty] | 1 |  | 1
9 |  | 70240 |  | SENT FOR PRICING |  | FLAT 12 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss T Heathcote |  | 07938 590 661 | tracy.hat@blueyonder.co.uk |  | Windows & Doors | M Turpin | 2024-06-06 | 8am to 2pm |  |  | (Access via 8 Cosford & 2 Abingdon) 20/05 SMS text sent for 06/06. CONFIRMED for 06/06. 20/6/2024; AC sent to pricing. | [28 empty] | Acess via 8 Cosford & 2 Abingdon | [11 empty] | (Access via 8 Cosford & 2 Abingdon)
9 |  | 59739 |  | SENT FOR PRICING |  | 1 | Donibristle Croft | Birmingham |  | B35 6BL |  | Mrs L Hughes | 01217486954 | 07359072372 |  |  | Windows & Doors | M Turpin | 2024-05-15 |  |  |  | TS-03/05/24 Text sent offering 15/05/24. TS-03/05/24 Survey CONFIRMED for 15/05/24.
9 |  | 55686 |  | SENT FOR PRICING |  | 5 | Donibristle Croft | Birmingham |  | B35 6BL |  | Mrs L C Rogers | 07445263092 |  | lroje@aol.com |  | Windows & Doors | M Turpin | 2024-05-16 |  |  |  | TS-03/05/24 Text sent for 16/05/24. TS-03/05/24 Survey CONFIRMED for 16/05/24. |  |  |  |  | 9 | [10 empty] | 1 |  | 1 | [5 empty] | 1
9 |  | 63344 |  | SENT FOR PRICING |  | 6 | Donibristle Croft | Birmingham |  | B35 6BL |  | Mr K A Omitoyin | 01217494442 | 07877496683 |  |  | Windows & Doors | M Turpin | 2024-05-16 | 8am to 2pm |  |  | TS-03/05/24 Text sent for 16/05/24. TS-07/05/24 Ltr sent.08/05 SMS called N/A |  |  |  |  | 10 | [6 empty] | 1 |  |  |  | 1 | [7 empty] | 1
9 |  | 69334 |  | SENT FOR PRICING |  | 8 | Donibristle Croft | Birmingham |  | B35 6BL |  | Ms A Mensah | 07557792040 | 07557792040 |  |  | Windows & Doors | M Turpin | 2024-05-16 | 9am to 1pm |  |  | TS-03/05/24 Text sent for 16/05/24. TS-07/05/24 Ltr sent. CONFIRMED for 16/05/24 after 9AM |  |  |  |  | 10 | [6 empty] | 1 |  |  |  | 1 | [7 empty] | 1
9 |  | 68758 |  | SENT FOR PRICING |  | 12 | Donibristle Croft | Birmingham |  | B35 6BL |  | Mrs F Chowdhury | 07944918697 |  | chowdhuryfarhana88@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-05-16 |  |  |  | TS-03/05/24 Text sent for 16/05/24. TS-07/05/24 Survey CONFIRMED for 16/05/24. |  |  |  |  | 10 | [6 empty] | 1 |  |  |  | 1 | [7 empty] | 1
9 |  | 67512 |  | SENT FOR PRICING |  | 18 | Donibristle Croft | Birmingham |  | B35 6BL |  | Mrs S Nicholls | 01217475303 | 07307626475 |  |  | Windows & Doors | M Turpin | 2024-05-15 |  |  |  | TS-03/05/24 Text sent offering 15/05/24. TS-07/05/24 Survey CONFIRMED for 15/05/24.
9 |  | 62496 |  | SENT FOR PRICING |  | 23 | Donibristle Croft | Birmingham |  | B35 6BL |  | Mrs T Hayes |  | 07508118298 | Tammyarnold1977@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-05-15 |  |  |  | TS-03/05/24 Text sent offering 15/05/24. TS-03/05/24 Survey CONFIRMED for 15/05/24.
9 |  | 64961 |  | SENT FOR PRICING |  | 26 | Donibristle Croft | Birmingham |  | B35 6BL |  | Miss S Taylor |  | 07852810599 |  |  | Windows & Doors | M Turpin | 2024-05-16 |  |  |  | TS-03/05/24 Text sent for 16/05/24. TS-07/05/24 Survey CONFIRMED for 16/05/24.
9 |  | 63228 |  | SENT FOR PRICING |  | 28 | Donibristle Croft | Birmingham |  | B35 6BL |  | Mr V Hepburn |  | 07939 567 290 |  |  | Windows & Doors | M Turpin | 2024-05-16 | 8am to 2pm |  |  | TS-03/05/24 Text sent for 16/05/24. CONFIRMED for 16/05/24. NWR on doors tenant doesn’t want changing |  |  |  |  | 6
9 |  | 69710 |  | SENT FOR PRICING |  | 29 | Donibristle Croft | Birmingham |  | B35 6BL |  | Mrs A Bevan |  | 07816780788 |  |  | Windows & Doors | M Turpin | 2024-05-15 |  |  |  | TS-03/05/24 Text sent offering 15/05/24. TS-07/05/24 Survey CONFIRMED for 15/05/24. | *Scaffold req | [25 empty] | Independent Scaffold |  | *Scaffold req | [11 empty] | *Scaffold req
9 |  | 68228 |  | SENT FOR PRICING |  | 31 | Donibristle Croft | Birmingham |  | B35 6BL |  | Mrs N S Khdir | 07305545492 |  |  |  | Windows & Doors | M Turpin | 2024-05-15 |  |  |  | TS-03/05/24 Text sent offering 15/05/24. TS-03/05/24 Survey CONFIRMED for 15/05/24.
9 |  | 59750 |  | SENT FOR PRICING |  | 33 | Donibristle Croft | Birmingham |  | B35 6BL |  | Miss C Styche | 07856104283 |  | clairestyche@gmail.com |  | Windows & Doors | M Turpin | 2024-05-15 |  |  |  | TS-03/05/24 Text sent offering 15/05/24. TS-07/05/24 Ltr sent. 08/05 SMS left voicemail for 15/05
9 |  | 66144 |  | SENT FOR PRICING |  | 22 | Donibristle Croft | Birmingham |  | B35 6BL |  | Mrs C Brotherson | 01212930867 | 07710 599 502 |  |  | Windows & Doors | M Turpin | 2024-05-16 |  |  |  | TS-03/05/24 Text sent for 16/05/24. TS-07/05/24 Survey CONFIRMED for 16/05/24. |  |  |  |  | 5 | [10 empty] | 1 |  | 1
9 |  | 67611 |  | SENT FOR PRICING |  | 19 | Donibristle Croft | Birmingham |  | B35 6BL |  | Miss E Chick |  |  |  |  | Windows & Doors | M Turpin | 2024-05-16 | 8am to 2pm |  |  | TS-07/05/24 Ltr sent for 16/05/24.*Door choice in tray |  |  |  |  | 9 | [10 empty] | 1 |  | 1 | [5 empty] | 1 | [16 empty] | *Door choice in tray
9 |  | 69352 |  | CALLED OFF |  | 107 | Hawker Drive | Birmingham |  | B35 7EA |  | Miss D Johns |  | 077 292 55 769 | dawnjohns1963@yahoo.com |  | Windows & Doors | M Turpin | 2024-05-13 | 8am to 2pm |  |  | TS-03/05/24 Text sent for 13/05/24. TS-03/05/24 Survey CONFIRMED for 13/05/24. |  |  |  |  | 13 | [6 empty] | 1 |  |  |  | 1 | [13 empty] | PG11(W) | 2024-07-18 | 2024-08-05 | Depot | [7 empty] | *TLO to attend on fitting date
9 |  | 69507 |  | SENT FOR PRICING |  | 1 | Merlin Close | Birmingham |  | B35 7JW |  | Miss D Lewis |  | 07897 482 067 | dianelewis80@outlook.com |  | Windows & Doors | M Turpin | 2024-05-24 | 8am to 2pm |  |  | 13/05 SMS text sent for 24/05. 16/05 SMS lttr sent. 24.05.24 SF CANCELLED via phone, LM and sent text. 24.05.24 SF Martin Turpin did actually attend, his van probably got fixed quicker than he thought, he attended the proper and surveyed the doors & windows. 20/6/2024; AC sent to pricing. |  |  |  |  | 10 | [10 empty] | 1 |  | 1 | [10 empty] | PETS. Alarms fitted to doors will be removed prior to install by tenant. CCTV camera wires through frames will be removed too.
9 |  | 65275 |  | SENT FOR PRICING |  | 3 | Merlin Close | Birmingham |  | B35 7JW |  | Miss H Cother |  | 07588 615 469 | hayco79@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-06-05 | 8am to 2pm |  |  | 20/05 SMS text sent for 05/06. CONFIRMED for 05/06. 20/6/2024; AC sent to pricing. |  |  |  |  | 10 | [10 empty] | 1 |  | 1
9 |  | 70573 |  | SENT FOR PRICING |  | 5 | Merlin Close | Birmingham |  | B35 7JW |  | Miss J Wardle |  | 07506 220 380 | jenniferwardle@icloud.com |  | Windows & Doors | M Turpin | 2024-06-05 | 8am to 2pm |  |  | 20/05 SMS text sent for 05/06. CONFIRMED for 05/06 need to call tenant before attending to confirm time. 20/6/2024; AC sent to pricing. |  |  |  |  | 10 | [10 empty] | 1 |  | 1
9 |  | 68399 |  | SENT FOR PRICING |  | 7 | Merlin Close | Birmingham |  | B35 7JW |  | Mr D Milson | 0121 749 6885 |  | davidmilson2018@gmail.com |  | Windows & Doors | M Turpin | 2024-06-05 | 8am to 2pm |  |  | 20/05 SMS sent email for 05/06 to survey. 23.05.24 SF Sent another email, but the email came back undelivered, sent letter out. 20/6/2024; AC sent to pricing. |  |  |  |  | 10 | [10 empty] | 1 |  | 1 | [10 empty] | Alarms do not work and can come off windows and doors.
9 |  | 59900 |  | SENT FOR PRICING |  | 9 | Merlin Close | Birmingham |  | B35 7JW |  | Mr R Wilkes | 07717 106 818 |  | sarahoregan1@sky.com |  | Windows & Doors | M Turpin | 2024-06-05 | 8am to 2pm |  |  | 20/05 SMS text sent for 05/06. CONFIRMED for 05/06. 20/6/2024; AC sent to pricing. |  |  |  |  | 10 | [10 empty] | 1 |  | 1
9 |  | 64502 |  | SENT FOR PRICING |  | 10 | Merlin Close | Birmingham |  | B35 7JW |  | Miss E C Wilson |  | 07988 628 588 |  |  | Windows & Doors | M Turpin | 2024-06-05 | 8am to 2pm |  |  | 20/05 SMS text sent for 05/06. CONFIRMED for 05/06. 20/6/2024; AC sent to pricing. |  |  |  |  | 11 | [10 empty] | 1 |  | 1 | [10 empty] | W/C room is full of clutter and needs clearing before window can be installed.
9 |  | 69506 |  | SENT FOR PRICING |  | 11 | Merlin Close | Birmingham |  | B35 7JW |  | Miss A Taylor |  | 07930 525 324 | allytaylor2020@icloud.com |  | Windows & Doors | M Turpin | 2024-06-05 | 8am to 2pm |  |  | 20/05 SMS text sent for 05/06. CONFIRMED for 05/06. 20/6/2024; AC sent to pricing. |  |  |  |  | 10 | [10 empty] | 1 |  | 1 | [10 empty] | Rubbish to side elevation to be cleared before installation.
9 |  | 69537 |  | SENT FOR PRICING |  | 3 | Montrose Drive | Birmingham |  | B35 6DH |  | Miss K Eyles |  | 07949994313 | katieleigheyles@outlook.com |  | Windows & Doors | M Turpin | 2024-06-12 | 8am to 2pm |  |  | 10/06 SMS text sent for 12/06. CONFIRMED for 12/06. 24.06.24 SF Cleansed by Darren, sent for pricing to Dawn. |  |  |  |  | 4 | [10 empty] | 1
9 |  | 69489 |  | SENT FOR PRICING |  | 5 | Montrose Drive | Birmingham |  | B35 6DH |  | Miss R Pilawski |  | 07860824519 | xox_bex_xox@hotmail.com |  | Windows & Doors | M Turpin | 2024-06-12 | 8am to 2pm |  |  | 10/06 SMS text sent for 12/06. CONFIRMED for 12/06. 24.06.24 SF Cleansed by Darren, sent for pricing to Dawn. |  |  |  |  | 4 | [10 empty] | 1
9 |  | 59904 |  | SENT FOR PRICING |  | 12 | Montrose Drive | Birmingham |  | B35 6DH |  | Mr S Walker |  | 07783756626 | swalker12@talktalk.net |  | Windows & Doors | M Turpin | 2024-06-12 | 8am to 2pm |  |  | 10/06 SMS text sent for 12/06. CONFIRMED for 12/06. 24.06.24 SF Cleansed by Darren, sent for pricing to Dawn.
9 |  | 61780 |  | SENT FOR PRICING |  | 15 | Montrose Drive | Birmingham |  | B35 6DH |  | Mr D R Branson |  |  |  |  | Windows & Doors | M Turpin | 2024-06-12 | 8am to 2pm |  |  | CONFIRMED for 12/06. 24.06.24 SF Cleansed by Darren, sent for pricing to Dawn. |  |  |  |  | 4 | [10 empty] | 1
9 |  | 56205 |  | SENT FOR PRICING |  | FLAT 2 Block 1 | Montrose Drive | Castle Vale |  | B35 6DH | Flat | Mrs B Mosson | 0121 748 6377 |  |  |  | Windows & Doors | M Turpin | 2024-06-20 | 8am to 2pm |  |  | 24.06.24 SF Received top sheet from Martin, survey received waiting for photos. Darren will query Martin top sheet regarding 8 windows & 2 doors, but the survey says 8 windows, 1 door & 1 side screen. 1/7/2024; AC SENT TO PRICING. |  |  |  |  | 8 | [12 empty] | 1 | [5 empty] | 1 |  | No | Jammer System | Brick | BUSHES NEED CUTTING BACK PRIOR TO INSTALL. | [11 empty] | Shubs over grown outside the kitchen window.
9 |  | 64975 |  | SENT FOR PRICING |  | FLAT 6 Block 1 | Montrose Drive | Castle Vale |  | B35 6DH | Flat | Mr N A Ryan | 07741 522 697 |  | Nicho_Ryan@hotmail.com |  | Windows & Doors | M Turpin | 2024-06-20 | 8am to 2pm |  |  | 11/06 text sent for 20/06. 13/06 SMS called N/A, lttr sent. 24.06.24 SF Received top sheet from Martin, survey received waiting for photos. 1/7/2024; AC SENT TO PRICING. |  |  |  |  | 7 | [20 empty] | No | Independent Scaffold | Brick | SCAFFOLD.
9 |  | . |  | SENT FOR PRICING | Asbestos Report Required | Communals 1 - 7 | Northolt Drive | Birmingham |  | B35 6QX | [6 empty] | Windows & Doors | S Burgess | 2024-04-16 |  |  |  | TS-29/04/24 Survey cleansed and sent for pricing. 28/05 SMS Neil amended survey, scanned through for pricing. |  |  |  |  | 4 | [20 empty] | No | Jammer System | Brick | 2nd floor window remove sash and fit with door jammer
9 |  | . |  | SENT FOR PRICING | Asbestos Report Required | Communals 2 - 8 | Northolt Drive | Birmingham |  | B35 6QX | [6 empty] | Windows & Doors | [5 empty] | TS-29/04/24 Survey cleansed and sent for pricing. 28/05 SMS Neil amended survey, scanned through for pricing. |  |  |  |  | 4 | [20 empty] | No | Jammer System | Brick | 2nd floor window remove sash and fit with door jammer
9 |  |  |  | SENT FOR PRICING |  | Communal 34 - 40 | Northolt Drive | Birmingham |  | B35 6QX | [6 empty] | Windows & Doors | S Burgess | 2024-04-24 |  |  |  | TS-30/04/24 Survey received and passed to DA to cleanse.28/05 SMS Neil amended survey, scanned through for pricing. |  | Yes |  |  | 4
9 |  |  |  | SENT FOR PRICING |  | Communals 27 - 33 | Northolt Drive | Birmingham |  | B35 6QX | [6 empty] | Windows & Doors | S Burgess | 2024-04-23 |  |  |  | TS-30/04/24 Survey received and passed to DA to cleanse.28/05 SMS Neil amended survey, scanned through for pricing. |  | Yes |  |  | 4 | [6 empty] | `
9 |  | 69576 |  | SENT FOR PRICING |  | FLAT 33 | Northolt Drive | Birmingham |  | B35 6QX | Flat | Miss S McClune |  | 07392 784 074 | shakhmcc1@gmail.com |  | Windows & Doors | S Burgess | 2024-04-23 | 11am to 3pm |  |  | TS-12/04/24 Text sent for 23/04/24. TS-18/04/24 Called tenant no answer text & ltr sent for 23/04/24. TS-30/04/24 Survey received and passed to DA to cleanse.28/05 SMS Neil amended survey, scanned through for pricing. 21/6/2024 AC sent to re-pricing. |  | Yes |  |  | 5 | [5 empty] | 1 | [12 empty] | 1 |  |  | Independent Scaffold | Brick | SCAFFOLD - wheel/pulley - 2nd Floor flat - Acess via 18 Mere Avenue & 25 Northolt Drive | [11 empty] | Await scaffold quote. SCAFFOLD REQUIRED
9 |  | 63212 |  | SENT FOR PRICING |  | FLAT 31 | Northolt Drive | Birmingham |  | B35 6QX |  | Mr M Phillips |  | 07598 421 064 |  |  | Windows & Doors | S Burgess | 2024-06-18 |  |  | 1 | TS-12/04/24 Text sent for 23/04/24. TS-18/04/24 Text sent cancelling the survey of 23/04/24 and offering 14/05/24. 08/05 SMS left voicemail for 14/05. 15/05 SMS srvey no access on 14/05 at 9.20am client emailed. 04/06 SMS text sent for 18/06. 11/06 SMS left voicemail. 13/06 SMS called N/A Lttr sent. 1/7/2024; AC SENT TO PRICING. |  |  |  |  | 6 | [5 empty] | 1 | [15 empty] | Independent Scaffold |  | Access via 18 Mere Avenue & 25 Northolt Drive. SCAFFOLD.
9 |  | 70337 |  | SENT FOR PRICING |  | 20 | Northolt Drive | Birmingham |  | B35 6QX |  | Miss T Benjamin | 07507 642 265 | 07464732550 | tlb2001@hotmail.co.uk |  | Windows & Doors | S Burgess | 2024-06-18 |  |  |  | TS-04/04/24 Text sent for 19/04/24. TS-08/04/24 Tenant text back no, replied asking what days are better. TS-08/04/24 Tenant called she is away from 15/04 to 29/04 and she is only available after 1pm.04/06 SMS text sent for 18/06. CONFIRMED for 18/06. 1/7/2024; AC SENT TO PRICING. |  |  |  |  | 4 | [10 empty] | 1 |  | 1
9 |  | 65945 |  | SENT FOR PRICING |  | FLAT 36 | Northolt Drive | Birmingham |  | B35 6QX |  | Miss K Taylor |  | 07857 917 151 |  |  | Windows & Doors | S Burgess | 2024-06-18 | 8am to 12 noon |  | 2 | TS-15/04/24 Text sent for 24/04/24. TS-18/04/24 Called left vm, text & ltr sent. TS-25/04/24 No access for survey 24/04/24 carded @ 10.50am - emailed client to advise. 23.05.24 SF Sent text for 07.07 to survey.23.05.24 29/05 SMS left voicemail. 30/05 SMS called N/A lttr sent. 10/06 SMS 2nd no access survey on 07/06 @8.35am, emailed client to advise and to arrange access on new date 18/06. 11/06 SMS text sent for 18/06. 1/7/2024; AC SENT TO PRICING. |  |  |  |  | 4 | [21 empty] | Independent Scaffold |  | Access via 32 Northolt Drive & 20 Mere Avenue. NO SOLVENT. SCAFFOLD IN GROUNDS OF NUMBER 20. | [11 empty] | (Access via 32 Northolt Drive & 20 Mere Avenue.) *No solvent
9 |  | 61450 |  | SENT FOR PRICING |  | 6 | School Close | Birmingham |  | B35 7NU |  | Mrs D Price | CARER; 07463 427 409 |  |  |  | Windows & Doors | M Turpin | 2024-06-06 | 8am to 2pm |  |  | 20/05 SMS text sent for 06/06.CONFIRMED for 06/06. 20/6/2024; AC sent to pricing. |  |  |  |  | 5 | [10 empty] | 1 |  | 1 | [10 empty] | WILL NEED TLO TO HELP MOVE ITEMS. TENANT SUFFERS MOBILITY ISSUES.
9 |  | 68733 |  | SENT FOR PRICING |  | 12 | School Close | Birmingham |  | B35 7NU |  | Mrs P Sinclair |  | 07949 806 674 | sinclair580@btinternet.com |  | Windows & Doors | M Turpin | 2024-06-06 | 8am to 2pm |  |  | 20/05 SMS sent email for 06/06 to survey. 23.05.24 SF Sent another email, tenant called and CONFIRMED for 06.06 to survey. 20/6/2024; AC sent to pricing. |  |  |  |  | 5 | [10 empty] | 1 |  | 1 | [10 empty] | PETS.
9 |  | 70757 |  | SENT FOR PRICING |  | 14 | School Close | Birmingham |  | B35 7NU |  | Miss J Harris | 0121 537 4644 | 07517 434 464 |  |  | Windows & Doors | M Turpin | 2024-06-06 | 8am to 2pm |  |  | 20/05 SMS text sent for 06/06. CONFIRMED for 06/06. 20/6/2024; AC sent to pricing. |  |  |  |  | 5 | [10 empty] | 1 |  | 1
9 |  | 69906 |  | SENT FOR PRICING |  | 2 | St Athan Croft | Birmingham |  | B35 7LS |  | Mr J C Thompson | 07860 550 452 |  | joethompson-88@hotmail.com |  | Windows & Doors | M Turpin | 2024-06-06 | 8am to 2pm |  |  | 23/05 SMS Lttr sent for 06/06. 20/6/2024; AC sent to pricing. |  |  |  |  | 10 | [10 empty] | 1 |  | 1
9 |  | 70377 |  | SENT FOR PRICING | Electrician Required | 86 | Watton Green | Birmingham |  | B35 7JR |  | Miss L E Oldham | 07535 616 416 |  | lyssa_oldham@yahoo.co.uk |  | Windows & Doors | M Turpin | 2024-05-23 | 8am to 2pm |  |  | 13/05 SMS lttr sent for 23/05. 24.05.24 SF Martin Turpin attended, received top sheet, survey sent for cleansing, doors & windows, surveyed awaiting photos. 20/6/2024; AC sent to pricing but passed back to DA to check if electrician is actually required. If so, he needs to find one and get a quote. |  |  |  |  | 11 | [6 empty] | 1 |  |  |  | 1 |  | 1 | [10 empty] | Electrician Required
9 |  | 64575 |  | SENT FOR PRICING | Electrician Required | 88 | Watton Green | Birmingham |  | B35 7JR |  | Mr P Nicholas | 01217494548 | 07868 348 313 |  |  | Windows & Doors | M Turpin | 2024-05-23 | 8am to 2pm |  |  | 13/05 SMS text sent for 23/05. CONFIRMED for 23/05. 24.05.24 SF Martin Turpin attended, received top sheet, survey sent for cleansing, doors & windows, surveyed awaiting photos. 20/6/2024; AC sent to pricing but passed back to DA to check if electrician is actually required. If so, he needs to find one and get a quote. |  |  |  |  | 11 | [6 empty] | 1 |  |  |  | 1 |  | 1 | [10 empty] | Electrician Required
9 |  | 56840 |  | SENT FOR PRICING | Electrician Required | 92 | Watton Green | Birmingham |  | B35 7JR |  | Mr A Russon | 7474 341 776 or 021 7492185 | 7891567847 |  |  | Windows & Doors | M Turpin | 2024-05-23 | 8am to 2pm |  |  | 13/05 SMS text sent for 23/05. 15/05 SMS left voicemail. CONFIRMED for 23/05. 24.05.24 SF Martin Turpin attended, received top sheet, survey sent for cleansing, doors & windows, surveyed awaiting photos. 20/6/2024; AC sent to pricing but passed back to DA to check if electrician is actually required. If so, he needs to find one and get a quote. . |  |  |  |  | 11 | [6 empty] | 1 |  |  |  | 1 |  | 1 | [10 empty] | Electrician Required
9 |  | 67626 |  | SENT FOR PRICING |  | 132 | Watton Green | Birmingham |  | B35 7JT |  | Mrs MT Butcher | 01217485045 | 07947 397 800 | theresa.butcher@hotmail.co.uk or steve82but@yahoo.co.uk |  | Windows & Doors | M Turpin | 2024-05-24 | 8am to 2pm |  |  | 13/05 SMS text sent for 24/05. CONFIRMED for 24/05. 24.05.24 SF CANCELLED via phone, tenant not happy, she booked time off work. 24.05.24 SF Martin Turpin did actually attend, his van probably got fixed quicker than he thought, he attended the proper and surveyed the doors & windows. 20/6/2024; AC sent to pricing. |  |  |  |  | 9 | [10 empty] | 1 |  | 1
9 |  | 60113 |  | SENT FOR PRICING |  | 134 | Watton Green | Birmingham |  | B35 7JT |  | Mrs A Maglie |  | 07379 130 013 | angelamaglie@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-05-24 | 8am to 2pm |  |  | 13/05 SMS text sent for 24/05. CONFIRMED for 24/05 Between 8 - 10am pls. 24.05.24 SF CANCELLED via phone, LM and sent a text. 24.05.24 SF Martin Turpin did actually attend, his van probably got fixed quicker than he thought, he attended the proper and surveyed the doors & windows. 20/6/2024; AC sent to pricing. |  |  |  |  | 10 | [10 empty] | 1 |  | 1
9 |  | 66021 |  | SENT FOR PRICING | Asbestos removal req'd? | 27 | Watton Green | Birmingham |  | B35 7JS | House | Miss DA Hope | 01215373224 | 07969 774 937 | maccaboo@live.com |  | Windows & Doors | M Turpin | 2024-05-02 | 8am to 2pm |  |  | TS-24/04/24 Called no answer unable to leave vm, ltr sent. TS-01/05/24 DM did a site visit and tenant has CONFIRMED and number updated. TS-03/05/24 Survey received photosm to follow. Kitchen door UPVC about 4 years old NWR.20/6/2024 AC sent to pricing. |  |  |  |  | 7 | [6 empty] | 1 |  |  |  | 1 |  | 1 | [7 empty] | No | Jammer System |  | Possible asbestos removal to panel in small bed.
9 |  | 67689 |  | SENT FOR PRICING | Asbestos removal req'd? AND Lintel req'd | 42 | Watton Green | Birmingham |  | B35 7JP |  | Miss C Hatton | 7909 153 474 | 07526178752 - don't use | cobyjanehatton@yahoo.com |  | Windows & Doors | M Turpin | 2024-05-07 | 8am to 2pm |  |  | TS-25/04/24 Text sent for 07/05/24. TS-26/04/24 Survey CONFIRMED for 07/05/24. 20/6/2024 AC sent to re-pricing. | [25 empty] | Yes |  |  | Possible asbestos soffit removal required in porch and lintel repair needed.
9 |  | 64539 |  | SENT FOR PRICING |  | 44 | Watton Green | Birmingham |  | B35 7JP |  | Mrs K Guest | 7708 386 172 | 07340357377 - nis | Kimmywinna66@icloud.com |  | Windows & Doors | M Turpin | 2024-05-07 | 8am to 2pm |  |  | TS-25/04/24 Text sent for 07/05/24. TS-29/04/24 Called tenant number nis letter sent offering 07/05/24. TS-01/05/24 Tenant called survey CONFIRMED for 07/05/24 as first call numeber updated. 23.05.24 SF Sent to Dawn for pricing. 20/6/2024 AC sent to re-pricing.
9 |  | 68413 |  | SENT FOR PRICING | Electrician Required | 68 | Watton Green | Birmingham |  | B35 7JP |  | Mrs R Mohamed |  | 07405 163 499 |  |  | Windows & Doors | M Turpin | 2024-05-07 | 8am to 2pm |  |  | TS-25/04/24 Text sent for 07/05/24. TS-30/04/24 Survey CONFIRMED for 07/05/24. 20/6/2024 AC sent to pricing but passed back to DA to check if electrician is actually required. If so, he needs to find one and get a quote. |  |  |  |  | 12 | [6 empty] | 1 |  |  |  | 1 |  | 1 | [10 empty] | Electrician Required
9 |  | 63168 |  | SENT FOR PRICING | Electrician Required | 80 | Watton Green | Birmingham |  | B35 7JR |  | Mrs J Bradley |  | 07488 358 594 |  |  | Windows & Doors | M Turpin | 2024-05-07 | 8am to 2pm |  |  | TS-25/04/24 Text sent for 07/05/24. TS-26/04/24 Survey CONFIRMED for 07/05/24 after 2.30pm. 20/6/2024; AC sent to pricing but passed back to DA to check if electrician is actually required. If so, he needs to find one and get a quote. | [28 empty] | Electrician Required
9 |  | 66783 |  | SENT FOR PRICING | Asbestos removal req'd? | 35 | Watton Green | Birmingham |  | B35 7JS |  | Miss V Davies | 07753 325 107 |  | victoria.davies@sainsbury.co.uk |  | Windows & Doors | M Turpin | 2024-05-07 | 8am to 2pm |  |  | TS-25/04/24 Text sent for 07/05/24. TS-26/04/24 Survey CONFIRMED for 07/05/24. TS-07/05/24 Tenant called they have a family emergency and need to cancel - text MT. 13/05 SMS text sent for 23/05. CONFIRMED for 23/05. 22/05 SMS tenant called to cancel. 20/6/2024 AC sent to re-pricing. |  |  |  |  | 7 | [6 empty] | 1 | [5 empty] | 1 | [10 empty] | Possible asbestos to jamb.
9 |  | 67259 |  | SENT FOR PRICING |  | 136 | Watton Green | Birmingham |  | B35 7JT |  | Miss R Brown | 01214398486 | 07884 087 109 | rachelb1987@live.co.uk |  | Windows & Doors | M Turpin | 2024-06-05 | 9am to 1pm |  |  | 13/05 SMS text sent for 24/05. 13/05 SMS tenant text to decline this date. 14/05 SMS text for 05/06. CONFIRMED for 05/06 between 9am and 2pm please *Door choice form is in query box*. 20/6/2024; AC sent to pricing. 21.06.24 SF Attached amended door choice from the tenant to the survey for pricing. |  |  |  |  | 10 | [10 empty] | 1 |  | 1
9 |  | 60144 |  | SENT FOR PRICING |  | 349 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Mr P Mattey |  |  |  |  | Windows & Doors | M Turpin | 2024-06-11 | 8am to 2pm |  |  | 17/6; AC chased photos. 24.06.24 SF Cleansed by Darren, sent for pricing to Dawn. |  |  |  |  | 6 | [10 empty] | 1 |  | 1
9 |  | 69231 |  | SENT FOR PRICING |  | FLAT 339 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Mr A Rainbird |  | 07899 568 735 |  |  | Windows & Doors | M Turpin | 2024-06-11 | 8am to 2pm |  |  | (Access via 349 Yatesbury & 2 Cosford Crescent)29/05 SMS text sent for 11/06. CONFIRMED for 11/06. 17/6; AC chased photos. 24.06.24 SF Cleansed by Darren, sent for pricing to Dawn. |  |  |  |  | 5 | [23 empty] | Access via 349 Yatesbury & 2 Cosford | [11 empty] | (Access via 349 Yatesbury & 2 Cosford Crescent)
9 |  | 69638 |  | SENT FOR PRICING |  | FLAT 341 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Mr G Walton |  | 07443730616 | gareth.walton1988@icloud.com |  | Windows & Doors | M Turpin | 2024-06-11 | 8am to 2pm |  |  | (Access via 349 Yatesbury & 2 Cosford Crescent)29/05 SMS text sent for 11/06. CONFIRMED for 11/06. 17/6; AC chased photos. 24.06.24 SF Cleansed by Darren, sent for pricing to Dawn. |  |  |  |  | 7 | [23 empty] | Access via 349 Yatesbury & 2 Cosford | [11 empty] | (Access via 349 Yatesbury & 2 Cosford Crescent)
9 |  | 67682 |  | SENT FOR PRICING |  | 327 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Mrs A Clarke |  | 07838 705 905 | annie-clarke@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-06-10 | 8am to 2pm |  |  | 29/05 SMS text sent for 10/06. CONFIRMED for 10/06. 17/6; AC chased photos. 21/6/2024 AC sent for pricing. |  |  |  |  | 6 | [10 empty] | 1 |  | 1
9 |  | 63710 |  | SENT FOR PRICING |  | FLAT 329 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Miss S L Reid | 0121 730 2729 | 07977 348 224 | Louisejet@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-06-10 | 8am to 2pm |  |  | (Access via 327 Yatesbury & 1 Cosford Crescent)29/05 SMS text sent for 10/06. 31/05 SMS called N/A. CONFIRMED for 10/06. 17/6; AC chased photos. 21/6/2024 AC SENT FOR PRICING. |  |  |  |  | 5 | [5 empty] | 2 | [15 empty] | Independent Scaffold |  | DOG. SCAFFOLD. | [11 empty] | (Access via 327 Yatesbury & 1 Cosford Crescent). Await scaffold quote. SCAFFOLD REQUIRED.
9 |  | 70004 |  | SENT FOR PRICING |  | FLAT 333 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Miss K Welburn |  | 07460 716 756 | kayleighwelburn@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-06-10 | 8am to 2pm |  |  | (Access via 327 Yatesbury & 1 Cosford Crescent)29/05 SMS text sent for 10/06. CONFIRMED for 10/06. 17/6; AC chased photos. 21/6/2024 AC SENT FOR PRICING. | [26 empty] | Independent Scaffold |  | SCAFFOLD. | [11 empty] | (Access via 327 Yatesbury & 1 Cosford Crescent). Await scaffold quote. SCAFFOLD REQUIRED.
7 |  | 59667 |  | AWAIT CLIENT APPROVAL |  | 64 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mr J Daly | 01217767133 | 07982 712 498 | Jd2ippy@hotmail.com |  | Windows & Doors | M Turpin | 2024-06-24 | 8am to 2pm |  |  | 13.06.24 SF sent text for survey on the 24.06.24, waiting confirmation. 18.06.24 SF LM again & sent letter. 3/7; AC sent to PM to cleanse. 10/7/2034; AC sent to pricing. |  |  |  |  | 7 | [12 empty] | 1 | [10 empty] | Wires through rear door and tenant advised he will remove them.
9 |  | 70486 |  | SENT FOR PRICING |  | FLAT 44 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss C Hassall | 07821 914 116 |  | charlie.hassall@yahoo.com |  | Windows & Doors | M Turpin | 2024-06-24 | 8am to 2pm |  |  | (Access via 30 & 46 Cosford Crescent). 13.06.24 SF sent text for survey on the 24.06.24, tenant text back, but hasn't confirmed the survey date. 18.06.24 SF Tenant CONFIRMED between 12pm - 1pm, surveyor to call 30min prior and she'll leave work during her lunch break to come home and give access. 3/7; AC sent to PM to cleanse. 10/7/2034; AC sent to pricing. |  |  |  |  | 5 | [5 empty] | 1 | [12 empty] | 2 |  |  | Independent Scaffold |  | Access via 30 & 46 Cosford Crescent. PETS. SCAFFOLD.
7 |  | 59668 |  | AWAIT CLIENT APPROVAL |  | FLAT 66 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mr H Troman | 0121 748 2984 |  |  |  | Windows & Doors | M Turpin | 2024-06-24 | 8am to 2pm |  |  | 13.06.24 SF No contact number, email address undelivered, sent letter out, waiting confirmation. 18.06.24 SF Sent another letter. 3/7; AC sent to PM to cleanse. 10/7/2034; AC sent to pricing. |  |  |  |  | 5 | [5 empty] | 2 | [17 empty] | Access via 64 Cosford & 21 Cranwell Way. COPD.
7 |  | 70277 |  | AWAIT CLIENT APPROVAL |  | FLAT 76 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss D Broderick |  | 07947 630 130 | DBroderick@live.co.uk |  | Windows & Doors | M Turpin | 2024-06-25 | 8am to 2pm |  |  | 14/06 SMS text sent for 25/06. CONFIRMED for 25/06.25/06 SMS I have just had a call from the contact we have been given for this address, she moved out 10 years ago and is now living on Viscount Close, i have emailed the client to request upto date tenant information for the below address so we can update the old details provided. 10/7/2034; AC sent to pricing. |  |  |  |  | 6 | [5 empty] | 1 | [17 empty] | Access via 64 Cosford & 21 Cranwell Way
9 |  | 69196 |  | SENT FOR PRICING | Survey Rec'd, awaiting photos | 2 | Cranwell Way | Birmingham |  | B35 6QH | Flat | Mr RA Mitchell | 07518 496 711 | Carer Sandra 07518 496 711 |  |  | Windows & Doors | M Turpin | 2024-06-25 | First Call |  |  | Access via 2 Cranwell & 381 Yatesbury. 14/06 SMS text sent for 25/06. CONFIRMED for 25/06 first call please. 12.07.24 SF Sent for pricing. |  |  |  |  | 6 | [10 empty] | 1 |  | 1 | [10 empty] | Mobility issues. Has a carer.
9 |  | 67030 |  | SENT FOR PRICING |  | 2 | Drem Croft | Birmingham |  | B35 7HW |  | Ms J Sheridan |  | 07752 744 103 | juliesheridan712@gmail.com |  | Windows & Doors | M Turpin | 2024-06-27 | 8am to 2pm |  |  | 14/06 SMS text sent for 27/06. 19/6; AC rang and confirmed survey 27/6. 10/7/2034; AC sent to pricing. |  |  |  |  | 7 | [6 empty] | 1 |  |  |  | 1 |  | 1
9 |  | 69569 |  | SENT FOR PRICING |  | 4 | Drem Croft | Birmingham |  | B35 7HW |  | Mrs H Symonds |  | 07754 122 094 |  |  | Windows & Doors | M Turpin | 2024-06-27 | 8am to 2pm |  |  | 14/06 SMS text sent for 27/06. CONFIRMED for 27/06. 27.06.24 SF Tenant called, she's just arrived home from her holiday, can't do the survey today, re-booked for 01.07.24 and CONFIRMED we can attend. MARTIN KNIOCKED DOOR AND DID SURVEY ANYWAY. . 10/7/2034; AC sent to pricing. |  |  |  |  | 7 | [6 empty] | 1 |  |  |  | 1 |  | 1 | [10 empty] | PETS. DIRTY HOUSE, SMELLS OF CAT WEE.
7 |  | 60276 |  | AWAIT CLIENT APPROVAL |  | 381 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Mr G Wilkes |  | 07444 577 903 |  |  | Windows & Doors | M Turpin | 2024-06-26 | 8am to 2pm |  |  | 13/06 SMS text sent for 26/06. CONFIRMED for 26/06. 28.06.24 SF Surveys received from Martin, still waiting photos. 3/7; AC SENT TO PM TO CLEANSE. 10/7/2024; AC sent to pricing. |  |  |  |  | 7 | [10 empty] | 1 |  | 1 | [10 empty] | Dirty flat, dog wee on floor. PETS.
7 |  | 68588 |  | AWAIT CLIENT APPROVAL |  | FLAT 365 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Mr J Donnelly |  | 07394 020 678 | jamesdonnelly179@gmail.com |  | Windows & Doors | M Turpin | 2024-06-26 | 8am to 2pm |  |  | 13/06 SMS text sent for 26/06. CONFIRMED for 26/06. 3/7; AC SENT TO PM TO CLEANSE. 10/7/2024; AC sent to pricing. |  |  |  |  | 5 | [5 empty] | 2 | [17 empty] | Access via 1 Cranwell & 363 Yatesbury
7 |  | 62667 |  | AWAIT CLIENT APPROVAL |  | FLAT 367 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Mr J Smith | 0121 748 6274 | 07858 350 344 | Jaystorm74@hotmail.com |  | Windows & Doors | M Turpin | 2024-06-26 | 8am to 2pm |  |  | 19/06 SMS called N/A Lttr sent. 28.06.24 SF Surveys received from Martin, still waiting photos. 3/7; AC SENT TO PM TO CLEANSE. 10/7/2024; AC sent to pricing. |  |  |  |  | 5 | [5 empty] | 1 | [12 empty] | 1 |  |  |  |  | Access via 1 Cranwell & 363 Yatesbury
7 |  | 61672 |  | AWAIT CLIENT APPROVAL |  | FLAT 369 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Miss A Ward |  | 07460 550 187 | adrianholloway311@outlook.com |  | Windows & Doors | M Turpin | 2024-06-26 | 8am to 2pm |  |  | 13/06 SMS text sent for 26/06. 19/06 SMS left voicemail. 3/7; AC SENT TO PM TO CLEANSE. 10/7/2024; AC sent to pricing. |  |  |  |  | 5 | [5 empty] | 2 | [17 empty] | Access via 1 Cranwell & 363 Yatesbury
7 |  | 66071 |  | AWAIT CLIENT APPROVAL |  | FLAT 373 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Mr GA Tucker |  | 07895 025 893 | garytucker4321@gmail.co.uk |  | Windows & Doors | M Turpin | 2024-06-26 | 8am to 2pm |  |  | 19/06 SMS called no. NIS lttr sent. 3/7; AC SENT TO PM TO CLEANSE. 10/7/2024; AC sent to pricing. |  |  |  |  | 5 | [5 empty] | 2 | [17 empty] | Access via 2 Cranwell & 381 Yatesbury
7 |  | 65186 |  | AWAIT CLIENT APPROVAL |  | FLAT 377 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Mr R Riddell | 0121 747 5544 | 07958 186 063 |  |  | Windows & Doors | M Turpin | 2024-06-26 | 8am to 2pm |  |  | 19/06 SMS called no. NIS lttr sent. 28.06.24 SF Surveys received from Martin, still waiting photos. 3/7; AC SENT TO PM TO CLEANSE. 10/7/2024; AC sent to pricing. |  |  |  |  | 5 | [5 empty] | 2 | [17 empty] | Access via 2 Cranwell & 381 Yatesbury
7 |  | 60161 |  | AWAIT CLIENT APPROVAL |  | FLAT 379 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Mr K Woolley | 0121 749 3031 | 07479 550 144 | kevin.woolley3@gmail.com |  | Windows & Doors | M Turpin | 2024-06-26 | 8am to 2pm |  |  | 13/06 SMS text sent for 26/06. CONFIRMED for 26/06. 3/7; AC SENT TO PM TO CLEANSE. 10/7/2024; AC sent to pricing. |  |  |  |  | 6 | [5 empty] | 1 | [12 empty] | 1 |  |  |  |  | Access via 2 Cranwell & 381 Yatesbury. BOILER FLUE THROUGH PANEL.
9 |  | 68497 |  | SENT FOR PRICING |  | FLAT 2 Block 33 | Concorde Drive | Castle Vale |  | B35 7EE | Flat | Mrs P Burden |  | 07729029722 |  |  | Windows & Doors | M Turpin | 2024-06-19 | 8am to 2pm |  |  | 05/06 SMS text sent for 19/06. 11/06 SMS left voicemail. 13/06 SMS spoke to Miss M Proffitt who advise not at this address as house swapped. Emailed client to get new details before we schedule a survey.13/06client advise new tenant details, SMS text sent for 19/06. CONFIRMED for 19/06. 21.06.24 SF Received top sheet from Martin, survey received, waiting for photos. 10/7/2024; AC sent to pricing. |  |  |  |  | 8 | [22 empty] | Brick
9 |  | 67962 |  | SENT FOR PRICING |  | FLAT 4 Block 33 | Concorde Drive | Castle Vale |  | B35 7EE | Flat | Mrs S Mohammad | 07479559511 |  | shahen452@hotmail.com |  | Windows & Doors | M Turpin | 2024-06-19 | 8am to 2pm |  |  | 05/06 SMS text sent for 19/06.CONFIRMED for 19/06. 21.06.24 SF Received top sheet from Martin, survey received, photos waiting for. 10/7/2024; AC sent to pricing. |  |  |  |  | 7 | [12 empty] | 1
9 |  | 70286 |  | SENT FOR PRICING |  | FLAT 5 Block 33 | Concorde Drive | Castle Vale |  | B35 7EE | Flat | Miss D Styche |  | 07512756223 | dolciestyche@icloud.com |  | Windows & Doors | M Turpin | 2024-06-19 | 8am to 2pm |  |  | 05/06 SMS text sent for 19/06. 11/06 SMS called no. NIS lttr sent. 21.06.24 SF Received top sheet from Martin, survey received, photos waiting for, independent scaffold required. 10/7/2024; AC sent to pricing. |  |  |  |  | 7 | [12 empty] | 1 | [8 empty] | Independent Scaffold | Brick | [12 empty] | Awaiting quote SCAFFOLD REQUIRED :-
9 |  | 64884 |  | SENT FOR PRICING |  | FLAT 6 Block 33 | Concorde Drive | Castle Vale |  | B35 7EE | Flat | Miss L Pettitt |  | 07982 174 217 |  |  | Windows & Doors | M Turpin | 2024-06-19 | PM |  |  | 05/06 SMS text sent for 19/06. 11/06 SMS left voicemail. CONFIRMED for 19/06 after 12noon pls. 21.06.24 SF Received top sheet from Martin, survey received waiting for photos, independent scaffold required. 10/7/2024; AC sent to pricing. |  |  |  |  | 7 | [12 empty] | 1 | [8 empty] | Independent Scaffold | Brick | [12 empty] | Awaiting quote SCAFFOLD REQUIRED :-
7 |  | 61359 |  | AWAIT CLIENT APPROVAL |  | 11 | Concorde Drive | Birmingham |  | B35 7EE |  | Miss S Strachan |  | 07811487664 | sharonbrown1970@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-06-18 | 8am to 2pm |  |  | 04/06 SMS text sent for 18/06. CONFIRMED for 18/06. 20.06.24 SF Received top sheet from Martin, survey received, not photos received. 10/7/2024; AC sent to pricing.
9 |  | 62358 |  | SENT FOR PRICING |  | FLAT 1 Block 64 | Heyford Way | Castle Vale |  | B35 6HU |  | Mr J I Mitchell |  | 07828 777 910 | jim.mitchell38@live.com | Breathing Difficulties | Windows & Doors | P Beahan | 2024-04-16 | 8am to 12 noon |  |  | TS-04/04/24 Text sent for 16/04/24. TS-045/04/24 Survey CONFIRMED for 16/04/24. TS-15/04/24 Door choice emailed to client.. 10/7/2034; AC sent to pricing. |  |  |  |  | 7 | [6 empty] | 1 | [14 empty] | Independent Scaffold |  | Astma no solvents. *Scaffold req for whole block 64* | [11 empty] | Astma no solvents
9 |  | 69761 |  | SENT FOR PRICING |  | FLAT 2 Block 64 | Heyford Way | Castle Vale |  | B35 6HU |  | Mr C Hosef |  | 07495 270 872 |  |  | Windows & Doors | P Beahan | 2024-04-16 | 8am to 12 noon |  |  | TS-04/04/24 Text sent for 16/04/24. TS-08/04/24 Called tenant and he hung up, sent text and letter offering 16/04/24. TS-08/04/24 Survey CONFIRMED for 16/04/24.. 10/7/2034; AC sent to pricing. |  |  |  |  | 7 | [6 empty] | 1 | [14 empty] | Independent Scaffold |  | *Scaffold req for whole block 64*
9 |  | 63840 |  | SENT FOR PRICING |  | FLAT 5 Block 64 | Heyford Way | Castle Vale |  | B35 6HU |  | Miss S Benjamin |  | 07548 670 282 |  |  | Windows & Doors | P Beahan | 2024-04-16 | 8am to 12 noon |  |  | TS-04/04/24 Text sent for 16/04/24. TS-08/04/24 Called tenant survey CONFIRMED for 16/04/24.. 10/7/2034; AC sent to pricing. |  |  |  |  | 7 | [21 empty] | Independent Scaffold |  | *Scaffold Req for whole of block 64 | [11 empty] | *Scaffold Req for whole of block 64
9 |  | 58325 |  | SENT FOR PRICING |  | FLAT 6 Block 64 | Heyford Way | Castle Vale |  | B35 6HU |  | Mr Spragg | 0740 740 3601 |  | tonymagoo202@gmail.com |  | Windows & Doors | P Beahan | 2024-04-16 | 8am to 12 noon |  |  | TS-04/04/24 Text sent for 16/04/24. TS-08/04/24 Called left vm, txt & ltr sent for 16/04/24. TS-08/04/24 Tenant called and CONFIRMED for 16/04/24. TS-15/04/24 Door choice emailed to client.. 10/7/2034; AC sent to pricing. |  |  |  |  | 7 | [21 empty] | Independent Scaffold |  | *Scaffold req for whole block 64* | [11 empty] | *Scaffold req for whole block 64*
9 |  | 59669 |  | SENT FOR PRICING | Survey Rec'd, awaiting photos | FLAT 68 | Cosford Crescent | Birmingham |  | B35 6QE | Flat | Miss J Nicholls | 0121 748 7100 | 07931 111 161 |  |  | Windows & Doors | M Turpin | 2024-06-25 | 8am to 2pm |  |  | 14/06 SMS text sent for 25/06. CONFIRMED for 25/06. 12.07.24 SF Sent for pricing. |  |  |  |  | 6 | [5 empty] | 1 | [12 empty] | 1 |  |  |  |  | Access via 64 Cosford & 21 Cranwell Way
9 |  | 66801 |  | SENT FOR PRICING | Survey Rec'd, awaiting photos | FLAT 70 | Cosford Crescent | Birmingham |  | B35 6QE | Flat | Miss D C Jacques | 0121 572 3707 | 07889 917 444 | dcjacques@hotmail.com |  | Windows & Doors | M Turpin | 2024-06-25 | 8am to 2pm |  |  | 14/06 SMS text sent for 25/06. CONFIRMED for 25/06. 12.07.24 SF Sent for pricing. |  |  |  |  | 5 | [5 empty] | 2 | [17 empty] | Access via 64 Cosford & 21 Cranwell Way | [11 empty] | Access via 64 Cosford & 21 Cranwell Way. Balcony needs clearing/cleaning prior to install
9 |  | 69228 |  | SENT FOR PRICING | Survey Rec'd, awaiting photos | FLAT 74 | Cosford Crescent | Birmingham |  | B35 6QE | Flat | Miss T Forrester |  | 07900 023 270 | Tamaya.forrester@yahoo.co.uk |  | Windows & Doors | M Turpin | 2024-06-25 | 8am to 2pm |  |  | 14/06 SMS text sent for 25/06. CONFIRMED for 25/06. 12.07.24 SF Sent for pricing. |  |  |  |  | 6 | [5 empty] | 1 | [12 empty] | 1 |  |  | Independent Scaffold |  | Access via 64 Cosford & 21 Cranwell Way. SCAFFOLD. | [11 empty] | Access via 64 Cosford & 21 Cranwell Way. SCAFFOLD.
9 |  | 68039 |  | SENT FOR PRICING | Survey Rec'd, awaiting photos | 1 | Cranwell Way | Birmingham |  | B35 6QH | Flat | Mr T Barnfield | 07967 191 780 |  | pumpuytom@hotmail.com |  | Windows & Doors | M Turpin | 2024-06-25 | 8am to 2pm |  |  | Access via 1 Cranwell & 363 Yatesbury. 14/06 SMS text sent for 25/06. 18/6; AC rang and confirmed survey for after 10am. 12.07.24 SF Sent for pricing. |  |  |  |  | 6
9 |  | 59710 |  | SENT FOR PRICING | Survey Rec'd, awaiting photos | 5 | Cranwell Way | Birmingham |  | B35 6QH | Flat | Mr TJ Quinn | 07311 282 274 |  | tj.quinn@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-06-25 | 8am to 2pm |  |  | 14/06 SMS text sent for 25/06. CONFIRMED for 25/06. 12.07.24 SF Sent for pricing. |  |  |  |  | 5 | [6 empty] | 1 | [16 empty] | Uses mobility scooter.
9 |  | 66226 |  | SENT FOR PRICING |  | 363 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Mr DJ Worswick | 01215376063 | 07885 985 151 | derekworswick@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-06-26 | 8am to 2pm |  |  | 13/06 SMS text sent for 26/06. 13/06 SMS text sent for 27/06. 28.06.24 SF Surveys received from Martin, still waiting photos. Photos received. Tenant wants top openers for fresh air to help him breathe. 3/7; AC SENT TO PM TO CLEANSE. |  |  |  |  | 6 | [10 empty] | 1 | [12 empty] | Breathing difficulties - COPD.
9 |  | 63652 |  | SENT FOR PRICING |  | 1 | Coltishall Close | Birmingham |  | B35 7EF |  | Miss C Tomkins |  | 07496 782816 | twiggy143@hotmail.com |  | Windows & Doors | M Turpin | 2024-06-17 | 8am to 2pm |  |  | 03/06 SMS text sent for 17/06. CONFIRMED for 17/06. 20.06.24 SF Received top sheet from Martin, survey received, no photos yet. |  |  |  |  | 6 | [10 empty] | 1 |  | 1 | [8 empty] | Independent Scaffold |  | *Scaffold Req, quote in file | [11 empty] | *Scaffold Req, quote in file - No 1 & 3 need booking for install together due to Scaffolding
9 |  | 68262 |  | SENT FOR PRICING |  | 3 | Coltishall Close | Birmingham |  | B35 7EF |  | Miss S Ward | 07961 649 549 | 07961649549 | sarswardy@gmail.com |  | Windows & Doors | M Turpin | 2024-06-17 | 8am to 2pm |  |  | 03/06 SMS text sent for 17/06. CONFIRMED for 17/06. 20.06.24 SF Received top sheet from Martin, survey received, no photos yet. |  |  |  |  | 6 | [21 empty] | Independent Scaffold |  | *Scaffold Req, quote in file | [11 empty] | *Scaffold Req, quote in file. No 1 & 3 need booking for install together due to Scaffolding
9 |  | 69882 |  | SENT FOR PRICING |  | 5 | Coltishall Close | Birmingham |  | B35 7EF |  | Miss S Wiggett |  | 07590 912 308 | samwiggett@outlook.com |  | Windows & Doors | M Turpin | 2024-06-17 | 8am to 2pm |  |  | 03/06 SMS text sent for 17/06. CONFIRMED for 17/06. 20.06.24 SF Received top sheet from Martin, survey received, no photos yet. |  |  |  |  | 5 | [21 empty] | Independent Scaffold |  | *Scaffold Req, quote in file | [11 empty] | *Scaffold Req, quote in file
9 |  | 69755 |  | SENT FOR PRICING |  | 7 | Coltishall Close | Birmingham |  | B35 7EF | House | Miss M J Chantler |  | 07507 013 678 | mchantler@live.co.uk |  | Windows & Doors | M Turpin | 2024-06-19 | 8am to 2pm |  |  | 03/06 SMS text sent for 17/06. 17/06 SMs tenant called very upset and shouting chasing her survey, she would not let me speak when ive tried to ask what dates we can arrange this for, ref to Dominie to speak to her to arrange something, she was warned if she continued to shout over me i would end the call.Dominie arranged 19/06 direct with MT and Tenant. 21.06.24 SF Top sheet received from Martin, surveys received, waiting photos |  |  |  |  | 6 | [12 empty] | 1 | [8 empty] | Independent Scaffold | Brick | [12 empty] | *Scaffold Req
9 |  | 55656 |  | SENT FOR PRICING |  | 9 | Coltishall Close | Birmingham |  | B35 7EF |  | Miss N Horton |  | 07876 31 78 98 | nicolahorton1968@gmail.com |  | Windows & Doors | M Turpin | 2024-06-17 | 8am to 2pm |  |  | 03/06 SMS text sent for 17/06.CONFIRMED for 17/06 (No. 11 has the key). 20.06.24 SF Received top sheet from Martin, survey received, no photos yet. |  |  |  |  | 6 | [10 empty] | 1 |  | 1 | [8 empty] | Independent Scaffold |  | *Scaffold Req, quote in file | [11 empty] | *Scaffold Req, quote in file. No 9 & 11 need booking for install together due to Scaffolding
9 |  | 66813 |  | SENT FOR PRICING |  | 11 | Coltishall Close | Birmingham |  | B35 7EF |  | Mrs P Clohessy | 07596 264 656 |  | pam64@live.co.uk |  | Windows & Doors | M Turpin | 2024-06-17 |  |  |  | 06/06 SMS lttr sent for 17/06. 20.06.24 SF Received top sheet from Martin, survey received, no photos yet. |  |  |  |  | 5 | [10 empty] | 1 | [10 empty] | Independent Scaffold | Brick & Render | *Scaffold Req, quote in file | [11 empty] | *Scaffold Req, quote in file. No 9 & 11 need booking for install together due to Scaffolding
9 |  | 67314 |  | SENT FOR PRICING |  | 15 | Coltishall Close | Birmingham |  | B35 7EF |  | Miss JP Johnson | 07472 605 384 |  |  |  | Windows & Doors | M Turpin | 2024-06-17 | 8am to 2pm |  |  | 03/06 SMS text sent for 17/06. CONFIRMED for 17/06. 20.06.24 SF Received top sheet from Martin, survey received, no photos yet. |  |  |  |  | 7 | [21 empty] | Independent Scaffold |  | *Scaffold Req, quote in file | [11 empty] | *Scaffold Req, quote in file
9 |  | 63167 |  | SENT FOR PRICING | Survey Rec'd, awaiting photos | 6 | Mere Avenue | Birmingham |  | B35 6QT | House | Mrs D Tuckey |  | 07818 743 552 | donnatuckey1@icloud.com |  | Windows & Doors | P Beahan | 2024-04-22 | 8am to 12 noon |  |  | TS-12/04/24 Text sent offering 22/04/24 for survey. TS-12/04/24 Survey CONFIRMED for 22/04/24. 12.07.24 SF Sent for pricing. |  |  |  |  | 12 | [5 empty] | 1 |  |  |  |  | 1 |  | 1 | [8 empty] | Independent Scaffold | Brick | SCAFFOLD REQUIRED - Door jammer | [11 empty] | SCAFFOLD REQUIRED - Door jammer
9 |  | 62773 |  | SENT FOR PRICING | Survey Rec'd, awaiting photos | 8 | Mere Avenue | Birmingham |  | B35 6QT | House | Ms F F Benjamin | 07400919538 | 07922304111 | farrah7benjamin@yahoo.co.uk |  | Windows & Doors | P Beahan | 2024-04-22 | 8am to 12 noon |  |  | TS-12/04/24 Text sent offering 22/04/24 for survey. TS-15/04/24 Survey CONFIRMED for 22/04/24. 12.07.24 SF Sent for pricing. |  |  |  |  | 12 | [5 empty] | 1 |  |  |  |  | 1 |  | 1 | [8 empty] | Independent Scaffold | Brick | SCAFFOLD REQUIRED - Door jammer, tenant has asthma, no solvents to be used | [11 empty] | SCAFFOLD REQUIRED - Door jammer, tenant has asthma, no solvents to be used
9 |  | 70438 |  | SENT FOR PRICING | Survey Rec'd, awaiting photos | 12 | Mere Avenue | Birmingham |  | B35 6QT | House | Miss KA Buchanan |  | 07460 516 629 | katieamandab95@gmail.com |  | Windows & Doors | P Beahan | 2024-04-22 | 8am to 12 noon |  |  | TS-12/04/24 Text sent offering 22/04/24 for survey. TS-12/04/24 Survey CONFIRMED for 22/04/24. 12.07.24 SF Sent for pricing. |  |  |  |  | 12 | [5 empty] | 1 | [15 empty] | Independent Scaffold | Brick | SCAFFOLD REQUIRED - Door jammer, tenant has asthma, no solvents to be used | [11 empty] | SCAFFOLD REQUIRED - Door jammer, tenant has asthma, no solvents to be used
9 |  | 66372 |  | SENT FOR PRICING | Survey Rec'd, awaiting photos | 14 | Mere Avenue | Birmingham |  | B35 6QT | House | Ms L Cole | 07902 951 923 |  |  |  | Windows & Doors | P Beahan | 2024-04-22 | 8am to 12 noon |  |  | TS-12/04/24 Text sent offering 22/04/24 for survey. TS-12/04/24 Survey CONFIRMED for 22/04/24. 12.07.24 SF Sent for pricing. |  |  |  |  | 12 | [5 empty] | 1 |  |  |  |  | 1 |  | 1 | [8 empty] | Independent Scaffold | Brick | SCAFFOLD REQUIRED - | [11 empty] | SCAFFOLD REQUIRED -
9 |  | 68536 |  | SENT FOR PRICING | Survey Rec'd, awaiting photos | 16 | Mere Avenue | Birmingham |  | B35 6QT | House | Miss S Salmon | 07342977113 | 07473697233 | shantelsalmon22@gmail.com |  | Windows & Doors | P Beahan | 2024-04-22 | 11am to 3pm |  |  | TS-12/04/24 Text sent offering 22/04/24 for survey. TS-12/04/24 Survey CONFIRMED for 22/04/24. 12.07.24 SF Sent for pricing. |  |  |  |  | 10 | [10 empty] | 1 |  | 1 | [8 empty] | Independent Scaffold | Brick | SCAFFOLD REQUIRED - Tenant advised to isolate pet (XL Bully) during installation | [11 empty] | SCAFFOLD REQUIRED - Tenant advised to isolate pet (XL Bully) during installation
9 |  | 59861 |  | SENT FOR PRICING | Survey Rec'd, awaiting photos | 24 | Mere Avenue | Birmingham |  | B35 6QT | House | Mrs D Somers | 01214088137 | 07415 308 670 | donnas1402@icloud.com |  | Windows & Doors | P Beahan | 2024-04-23 | 8am to 12 noon |  |  | TS-12/04/24 Text sent for 23/04/24. TS-15/04/24 Survey CONFIRMED for 23/04/24. 12.07.24 SF Sent for pricing. |  |  |  |  | 12 | [5 empty] | 1 |  |  |  |  | 1 |  | 1 | [8 empty] | Independent Scaffold | Brick | SCAFFOLD REQUIRED - | [11 empty] | SCAFFOLD REQUIRED -
9 |  | 67010 |  | SENT FOR PRICING | Survey Rec'd, awaiting photos | 28 | Mere Avenue | Birmingham |  | B35 6QT | House | Mrs LM Jones | 07557 558 772 |  | l.jones844@btinternet.com |  | Windows & Doors | P Beahan | 2024-04-23 | 8am to 12 noon |  |  | TS-12/04/24 Text sent for 23/04/24. TS-15/04/24 Survey CONFIRMED for 23/04/24. 12.07.24 SF Sent for pricing. |  |  |  |  | 10 | [10 empty] | 1 | [10 empty] | Independent Scaffold | Brick | SCAFFOLD REQUIRED - | [11 empty] | SCAFFOLD REQUIRED -
9 |  | 68580 |  | SENT FOR PRICING | Survey Rec'd, awaiting photos | 30 | Mere Avenue | Birmingham |  | B35 6QT | House | Miss S A Davis | 07784 507 842 | 07481967330 | sammiiee_ann@hotmail.com |  | Windows & Doors | P Beahan | 2024-04-24 | 11am to 3pm |  |  | TS-12/04/24 Text sent for 23/04/24. TS-18/04/24 Text sent cancelling the survey of 23/04/24 and offering 13/05/24. TS-26/04/24 PB advised that he completed the survey on the 24/04/24. 12.07.24 SF Sent for pricing. |  |  |  |  | 10 | [21 empty] | Independent Scaffold | Brick | SCAFFOLD REQUIRED - | [11 empty] | SCAFFOLD REQUIRED -
9 |  | 64294 |  | SENT FOR PRICING | Survey Rec'd, awaiting photos | 32 | Mere Avenue | Birmingham |  | B35 6QT | House | Mrs H Lally | 01215375815 | 07850 323 036 | hayley_lally08@hotmail.co.uk |  | Windows & Doors | P Beahan | 2024-04-23 | 11am to 3pm |  |  | TS-12/04/24 Text sent for 23/04/24. TS-12/04/24 Tenant text back no, replied asking what days are better. TS-15/04/24 Tenant text back that they can only do after 2.30pm - replied offering them the last call of the day after 2.30pm CONFIRMED for 23/04/23. 12.07.24 SF Sent for pricing. |  |  |  |  | 10 | [21 empty] | Independent Scaffold | Brick | SCAFFOLD REQUIRED - | [11 empty] | SCAFFOLD REQUIRED -
9 |  | 70749 |  | SENT FOR PRICING | Survey Rec'd, awaiting photos | 38 | Mere Avenue | Birmingham |  | B35 6QT | House | Miss R Kirby | 07808 520 505 |  | roxanne1971@tiscili.co.uk |  | Windows & Doors | P Beahan | 2024-04-24 | 8am to 12 noon |  |  | TS-15/04/24 Text sent for 24/04/24. TS-18/04/24 Called left vm, text & ltr sent. 12.07.24 SF Sent for pricing. |  |  |  |  | 12 | [5 empty] | 1 |  |  |  |  | 1 |  | 1 | [8 empty] | Independent Scaffold | Brick | SCAFFOLD REQUIRED - | [11 empty] | SCAFFOLD REQUIRED -
9 |  | 59870 |  | SENT FOR PRICING | Survey Rec'd, awaiting photos | 40 | Mere Avenue | Birmingham |  | B35 6QT | House | Miss E Davis | 7576 487 106 |  |  |  | Windows & Doors | P Beahan | 2024-04-24 | 8am to 12 noon |  |  | TS-15/04/24 Text sent for 24/04/24. TS-18/04/24 Called left vm, text & ltr sent. 12.07.24 SF Sent for pricing. |  |  |  |  | 10 | [5 empty] | 1 | [15 empty] | Independent Scaffold | Brick | SCAFFOLD REQUIRED - | [11 empty] | SCAFFOLD REQUIRED -
9 |  | 59867 |  | SENT FOR PRICING | Survey Rec'd, awaiting photos | 34 | Mere Avenue | Birmingham |  | B35 6QT | House | Miss V Brierley | 07742 701 034 |  | vickyplj@aol.com |  | Windows & Doors | P Beahan | 2024-04-23 | 11am to 3pm |  |  | TS-12/04/24 Text sent for 23/04/24. TS-15/04/24 CONFIRMED for 23/04/24. 12.07.24 SF Sent for pricing. |  |  |  |  | 10 | [21 empty] | Independent Scaffold | Brick | SCAFFOLD REQUIRED - | [11 empty] | SCAFFOLD REQUIRED -
9 |  | 61630 |  | SENT FOR PRICING | Survey Rec'd, awaiting photos | 36 | Mere Avenue | Birmingham |  | B35 6QT | House | Mr A Gardner | 0121 747 4129 | 07464 074 493 | apg6691@gmail.com |  | Windows & Doors | P Beahan | 2024-04-23 | 11am to 3pm |  |  | TS-12/04/23 Called and left vm offering 23/04/24. 12.07.24 SF Sent for pricing. |  |  |  |  | 12 | [5 empty] | 1 |  |  |  |  | 1 |  | 1 | [8 empty] | Independent Scaffold | Brick | SCAFFOLD REQUIRED - | [11 empty] | SCAFFOLD REQUIRED -
10 |  | 67442 |  | PM TO CLEANSE |  | FLAT 1 Block 16 | Bicester Square | Castle Vale |  | B35 6HR | Flat | Miss S Smith | 07305 123 009 |  | shereenago@me.com |  | Windows & Doors | S Burgess | 2024-04-12 | 8am to 12 noon |  |  | TS-02/04/24 Text sent for 12/04/24. TS-02/04/24 Tenant CONFIRMED for 12/04/24. TS-22/04/24 Survey & photos received passed to DA to cleanse. Door combi was recently replaced. |  |  |  |  | 5 | [20 empty] | No | Independent Scaffold | Brick & Cladding | SCAFFOLD - Block will have scaffold
10 |  | 62869 |  | PM TO CLEANSE |  | FLAT 2 Block 16 | Bicester Square | Castle Vale |  | B35 6HR | Flat | Ms S Price | 07928 725 629 | 07928 725 629 | sueprice1948@hotmail.co.uk |  | Windows & Doors | S Burgess | 2024-04-12 | 11am to 3pm |  |  | TS-02/04/24 Text sent for 12/04/24. TS-04/04/24 Called tenant survey CONFIRMED for 12/04/24. TS-22/04/24 Survey & photos received passed to DA to cleanse. |  |  |  |  | 7 | [20 empty] | No |  | Brick & Cladding | No Solvent
10 |  | 68019 |  | SENT FOR PRICING |  | 1 | Bond Drive | Birmingham |  | B35 7QQ |  | Mrs V Kerr |  | 07751977656 |  |  | Windows & Doors | S Burgess | 2024-06-19 | 8am to 12 noon |  |  | 05/06 SMS text sent for 19/06. CONFIRMED for 19/06. 18/7/2024; AC sent to pricing. |  |  |  |  | 6 | [8 empty] | 1 |  | 1 |  | 1 | [10 empty] | PILOT PROPERTY. 125mm FLAT BOARD REQUIRED TO SIDES AND HEAD OF ALL WINDOWS. 95mm TRIM TO DOOR SIDES AND HEAD. 140mm HARDWOOD CILL REQUIRED. TENANT USES SCOOTER. NO SOLVENT.
10 |  | 68812 |  | SENT FOR PRICING |  | 2 | Bond Drive | Birmingham |  | B35 7QQ |  | Miss K-M Goodwin |  | 07361881089 | katiegoodwin1991@outlook.com |  | Windows & Doors | S Burgess | 2024-06-19 | 8am to 12 noon |  |  | 05/06 SMS text sent for 19/06. 11/06 SMS called no. NIS lttr sent. 18/7/2024; AC sent to pricing. |  |  |  |  | 13 | [12 empty] | 1 | [8 empty] | Independent Scaffold |  | Scaffold required.
10 |  | 61291 |  | SENT FOR PRICING |  | 3 | Bond Drive | Birmingham |  | B35 7QQ |  | Miss S P Mann | 01217491004 | 07526979351 |  |  | Windows & Doors | S Burgess | 2024-06-19 | 8am to 12 noon |  |  | 05/06 SMS text sent for 19/06. 11/06 SMS called no. NIS lttr sent. 18/7/2024; AC sent to pricing. |  |  |  |  | 6 | [8 empty] | 1 |  | 1 |  | 1 | [10 empty] | Blinds fixed to existing windows.
10 |  | 70407 |  | SENT FOR PRICING |  | 6 | Bond Drive | Birmingham |  | B35 7QQ |  | Miss L Collingwood |  | 07541830345 | laura.collingwood93@hotmail.com |  | Windows & Doors | S Burgess | 2024-06-19 | 11am to 3pm |  |  | 05/06 SMS text sent for 19/06. CONFIRMED for 19/06. 02/07 SMS surveyor reported NWR for doors. 18/7/2024; AC sent to pricing. |  |  |  |  | 12
10 |  | 66820 |  | SENT FOR PRICING |  | 8 | Bond Drive | Birmingham |  | B35 7QQ |  | Miss J Walsh |  | 07943 517 988 | jacqueline.07@hotmail.co.uk |  | Windows & Doors | S Burgess | 2024-06-27 | 8am to 12 noon |  |  | 13/06 SMS text sent for 27/06. CONFIRMED for 27/06. 18/7/2024; AC sent to pricing. |  |  |  |  | 12 | [10 empty] | 1 |  | 1
10 |  | 70643 |  | SENT FOR PRICING |  | 10 | Bond Drive | Birmingham |  | B35 7QQ |  | Miss J Wilkins |  | 07792145097 | jessy_mariewilkins@hotmail.co.uk |  | Windows & Doors | S Burgess | 2024-06-27 | 8am to 12 noon |  |  | 13/06 SMS text sent for 27/06. 19/6; AC rang and confirmed survey. 18/7/2024; AC sent to pricing. |  |  |  |  | 11 | [10 empty] | 1 |  | 2
10 |  | 61342 |  | PM TO CLEANSE |  | 12 | Bond Drive | Birmingham |  | B35 7QQ |  | Mr S Tonks |  | 07950800156 |  |  | Windows & Doors | S Burgess | 2024-06-27 | 11am to 3pm |  |  | 13/06 SMS text sent for 27/06. CONFIRMED for 27/06 |  |  |  |  | 11 | [10 empty] | 1 |  | 1
10 |  | 60257 |  | SENT FOR PRICING |  | 16 | Bond Drive | Birmingham |  | B35 7QQ |  | Mr D Raven | 01217481669 |  | draven159@aol.com |  | Windows & Doors | S Burgess | 2024-06-27 |  |  |  | 19/6; AC rang for survey 27/6, LM, emailed and sent letter. 18/7/2024; AC sent to pricing. |  |  |  |  | 12 | [10 empty] | 1 |  | 1
10 |  | 60256 |  | SENT FOR PRICING |  | 14 | Bond Drive | Birmingham |  | B35 7QQ |  | Miss R Key | 07708338388 | 07708 338 388 | becki.26@hotmail.co.uk |  | Windows & Doors | S Burgess | 2024-06-27 | 11am to 3pm |  |  | 13/06 SMS text sent for 27/06. CONFIRMED for 27/06. 18/7/2024; AC sent to pricing. |  |  |  |  | 10 | [10 empty] | 1 |  | 1
10 |  | 65109 |  | PM TO CLEANSE |  | 8 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mrs S C Brice |  | 07368490634 | suzannewestbury@hotmail.com |  | Windows & Doors | M Turpin | 2024-06-06 | 8am to 2pm |  |  | 20/05 SMS sent email for 06/06 / 23.05.24 SF Sent another text & email. 29/05 SMS called N/A lttr sent. |  |  |  |  | 6 | [12 empty] | 1
10 |  | 68454 |  | PM TO CLEANSE |  | FLAT 14 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mr G P Casey |  | 07903577086 | glencasey33@yahoo.co.uk |  | Windows & Doors | M Turpin | 2024-06-11 | 8am to 2pm |  |  | (Access via 8 Cosford & 2 Abingdon)29/05 SMS text sent for 11/06. CONFIRMED for 11/06. 17/6; AC chased photos. | [28 empty] | Acess via 8 Cosford & 2 Abingdon | [11 empty] | (Access via 8 Cosford & 2 Abingdon)
10 |  | 64990 |  | PM TO CLEANSE |  | FLAT 16 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss J Mulholland | 07526535273 |  |  |  | Windows & Doors | M Turpin | 2024-06-11 | 8am to 2pm |  |  | (Access via 8 Cosford & 2 Abingdon)29/05 SMS text sent for 11/06. CONFIRMED for 11/06. 17/6; AC chased photos. | [28 empty] | Acess via 8 Cosford & 2 Abingdon | [11 empty] | (Access via 8 Cosford & 2 Abingdon)
10 |  | 60263 |  | PM TO CLEANSE |  | FLAT 18 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mr P McCormick | 01216490938 |  |  |  | Windows & Doors | M Turpin | 2024-06-11 | 8am to 2pm |  |  | (Access via 8 Cosford & 2 Abingdon)31/05 SMS called for 11/06 N/A. 03/06 SMS called N/A Lttr sent. 17/6; AC chased photos. | [26 empty] | Independent Scaffold |  | Acess via 8 Cosford & 2 Abingdon. *Scaffold Req? | [11 empty] | (Access via 8 Cosford & 2 Abingdon) *Scaffold Req?
10 |  | 65839 |  | PM TO CLEANSE |  | 24 | Donibristle Croft | Birmingham |  | B35 6BL |  | Mrs G A Thomas | 0121 218 2260 | 07775 709 656 | glynisandderek@gmail.com |  | Windows & Doors | M Turpin | 2024-06-10 | 8am to 2pm |  |  | TS-03/05/24 Text sent for 16/05/24. TS-07/05/24 Ltr sent. CONFIRMED for 16/05/24 after 10am only as has carer in morning. 15/05 SMS tenant called to cancel. 30/05 SMS text sent for 10/06. CONFIRMED for 10/06 after 10am. 17/6; AC chased photos. 21/6/2024 AC SENT FOR PRICING. |  |  |  |  | 6 | [10 empty] | 1 |  | 1 | [10 empty] | TENANT USES SCOOTER.
10 |  | 65426 |  | PM TO CLEANSE |  | 8 | Merlin Close | Birmingham |  | B35 7JW |  | Mrs V Brobbey-Sarpong | 07713 246696 | 07713 246696 |  |  | Windows & Doors | M Turpin | 2024-06-05 | 8am to 2pm |  |  | 20/05 SMS text sent for 05/06. CONFIRMED for 05/06. 11/06 SMS on hold until we receive a door choice, paperwork is in the query box, req Dominie to chase from tenant
10 |  | 70353 |  | PM TO CLEANSE |  | 32 | Northolt Drive | Birmingham |  | B35 6QX |  | Miss L Jones | 07826 723 539 |  | laneyjones@live.co.uk |  | Windows & Doors | S Burgess | 2024-05-14 | 8am to 12 noon |  |  | TS-12/04/24 Text sent for 23/04/24. TS-18/04/24 Text sent cancelling the survey of 23/04/24 and offering 14/05/24. TS-03/05/24 Survey CONFIRMED for 14/05/24.
10 |  | 65131 |  | PM TO CLEANSE |  | FLAT 40 | Northolt Drive | Birmingham |  | B35 6QX |  | Mr D Johnson | 07950667035 |  |  |  | Windows & Doors | S Burgess | 2024-05-14 | 8am to 12 noon |  |  | TS-15/04/24 Text sent for 24/04/24. TS-18/04/24 Text sent cancelling 24/04 and offering 14/05/24. TS-07/05/24 Ltr sent. 08/05 SMS called N/A. 21.06.24 SF Survey & photos received, ON HOLD, asked Darrem, but ready for PM to Cleanse | [28 empty] | Access via 32 Northolt Drive & 20 Mere Avenue. | [11 empty] | Flat 38 & 40 need Scaff & install together
10 |  | 68314 |  | PM TO CLEANSE |  | 10 | School Close | Birmingham |  | B35 7NU |  | Mrs K Smith |  | 07368456033 |  |  | Windows & Doors | M Turpin | 2024-06-06 | 8am to 2pm |  |  | 20/05 SMS text sent for 06/06. CONFIRMED for 06/06 |  |  |  |  | 5 | [10 empty] | 1 |  | 1
10 |  | 65354 |  | PM TO CLEANSE |  | 138 | Watton Green | Birmingham |  | B35 7JT |  | Miss Z L Harding | 07487 409 019 |  |  |  | Windows & Doors | M Turpin | 2024-06-12 | 8am to 2pm |  | 1 | 13/05 SMS text sent for 24/05. 15/05 SMS mob no NIS . 16/05 SMS lttr sent. 24.05.24 SF CANCELLED via text message as number NIS. 24.05.24 SF Martin Turpin did actually attend, he van probably got fixed quicker than he thought, he attended the proper and NO ACCESS, need to re-book.10/06 SMS text sent for 12/06. CONFIRMED for 12/06 |  |  |  |  | 10 | [10 empty] | 1 |  | 1
10 |  | 67072 |  | PM TO CLEANSE |  | FLAT 343 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Miss P Fisher |  | 07711581016 | paulinefisher21@hotmail.com |  | Windows & Doors | M Turpin | 2024-06-11 | 8am to 2pm |  |  | (Access via 349 Yatesbury & 2 Cosford Crescent)29/05 SMS text sent for 11/06. 31/05 SMS called N/A. 03/06 SMS called N/A Lttr sent. CONFIRMED for 11/06. 17/6; AC chased photos. |  |  |  |  | 5 | [23 empty] | Access via 349 Yatesbury & 2 Cosford | [11 empty] | (Access via 349 Yatesbury & 2 Cosford Crescent)
10 |  | 68456 |  | PM TO CLEANSE |  | FLAT 345 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Mr HA Zare | 07474530394 | 07474530394 | hosseinali1980zare@gmail.com |  | Windows & Doors | M Turpin | 2024-06-11 | 8am to 2pm |  |  | (Access via 349 Yatesbury & 2 Cosford Crescent)29/05 SMS text sent for 11/06. 17/6; AC chased photos. | [28 empty] | Access via 349 Yatesbury & 2 Cosford | [11 empty] | (Access via 349 Yatesbury & 2 Cosford Crescent)
10 |  | 64308 |  | SENT FOR PRICING |  | 10 | Kemble Drive | Birmingham |  | B35 6QS |  | Mrs M Powell | 07568 358 706 |  |  | Mobility Issues | Windows & Doors | P Beahan | 2024-04-17 | 8am to 12 noon |  |  | TS-04/04/24 Text sent fotr 17/04/24. TS-08/04/24 Called tenant left vm, txt & ltr sent. TS-11/04/24 Tenant CONFIRMED for 17/04/24. 18/7/2024; AC sent to pricing. |  |  |  |  | 6 | [10 empty] | 1 |  | 1 | [22 empty] | *Tenant is wheelchair user
10 |  | 59790 |  | SENT FOR PRICING |  | 12 | Kemble Drive | Birmingham |  | B35 6QS |  | Mrs J Mullan | 07788598163 | 07541 626 032 |  |  | Windows & Doors | P Beahan | 2024-04-17 | 8am to 12 noon |  |  | TS-04/04/24 Text sent fotr 17/04/24. TS-08/04/24 Called tenant both numbers are nis, ltr sent. 18/7/2024; AC sent to pricing. |  |  |  |  | 7 | [10 empty] | 1 |  | 1 | [5 empty] | 1
10 |  | 59793 |  | SENT FOR PRICING |  | 18 | Kemble Drive | Birmingham |  | B35 6QS |  | Miss D Bree |  | 07900 288 081 |  |  | Windows & Doors | P Beahan | 2024-04-17 | 11am to 3pm |  |  | TS-04/04/24 Text sent fotr 17/04/24. TS-04/04/24 Survey CONFIRMED for 17/04/24. 18/7/2024; AC sent to pricing. |  |  |  |  | 10 | [12 empty] | 1 | [10 empty] | Query over if we are replacing front door, DA to advise
10 |  | 69749 |  | SENT FOR PRICING |  | 20 | Kemble Drive | Birmingham |  | B35 6QS |  | Mr Z Amar |  | 07450 214 240 |  |  | Windows & Doors | P Beahan | 2024-04-17 | 11am to 3pm |  |  | TS-04/04/24 Text sent fotr 17/04/24. TS-08/04/24 Survey CONFIRMED for 17/04/24. 18/7/2024; AC sent to pricing. |  |  |  |  | 10 | [12 empty] | 1
10 |  | 59796 |  | SENT FOR PRICING |  | 24 | Kemble Drive | Birmingham |  | B35 6QS |  | Miss J Pratt |  | 07932 362 321 | teddys@talktalk.net |  | Windows & Doors | P Beahan | 2024-04-17 | First Call |  |  | TS-04/04/24 Text sent fotr 17/04/24. TS-04/04/24 Tenant called to CONFIRM but have asked for the first call of they day have amended the diary to reflect this. TS-15/04/24 Door choice emailed to client. 18/7/2024; AC sent to pricing. |  |  |  |  | 7 | [10 empty] | 1 |  | 1 |  |  |  |  | 1 | [17 empty] | No Solvents
10 |  | 67540 |  | SENT FOR PRICING |  | FLAT 8 | Kemble Drive | Birmingham |  | B35 6QS |  | Mr M Shutt |  | 07496 139 339 | shuttmartin@gmail.com |  | Windows & Doors | P Beahan | 2024-04-17 | 8am to 12 noon |  |  | TS-04/04/24 Text sent fotr 17/04/24. TS-08/04/24 Called tenant no answer or vm, txt, email & ltr sent. TS-12/04/24 Survey CONFIRMED for 17/04/24. TS-15/04/24 Door choice emailed to client. 18/7/2024; AC sent to pricing. |  |  |  |  | 5 | [5 empty] | 1 | [11 empty] | 1 |  |  |  | Independent Scaffold |  | Access Via 10 Kemble & 469 Yatesbury Avenue | [11 empty] | Access Via 10 Kemble & 469 Yatesbury Avenue *Scaffold Req
10 |  | 59862 |  | PM TO CLEANSE | Survey Rec'd, awaiting photos | 26 | Mere Avenue | Birmingham |  | B35 6QT | House | Miss S Ansell | 0121 746 7508 | 07745 744 858 |  | Breathing Difficulties | Windows & Doors | P Beahan | 2024-04-23 | 8am to 12 noon |  |  | TS-12/04/24 Text sent for 23/04/24. TS-15/04/24 Survey CONFIRMED for 23/004/24. 12.07.24 SF Survey received, Chris cleansed, but ON HOLD due to security gate query, check with Darren. Sent email to Darren & Chris to advise when we can send for pricing. |  |  |  |  | 10 | [10 empty] | 1 | [10 empty] | Independent Scaffold | Brick | SCAFFOLD REQUIRED - Door jammer, tenant has asthma, no solvents to be used, tenant advised to isolate pets during installation. | [11 empty] | SCAFFOLD REQUIRED - Door jammer, tenant has asthma, no solvents to be used, tenant advised to isolate pets during installation.
10 |  | 69958 |  | PM TO CLEANSE |  | 8 | Watton Green | Birmingham |  | B35 7JS |  | Miss NL Cabena | 07460 785 785 |  | ninalcabena@gmail.com |  | Windows & Doors | M Turpin | 2024-05-01 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 01/05/24. TS-24/04/24 Called left vm, text & ltr sent. TS-24/040/24 Survey CONFIRMED for 01/05/24. 12/7/2024; AC sent to PM to cleanse. |  |  |  |  | 9 | [10 empty] | 1 |  | 1 | [5 empty] | 2 |  |  | Jammer System |  | PETS. DOOR JAMMER REQUIRED.
10 |  | 68960 |  | PM TO CLEANSE |  | 12 | Watton Green | Birmingham |  | B35 7JS |  | Miss M M Rose-Lewis |  | 07456 459 459 | maureenlewis.mmrl@gmail.com |  | Windows & Doors | M Turpin | 2024-05-01 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 01/05/24. TS-19/04/24 Survey CONFIRMED for 01/05/24.12/7/2024; AC sent to PM to cleanse. |  |  |  |  | 13 | [10 empty] | 1 |  | 1 | [5 empty] | 2 |  |  | Jammer System |  | JAMMER REQUIRED.
10 |  | 60103 |  | PM TO CLEANSE |  | 14 | Watton Green | Birmingham |  | B35 7JS |  | Miss K Bennett | 07960 089 498 | 07522094660 - nis |  |  | Windows & Doors | M Turpin | 2024-05-02 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 02/05/24. TS-24/04/24 Called number nis, ltr sent. TS-30/04/24 DM did a site visit survey CONFIRMED and number updated. 12/7/2024; AC sent to PM to cleanse. |  |  |  |  | 8 | [10 empty] | 1 |  | 1 | [5 empty] | 3 |  |  |  |  | PETS.
10 |  | 60104 |  | PM TO CLEANSE |  | 16 | Watton Green | Birmingham |  | B35 7JS |  | Miss L Millington | 0121 730 1599 | 07921 008 420 | Lisa-blues@live.co.uk |  | Windows & Doors | M Turpin | 2024-05-23 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 02/05/24. TS-24/04/24 Called no answer or vm, text & ltr sent. TS-30/04/24 Tenant emailed in they are at work and would need it to be inbetween 11am - 3pm replied advising that we will remove and will be back in touch to offer a new date.13/05 SMS text sent for 23/05. 15/05 SMS called N/A. 16/05 SMS letter sent. 24.05.24 SF Martin Turpin attended, received top sheet, survey sent for cleansing, doors & windows surveyed, awaiting photos. 17/6; AC chased photos. 12/7/2024; AC sent to PM to cleanse. |  |  |  |  | 6 | [10 empty] | 1 |  | 1 | [5 empty] | 3 |  |  | Jammer System |  | JAMMER REQUIRED
10 |  | 61921 |  | PM TO CLEANSE |  | 10 | Watton Green | Birmingham |  | B35 7JS |  | Miss L Da-Costa |  | 07709 094 089 | 3rdileading@gmail.com |  | Windows & Doors | M Turpin | 2024-05-01 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 01/05/24. TS-24/004/24 Called tenant survey CONFIRMED for 01/05/24.12/7/2024; AC sent to Pm to cleanse. |  |  |  |  | 8 | [10 empty] | 1 |  | 1 | [5 empty] | 3 |  |  | Jammer System |  | JAMMER REQUIRED.
10 |  | 65126 |  | PM TO CLEANSE |  | 18 | Watton Green | Birmingham |  | B35 7JS |  | Mr RP King |  | 07383235133 |  |  | Windows & Doors | M Turpin | 2024-05-02 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 02/05/24. TS-24/04/24 Called left vm, text & ltr sent. TS-01/05/24 DM did a site visit and survey is CONFIRMED and tenant wants it as earliest call.12/7/2024; AC sent to Pm to cleanse. Front door already new. |  |  |  |  | 7 | [12 empty] | 1 | [5 empty] | 1 |  |  |  |  | Tenst suffer Bipolar and struggles with people.
10 |  | 69048 |  | PM TO CLEANSE |  | 20 | Watton Green | Birmingham |  | B35 7JS |  | Miss S Khan | 07414 146 089 | 07704907888 - nis |  |  | Windows & Doors | M Turpin | 2024-05-02 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 02/05/24. TS-24/04/24 Called number nis, ltr sent. TS-30/04/24 DM did a site visit survey CONFIRMED requested latest calll and number updated. Both doors are ok. 12/7/2024; AC sent to PM to cleanse. |  |  |  |  | 6 | [23 empty] | PETS.
10 |  | 66998 |  | PM TO CLEANSE |  | 24 | Watton Green | Birmingham |  | B35 7JS |  | Mr AJ Delemere | 07896 765 025 |  | adelemere@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-05-02 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 02/05/24. TS-19/04/24 Survey CONFIRMED for 02/05/24. 12/7/2024; AC sent to PM to cleanse. |  |  |  |  | 8 | [10 empty] | 1 |  | 1 | [5 empty] | 3
10 |  | 65933 |  | PM TO CLEANSE |  | 28 | Watton Green | Birmingham |  | B35 7JS |  | Miss L Johnson | 07941 637 777 |  | Ilovemyjob@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-05-02 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 02/05/24. TS-19/04/24 Survey CONFIRMED for 02/05/24. *Door choice in tray*. 12/7/2024; AC sent to PM to cleanse. |  |  |  |  | 9 | [10 empty] | 1 |  | 1 | [5 empty] | 3 |  |  | Jammer System |  | *Tenant will need RLO support during fitting. TENANT HAS ASTHMA. PETS. WHEELCHAIR ACCESS REQUIRED TO REAR. DOOR JAMMER REQUIRED. | [11 empty] | *Tenant will need RLO support during fitting
10 |  | 65893 |  | PM TO CLEANSE |  | 15 | Javelin Avenue | Birmingham |  | B35 7LH |  | Miss M Harris |  | 07851 914 080 |  |  | Windows & Doors | M Turpin | 2024-04-22 | 8am to 2pm |  |  | TS-12/04/24 Text sent for 22/04/24. TS-12/04/24 Survey CONFIRMED for 22/04/24. |  |  |  |  | 13 | [10 empty] | 1 |  | 2
10 |  | 67016 |  | PM TO CLEANSE |  | 17 | Javelin Avenue | Birmingham |  | B35 7LH |  | Mrs N Farrukh | 01217493816 | 07851 877 200 |  |  | Windows & Doors | M Turpin | 2024-04-23 | 8am to 2pm |  |  | TS-17/04/24 Called could get past the call minder system - ltr sent. |  |  |  |  | 13 | [10 empty] | 1 |  | 2
10 |  | 69494 |  | PM TO CLEANSE |  | 19 | Javelin Avenue | Birmingham |  | B35 7LH |  | Ms T Griffiths |  | 07897 591 718 | theresa_griffiths@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-04-23 | 8am to 2pm |  |  | TS-12/04/24 Text sent for 23/04/24. TS-15/04/24 Survey CONFIRMED for 23/04/24. |  |  |  |  | 13 | [10 empty] | 1 |  | 2
10 |  | 68283 |  | PM TO CLEANSE |  | 26 | Javelin Avenue | Birmingham |  | B35 7LW |  | Mr A Lo | 07990 864 871 | 07908 828 649 | saabalo@hotmail.it |  | Windows & Doors | M Turpin | 2024-04-23 | 8am to 2pm |  |  | TS-12/04/24 Text sent for 23/04/24. TS-17/04/24 Called left vm, text & ltr sent. TS-17/04/24 Tenant called survey CONFIRMED for 23/04/24. |  |  |  |  | 13 | [10 empty] | 1 |  | 2
10 |  | 67707 |  | PM TO CLEANSE |  | 28 | Javelin Avenue | Birmingham |  | B35 7LW |  | Miss B K Kirwan | 07772 526 747 |  | bianca-88@hotmail.co.uk | Breathing Difficulties | Windows & Doors | M Turpin | 2024-04-25 | 8am to 2pm |  |  | TS-12/04/24 Text sent for 23/04/24. TS-24/04/24 Called left vm, text & ltr sent. TS-17/04/24 Tenant txt back they can't do this day, offered them anytime this week. TS-17/04/24 Survey CONFIRMED for 25/04/24. |  |  |  |  | 13 | [10 empty] | 1 |  | 2 | [22 empty] | *Prev Heart issues and child with Astma
10 |  | 69883 |  | PM TO CLEANSE |  | 30 | Javelin Avenue | Birmingham |  | B35 7LW |  | Mr L Flatley | 07557 206 388 | 07388692700 | lukeflatley7@gmail.com |  | Windows & Doors | M Turpin | 2024-04-23 | 8am to 2pm |  |  | TS-12/04/24 Text sent for 23/04/24. TS-17/04/24 Callled number would not connect letter sent offering 23/04/24. |  |  |  |  | 13 | [10 empty] | 1 |  | 2
10 |  | 63925 |  | PM TO CLEANSE |  | 38 | Javelin Avenue | Birmingham |  | B35 7LW |  | Miss N C Palgrave | 07379 847 080 |  |  | Mobility Issues | Windows & Doors | M Turpin | 2024-04-24 | 8am to 2pm |  |  | TS-15/04/24 Text sent for 24/04/24. TS-15/04/24 Survey CONFIRMED for 24/04/24. |  |  |  |  | 13 | [10 empty] | 1 |  | 2 | [22 empty] | Walks with sticks & no solvent to be used
10 |  | 67235 |  | PM TO CLEANSE |  | 40 | Javelin Avenue | Birmingham |  | B35 7LW |  | Miss H Gough |  | 07951 906 468 |  |  | Windows & Doors | M Turpin | 2024-04-24 | 8am to 2pm |  |  | TS-15/04/24 Text sent for 24/04/24. TS-15/04/24 Survey CONFIRMED for 24/04/24. |  |  |  |  | 13 | [10 empty] | 1 |  | 2
10 |  | 64596 |  | PM TO CLEANSE |  | 42 | Javelin Avenue | Birmingham |  | B35 7LW |  | Mr E Frisenfelds | 01217 494 666 |  |  |  | Windows & Doors | M Turpin | 2024-04-24 | 8am to 2pm |  |  | TS-17/04/24 Called tenant survey CONFIRMED for 24/04/24. |  |  |  |  | 13 | [10 empty] | 1 |  | 2
10 |  | 68605 |  | PM TO CLEANSE |  | 72 | Javelin Avenue | Birmingham |  | B35 7LW |  | Miss C Hill | 07385 238 097 |  | c07hill@aol.com |  | Windows & Doors | M Turpin | 2024-04-25 | 8am to 2pm |  |  | TS-15/04/24 Text sent for 25/04/24. TS-15/04/24 Survey CONFIRMED for 25/04/24. |  |  |  |  | 13 | [10 empty] | 1 |  | 2
10 |  | 65349 |  | PM TO CLEANSE |  | 74 | Javelin Avenue | Birmingham |  | B35 7LW |  | Miss S Sheekey |  | 07521 632 438 | stacysheekey@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-04-25 | 8am to 2pm |  |  | TS-15/04/24 Text sent for 25/04/24. TS-17/04/24 Called left vm, text & ltr sent for 25/04/24. TS-18/04/24 Survey CONFIRMED for 25/04/24. |  |  |  |  | 13 | [10 empty] | 1 |  | 2
10 |  | 64148 |  | PM TO CLEANSE |  | 32 | Javelin Avenue | Birmingham |  | B35 7LW |  | Mr W Hands |  | 07359 004 198 | waynehands@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-04-23 | 8am to 2pm |  |  | TS-12/04/24 Text sent for 23/04/24. TS-15/04/24 Survey CONFIRMED for 23/04/24. |  |  |  |  | 13 | [10 empty] | 1 |  | 2
10 |  | 61748 |  | PM TO CLEANSE |  | 36 | Javelin Avenue | Birmingham |  | B35 7LW |  | Mrs K M Disha | 07842 231 678 | 07402 672742 | sweetniss56@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-04-24 | 8am to 2pm |  |  | TS-15/04/24 Text sent for 24/04/24. TS-14/04/24 Called tenant the line could not accept this call, text and ltr sent. |  |  |  |  | 13 | [10 empty] | 1 |  | 2
10 |  | 61751 |  | PM TO CLEANSE |  | 44 | Javelin Avenue | Birmingham |  | B35 7LW |  | Mr B B Jones | 7902 011 916 | 077723448749 | brianjoshjones@AOL.com |  | Windows & Doors | M Turpin | 2024-04-29 | 8am to 2pm |  | 1 | TS-15/04/24 Text sent for 24/04/24. TS-16/04/24 Tenant txt back no, they need a Thursday or Friday, replied offering them Thurs 25/04/24. TS-16/04/24 Survey CONFIRMED for 25/04/24. TS-30/04/24 No access for survey 25/04/24 carded @ 1.15pm. Re-booked for 29/04 |  |  |  |  | 13 | [10 empty] | 1 |  | 2
10 |  | 61490 |  | SENT FOR PRICING |  | 14 | Trident Boulevard | Birmingham |  | B35 7LZ |  | Mr R Beech | 07383 431 653 |  |  | Breathing Difficulties | Windows & Doors | M Turpin | 2024-07-02 | 8am to 2pm |  |  | 19/6; AC sent letter. 09.07.24 SF Photos received & printed, awaiting survey. 18/7/2024; AC sent to pricing. |  |  |  |  | 13 | [10 empty] | 1 |  | 2 | [22 empty] | Breathing issues no solvent
10 |  | 66844 |  | SENT FOR PRICING |  | 19 | Trident Boulevard | Birmingham |  | B35 7LZ |  | Miss AW Isaac | 07956 530 229 |  | adia3@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-07-02 | 8am to 2pm |  |  | 19/6; AC text for 2/7. 21/6; AC rang LM AND SENT LETTER. 09/07 SMS tenant wants to amend door choice, emailed door choice form awaiting reply. 09.07.24 SF Photos received & printed, awaiting survey. *Door choice in with photos in box. 18/7/2024; AC sent to pricing. |  |  |  |  | 13 | [10 empty] | 1 |  | 2 | [22 empty] | ..
10 |  | 65707 |  | PM TO CLEANSE |  | 22 | Trident Boulevard | Birmingham |  | B35 7LZ |  | Miss J Mytton | 07801 887 912 | 07801 887 912 | jaynemytton@talktalk.net |  | Windows & Doors | M Turpin | 2024-07-02 | 8am to 2pm |  |  | 19/6; AC text for 2/7 and emailed. CONFIRMED FOR 2/7. 09.07.24 SF Photos received & printed, awaiting survey. |  |  |  |  | 13 | [10 empty] | 1 |  | 2
10 |  | 60107 |  | PM TO CLEANSE |  | 22 | Watton Green | Birmingham |  | B35 7JS |  | Miss C Coope | 07983 203 104 |  | clarecoope73@gmail.com |  | Windows & Doors | M Turpin | 2024-06-17 | AM |  |  | TS-19/04/24 Text sent for 02/05/24. TS-24/04/24 Called tenant she will check to see if she can get someone at the property and will call us back on Friday. TS-01/05/24 DM did a site visit and tenant advised her that she needs a Friday only but after 10th May.13/05 SMS text sent for 24/05. 15/05 SMS called N/A. CONFIRMED for 24/05. 24.05.24 SF CANCELLED via phone, she has no more time off until July, but will get her Mom to be in the property and will email us her door choice at the time. 24.05.24 SF Martin Turpin did actually attend, he van probably got fixed quicker than he thought, he attended the proper and NO ACCESS, need to re-book.10/06 SMS text sent for 12/06. 11/06 SMS called N/A. 13/06 SMS text sent for 17/06 at 7.30am as per Martin instruction. 20.06.24 SF Received top sheet from Martin, not received the survey, emailed Martin to send the survey over. 12/7/2024 AC CHASED PHOTOS. 12/7 received. AC passed to PM to cleanse. |  |  |  |  | 7 | [10 empty] | 1 |  | 1 | [5 empty] | 2 |  |  | Jammer System |  | JAMMER REQUIRED.
10 |  | 70746 |  | SENT FOR PRICING |  | 14 | Drem Croft | Birmingham |  | B35 7HW | Bungalow | Mrs L Smith |  | 07730 792 476 |  |  | Windows & Doors | M Turpin | 2024-07-01 | 8am to 2pm |  |  | 19/06 SMS text sent for 01/07. CONFIRMED for 01/07. 15.07.24 SF Received photos, sent to PM to cleanse. 18/7/2024; AC sent to pricing. |  |  |  |  | 6 | [6 empty] | 1 |  |  |  | 1 |  | 1 | [7 empty] | No |  |  | Tenant has mobility issues & in a wheel chair, will need assistance of taking blinds down and putting back up plus moving objects, pets have been requested to be isolated during survey.
10 |  | 66177 |  | SENT FOR PRICING |  | 16 | Drem Croft | Birmingham |  | B35 7HW | Bungalow | Mrs P Hughes | 07554 161 518 |  |  |  | Windows & Doors | M Turpin | 2024-07-01 | 8am to 2pm |  |  | 19/06 SMS lttr sent. 15.07.24 SF Received photos, sent to PM to cleanse. 18/7/2024; AC sent to pricing. |  |  |  |  | 5 | [10 empty] | 1 |  | 1
10 |  | 61502 |  | PM TO CLEANSE |  | FLAT 127A | Farnborough Road | Birmingham |  | B35 7LQ |  | Miss S Horton | 07920 013 224 |  | symonehorton@yahoo.co.uk |  | Windows & Doors | M Turpin | 2024-07-10 | 8am to 2pm |  |  | 24/06 SMS text sent for 09/07. 24/06 SMS twnant called to decline, can only do Mon, Wed & Fridays. 28/06 AC rang and LM also text sent for 10/07 and email. |  |  | 5 | [14 empty] | 1 | [22 empty] | Mon, Wed & Fridays.
10 |  | 66184 |  | PM TO CLEANSE |  | FLAT 127B | Farnborough Road | Birmingham |  | B35 7LQ |  | Miss S Rutter |  | 07411 016 352 | sarahrutter1@live.co.uk |  | Windows & Doors | M Turpin | 2024-07-09 | 8am to 2pm |  |  | 24/06 SMS text sent for 09/07. CONFIRMED for 09/07 |  |  | 6 | [14 empty] | 1 | [10 empty] | 2 year old has chronic lung disease and on oxygen. Severely austistic and devevlopment delays.
10 |  | 66870 |  | PM TO CLEANSE |  | FLAT 127D | Farnborough Road | Birmingham |  | B35 7LQ |  | Mrs C Singleton | 07425 262 715 |  |  |  | Windows & Doors | M Turpin | 2024-07-09 | 8am to 2pm |  |  | 24/06 SMS text sent for 09/07. CONFIRMED for 09/07 |  |  | 5 | [14 empty] | 1 | [10 empty] | PETS
10 |  | 68907 |  | PM TO CLEANSE |  | FLAT 127E | Farnborough Road | Birmingham |  | B35 7LQ |  | Miss G E Kiely | 0121 747 8606 | 07545 314 563 | m.kiely2512@gmail.com | Breathing Difficulties | Windows & Doors | M Turpin | 2024-07-11 | 8am to 2pm |  |  | 24/06 SMS called no NIS, lttr sent |  |  | 6 | [14 empty] | 1 | [10 empty] | Daughter has severe asthma and son has ADHD, sensory and anxiety. | [11 empty] | Daughter has severe asthma and son has ADHD, sensory and anxiety.
10 |  | 69440 |  | PM TO CLEANSE |  | FLAT 129A | Farnborough Road | Birmingham |  | B35 7LQ |  | Miss S Perry |  | 07947 665 556 |  |  | Windows & Doors | M Turpin | 2024-07-10 | 8am to 2pm |  |  | 24/06 SMS text sent for 10/07. 25/06 SMS called N/A |  |  | 5 | [14 empty] | 1
10 |  | 69380 |  | PM TO CLEANSE |  | FLAT 129B | Farnborough Road | Birmingham |  | B35 7LQ |  | Miss G Hewston |  | 07398 222 790 | GenevieveHewston@Yahoo.com |  | Windows & Doors | M Turpin | 2024-07-10 | 8am to 2pm |  |  | 24/06 SMS called no. NIS lttr sent |  |  | 5 | [14 empty] | 1
10 |  | 70561 |  | PM TO CLEANSE |  | FLAT 129F | Farnborough Road | Birmingham |  | B35 7LQ |  | Mr D Lewis |  | 07877 843 613 |  |  | Windows & Doors | M Turpin | 2024-07-10 | First Call |  |  | 24/06 SMS text sent for 10/07. CONFIRMED for 10/07 first Call pls |  |  | 5 | [14 empty] | 1 | [8 empty] | Jammer System |  | SCAFFOLD/DOOR JAMMER REQUIRED? | [11 empty] | SCAFFOLD/DOOR JAMMER REQUIRED?
10 |  | 68162 |  | PM TO CLEANSE |  | FLAT 131A | Farnborough Road | Birmingham |  | B35 7LQ |  | Mrs A C Cattell |  | 07751 976 640 | AnitaCattell@icloud.com |  | Windows & Doors | M Turpin | 2024-07-10 | 8am to 2pm |  |  | 24/06 SMS text sent for 10/07. CONFIRMED for 10/07 |  |  | 9 | [20 empty] | 1 |  |  |  |  | CARER; Christine Cattell. Tenant suffers mobility and has walking aids and also suffers COPD. TLO TO VISIT - NEEDS HELP MOVING ITEMS AND BLINDS.
10 |  | 65823 |  | PM TO CLEANSE |  | 5 | Javelin Avenue | Birmingham |  | B35 7LH |  | Miss S Lacey | 07756 335 015 |  |  |  | Windows & Doors | M Turpin | 2024-04-22 | 8am to 2pm |  |  | TS-12/04/24 Text sent for 22/04/24. TS-17/04/24 Called left vm txt & ltr sent. TS-17/04/24 Tenant called to confirm the appointment for 22/04/24. |  |  |  |  | 14 | [10 empty] | 1 |  | 2
10 |  | 67695 |  | PM TO CLEANSE |  | 7 | Javelin Avenue | Birmingham |  | B35 7LH |  | Miss S Myers | 07958 391 696 |  |  |  | Windows & Doors | M Turpin | 2024-04-22 | 8am to 2pm |  |  | TS-12/04/24 Text sent for 22/04/24. TS-12/04/24 Survey CONFIRMED for 22/04/24. |  |  |  |  | 10 | [10 empty] | 1 |  | 3
10 |  | 62571 |  | PM TO CLEANSE |  | 9 | Javelin Avenue | Birmingham |  | B35 7LH |  | Mrs SE Johnson |  | 07545 825 999 | samanthahollis66@gmail.com |  | Windows & Doors | M Turpin | 2024-04-22 | 8am to 2pm |  |  | TS-12/04/24 Text sent for 22/04/24. TS-15/04/24 Survey CONFIRMED for 22/04/24. |  |  |  |  | 14 | [10 empty] | 1 |  | 2
10 |  | 61382 |  | PM TO CLEANSE |  | 6 | Javelin Avenue | Birmingham |  | B35 7LW |  | Miss C Fowler | 01217481882 | 07899 924 366 | KATIE-FLOWER@HOTMAIL.CO.UK |  | Windows & Doors | M Turpin | 2024-04-22 | 8am to 2pm |  |  | TS-12/04/24 Called and left vm for 22/04/24. TS-17/04/24 Called left vm, ltr sent. |  |  |  |  | 14 | [10 empty] | 1 |  | 2
10 |  | 66266 |  | PM TO CLEANSE |  | 8 | Javelin Avenue | Birmingham |  | B35 7LW |  | Mr G Boocock - Julie Evans? |  | 07513 144 613 | julierosina@yahoo.co.uk |  | Windows & Doors | M Turpin | 2024-04-22 | 8am to 2pm |  |  | TS-12/04/24 Text sent for 22/04/24. TS-15/04/24 Survey CONFIRMED for 22/04/24. |  |  |  |  | 14 | [9 empty] | 1 |  | 3
10 |  | 63912 |  | PM TO CLEANSE |  | 76 | Javelin Avenue | Birmingham |  | B35 7LW |  | Mr J Walton | 01217474833 | 07858 620 855 |  |  | Windows & Doors | M Turpin | 2024-04-23 | 8am to 2pm |  |  | TS-17/04/24 Called tenant Survey CONFIRMED for 23/04/24. |  |  |  |  | 13 | [10 empty] | 1 |  | 2
10 |  | 67725 |  | PM TO CLEANSE |  | 84 | Javelin Avenue | Birmingham |  | B35 7LW |  | Mrs L Hughes | 07879 656 796 | 07821 493552 |  |  | Windows & Doors | M Turpin | 2024-04-29 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 29/04/24. |  |  |  |  | 14 | [10 empty] | 1 |  | 2
10 |  | 61712 |  | PM TO CLEANSE |  | 124 | Javelin Avenue | Birmingham |  | B35 7LW |  | Miss S Francis | 01215378153 | 07495 316 562 |  |  | Windows & Doors | M Turpin | 2024-04-29 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 29/04/24. |  |  |  |  | 10 | [10 empty] | 1 |  | 3
10 |  | 70782 |  | PM TO CLEANSE |  | 126 | Javelin Avenue | Birmingham |  | B35 7LW |  | Mr R Teager | 07494 816 011 | 1214484726 |  |  | Windows & Doors | M Turpin | 2024-04-29 | 8am to 2pm |  |  | TS-19/04/24 Sent letter offering 29/04/24 as no contact numbers. TS-26/04/24 Survey CONFIRMED for 29/04/24 by DM, number updated. |  |  |  |  | 14 | [10 empty] | 1 |  | 2
10 |  | 68159 |  | PM TO CLEANSE |  | 86 | Javelin Avenue | Birmingham |  | B35 7LW |  | Mr Y L Yankam | 07577 779 744 |  | yankam92@yahoo.co.uk |  | Windows & Doors | M Turpin | 2024-06-29 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 29/04/24. TS-26/04/24 DM did a site visit and the tenant advised her that he can't make Monday.14/06 SMS text sent for 27/06 |  |  |  |  | 14 | [10 empty] | 1 |  | 2
10 |  | 63580 |  | PM TO CLEANSE |  | 6 | Lysander Way | Birmingham |  | B35 7JY |  | Miss E J Dove |  | 07915 260 427 |  |  | Windows & Doors | M Turpin | 2024-04-30 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 30/04/24. TS-23/04/24 Called left vm, text & ltr sent. TS-26/04/24 DM has CONFIRMED survey for 30/04/24. |  |  |  |  | 14 | [10 empty] | 1 |  | 2 | [10 empty] | Balcony area needs clearing to allow installation | [11 empty] | Balcony area needs clearing to allow installation
10 |  | 69379 |  | PM TO CLEANSE |  | 8 | Lysander Way | Birmingham |  | B35 7JY |  | Miss S Humphrey | 07841 560 208 |  |  |  | Windows & Doors | M Turpin | 2024-04-30 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 30/04/24. TS-22/04/24 Survey CONFIRMED for 30/04/24. |  |  |  |  | 10 | [10 empty] | 1 |  | 3
10 |  | 66095 |  | PM TO CLEANSE |  | 10 | Lysander Way | Birmingham |  | B35 7JY |  | Miss S R Thompson | 07450 700 720 | 07450700720 | sharon441@btinternet.com |  | Windows & Doors | M Turpin | 2024-04-30 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 30/04/24. TS-19/04/24 Survey CONFIRMED for 30/04/24. |  |  |  |  | 14 | [10 empty] | 1 |  | 2
10 |  | 61485 |  | SENT FOR PRICING |  | 6 | Trident Boulevard | Birmingham |  | B35 7LZ |  | Miss D Chapman | 07951 623 530 |  |  |  | Windows & Doors | M Turpin | 2024-07-01 | 8am to 2pm |  |  | 19/06 SMS text sent for 01/07. CONFIRMED for 01/07. 09.07.24 SF Photos received & printed, awaiting survey. 18/7/2024; AC sent to pricing. |  |  |  |  | 14 | [10 empty] | 1 |  | 2
10 |  | 65687 |  | SENT FOR PRICING |  | 21 | Trident Boulevard | Birmingham |  | B35 7LZ |  | Mr K Mohammed |  | 07411 980 335 | alekozaifamily@yahoo.com |  | Windows & Doors | M Turpin | 2024-07-02 | 8am to 2pm |  |  | 19/6; AC text for 2/7 and emailed. 21/6; AC rang LM AND SENT LETTER. 09.07.24 SF Photos received & printed, awaiting survey. 18/7/2024; AC sent to pricing. |  |  |  |  | 14 | [10 empty] | 1 |  | 2
10 |  | 61904 |  | SENT FOR PRICING |  | 23 | Trident Boulevard | Birmingham |  | B35 7LZ |  | void | Key safe 2405 |  |  |  | Windows & Doors | M Turpin | 2024-07-02 | 8am to 2pm |  |  | VOID. 20/06 SMS emailed client to request keysafe code. 09.07.24 SF Photos received & printed, awaiting survey. 18/7/2024; AC sent to pricing. |  |  |  |  | 11 | [6 empty] | 1 |  |  |  | 1 |  | 2
10 |  | 67957 |  | SENT FOR PRICING |  | 5 | Concorde Drive | Birmingham |  | B35 7EE |  | Miss A S Rutter | 0121 408 0283 | 07534 950 731 | amandarutter01@outlook.com |  | Windows & Doors | M Turpin | 2024-07-09 | 8am to 2pm |  |  | 04/06 SMS text sent for 18/06.Tenant declined 18/06. CONFIRMED for 19/06. 18/06 SMS tenent called to cancel. 01/07 SMS text sent for 09/07. *Door Choice in Photo/survey box. 18/7/2024; AC sent to pricing. |  |  | 11 | [12 empty] | 1 |  | 1 | [8 empty] | Independent Scaffold |  | SCAFFOLD & JAMMER REQUIRED. CLUTTERED HOUSE. | [11 empty] | SCAFFOLD & JAMMER REQUIRED
10 |  | 56979 |  | PM TO CLEANSE |  | 8 | De Havilland Drive | Birmingham |  | B35 7FP |  | Mr S Plant | 01217492697 | 07815 443 140 |  |  | Windows & Doors | M Turpin | 2024-07-09 | 8am to 2pm |  |  | 05/06 SMS text sent for 19/06. Declined 19/06. CONFIRMED for 09/07 |  |  | 11 | [8 empty] | 1 |  |  |  | 2 | [10 empty] | Independent Scaffold |  | *Scaffold Req | [11 empty] | *Scaffold Req
10 |  | 69929 |  | PM TO CLEANSE |  | 10 | Drem Croft | Birmingham |  | B35 7HW |  | Mr T Finn | 07552 168 904 |  |  |  | Windows & Doors | M Turpin | 2024-07-09 | 8am to 2pm |  |  | 19/06 SMS lttr sent.25/06 SMS tenant called to decline this date and gave a contact number. CONFIRMED for 09/07 |  |  | 7 | [8 empty] | 1 |  |  |  | 1 |  | 1
10 |  | 70034 |  | PM TO CLEANSE |  | FLAT 131B | Farnborough Road | Birmingham |  | B35 7LQ |  | Ms M Kerr |  | 07861 385 674 | antonia-adams@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-07-10 | 8am to 2pm |  |  | 24/06 SMS text sent for 10/07. CONFIRMED for 10/07 |  |  | 6 | [14 empty] | 1
10 |  | 64422 |  | PM TO CLEANSE |  | FLAT 131C | Farnborough Road | Birmingham |  | B35 7LQ |  | Mr D Capper | 07944 611 428 |  |  |  | Windows & Doors | M Turpin | 2024-07-10 | 8am to 2pm |  |  | 24/06 SMS text sent for 10/07 |  |  | 5 | [14 empty] | 1
10 |  | 61517 |  | PM TO CLEANSE |  | FLAT 131D | Farnborough Road | Birmingham |  | B35 7LQ |  | Mr L Morley | 0121 747 0291 | 07739 446 536 | Lrmorley49@gmail.com |  | Windows & Doors | M Turpin | 2024-07-11 | 8am to 2pm |  |  | 24/06 SMS called for 11/07 N/A. CONFIRMED for 11/07 Lttr sent on tenants req |  |  | 9 | [20 empty] | 1 |  |  | Independent Scaffold |  | SCAFFOLD REQUIRED
10 |  | 69663 |  | PM TO CLEANSE |  | FLAT 131E | Farnborough Road | Birmingham |  | B35 7LQ |  | Miss K Mckenzie |  | 07359 526 982 | keishaadelle@icloud.com |  | Windows & Doors | M Turpin | 2024-07-11 | 8am to 2pm | [5 empty] | 6 | [14 empty] | 1
10 |  | 68705 |  | PM TO CLEANSE |  | FLAT 131G | Farnborough Road | Birmingham |  | B35 7LQ |  | Miss G Grant |  | 07929 020 526 | maxgrant330@gmail.com |  | Windows & Doors | M Turpin | 2024-07-11 | 8am to 2pm |  |  | 24/06 SMS text sent for 11/07. 25/06 SMS called N/A. CONFIRMED for 11/07 |  |  | 8 | [20 empty] | 1 |  |  | Independent Scaffold |  | SCAFFOLD REQUIRED | [11 empty] | SCAFFOLD REQUIRED
10 |  | 65995 |  | PM TO CLEANSE |  | FLAT 133B | Farnborough Road | Birmingham |  | B35 7LQ |  | Mrs C Kenny | 0121 448 4649 | 07946073502 |  |  | Windows & Doors | M Turpin | 2024-07-11 | 8am to 2pm |  |  | 24/06 SMS text sent for 11/07. CONFIRMED for 11/07 |  |  | 6 | [14 empty] | 1
10 |  | 68308 |  | PM TO CLEANSE |  | FLAT 133D | Farnborough Road | Birmingham |  | B35 7LQ |  | Miss J Bassett | 07368 423 999 |  | jadelouisebassett@outlook.com |  | Windows & Doors | M Turpin | 2024-07-11 | 8am to 2pm |  |  | 24/06 SMS text sent for 11/07. 25/06 SMS called N/A |  |  | 5 | [14 empty] | 1
10 |  | 69560 |  | PM TO CLEANSE |  | 12 | Merlin Close | Birmingham |  | B35 7JW |  | Miss J Rudd | 07444 639 584 |  | Jennyrudd@gmail.com |  | Windows & Doors | M Turpin | 2024-07-09 | 8am to 2pm |  | 1 | 20/05 SMS text sent for 06/06 to survey. 23.05.24 SF Sent another text.CONFIRMED for 05/06. 11/06 SMS tenant turned surveyor away on arrival on 05/06, client advised. 11/06 SMS text sent for 18/06. 24/06 SMS text sent for 09/07. CONFIRMED for 09/07 |  |  | 11 | [12 empty] | 1 |  | 1 | [10 empty] | WARDROBE IN FRONT OF KITCHEN WINDOW.
10 |  | 65832 |  | PM TO CLEANSE |  | 25 | Trident Boulevard | Birmingham |  | B35 7LZ |  | Mr M M Jones |  | 07917 809 148 |  |  | Windows & Doors | M Turpin | 2024-07-09 | 8am to 2pm |  |  | 24/06 SMS text sent for 09/07. 25/06 SMS left voicemail. CONFIRMED for 09/07 |  |  |  |  | 14 | [10 empty] | 1 |  | 2
10 |  | 69381 |  | PM TO CLEANSE |  | 28 | Trident Boulevard | Birmingham |  | B35 7LZ |  | Mrs K Parsons | 07856412925 | 07411 372 543 |  |  | Windows & Doors | M Turpin | 2024-07-09 | 8am to 2pm |  |  | 24/06 SMS text sent for 09/07. 25/06 SMS called NIS |  |  |  |  | 13 | [10 empty] | 1 |  | 2
10 |  | 58383 |  | PM TO CLEANSE |  | 12 | Drem Croft | Birmingham |  | B35 7HW |  |  | VOID |  |  |  | Windows & Doors | M Turpin | 2024-07-09 | 8am to 2pm |  | 1 | 19/06 SMS lttr sent. 19/6 AC emailed. EMAIL BOUNCED BACK INCORRECT. 1/7/2024; NO ACCESS, CARDED.15/07 SMS email sent for 1st no access survey to TLO. 9/7/2024; MT surveyed as void. |  |  | 6 | [8 empty] | 1 |  |  |  | 1 |  | 1
11 |  | 59442 |  | SURVEY RECEIVED | Waiting for survey & photos | 4 | Abingdon Way | Birmingham |  | B35 6QF |  | Miss J La Touche | 7931353477 |  |  |  | Windows & Doors | P Beahan | 2024-05-10 |  |  |  | TS-29/04/24 Letter sent for 10/05/24. TS-30/04/24 Survey CONFIRMED for 10/05/24. 17/6; AC chased survey. | [28 empty] | Works Shifts needs plenty of notice for install
11 |  | 59444 |  | SURVEY RECEIVED | Waiting for survey & photos | 6 | Abingdon Way | Birmingham |  | B35 6QF |  | Miss S Ashford | 0121 749 1629 | 07774761517 | brumgirlsharon@outlook.com |  | Windows & Doors | P Beahan | 2024-05-10 |  |  |  | TS-26/04/24 Text sent offering 10/05/24.TS-01/05/24 Called tenant offering 10/05/24 survey CONFIRMED. 17/6; AC chased survey.
11 |  | 59446 |  | SURVEY RECEIVED | Waiting for survey & photos | 8 | Abingdon Way | Birmingham |  | B35 6QF |  | Miss S Chambers | 07780469695 | 07780469586 |  |  | Windows & Doors | P Beahan | 2024-05-10 |  |  |  | TS-29/04/24 Text sent offering 10/05/24. TS-29/04/24 Survey CONFIRMED for 10/05/24. 17/6; AC chased survey.
11 |  | 68414 |  | SURVEY RECEIVED | Waiting for survey & photos | FLAT 3 | Abingdon Way | Birmingham |  | B35 6QF |  | Miss M Hanson |  | 07497303467 |  |  | Windows & Doors | P Beahan | 2024-05-10 |  |  |  | TS-26/04/24 Text sent offering 10/05/24. TS-01/05/24 Called tenant no answer or vm, text & ltr sent. 17/6; AC chased survey. | [28 empty] | Acess via 17 Abingdon Way & 24 Cosford
11 |  | 66863 |  | SURVEY RECEIVED | SEE COMMENTS | FLAT 5 | Abingdon Way | Birmingham |  | B35 6QF |  | Miss L Bennett | 07449479838 | 07449479838 |  |  | Windows & Doors | P Beahan | 2024-05-10 |  |  |  | TS-26/04/24 Text sent offering 10/05/24. TS-26/04/24 Survey CONFIRMED for 10/05/24.14/05 SMS PB advised in query with DA, will be updated as to if we need to re-book another survey or not. 17/6; AC chased survey. | [28 empty] | Acess via 17 Abingdon Way & 24 Cosford
11 |  | 66880 |  | SURVEY RECEIVED | Waiting for survey & photos | FLAT 7 | Abingdon Way | Birmingham |  | B35 6QF |  | Miss K Smart | 07940202851 |  | k.smart1969@gmail.com |  | Windows & Doors | P Beahan | 2024-05-10 |  |  |  | TS-26/04/24 Text sent offering 10/05/24. TS-01/05/24 Called tenant survey CONFIRMED. 17/6; AC chased survey. | [28 empty] | Acess via 17 Abingdon Way & 24 Cosford
11 |  | 70348 |  | SURVEY RECEIVED | Waiting for survey & photos | 49 | Abingdon Way | Birmingham |  | B35 6QF |  | Miss S Phillips |  | 07397891865 | sophiedadon14@gmail.com |  | Windows & Doors | P Beahan | 2024-06-06 | 8am to 12 noon |  |  | 20/05 SMS text sent for 06/06 for survey. 23.05.24 SF Sent another text. Tenant replied by text to CONFIRM the 06.06 for the survey.
11 |  | 61702 |  | SURVEY RECEIVED | Waiting for survey & photos | 10 | Abingdon Way | Birmingham |  | B35 6QF |  | Miss P Caraher |  | 07823771871 | Paula.Caraher@sky.com |  | Windows & Doors | P Beahan | 2024-05-23 | 8am to 12 noon |  |  | 13/05 SMS text sent for 23/05. 15/05 SMS left voicemail. 16/05 SMS lttr sent. 17/6; AC chased survey.
11 |  | 70150 |  | SURVEY RECEIVED | Waiting for survey & photos | 12 | Abingdon Way | Birmingham |  | B35 6QF |  | Miss S Palmer |  | 07309493666 | sylviapalmer67@gmail.com |  | Windows & Doors | P Beahan | 2024-05-23 | 11am to 3pm |  |  | 13/05 SMS text sent for 23/05. CONFIRMED for 23/05. 17/6; AC chased survey.
11 |  | 65697 |  | SURVEY RECEIVED | Waiting for survey & photos | 14 | Abingdon Way | Birmingham |  | B35 6QF |  | Miss D Smith | 07388043944 |  |  |  | Windows & Doors | P Beahan | 2024-05-23 | 11am to 3pm |  |  | 13/05 SMS text sent for 23/05. 16/05 SMS lttr sent. 17/6; AC chased survey.
11 |  | 65650 |  | SURVEY RECEIVED | Waiting for survey & photos | 16 | Abingdon Way | Birmingham |  | B35 6QF |  | Mr K Murphy | 0121 439 3727 |  |  |  | Windows & Doors | P Beahan | 2024-05-24 | 8am to 12 noon |  |  | 17/6; AC chased survey.
11 |  | 68504 |  | SURVEY RECEIVED | Waiting for survey & photos | 17 | Abingdon Way | Birmingham |  | B35 6QF |  | Miss M Meadley |  | 07798934679 |  |  | Windows & Doors | P Beahan | 2024-05-24 | 8am to 12 noon |  |  | 13/05 SMS text sent for 24/05. 15/05 SMS left voicemail. CONFIRMED. 17/6; AC chased survey.
11 |  | 70016 |  | SURVEY RECEIVED | Waiting for survey & photos | 18 | Abingdon Way | Birmingham |  | B35 6QF |  | Miss S Henry |  | 07375076318 | shakerah25@gmail.com |  | Windows & Doors | P Beahan | 2024-05-24 | 11am to 3pm |  |  | 13/05 SMS text sent for 24/05. 15/05 SMS left voicemail. 16/05 SMS lttr sent. 17/6; AC chased survey. | [28 empty] | Access via 16 Abingdon Way
11 |  | 69361 |  | SURVEY RECEIVED | Waiting for survey & photos | 19 | Abingdon Way | Birmingham |  | B35 6QF |  | Miss A Jackson |  | 07713605361 | jacksonalison00@gmail.com |  | Windows & Doors | P Beahan | 2024-05-24 | 11am to 3pm |  |  | 13/05 SMS text sent for 24/05. CONFIRMED for 24/05. 17/6; AC chased survey.
11 |  | 65836 |  | SURVEY RECEIVED | Waiting for survey & photos | 20 | Abingdon Way | Birmingham |  | B35 6QF |  | Mr M Edwards |  | 07904591717 | eddybcfc@googlemail.com |  | Windows & Doors | P Beahan | 2024-05-24 | 11am to 3pm |  |  | 13/05 SMS text sent for 24/05. CONFIRMED for 24/05. 17/6; AC chased survey. | [28 empty] | Access via 9 Cranwell
11 |  | 70328 |  | SURVEY RECEIVED | Waiting for survey & photos | 21 | Abingdon Way | Birmingham |  | B35 6QF |  | Miss R Groves |  | 07951756553 | rg012h5048@blueyonder.co.uk |  | Windows & Doors | P Beahan | 2024-05-30 | 8am to 12 noon |  |  | 16/05 SMS text sent for 30/05. CONFIRMED for 30/05. 17/6; AC chased survey.
11 |  | 59455 |  | SURVEY RECEIVED | Waiting for survey & photos | 23 | Abingdon Way | Birmingham |  | B35 6QF |  | Miss G Croton | 07392426449 | 0121 439 3893 |  |  | Windows & Doors | P Beahan | 2024-05-30 | 8am to 12 noon |  |  | 16/05 SMS text sent for 30/05. 17/05 SMS called N/A lttr sent. 17/6; AC chased survey.
11 |  | 67860 |  | SURVEY RECEIVED | Waiting for survey & photos | 24 | Abingdon Way | Birmingham |  | B35 6QF |  | Miss N Asghar |  | 07597117573 |  |  | Windows & Doors | P Beahan | 2024-05-30 | 11am to 3pm |  |  | 16/05 SMS text sent for 30/05. CONFIRMED for 30/05. 17/6; AC chased survey.
11 |  | 61564 |  | SURVEY RECEIVED | Waiting for survey & photos | 25 | Abingdon Way | Birmingham |  | B35 6QF |  | Miss A Taylor | 07534095490 | 07534095490 |  |  | Windows & Doors | P Beahan | 2024-05-30 | 11am to 3pm |  |  | 16/05 SMS text sent for 30/05. 17/05 SMS called N/A lttr sent. 17/6; AC chased survey.
11 |  | 70144 |  | SURVEY RECEIVED | Waiting for survey & photos | 27 | Abingdon Way | Birmingham |  | B35 6QF |  | Miss D Ward |  | 07535633828 | demi.p.ward96@hotmail.co.uk |  | Windows & Doors | P Beahan | 2024-05-31 | 8am to 12 noon |  |  | 16/05 SMS text sent for 31/05. CONFIRMED for 31/05. 17/6; AC chased survey.
11 |  | 59459 |  | SURVEY RECEIVED | Waiting for survey & photos | 29 | Abingdon Way | Birmingham |  | B35 6QF |  | Mrs C Reeves | 07731361252 |  | clare.reeves.72@BTinternet.com |  | Windows & Doors | P Beahan | 2024-05-31 | 8am to 12 noon |  |  | 16/05 SMS text sent for 31/05. CONFIRMED for 31/05. 17/6; AC chased survey.
11 |  | 59477 |  | SURVEY RECEIVED | Waiting for survey & photos | 30 | Abingdon Way | Birmingham |  | B35 6QF |  | Mrs D Douglas | 07799 041 566 |  |  |  | Windows & Doors | P Beahan | 2024-05-31 | 8am to 12 noon |  |  | 16/05 SMS text sent for 31/05. 17/05 SMS called N/A lttr sent
11 |  | 59460 |  | SURVEY RECEIVED | Waiting for survey & photos | 31 | Abingdon Way | Birmingham |  | B35 6QF |  | Mr G Blackburn | 01214393727 | 07847214967 |  |  | Windows & Doors | P Beahan | 2024-05-31 | 11am to 3pm |  |  | 16/05 SMS text sent for 31/05. 17/05 SMS called N/A lttr sent. CONFIRMED for 31/05. 17/6; AC chased survey.
11 |  | 60252 |  | SURVEY RECEIVED | Waiting for survey & photos | 32 | Abingdon Way | Birmingham |  | B35 6QF |  | Miss S C McNally |  | 07983580836 | sandie123@19680talktalk.net |  | Windows & Doors | P Beahan | 2024-05-31 | 11am to 3pm |  |  | 16/05 SMS text sent for 31/05. CONFIRMED for 31/05. 17/6; AC chased survey.
11 |  | 68651 |  | SURVEY RECEIVED | Waiting for survey & photos | 33 | Abingdon Way | Birmingham |  | B35 6QF |  | Miss C Lewin | 07930748765 | 07930748765 |  |  | Windows & Doors | P Beahan | 2024-05-31 | 11am to 3pm |  |  | (Access via 31 Abingdon Way) 16/05 SMS text sent for 31/05. 17/05 SMS called N/A lttr sent. CONFIRMED for 31/05. 17/6; AC chased survey. | [28 empty] | Access via 31 Abingdon Way | [11 empty] | (Access via 31 Abingdon Way)
11 |  | 67767 |  | SURVEY RECEIVED | Waiting for survey & photos | 34 | Abingdon Way | Birmingham |  | B35 6QF |  | Miss V Lindsey |  | 07738 706165 |  |  | Windows & Doors | P Beahan | 2024-06-05 | 8am to 12 noon |  |  | 20/05 SMS text sent for 05/06. CONFIRMED for 05/06
11 |  | 70478 |  | SURVEY RECEIVED | Waiting for survey & photos | 37 | Abingdon Way | Birmingham |  | B35 6QF |  | Miss T Hannaby |  | 07301564265 | toni_hannaby@hotmail.com |  | Windows & Doors | P Beahan | 2024-06-05 | 8am to 12 noon |  |  | 20/05 SMS text sent for 05/06. CONFIRMED for 05/06
11 |  | 67726 |  | SURVEY RECEIVED | Waiting for survey & photos | 41 | Abingdon Way | Birmingham |  | B35 6QF |  | Mrs M Hulme |  | 07519 506 990 |  |  | Windows & Doors | P Beahan | 2024-06-05 | 11am to 3pm |  |  | 20/05 SMS text sent for 05/06. CONFIRMED for 05/06
11 |  | 68272 |  | SURVEY RECEIVED | Waiting for survey & photos | 45 | Abingdon Way | Birmingham |  | B35 6QF |  | Mr DK White | 07703345794 |  |  |  | Windows & Doors | P Beahan | 2024-06-05 | 11am to 3pm |  |  | 20/05 SMS text sent for 05/06. CONFIRMED for 05/06
11 |  | 69629 |  | SURVEY RECEIVED | Waiting for survey & photos | 47 | Abingdon Way | Birmingham |  | B35 6QF |  | Miss S Ashe |  | 07746236858 |  |  | Windows & Doors | P Beahan | 2024-06-06 | 8am to 12 noon |  |  | 20/05 SMS text sent for 06/06 / 23.05.24 SF Sent another text. 29/05 SMS left voicemail. CONFIRMED for 06/06 | [28 empty] | Tenant will need calls only to arrange/confirm appointments | [11 empty] | *Tenant will need calls only to arrange/confirm appointments
11 |  | 69461 |  | SURVEY RECEIVED |  | FLAT 1 | Abingdon Way | Birmingham |  | B35 6QF |  | Mr T Hunt | 0121 730 2073 | 07455090417 | tghunt.1968@yahoo.co.uk |  | Windows & Doors | P Beahan | 2024-05-14 | 11am to 3pm |  |  | TS-26/04/24 Text sent offering 10/05/24. TS-26/04/24 Tenant text back no need a different date, removed from the diary. 08/05 SMS left voicemail offering 14/05. CONFIRMED for 14/05. 17/6; AC chased survey. | [28 empty] | Acess via 17 Abingdon Way & 24 Cosford
11 |  | 68669 |  | SURVEY RECEIVED | Waiting for survey & photos | FLAT 11 | Abingdon Way | Birmingham |  | B35 6QF |  | Miss Natalie Redmond | 07818 754 543 |  |  |  | Windows & Doors | P Beahan | 2024-05-23 | 11am to 3pm |  |  | 13/05 SMS text sent for 23/05. 15/05 SMS told tenant moved out over the weekend so emailed client to advise. 15/05 SMS new tenant details given.CONFIRMED for 23/05. 17/6; AC chased survey. | [28 empty] | Acess via 17 Abingdon Way & 24 Cosford
11 |  | 69168 |  | SURVEY RECEIVED | Waiting for survey & photos | FLAT 9 | Abingdon Way | Birmingham |  | B35 6QF |  | Miss L Barnfield |  | 07415122085 | lindsaybar@icloud.com |  | Windows & Doors | P Beahan | 2024-05-23 | PM |  |  | 13/05 SMS text sent for 23/05. 13/05 SMS tenant text back to decline this survey date. CONFIRMED after 12 only, also needs a phone call before attending pls. 17/6; AC chased survey. | [28 empty] | Acess via 17 Abingdon Way & 24 Cosford
11 |  | 66879 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 5 | Avro Way | Birmingham |  | B35 7NW |  | Mrs B Turner | 07972277089 | 07972277089 |  |  | Windows & Doors | S Burgess | 2024-07-02 | 8am to 12 noon |  |  | 19/6; AC text for 2/7. CONFIRMED FOR 21/6. | [28 empty] | WILL REQUIRE ASSISTANCE WITH TAKING BLIINDS DOWN AND REFIXING BACK UP.
11 |  | 67696 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 6 | Avro Way | Birmingham |  | B35 7NW |  | Mrs W Hickin | 01217302863 | 07771952042 |  |  | Windows & Doors | S Burgess | 2024-07-02 | 11am to 3pm |  |  | 19/6; AC text for 2/7. confirmed for 2/7
11 |  | 68082 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 7 | Avro Way | Birmingham |  | B35 7NW |  | Mr RWJ Lynch | 07581 300 286 |  | rlynchmufc@aol.com |  | Windows & Doors | S Burgess | 2024-07-02 | 11am to 3pm |  |  | 19/6; AC text for 2/7 and emailed. EMAIL BOUNCED BACK. 19/6; TENANT CONFIRMED BY TEXT.
11 |  | 65730 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 8 | Avro Way | Birmingham |  | B35 7NW |  | Mrs L Payne | 07724 237324 |  |  |  | Windows & Doors | S Burgess | 2024-07-02 | 11am to 3pm |  |  | 19/6; AC text for 2/7. CONFIRMED.
11 |  | 59523 |  | SURVEY RECEIVED | Waiting for survey & photos | 2 | Bovingdon Road | Birmingham |  | B35 6QD |  | Mrs J A Rutter |  | 07903 402 107 | janiutter2@sky.com |  | Windows & Doors | P Beahan | 2024-06-06 | 8am to 2pm |  |  | 20/05 SMS text sent for 06/06. CONFIRMED for 06/06
11 |  | 69902 |  | SURVEY RECEIVED | Waiting for survey & photos | 4 | Bovingdon Road | Birmingham |  | B35 6QD |  | Miss K Shaheen |  | 07748442175 | kiran2400@icloud.com |  | Windows & Doors | P Beahan | 2024-06-06 | 8am to 2pm |  |  | 20/05 SMS text sent for 06/06. CONFIRMED for 06/06
11 |  | 60420 |  | SURVEY RECEIVED | Waiting for survey & photos | 6 | Bovingdon Road | Birmingham |  | B35 6QD |  | Mr M Holliday | 07794786720 | 07854569077 | malcolmholliday@hotmail.co.uk |  | Windows & Doors | P Beahan | 2024-06-06 | 8am to 2pm |  |  | 20/05 SMS text sent for 06/06. CONFIRMED for 06/06
11 |  | 70792 |  | SURVEY RECEIVED | Waiting for survey & photos | 8 | Bovingdon Road | Birmingham |  | B35 6QD |  | Miss C Anderson-Wood |  | 07766743505 | booanderson2016@gmail.com |  | Windows & Doors | P Beahan | 2024-06-06 | 8am to 2pm |  |  | 20/05 SMS text sent for 06/06. CONFIRMED for 06/06
11 |  | 67324 |  | SURVEY RECEIVED | Waiting for survey & photos | 10 | Bovingdon Road | Birmingham |  | B35 6QD |  | Ms J Oliver | 07985476899 | 07985476899 |  |  | Windows & Doors | P Beahan | 2024-06-12 | 8am to 2pm |  |  | 29/05 SMS text sent for 12/06. CONFIRMED for 12/06
11 |  | 59527 |  | SURVEY RECEIVED | Waiting for survey & photos | 12 | Bovingdon Road | Birmingham |  | B35 6QD |  | Miss D Webb | 01217484992 | 07961 964 356 | donnawebb123@hotmail.com |  | Windows & Doors | P Beahan | 2024-06-12 | 8am to 2pm |  |  | 29/05 SMS text sent for 12/06. CONFIRMED for 12/06
11 |  | 64369 |  | SURVEY RECEIVED | Waiting for survey & photos | 34 | Bovingdon Road | Birmingham |  | B35 6QD |  | Miss KA Day | 07472329129 |  |  |  | Windows & Doors | P Beahan | 2024-06-12 | 8am to 2pm |  |  | 29/05 SMS text sent for 12/06. CONFIRMED for 12/06
11 |  | 68318 |  | SURVEY RECEIVED | Waiting for survey & photos | 36 | Bovingdon Road | Birmingham |  | B35 6QD |  | Mrs W Ward |  | 07531370562 | ww249@aol.com |  | Windows & Doors | P Beahan | 2024-06-13 | 11am to 3pm |  |  | 29/05 SMS text sent for 13/06. CONFIRMED for 13/06
11 |  | 70370 |  | SURVEY RECEIVED | Waiting for survey & photos | 38 | Bovingdon Road | Birmingham |  | B35 6QD |  | Miss E Butler |  | 07983689667 | emilybutler@msn.com |  | Windows & Doors | P Beahan | 2024-06-14 | 11am to 3pm |  |  | 29/05 SMS text sent for 13/06. CONFIRMED for 13/06. Tenant called to amend to CONFIRMED for 14/06
11 |  | 69082 |  | SURVEY RECEIVED | Waiting for survey & photos | 40 | Bovingdon Road | Birmingham |  | B35 6QD |  | Miss D Maylor |  | 07951 616 000 |  |  | Windows & Doors | P Beahan | 2024-06-13 | 11am to 3pm |  |  | 14/06 SMS text sent for 25/06
11 |  | 69850 |  | SURVEY RECEIVED | Waiting for survey & photos | FLAT 20 | Bovingdon Road | Birmingham |  | B35 6QD |  | Mrs Z Ahmadi |  | 07305904298 | zoheeh_ahmadi@yahoo.com |  | Windows & Doors | P Beahan | 2024-06-13 | 8am to 12 noon |  |  | 29/05 SMS text sent for 13/06. CONFIRMED for 13/06
11 |  | 64780 |  | SURVEY RECEIVED | Waiting for survey & photos | FLAT 22 | Bovingdon Road | Birmingham |  | B35 6QD |  | Mrs D P Loughran |  | 07454351543 | dawnloughran@aol.com |  | Windows & Doors | P Beahan | 2024-06-13 | 8am to 12 noon |  |  | 29/05 SMS text sent for 13/06. CONFIRMED for 13/06
11 |  | 59534 |  | SURVEY RECEIVED | Waiting for survey & photos | FLAT 26 | Bovingdon Road | Birmingham |  | B35 6QD |  | Mr P Owen | 07575386715 | 07575386715 |  |  | Windows & Doors | P Beahan | 2024-05-30 | 11am to 3pm |  |  | 20/05 SMS text sent for 30/05. CONFIRMED for 30/05. 17/6; AC chased survey.
11 |  | 59535 |  | SURVEY RECEIVED | Waiting for survey & photos | FLAT 28 | Bovingdon Road | Birmingham |  | B35 6QD |  | Miss K Moxam |  | 07815443584 |  |  | Windows & Doors | P Beahan | 2024-06-27 | 11am to 3pm |  |  | 20/05 SMS text sent for 05/06. 29/05 SMS left voicemail. 30/05 SMS called N/A lttr sent.CONFIRMED for 27/06
11 |  | 59536 |  | SURVEY RECEIVED | Waiting for survey & photos | FLAT 30 | Bovingdon Road | Birmingham |  | B35 6QD |  | Mr R Oldland |  | 7585037291 | robinoldland@gmail.com |  | Windows & Doors | P Beahan | 2024-06-05 | 11am to 3pm |  |  | 20/05 SMS text sent for 05/06. 29/05 SMS no. NIS Lttr sent
11 |  | 63795 |  | SURVEY RECEIVED | Survey Rec'd, awaiting photos | 26 | Brabazon Grove | Birmingham |  | B35 6DT |  | Miss R Haycock |  | 07455 966 933 | rhaycock1980@gmail.com |  | Windows & Doors | M Turpin | 2024-05-15 | AM |  |  | TS-03/05/24 Text sent for 13/05/24. TS-07/05/24 Ltr sent. 08/05 SMS spoke to tenant and re-arrange for 15/05 CONFIRMED after 9.30am. 17/6; AC chased photos from Martin.
11 |  | 70567 |  | SURVEY RECEIVED | Survey Rec'd, awaiting photos | 44 | Brabazon Grove | Birmingham |  | B35 6DT |  | Mr C Williams |  | 07894726478 |  |  | Windows & Doors | M Turpin | 2024-05-13 | 8am to 2pm |  |  | TS-03/05/24 Text sent for 13/05/24. TS-03/05/24 Survey CONFIRMED for 13/05/24.. 23/05 SMS emailed surveyor to chase photos. 17/6; AC chased photo from Martin.
11 |  | 55574 |  | SURVEY RECEIVED | Survey rcvd, awaiting all paperwork | 2 | Chigwell Close | Birmingham |  | B35 7HH |  | Miss L Lloyd | 0121 749 4567 |  |  |  | Windows & Doors | P Beahan | 2024-06-27 |  |  |  | 19/6; AC rang but rang out and cannot leave message. Letter sent.
11 |  | 69303 |  | SURVEY RECEIVED | Survey rcvd, awaiting all paperwork | 6 | Chigwell Close | Birmingham |  | B35 7HH |  | Ms L Cahill | 0798550451 | 07720301863 | leanne79lou@gmail.com |  | Windows & Doors | P Beahan | 2024-06-27 | 11am to 3pm |  |  | 14/06 SMS text sent for 27/06. CONFIRMED for 27/06
11 |  | 67459 |  | SURVEY RECEIVED | Waiting for survey & photos | 14 | Chigwell Close | Birmingham |  | B35 7HH |  | Ms L Mullen |  | 07496 570635 |  |  | Windows & Doors | P Beahan | 2024-06-14 | 8am to 12 noon |  |  | 03/06 SMS text sent for 14/06. CONFIRMED for 14/06
11 |  | 69333 |  | SURVEY RECEIVED | Survey rcvd, awaiting all paperwork | 16 | Chigwell Close | Birmingham |  | B35 7HH |  | Mrs V Cattell |  | 07547468483 | vgaunt61@gmail.com |  | Windows & Doors | P Beahan | 2024-06-28 | 11am to 3pm |  |  | 19/06 SMS text sent for 28/06. 19/6; AC emailed. Tenant emailed back to confirm.
11 |  | 70264 |  | SURVEY RECEIVED | Nothing rec'd on hold with surveyor / DA | 3 | Concorde Drive | Birmingham |  | B35 7EE |  | Miss L Fox |  | 07904003519 |  |  | Windows & Doors | M Turpin | 2024-06-18 | 8am to 2pm |  |  | 04/06 SMS text sent for 18/06. 11/06 SMS called N/A. 13/06 SMS called N/A Lttr sent. 20.06.24 SF Received top sheet from Martin, survey received, not photos received.
11 |  | 64125 |  | SURVEY RECEIVED | Survey Rec'd, awaiting photos | 35 | Donibristle Croft | Birmingham |  | B35 6BL |  | Miss L Adams |  | 07462244999 | georgia.6@live.co.uk |  | Windows & Doors | M Turpin | 2024-05-15 | 8am to 2pm |  |  | TS-03/05/24 Text sent offering 15/05/24. TS-03/05/24 Survey CONFIRMED for 15/05/24.23/05 SMS emailed surveyor to chase photos. 17/6; AC chased photos from Martin.
11 |  | 61524 |  | SURVEY BOOKED |  | FLAT 133E | Farnborough Road | Birmingham |  | B35 7LQ |  | Mr D Phillips |  | 07902773605 |  |  | Windows & Doors | M Turpin | 2024-07-17 | 8am to 2pm |  |  | 03.07.24 SF Sent text message for the survey. 03.07.24 SF Tenant text back saying YES survey CONFIRMED for 17.07.24.
11 |  | 70027 |  | SURVEY BOOKED |  | FLAT 133F | Farnborough Road | Birmingham |  | B35 7LQ |  | Miss Z Garratty |  | 07834836241 |  |  | Windows & Doors | M Turpin | 2024-07-17 | 8am to 2pm |  |  | 03.07.24 SF Sent text message for the survey. 03.07.24 SF Tenant text back saying YES survey CONFIRMED for 17.07.24.
11 |  | 68487 |  | SURVEY BOOKED |  | FLAT 133G | Farnborough Road | Birmingham |  | B35 7LQ |  | Miss L Capper | 07704560976 |  |  |  | Windows & Doors | M Turpin | 2024-07-17 | 8am to 2pm |  |  | 03.07.24 SF Sent text message for the survey. 04.07.24 SF Tenant called back to CONFIRM the 17.07.24 for the survey.
11 |  | 70385 |  | SURVEY BOOKED |  | FLAT 135A | Farnborough Road | Birmingham |  | B35 7LQ |  | Mr S Rahman |  | 07402352462 | sid8810@outlook.com |  | Windows & Doors | M Turpin | 2024-07-17 | 8am to 2pm |  |  | 03.07.24 SF Sent text message for the survey. 03.07.24 SF Tenant text back saying YES survey CONFIRMED for 17.07.24.
11 |  | 65979 |  | SURVEY BOOKED |  | FLAT 135B | Farnborough Road | Birmingham |  | B35 7LQ |  | Mrs C Fletcher | 07954896701 | 07389700395 |  |  | Windows & Doors | M Turpin | 2024-07-17 | 8am to 2pm |  |  | 03.07.24 SF Sent text message for the survey. 03.07.24 SF Tenant text back saying YES survey CONFIRMED for 04.07.24.
11 |  | 69874 |  | SURVEY BOOKED |  | FLAT 135C | Farnborough Road | Birmingham |  | B35 7LQ |  | Ms M Stawna |  | 07904642860 | magdalenastawna7@gmail.com |  | Windows & Doors | M Turpin | 2024-07-17 | First Call |  |  | 03.07.24 SF Sent text message for the survey.CONFIRMED first call
11 |  | 61530 |  | SURVEY BOOKED |  | FLAT 135D | Farnborough Road | Birmingham |  | B35 7LQ |  | Miss S Martin | 07888 296 587 NIS | 07517 015137 | Sandra_26@live.co.uk |  | Windows & Doors | M Turpin | 2024-07-17 | 8am to 2pm |  |  | 03.07.24 SF Sent text message. 04/07 SMS called No ending 587 is NIS. 10/07 SMS called N/A lttr sent
11 |  | 70743 |  | SURVEY BOOKED |  | FLAT 135E | Farnborough Road | Birmingham |  | B35 7LQ |  | Miss D Kirby |  | 07519452670 | dparrish520@gmail.com |  | Windows & Doors | M Turpin | 2024-07-17 | 8am to 2pm |  |  | 03.07.24 SF Sent text message for the survey.CONFIRMED for 17.07.24
11 |  | 68775 |  | SURVEY BOOKED |  | FLAT 135F | Farnborough Road | Birmingham |  | B35 7LQ |  | Ms M Gome | 07950704659 | 07950704659 | maggygome@yahoo.co.uk |  | Windows & Doors | M Turpin | 2024-07-17 | 8am to 2pm |  |  | 03.07.24 SF Sent text message for the survey.CONFIRMED for 17.07.24 after 9am
11 |  | 70763 |  | SURVEY BOOKED |  | FLAT 137A | Farnborough Road | Birmingham |  | B35 7LQ |  | Miss M Johnson | 07522 319 231 |  |  |  | Windows & Doors | M Turpin | 2024-07-17 | 8am to 2pm |  |  | 10/07 SMS text sent for 17/07. 11/07 SMS left voicemail & Lttr sent
11 |  | 70323 |  | SURVEY BOOKED |  | FLAT 137B | Farnborough Road | Birmingham |  | B35 7LQ |  | Miss N Burley Hanson |  | 07494283968 | xnicolehansonx@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-07-17 | 8am to 2pm |  |  | 03.07.24 SF Sent text message for the survey.10/07 SMS left voicemail. 11/07 SMS called N/A Lttr sent
12 |  | 65800 |  | COMMENCEMENT PENDING |  | FLAT 141F | Farnborough Road | Birmingham |  | B35 7LQ |  | Ms A A Taylor | 01212940421 |  | aggyfox@hotmail.co.uk |  | Windows & Doors | M Turpin |  |  |  |  | 03.07.24 SF NA, can't leave a message, sent letter. 15.07.24 SF Tenant called and CONFIRMED the 17.07.24 for the survey, sent Martin and email to advise.
11 |  | 63566 |  | SURVEY BOOKED |  | FLAT 127F | Farnborough Road | Birmingham |  | B35 7LQ |  | Miss A Evetts | 01217482950 | 07817842712 |  |  | Windows & Doors | M Turpin | 2024-07-30 | 8am to 2pm |  |  | 24/06 SMS text sent for 10/07. 25/06 SMS called N/A. 03.07.24 SF Tenant called & cancelled the 10.07.24 as she can ONLY do a Tuesday, she CONFIRMED the 30.07.24 for the survey to be done.
11 |  | 70554 |  | SURVEY BOOKED |  | FLAT 143A | Farnborough Road | Birmingham |  | B35 7LQ |  | Mrs S Williams | 07594515544 |  | sowilliams23@gmail.com |  | Windows & Doors | M Turpin | 2024-07-16 | 8am to 2pm |  |  | 04.07.24 SF Sent text message. CONFIRMED for 16/07
11 |  | 68150 |  | SURVEY BOOKED |  | FLAT 143B | Farnborough Road | Birmingham |  | B35 7LQ |  | Miss E Ashmore | 07958626988 | 07487792466 | elleashmore@yahoo.com |  | Windows & Doors | M Turpin | 2024-07-16 | 8am to 2pm |  |  | 04.07.24 SF Sent text message. 05/07 SMS left voicemail. 08/07 SMS called N/A lttr sent
11 |  | 68809 |  | SURVEY BOOKED |  | FLAT 143C | Farnborough Road | Birmingham |  | B35 7LQ |  | Miss C Ricketts |  | 07811487664 | charnelle1@live.co.uk |  | Windows & Doors | M Turpin | 2024-07-16 | 8am to 2pm |  |  | 04.07.24 SF Sent text message. CONFIRMED for 16/07
11 |  | 68496 |  | SURVEY BOOKED |  | FLAT 143D | Farnborough Road | Birmingham |  | B35 7LQ |  | Miss S Mason |  |  |  |  | Windows & Doors | M Turpin | 2024-07-16 | 8am to 2pm |  |  | 04.07.24 SF Sent letter, no contact details at all.
11 |  | 61551 |  | SURVEY BOOKED |  | FLAT 143E | Farnborough Road | Birmingham |  | B35 7LQ |  | Mr D McEwen | 07896744634 | 07802263271 |  |  | Windows & Doors | M Turpin | 2024-07-16 | 8am to 2pm |  |  | 04.07.24 SF Sent text message. 08/07 SMS called N/A lttr sent
11 |  | 61552 |  | SURVEY BOOKED |  | FLAT 143F | Farnborough Road | Birmingham |  | B35 7LQ |  | Mr N Smith |  |  | nigel_smith2007@yahoo.co.uk |  | Windows & Doors | M Turpin | 2024-07-16 | 8am to 2pm |  |  | 04.07.24 SF Sent letter & email
11 |  | 69120 |  | SURVEY BOOKED |  | FLAT 141A | Farnborough Road | Birmingham |  | B35 7LQ |  | Miss M J Ancill |  | 07488361831 |  |  | Windows & Doors | M Turpin | 2024-07-16 | 8am to 2pm |  |  | 04.07.24 SF Sent text message. CONFIRMED for 16/07
11 |  | 70672 |  | SURVEY BOOKED |  | FLAT 141B | Farnborough Road | Birmingham |  | B35 7LQ |  | Miss S Hinds | 07542648635 |  | princessrylee17@outlook.com |  | Windows & Doors | M Turpin | 2024-07-16 | 8am to 2pm |  |  | 04.07.24 SF Sent text message. CONFIRMED for 16/07
11 |  | 62546 |  | SURVEY BOOKED |  | FLAT 141D | Farnborough Road | Birmingham |  | B35 7LQ |  | Mr K Sullivan | 07795551880 |  |  |  | Windows & Doors | M Turpin | 2024-07-16 | 8am to 2pm |  |  | 04.07.24 SF Sent text message. 10/07 SMS called N/A, lttr sent
11 |  | 67749 |  | SURVEY BOOKED |  | FLAT 141E | Farnborough Road | Birmingham |  | B35 7LQ |  | Mr A Wornast |  | 07907914379 |  |  | Windows & Doors | M Turpin | 2024-07-16 | 8am to 2pm |  |  | 04.07.24 SF Sent text message. 10/07 SMS called NIS, lttr sent
11 |  | 55912 |  | SURVEY RECEIVED | Survey with surveyor | 48 | Heyford Way | Birmingham |  | B35 6HU |  | Mrs P Watkins | 0121 244 5837 |  |  |  | Windows & Doors | P Beahan | 2024-04-15 | 11am to 3pm |  |  | TS-08/04/24 Called tenant to book in for survey on the 15/04/24 CONFIRMED after 12pm. |  |  |  |  | 11
11 |  | 67958 |  | SURVEY RECEIVED | Photos rec'd, await survey. | FLAT 4 Block 64 | Heyford Way | Castle Vale |  | B35 6HU |  | Miss S McCann | 07470672942 | 07949552355 |  |  | Windows & Doors | P Beahan | 2024-04-18 | 11am to 3pm |  |  | TS-04/04/24 Text sent for 16/04/24. TS-04/04/24 Tenant text back no, replied asking for them to advise of which days are better. TS-08/04/24 Survey CONFIRMED for 18/04/24. |  |  |  |  | 7 | [21 empty] | Independent Scaffold |  | *Scaffold req for whole block 64*
11 |  | 66763 |  | SURVEY RECEIVED | Photos rec'd, await survey | 8 | Heyford Way | Birmingham |  | B35 6JH |  | Mrs CEJ Cluley |  | 07596 913229 | catbro09@hotmail.com |  | Windows & Doors | P Beahan | 2024-04-10 | 11am to 3pm |  |  | TS-02/04/24 Text sent for 10/04/24. TS-02/04/24 Tenant CONFIRMED for 10/04/24 |  |  |  |  | 8
11 |  | 66853 |  | SURVEY RECEIVED | Survey with surveyor | 16 | Heyford Way | Birmingham |  | B35 6JH |  | Miss C Ryley |  | 07517 709 503 |  |  | Windows & Doors | P Beahan | 2024-04-15 | 11am to 3pm |  |  | TS-04/04/24 Text sent for 15/04/24. TS-04/04/24 Tenant CONFIRMED for 15/04/24.
11 |  | 59772 |  | SURVEY RECEIVED | Waiting for survey & photos | 72 | Heyford Way | Birmingham |  | B35 6HU |  | Mrs S Goulding | 01217485932 | 07951645495 |  |  | Windows & Doors | P Beahan | 2024-04-25 | 11am to 3pm |  | 1 | TS-02/04/24 Text sent for 09/04/24. Ts-03/04/24 Called tenant and CONFIRMED for 09/04/24. TS-11/04/24 Tenant called claiming that she was moved to the 11 April, but we have her as being confirmed for 09/04/24. Her daughter is due to give birth in late Sept and wants her windows completing before then. TS-15/04/24 No access 09/04/24, carded @ 2.15pm & 3pm. TS-15/04/24 Text sent offering 25/04/24. TS-18/04/24 Called left vm, text & ltr sent. TS-19/04/24 Survey CONFIRMED for 25/04/24. 17/6; AC chased survey. |  |  |  |  | 10
11 |  | 55904 |  | SURVEY RECEIVED | Waiting for survey & photos | 31 | Heyford Way | Birmingham |  | B35 6HY |  | Miss N Hickin | 07810 473871 | 07762 385 162 |  |  | Windows & Doors | P Beahan | 2024-04-18 | 11am to 3pm |  |  | TS-02/04/24 Text sent for 11/04/24. TS-04/04/24 Called tenant left vm, txt & ltr sent. TS-08/04/24 Tenant text back no, replied back asking what days are better. TS-11/04/24 Survey CONFIRMED for 18/04/24. 17/6; AC chased survey. |  |  |  |  | 9 | 1 | [22 empty] | (08/05 SMS emailed surveyor to chase paperwork)
11 |  | 68394 |  | SURVEY RECEIVED | Waiting for survey & photos | 37 | Heyford Way | Birmingham |  | B35 6HY |  | Miss S McIntosh |  | 07523 980992 |  |  | Windows & Doors | P Beahan | 2024-04-25 | 8am to 12 noon |  |  | TS-02/04/24 Text sent for 11/04/24. TS-02/04/24 Tenant CONFIRMED for the 11/04/24. TS-15/04/24 PB marked on the diary sheet tenant had to go out and left 16yr old in the property so PB left the property. TS-15/04/24 Text sent offering 25/04/24. TS-15/04/24 Survey CONFIRMED for 25/04/24. 17/6; AC chased survey. 16.07.24 SF Pioneer Customer Advisor emailed regarding the tenant chasing an update, I've emailed back letting them know once we have a date we will contact the tenant, it's a large estate, designs need to be agreed and approved first. |  |  |  |  | 8
11 |  | 67911 |  | SURVEY RECEIVED | Waiting for survey & photos | 57C | Heyford Way | Birmingham |  | B35 6HZ |  | Mr C Kinsella | 07359 238 603 |  |  |  | Windows & Doors | P Beahan | 2024-04-25 | 8am to 12 noon |  | 1 | TS-02/04/24 Text sent for 09/04/24. TS-03/04/24 Called number is NIS sent a letter to the tenant. TS-11/04/24 Tenant called he refused entry on the 09/04/24 as he was not aware of the appointment he apologise and would like to be booked back in, number updated. TS-15/04/24 Text sent offering 25/04/24. TS-15/04/24 Survey CONFIRMED for 25/04/24. 17/6; AC chased survey. |  |  |  |  | 6
11 |  | 59778 |  | SURVEY RECEIVED | Waiting for survey & photos | 80 | Heyford Way | Birmingham |  | B35 6HU |  | Miss S A Henry | 07955 990134 | 07931 261590 |  |  | Windows & Doors | P Beahan | 2024-05-23 | 8am to 12 noon |  |  | TS-02/04/24 Text sent for 10/04/24. TS-03/04/24 Tenant text back no, text them asking which days are better. TS-12/04/24 Tenant text back to advise that they are away until 1st May. TS-03/05/24 Text sent for 14/05/24. TS-07/05/24 Tenant text back no they need any day after 17th May.13/05 SMS text sent for 23/05. 15/05 SMS called N/A. 16/05 SMS lttr sent. 17/6; AC chased survey.
11 |  | 63947 |  | SURVEY RECEIVED | Survey rcvd, awaiting all paperwork | 57D | Heyford Way | Birmingham |  | B35 6HZ |  | KEYSAFE 2404 |  |  |  |  | Windows & Doors | P Beahan | 2024-06-27 | 8am to 12 noon |  |  | TS-02/04/24 Letter sent for 09/04/24 as no contact number. TS-12/04/24 Noted on PB's diary that the tenant has passed away. Will emal the client to ask for the key safe code. TS-15/04/24 Emailed client asking for the key safe code. 08/05 SMS emailed client chasing a keysafe code available yet, awaiting reply. KEYSAFE 2404*Door choice in with survey top sheet*
11 |  | 64817 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 21 | Javelin Avenue | Birmingham |  | B35 7LH |  | Mrs E Hussain | 0121 216 0012 |  |  |  | Windows & Doors | M Turpin | 2024-04-23 | 8am to 2pm |  |  | TS-17/04/24 Called tenant left vm, ltr sent.
11 |  | 67549 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 35 | Javelin Avenue | Birmingham |  | B35 7LH |  | Miss K Shabir | 07885 646725 |  | kiranshabir@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-04-24 | 8am to 2pm |  |  | TS-15/04/24 Text sent for 24/04/24. TS-17/04/24 Called left vm, text & ltr sent. TS-17/04/24 Survey CONFIRMED for 24/04/24. TS-29/04/24 Tenant called in she will not choice door colour until she knows what colour the windows will be. 27.06.24 SF Tenant called for an update, explained we'll call her back when we have a date, she has bad mould around the windows, desperate for this to be done, sent her the door choice to make her decision, waiting for a reply. | [28 empty] | DOOR CHOICE
11 |  | 70675 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 37 | Javelin Avenue | Birmingham |  | B35 7LH |  | Miss C Harvey | 07842513779 | 07842513779 | carleyD2000@gmail.com |  | Windows & Doors | M Turpin | 2024-04-24 | 8am to 2pm |  |  | TS-15/04/24 Text sent for 24/04/24. TS-15/04/24 Survey CONFIRMED for 24/04/24.
11 |  | 66024 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 39 | Javelin Avenue | Birmingham |  | B35 7LH |  | Mrs J McNally-Ward | 07957 207224 |  |  |  | Windows & Doors | M Turpin | 2024-04-24 | 8am to 2pm |  |  | TS-15/04/24 Text sent for 24/04/24. TS-15/04/24 Survey CONFIRMED for 24/04/24.
11 |  | 65334 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 41 | Javelin Avenue | Birmingham |  | B35 7LH |  | Miss K Rafferty | 07454 980143 |  | NO1Prittyk@live.co.uk |  | Windows & Doors | M Turpin | 2024-04-24 | 8am to 2pm |  |  | TS-15/04/24 Text sent for 24/04/24. tS-15/04/24 Survey CONFIRMED for 24/04/24.
11 |  | 65262 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 10 | Javelin Avenue | Birmingham |  | B35 7LW |  | Miss K Houliston | 07986992099 | 07986992099 | kaz22@live.co.uk |  | Windows & Doors | M Turpin | 2024-04-22 | 8am to 2pm |  |  | TS-10/04/24 Called tenant to book in for survey CONFIRMED for 22/04/24.
11 |  | 61396 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 12 | Javelin Avenue | Birmingham |  | B35 7LW |  | Mr D McGahey | 01217301245 | 07960255278 |  |  | Windows & Doors | M Turpin | 2024-04-22 | 8am to 2pm |  |  | TS-12/04/24 Text sent for 22/04/24. TS-15/04/24 Survey CONFIRMED for 22/04/24.
11 |  | 62449 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 16 | Javelin Avenue | Birmingham |  | B35 7LW |  | Miss C Yearwood |  | 07481 700 725 |  |  | Windows & Doors | M Turpin | 2024-04-23 | 8am to 2pm |  |  | TS-12/04/24 Text sent for 23/04/24. TS-24/04/24 Called left vm, text & ltr sent. TS-1804/24 Survey CONFIRMED for 23/04/24.
11 |  | 66885 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 18 | Javelin Avenue | Birmingham |  | B35 7LW |  | Miss H Daly |  | 07732333535 | hayleydaly1@icloud.com |  | Windows & Doors | M Turpin | 2024-04-25 | 8am to 2pm |  |  | TS-12/04/24 Text sent for 23/04/24. TS-15/04/24 Tenant txt back that they are away but are at home on 25/04/24 text back offering 25/04/24. TS-15/04/24 Survey CONFIRMED for 25/04/24.
11 |  | 70192 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 54 | Javelin Avenue | Birmingham |  | B35 7LW |  | Miss A Lunn |  | 07939650369 | abbie.lunn@gmail.com |  | Windows & Doors | M Turpin | 2024-04-25 | 8am to 2pm |  |  | TS-15/04/24 Text sent for 25/04/24. TS-15/04/24 Survey CONFIRMED for 25/04/24.
11 |  | 69398 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 56 | Javelin Avenue | Birmingham |  | B35 7LW |  | Mrs JM Ward | 07908497768 | 07854 494 361 |  |  | Windows & Doors | M Turpin | 2024-04-25 | 8am to 2pm |  |  | TS-15/04/24 Text sent for 25/04/24. TS-16/04/24 Survey CONFIRMED for 25/04/24.
11 |  | 69254 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 58 | Javelin Avenue | Birmingham |  | B35 7LW |  | Mrs M Baldwin | 079208 73 703 |  |  |  | Windows & Doors | M Turpin | 2024-04-25 | 8am to 2pm |  |  | TS-15/04/24 Text sent for 25/04/24. TS-17/04/24 Called tenant and survey is CONFIRMED for 25/04/24.
11 |  | 67836 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 60 | Javelin Avenue | Birmingham |  | B35 7LW |  | Miss D Marshall | 07746 999 097 |  |  |  | Windows & Doors | M Turpin | 2024-04-25 | 8am to 2pm |  |  | TS-15/04/24 Text sent for 25/04/24. TS-15/04/24 Survey CONFIRMED for 25/04/24.
11 |  | 68037 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 68 | Javelin Avenue | Birmingham |  | B35 7LW |  | Mr G Evans | 07576 879 727 |  | mailmege@gmail.com |  | Windows & Doors | M Turpin | 2024-04-25 | 8am to 2pm |  |  | TS-15/04/24 Text sent for 25/04/24. TS-17/04/24 Called number nis - ltr sent. TS-22/04/24 Door choice KEMPTON in BLACK with BRASS door furniture.
11 |  | 61875 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 70 | Javelin Avenue | Birmingham |  | B35 7LW |  | Mr J Duffy | 07761130917 | 07761130917 |  |  | Windows & Doors | M Turpin | 2024-04-25 | 8am to 2pm |  |  | TS-15/04/24 Text sent for 25/04/24. TS-17/04/24 Called no answer or vm letter sent.
11 |  | 61867 |  | SURVEY RECEIVED | Photos rec'd, await survey | 46 | Javelin Avenue | Birmingham |  | B35 7LW |  | Miss S Small |  | 07875151911 | samanthasmall86@yahoo.co.uk |  | Windows & Doors | M Turpin | 2024-04-29 | 8am to 2pm |  |  | TS-15/04/24 Text sent for 24/04/24. TS-17/04/24 Called left vm, text & ltr sent. TS-18/04/24 Tenant text back replied asking what days are better for her. TS-18/04/24 Tenant txt she would like 22/04 or 29/04 text back offering 29/04/24. TS-02/05/24 Tenant called wanting to change the door choice emailed her over the door choice form.
11 |  | 61869 |  | SURVEY RECEIVED | Photos rec'd, await survey | 52 | Javelin Avenue | Birmingham |  | B35 7LW |  | Mr R Hill |  | 07786 824 141 |  |  | Windows & Doors | M Turpin | 2024-04-29 | 8am to 2pm |  |  | TS-15/04/24 Text sent for 25/04/24. TS-16/04/24 Tenant declined this appointment and asked for a different date. TS-19/04/24 Text sent for 29/04/24. TS-19/04/24 Survey CONFIRMED for 29/04/24.
11 |  | 69436 |  | SURVEY RECEIVED | Photos recvd, await survey | 88 | Javelin Avenue | Birmingham |  | B35 7LW |  | Miss V Keen |  | 07731948831 | keenvicky@yahoo.co.uk |  | Windows & Doors | M Turpin | 2024-06-06 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 29/04/24. TS-19/04/24 Tenant txt back no offered Tue/Wed/Thur of the same week tenant CONFIRMED for 02/05/24. 16/05 SMS emailed client survey photos and advised put on hold until conditions are rectified. Re-scheduled for 06/06 Dominie gave update and advised her new date.20/05 SMS text sent for 06/06. CONFIRMED for 06/06. 11/06 SMS photos recvd but no survey as on hold. Photos put in box. | [28 empty] | Untidy property
11 |  | 61737 |  | SURVEY RECEIVED | Photos rec'd, await survey | 120 | Javelin Avenue | Birmingham |  | B35 7LW |  | Miss C Collier | 0121 294 7041 | 07368168552 |  |  | Windows & Doors | M Turpin | 2024-04-29 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 29/04/24. TS-19/04/24 Survey CONFIRMED for 29/04. TS-30/04/24 Door choice received THIRSK in BLACK. | [29 empty] | DOOR CHOICE
11 |  | 67645 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 50 | Javelin Avenue | Birmingham |  | B35 7LW |  | Miss N Douglas | 07444 876856 | 07444 876856 | natalie91x@live.co.uk |  | Windows & Doors | M Turpin | 2024-05-14 | 8am to 2pm |  | 1 | TS-15/04/24 Text sent for 25/04/24. TS-15/04/24 Survey CONFIRMED for 25/04/24. TS-30/04/24 No access for 25/04/24 carded @ 1.12pm emailed client to advise. TS-03/05/24 Text sent offering 14/05/24. TS-07/05/24 Survey CONFIRMED for 14/05/24. Not surveyed on 14/05 awaiting info from surveyor to see if was another no access?
11 |  | 69693 |  | SURVEY RECEIVED | DOOR CHOICE | 122 | Javelin Avenue | Birmingham |  | B35 7LW |  | Mrs J S Belgrove Coldicott | 07939 235 459 | 07961 277 945 | jacquibelgrove70@icould.com INCORRECT EMAIL. |  | Windows & Doors | M Turpin | 2024-06-27 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 29/04/24. TS-19/04/24 Tenant3/7; photos re3c'd. text back no they are housebound, replied asking what days are better.14/06 SMS text sent for 27/06. 19/6; AC rang LM, emailed and sent letter. Email bounced back incorrect. 1/7; AC queried this survey and MT advise he cannot draw this one up yet. 3/7; photos received. 16/07 SMS surveyor noted TLO to get door choice from tenant, emailed TLO to request and put paperwork back in 'queries' box
11 |  | 68286 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 16 | Kemble Drive | Birmingham |  | B35 6QS |  | Miss G Hogan | 07443 531 782 |  | jilly_nn@hotmail.co.uk |  | Windows & Doors | P Beahan | 2024-04-17 | 8am to 12 noon |  |  | TS-04/04/24 Text sent fotr 17/04/24. TS-08/04/24 Called left vm, txt & ltr sent. TS-08/04/24 Tenant called to CONFIRM for 17/04/24. TS-15/04/24 Door choice emailed to client. |  |  |  |  | 10
11 |  | 66788 |  | SURVEY RECEIVED | DOOR CHOICE | 14 | Kemble Drive | Birmingham |  | B35 6QS |  | Miss T Gray |  | 07380795623 | terhagray@live.co.uk |  | Windows & Doors | P Beahan | 2024-04-25 | 8am to 12 noon |  |  | TS-04/04/24 Text sent fotr 17/04/24. TS-08/04/24 Called tenant left vm, txt & ltr sent for 17/04/24. TS-12/04/24 Tenant called she can't get time off from work for the appointment. TS-15/04/24 Text sent offering 25/04/24. TS-18/04/24 Called tenant survey CONFIRMED for 25/04/24. 04/06 SMS tenant called to amend door choice, emailed tenant new door choice form, awaiting reply. 17/6; AC chased survey, Door Choice in query tray. |  |  |  |  | 7
11 |  | 63994 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 26 | Kemble Drive | Birmingham |  | B35 6QS |  | Miss L Rhodes | 01217481778 | 07787140054 |  |  | Windows & Doors | P Beahan | 2024-04-18 | 8am to 12 noon |  |  | TS-04/04/24 Text sent for 18/04/24. TS-04/04/24 Survey CONFIRMED for 18/04/24. 17/6; AC chased survey. |  |  |  |  | 7 | [23 empty] | (08/05 SMS emailed surveyor to chase paperwork)
11 |  | 68874 |  | SURVEY RECEIVED | DOOR CHOICE | 28 | Kemble Drive | Birmingham |  | B35 6QS |  | Mrs S Faisal |  | 07498882503 |  |  | Windows & Doors | P Beahan | 2024-05-08 | 8am to 12 noon |  |  | TS-04/04/24 Text sent for 18/04/24. TS-08/04/24 Tenant text back no replied back asking what days are better. TS-08/04/24 Tenant txt back after 4th May but not 7th May. TS-26/04/24 Text sent for 08/05/24. TS-29/04/24 Survey CONFIRMED for 08/05/24. 17/6; AC chased survey. Door choice sheet in with survey top sheet | [28 empty] | *New door choice colour req, email in tray | [11 empty] | *New door choice colour req, email in tray
11 |  | 67851 |  | SURVEY RECEIVED | Waiting for survey & photos | FLAT 34 | Kemble Drive | Birmingham |  | B35 6QS |  | Mrs J Insley | 0121 493 6254 | 07765 161272 |  |  | Windows & Doors | P Beahan | 2024-04-18 | 8am to 12 noon |  |  | TS-04/04/24 Text sent for 18/04/24. TS-09/04/24 Called mob nis - landline temporary unavailable - ltr sent. 17/6; AC chased survey. |  |  |  |  | 5 | [23 empty] | Access Via 28 Kemble & 2 Mere Avenue. (08/05 SMS emailed surveyor to chase paperwork)
11 |  | 59802 |  | SURVEY RECEIVED | Waiting for survey & photos | FLAT 36 | Kemble Drive | Birmingham |  | B35 6QS |  | Miss W Stokes |  | 07445 945 554 | wendystokes@talktalk.net |  | Windows & Doors | P Beahan | 2024-05-07 | 8am to 12 noon |  |  | TS-04/04/24 Text sent for 18/04/24. Ts-04/04/24 Tenant txt back that they are at work and asked for Mondays or Tuesdays but not 22/04/24. TS-25/04/24 Text sent for 07/05/24. TS-26/04/24 Survey CONFIRMED for 07/05/24 at 12pm approx. 17/6; AC chased survey. | [28 empty] | Access Via 28 Kemble & 2 Mere Avenue
11 |  | 68330 |  | SURVEY RECEIVED | Photos rec'd, await survey | 4 | Lysander Way | Birmingham |  | B35 7JY |  | Miss T Wadrup |  | 07423 694 345 |  |  | Windows & Doors | M Turpin | 2024-04-30 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 30/04/24. TS-19/04/24 Survey CONFIRMED for 30/04/24.
11 |  | 69095 |  | SURVEY RECEIVED | Photos rec'd, await survey | 7 | Lysander Way | Birmingham |  | B35 7JY |  | Mr S Makadji | 07984 943066 |  | smak1010@yahoo.co.uk |  | Windows & Doors | M Turpin | 2024-04-30 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 30/04/24. TS-24/04/24 Called no answer/vm ltr and txt sent. TS-26/04/24 DM has CONFIRMED survey for 30/04/24.
11 |  | 69968 |  | SURVEY RECEIVED | Photos rec'd, await survey | 9 | Lysander Way | Birmingham |  | B35 7JY |  | Mrs LA Parrott | 07870996161 | 07870996161 | lesleyannp@aol.com |  | Windows & Doors | M Turpin | 2024-04-30 | 8am to 2pm |  |  | TS-12/04/24 Tenant has anxiety and will need Dominie to be at the property DA asked us not to book in yet. TS-25/04/24 DM attended and booked the survey in with the resident, confirmation text sent for 30/04/24.
11 |  | 70358 |  | SURVEY RECEIVED | Photos rec'd, await survey | 11 | Lysander Way | Birmingham |  | B35 7JY |  | Mrs C Birch |  | 07713918250 |  |  | Windows & Doors | M Turpin | 2024-04-30 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 30/04/24. TS-24/04/24 Called tenant survey CONFIRMED for 30/04/24.
11 |  | 69194 |  | SURVEY RECEIVED | Photos rec'd, await survey | 12 | Lysander Way | Birmingham |  | B35 7JY |  | Mrs B Amer | 07908977875 | 07908 977 875 |  |  | Windows & Doors | M Turpin | 2024-04-30 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 30/04/24. TS-19/04/24 Survey CONFIRMED for 30/04/24.
11 |  | 65686 |  | SURVEY RECEIVED | DOOR CHOICE | 14 | Lysander Way | Birmingham |  | B35 7JY |  | Miss J Walton | 0121 749 5995 |  |  |  | Windows & Doors | M Turpin | 2024-04-29 | 8am to 2pm |  |  | TS-23/04/24 Called number wouldn't connect ltr sent. TS-26/04/24 DM did site visit and survey is CONFIRMED for 29/04/24. *DOOR CHOICE FORM IN with survey top sheet*. 17/6; AC chased survey. | [40 empty] | *DOOR CHOICE FORM IN TRAY*
11 |  | 69174 |  | SURVEY RECEIVED | Photos rec'd, await survey | 15 | Lysander Way | Birmingham |  | B35 7JY |  | Mr M Duffy | 01217485808 |  | m.duffy100@btinternet.com |  | Windows & Doors | M Turpin | 2024-04-29 | 8am to 2pm |  |  | TS-23/04/24 Called tenant survey CONFIRMED for 29/04/24. 17/6; AC chased survey.
11 |  | 61424 |  | SURVEY RECEIVED | Photos rec'd, await survey | 16 | Lysander Way | Birmingham |  | B35 7JY |  | Mrs M Temple |  | 07503259162 |  |  | Windows & Doors | M Turpin | 2024-04-30 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 30/04/24. TS-24/04/24 Called tenant number nis ltr sent. TS-29/04/24 Tenant's granddaughter contacted DM and has CONFIRMED for 30/04/24. 17/6; AC chased survey.
11 |  | 61425 |  | SURVEY RECEIVED | Photos rec'd, await survey | 21 | Lysander Way | Birmingham |  | B35 7JY |  | Mr V Eames | 0121 749 1796 | 07917 021951 |  |  | Windows & Doors | M Turpin | 2024-04-30 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 30/04/24. TS-19/04/24 Survey CONFIRMED for 30/04/24.
11 |  | 68081 |  | SURVEY RECEIVED | Photos rec'd, await survey | 22 | Lysander Way | Birmingham |  | B35 7JY |  | Mrs P Carpenter |  | 07365990184 |  |  | Windows & Doors | M Turpin | 2024-05-01 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 01/05/24. TS-19/04/24 Survey CONFIRMED 01/05/24.
11 |  | 69248 |  | SURVEY RECEIVED | Photos rec'd, await survey | 23 | Lysander Way | Birmingham |  | B35 7JY |  | Mr N Doughty |  | 07555766851 | earl.salter@nhs.net |  | Windows & Doors | M Turpin | 2024-05-01 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 01/05/24. TS-24/04/24 Called number nis, letter sent. TS-29/04/24 DM visited tenant and they have confirmed for 01/05/24.
11 |  | 70333 |  | SURVEY RECEIVED | Photos rec'd, await survey | 24 | Lysander Way | Birmingham |  | B35 7JY |  | Mrs L Crisp | 01902352249 |  |  |  | Windows & Doors | M Turpin | 2024-05-01 | 8am to 2pm |  |  | TS-24/04/24 Called tenant number nis letter sent. TS-29/04/24 DM visited tenant and they have confirmed for 01/05/24.
11 |  | 64411 |  | SURVEY RECEIVED | Photos rec'd, await survey | 25 | Lysander Way | Birmingham |  | B35 7JY |  | Miss M Bhogal | 01217492763 | 07534514316 |  |  | Windows & Doors | M Turpin | 2024-05-01 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 01/05/24. TS-24/04/24 Called tenant left vm, text & ltr sent. TS-29/04/24 DM visited tenant and they have confirmed for 01/05/24.
11 |  | 65532 |  | SURVEY RECEIVED | Photos rec'd, await survey | 26 | Lysander Way | Birmingham |  | B35 7JY |  | Mrs A Hennessy |  | 07413172444 |  |  | Windows & Doors | M Turpin | 2024-05-01 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 01/05/24. TS-19/04/24 Survey CONFIRMED for 01/05/24.
11 |  | 70790 |  | SURVEY RECEIVED | Photos rec'd, await survey. Wheelchair user - needs resurveying - see comments | 27 | Lysander Way | Birmingham |  | B35 7JY |  | Mrs W Martin |  | 07592733771 | wendy1965@live.co.uk | Mobility Issues | Windows & Doors | M Turpin | 2024-05-01 | 8am to 2pm |  |  | TS-24/04/24 Emiled client to ask if the property is still void, or to supply new tenant details, letter sent to the property. Measured whilst void BUT new tenant is disabled in a wheelchair so we need to reattend to check survey suits wheelchair and provide all required DDA. | [29 empty] | do not call off UNLESS RE-SURVEYED
11 |  | 68557 |  | SURVEY RECEIVED | Photos rec'd, await survey | 30 | Lysander Way | Birmingham |  | B35 7JY |  | Mr R Palfrey |  | 07572126140 | richpalfrey@gmail.com |  | Windows & Doors | M Turpin | 2024-05-01 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 01/05/24. TS-19/04/24 Survey CONFIRMED for 01/05/24.
11 |  | 66873 |  | SURVEY RECEIVED | Photos rec'd, await survey | 5 | Lysander Way | Birmingham |  | B35 7JY |  | Miss L Sera | 07555587067 | 07769341460 |  |  | Windows & Doors | M Turpin | 2024-06-26 | 8am to 2pm |  |  | TS-19/04/24 Text sent for 30/04/24. TS-19/04/24 Tenant text back no, replied asking what days are better.13/06 SMS text sent for 26/06. 19/06 SMS called N/A Lttr sent. Await surveys designs to be agreed before surveyor can draw up.
11 |  | 69862 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 2 | Mere Avenue | Birmingham |  | B35 6QT |  | Mrs S Morgan |  | 07864538362 | gerty76.sm@gmail.com |  | Windows & Doors | P Beahan | 2024-04-18 | 11am to 3pm |  |  | TS-04/04/24 Text sent for 18/04/24. TS-04/04/24 Survey CONFIRMED for 18/04/24. TS-15/04/24 Door choice emailed to client. |  |  |  |  | 5
11 |  | 65864 |  | SURVEY RECEIVED | Survey with surveyor | 42 | Mere Avenue | Birmingham |  | B35 6QT |  | Mrs D Ismaili |  | 07476824765 | dianemorgan1973@hotmail.com |  | Windows & Doors | P Beahan | 2024-04-24 | 8am to 12 noon |  |  | TS-15/04/24 Text sent for 24/04/24. TS-15/04/24 Survey CONFIRMED for 24/04/24. 19.04.24 SF Tina sent the tenant the Door Choice to make her choice and send it back to us. 02.07.24 SF Tenant emailed chasing an installation date, replied sending her the door choice again as she's not sent it to us since April, also advised we would get back to her when we have a date for installation. |  |  |  |  | 6 | [10 empty] | 1 |  | 1
11 |  | 59876 |  | SURVEY RECEIVED | Survey with surveyor | 52 | Mere Avenue | Birmingham |  | B35 6QT |  | Mr D Thomas | 07935698548 | 07849947852 |  |  | Windows & Doors | P Beahan | 2024-04-24 | 11am to 3pm |  |  | TS-15/04/24 Text sent for 24/04/24. TS-15/04/24 Survey CONFIRMED for 24/04/24. |  |  |  |  | 5
11 |  | 60436 |  | SURVEY RECEIVED |  | 4 | Mere Avenue | Birmingham |  | B35 6QT |  | Mrs T Blunn | 7470198312 |  |  |  | Windows & Doors | P Beahan | 2024-05-14 | First Call |  | 1 | TS-04/04/24 Letter sent for 18/04/24 as no contact number. TS-19/04/24 Tenant called regarding the missed survey, rebooked for 14/05/24 as first call CONFIRMED. TS-19/04/24 No access for 18/04/24 carderd @ 11.05am. 17/6; AC chased survey.
11 |  | 59858 |  | SURVEY RECEIVED | Waiting for survey & photos | 18 | Mere Avenue | Birmingham |  | B35 6QT |  | Mr M Fitzgerald |  | 07919324496 | michael.fitzgerald3@sky.com |  | Windows & Doors | P Beahan | 2024-06-14 | 11am to 3pm |  |  | TS-12/04/24 Text sent offering 22/04/24 for survey. TS-18/04/24 Text sent cancelling the survey of 22/04/24 and offering 13/05/24. TS-03/05/24 Sent text offering 13/05/24. 08/05 SMS called no. NIS. 10/05 SMS tenant called to decline 13/05. CONFIRMED 14/06/2024
11 |  | 70674 |  | SURVEY RECEIVED |  | 20 | Mere Avenue | Birmingham |  | B35 6QT |  | Miss S Dhatt | 07734248580 |  | Simrendhatt@outlook.com |  | Windows & Doors | P Beahan | 2024-05-13 | 8am to 12 noon |  |  | TS-12/04/24 Text sent offering 22/04/24 for survey. TS-18/04/24 Text sent cancelling the survey of 22/04/24 and offering 13/05/24. TS-03/05/24 Sent text offering 13/05/24. 08/05 SMS left voicemail. 17/6; AC chased survey. 1/7; AC chased survey and PB advises the survey has been completed.
11 |  | 67833 |  | SURVEY RECEIVED | Waiting for survey & photos | 56 | Mere Avenue | Birmingham |  | B35 6QT |  | Miss N Hall | 07825 036783 |  | natalie.l.hall@outlook.com |  | Windows & Doors | P Beahan | 2024-05-08 | 8am to 12 noon |  |  | TS-25/04/24 Text sent for 07/05/24. TS-26/04/24 Survey CONFIRMED for 07/05/24. TS-26/04/24 Tenant called she forgot she has an appointment that she can't change, advised her that if we get a cancellation from the rest of the week we will book her in and if not it will be the 14th May. TS-01/05/24 Survey CONFIRMED for 08/05/24. 17/6; AC chased survey.
11 |  | 69282 |  | SURVEY RECEIVED | Waiting for survey & photos | 58 | Mere Avenue | Birmingham |  | B35 6QT |  | Ms E Bradnock | 07973 782 339 |  |  |  | Windows & Doors | P Beahan | 2024-05-07 | 11am to 3pm |  |  | TS-25/04/24 Text sent for 07/05/24. TS-26/04/24 Survey CONFIRMED for 07/05/24. 17/6; AC chased survey.
11 |  | 68828 |  | SURVEY RECEIVED | Waiting for survey & photos | 76 | Mere Avenue | Birmingham |  | B35 6QT |  | Mr G Rainsford | 07783084484 | 07783084484 | rainsfordg@googlemail.com |  | Windows & Doors | P Beahan | 2024-05-09 | 8am to 12 noon |  |  | TS-26/04/24 Text sent for 09/05/24. TS-26/04/24 Survey CONFIRMED for 09/05/24. 17/6; AC chased survey.
11 |  | 63410 |  | SURVEY RECEIVED | Waiting for survey & photos | 78 | Mere Avenue | Birmingham |  | B35 6QT |  | Miss K Webb |  | 07508420333 | Kaywebb911@gmail.com |  | Windows & Doors | P Beahan | 2024-05-09 | 8am to 12 noon |  |  | TS-26/04/24 Text sent for 09/05/24. TS-26/04/24 Survey CONFIRMED for 09/05/24. 17/6; AC chased survey.
11 |  | 65961 |  | SURVEY RECEIVED | Waiting for survey & photos | 80 | Mere Avenue | Birmingham |  | B35 6QT |  | Miss K Prince | 07985401739 |  | KimPrince1971@Hotmail.co.uk |  | Windows & Doors | P Beahan | 2024-05-09 | 11am to 3pm |  |  | TS-26/04/24 Text sent for 09/05/24. TS-26/04/24 Survey CONFIRMED for 09/05/24. 17/6; AC chased survey.
11 |  | 70677 |  | SURVEY RECEIVED | Waiting for survey & photos | 82 | Mere Avenue | Birmingham |  | B35 6QT |  | Miss M Jones | 07572404036 |  | jmatilda707@gmail.com |  | Windows & Doors | P Beahan | 2024-05-09 | 11am to 3pm |  |  | TS-26/04/24 Text sent for 09/05/24. TS-01/05/24 Called left vm, text & ltr sent.
11 |  | 68902 |  | SURVEY RECEIVED |  | FLAT 44 | Mere Avenue | Birmingham |  | B35 6QT |  | Miss T Rapier |  | 07341404533 | teeseliax@gmail.com |  | Windows & Doors | P Beahan | 2024-05-13 | 11am to 3pm |  |  | TS-15/04/24 Text sent for 24/04/24. TS-18/04/24 Text sent cancelling the survey of 24/04/24 and offering 13/05/24. TS-03/05/24 Sent text offering 13/05/24. 08/05 SMS called no. NIS. 17/6; AC chased survey. 1/7; AC chased survey and PB advises the survey has been completed. | [28 empty] | Access via 42 Mere Avenue & 52 Mere Avenue
11 |  | 67963 |  | SURVEY RECEIVED | Survey rcvd, awaiting all paperwork | FLAT 48 | Mere Avenue | Birmingham |  | B35 6QT |  | Mr T Hillier |  | 07456 500 282 | k1kel366@gmail.com |  | Windows & Doors | P Beahan | 2024-06-28 | 11am to 3pm |  |  | TS-15/04/24 Text sent for 24/04/24. TS-18/04/24 Text sent cancelling the survey of 24/04/24 and offering 13/05/24. TS-03/05/24 Sent text offering 13/05/24. 08/05 SMS called no. NIS. *NO Mondays or Thursday appointments after 11am* CONFIRMED for 28/06. (do not move this appointment) | [28 empty] | Access via 42 Mere Avenue & 52 Mere Avenue. *NO Mondays or Tuesday appointments* | [5 empty] | NO Mondays or Tuesdays
11 |  | 59875 |  | SURVEY RECEIVED | Waiting for survey & photos | FLAT 50 | Mere Avenue | Birmingham |  | B35 6QT |  | Mr J Flynn |  | 07908536618 |  |  | Windows & Doors | P Beahan | 2024-05-07 | 8am to 12 noon |  |  | TS-15/04/24 Text sent for 24/04/24. TS-15/04/24 Survey CONFIRMED for 24/04/24. TS-19/04/24 Tenant called he has an hospital appointment and now can't make the survey cancelled for 24/04/24. TS-26/04/24 Text sent for 07/05/24. TS-26/04/24 Survey CONFIRMED for 07/05/24.17/6; AC chased survey. | [28 empty] | Access via 42 Mere Avenue & 52 Mere Avenue
11 |  | 70309 |  | SURVEY RECEIVED | Waiting for survey & photos | FLAT 70 | Mere Avenue | Birmingham |  | B35 6QT |  | Mr K Higgs |  | 07856 089 210 |  |  | Windows & Doors | P Beahan | 2024-05-08 | 11am to 3pm |  |  | TS-26/04/24 Text sent for 08/05/24. TS-01/05/24 Called tenant and survey CONFIRMED for 08/05/24. 17/6; AC chased survey.
11 |  | 68805 |  | SURVEY RECEIVED | Waiting for survey & photos | FLAT 72 | Mere Avenue | Birmingham |  | B35 6QT |  | Mr R Hylton |  | 07784740360 |  |  | Windows & Doors | P Beahan | 2024-05-08 | 11am to 3pm |  |  | TS-26/04/24 Text sent for 08/05/24. TS-01/05/24 Called no answer/vm sent text and ltr. TS-01/05/24 Survey CONFIRMED for 0805/24. 17/6; AC chased survey.
11 |  | 59889 |  | SURVEY RECEIVED | Waiting for survey & photos | FLAT 74 | Mere Avenue | Birmingham |  | B35 6QT |  | Mr M Finney |  | 07723311622 | imicki@icloud.com |  | Windows & Doors | P Beahan | 2024-05-09 | 8am to 12 noon |  |  | TS-26/04/24 Text sent for 09/05/24. TS-26/04/24 Survey CONFIRMED for 09/05/24. 17/6; AC chased survey.
11 |  | 64885 |  | SURVEY RECEIVED |  | 10 | Mere Avenue | Birmingham |  | B35 6QT |  | Miss S Norton | 07895812824 |  |  |  | Windows & Doors | P Beahan | 2024-05-13 | 8am to 12 noon |  |  | TS-12/04/24 Text sent offering 22/04/24 for survey. TS-26/04/24 Tenant was in but declined the survey due to illness in the household. TS-03/05/24 Sent text offering 13/05/24. TS-07/05/24 Ltr sent. 08/05 SMS left voicemail. CONFIRMED for 13/05/2024. 17/6; AC chased survey. 1/7; AC chased survey and PB advises the survey has been completed.
11 |  | 64996 |  | SURVEY RECEIVED | Survey rcvd, awaiting all paperwork | FLAT 64 | Mere Avenue | Birmingham |  | B35 6QT |  | Mr A Kimberley | 0121 749 7045 | 07867361210 | tonykimberley83@hotmail.com |  | Windows & Doors | P Beahan | 2024-06-28 | 11am to 3pm |  |  | TS-26/04/24 Text sent for 08/05/24. TS-01/05/24 Tenant text no, replied back offering 07/05/24. TS-07/05/24 Tenant text back no, responed back asking which days are better. TS-07/05/24 Tenant messaged saying that 15th or 22nd May would be better. 03/06 SMS text sent for 14/06. 04/06 SMS called N/A. 05/06 SMS called N/A Lttr sent. Tenant declined 14/06, re-allocated to 28/06 CONFIRMED for 28/06 | [28 empty] | Access via 58 Mere & 37 Shawberry
11 |  | 67817 |  | SURVEY RECEIVED | Waiting for survey & photos | FLAT 66 | Mere Avenue | Birmingham |  | B35 6QT |  | Miss S Snelson |  | 07467587073 | sarahlouisesnelson@hotmail.com |  | Windows & Doors | P Beahan | 2024-06-14 | 8am to 12 noon |  |  | TS-26/04/24 Text sent for 08/05/24. TS-26/04/24 Survey CONFIRMED for 08/05/24. TS-08/05/24 Tenant called something has come up and she can't do today. 03/06 SMS text sent for 14/06. CONFIRMED for 14/06 | [28 empty] | Access via 58 Mere & 37 Shawberry
11 |  | 66789 |  | SURVEY RECEIVED | SEE COMMENTS | 24 | Montrose Drive | Birmingham |  | B35 6DH | House | Miss L Gordon | 07920 793 854 |  |  |  | Windows & Doors | M Turpin | 2024-06-20 | 8am to 2pm |  |  | 11/06 text sent for 20/06. CONFIRMED for 20/06. 24.06.24 SF Received top sheet from Martin, survey received waiting for photos. Also Dominie is speaking to client as lots of animal tanks that will mean cannot arrange to fit until Dominie has resolved and come back to us. |  |  |  |  | 11 | [10 empty] | 1 |  | 1 | [7 empty] | No |  | Brick | Tenant advised to isolate there dog. Surveyor requested a RLO to visit the property, cluttered house very dirty, lizard cage in the way, back garden & inside the house needs cleaning, electrical cables | [11 empty] | RLO - Dominie will take photos of cluttered house, lizard cage in the way, need house cleaning before installation and tenants dog needs to be isolated during installation.Dominie is speaking to client as lots of animal tanks that will mean cannot arrange to fit until Dominie has resolved and come back to us.
11 |  | 61182 |  | SURVEY RECEIVED | Survey Rec'd, awaiting photos | FLAT 1 Block 1 | Montrose Drive | Castle Vale |  | B35 6DH | Flat | Miss A McLaren | 01217478782 |  |  |  | Windows & Doors | M Turpin | 2024-06-20 | 8am to 2pm |  |  | 13/06 SMS called N/A . 14/06 SMS called N/A Lttr sent. 24.06.24 SF Received top sheet from Martin, survey received waiting for photos. Darren will query if the tenant can have the rear patio combi replaced the French Doors, if not remove the double door from the tracker. |  |  |  |  | 6 | [6 empty] | 1 | [13 empty] | No | Jammer System | Brick | Tenant advised to isolate pets during installation | [11 empty] | Tenant advised to isolate pets during installation.
11 |  | 68829 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 3 | Trident Boulevard | Birmingham |  | B35 7LZ |  | Miss M Lambert |  | 07369 280 512 |  |  | Windows & Doors | M Turpin | 2024-07-01 | 8am to 2pm |  |  | 19/06 SMS text sent for 01/07. CONFIRMED for 01/07. 09.07.24 SF Photos received & printed, awaiting survey.
11 |  | 61918 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 5 | Trident Boulevard | Birmingham |  | B35 7LZ |  | Mrs J Donovan |  | 07766513778 | joannedonovan00@outlook.com |  | Windows & Doors | M Turpin | 2024-07-01 | 8am to 2pm |  |  | 19/06 SMS text sent for 01/07. 19/6 AC emailed. Email failed to deliver. CONFIRMED for 01/07. 09.07.24 SF Photos received & printed, awaiting survey.
11 |  | 61486 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 8 | Trident Boulevard | Birmingham |  | B35 7LZ |  | Mr D Yelland |  | 07956045548 | deanyelland@hotmail.com |  | Windows & Doors | M Turpin | 2024-07-01 | 8am to 2pm |  |  | 19/06 SMS text sent for 01/07, 19/6 AC emailed. CONFIRMED for 01/07. 09.07.24 SF Photos received & printed, awaiting survey.
11 |  | 69899 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 12 | Trident Boulevard | Birmingham |  | B35 7LZ |  | Mr D Sztuk |  | 07498595415 | sztukdawid@gmail.com |  | Windows & Doors | M Turpin | 2024-07-01 | 10am to 2pm |  |  | 19/06 SMS text sent for 01/07. 19/6 AC emailed. CONFIRMED for 01/07 after 10am. 09.07.24 SF Photos received & printed, awaiting survey.
11 |  | 61899 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 15 | Trident Boulevard | Birmingham |  | B35 7LZ |  | Miss S Lynch | 07800777467 |  | shazlynch1971@hotmail.com |  | Windows & Doors | M Turpin | 2024-07-02 | 8am to 2pm |  |  | CONFIRMED for 2/7. 09.07.24 SF Photos received & printed, awaiting survey.
11 |  | 65063 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 16 | Trident Boulevard | Birmingham |  | B35 7LZ |  | Miss L Hanson | 01217493832 |  |  |  | Windows & Doors | M Turpin | 2024-07-02 | 8am to 2pm |  |  | 19/6; AC sent letter. 09.07.24 SF Photos received & printed, awaiting survey.
11 |  | 61860 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 18 | Trident Boulevard | Birmingham |  | B35 7LZ |  | Mrs T High |  |  |  |  | Windows & Doors | M Turpin | 2024-07-02 | 8am to 2pm |  |  | 19/6; AC sent letter. 09.07.24 SF Photos received & printed, awaiting survey.
11 |  | 61706 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 24 | Trident Boulevard | Birmingham |  | B35 7LZ |  | Miss K Collin |  | 07443 461 580 | kellycollin625@yahoo.co.uk |  | Windows & Doors | M Turpin | 2024-07-02 | 8am to 2pm |  |  | 19/6; AC text for 2/7 and emailed. CONFIRMED for 2/7 AFTER 8.30AM. 10.07.24 SF Emailed Martin to advise we've only got external photos, waiting for the internal photos.
11 |  | 70767 |  | SURVEY RECEIVED | Survey Rec'd, awaiting photos | 76 | Watton Green | Birmingham |  | B35 7JR |  | Lauren Heinz | 7850489726 |  |  |  | Windows & Doors | M Turpin | 2024-05-23 | 8am to 2pm |  |  | TS-26/04/24 Letter sent to property offering 07/05/24. TS-02/05/24 Tenant called she is unable to make the 07/05 as she is at work she needs either a Mon, Thurs or Friday.13/05 SMS text sent for 23/05. CONFIRMED for 23/05. 24.05.24 SF Martin Turpin attended, received top sheet, survey sent for cleansing, doors & windows surveyed, see photos for all windows when received. 17/6; AC chased photos.
11 |  | 61320 |  | SURVEY BOOKED |  | 14 | Avro Way | Birmingham |  | B35 7NW |  | Mr L Caulfield |  |  |  |  | Windows & Doors | S Burgess | 2024-07-25 | 8am to 12 noon |  | 1 | 19/6; AC sent letter for survey 3/7. 04/07 SMS 1st no access on 03/07. 08/07 SMS no contact details so lttr sent for 25/07
11 |  | 61319 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 16 | Avro Way | Birmingham |  | B35 7NW |  | Mr J Brennan | 01217482482 | 0121 748 2482 |  |  | Windows & Doors | S Burgess | 2024-07-03 | 8am to 12 noon |  |  | 19/6; AC rang NA, sent letter for survey 3/7.
11 |  | 64915 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 17 | Avro Way | Birmingham |  | B35 7NW |  | Mr M Fone | 07488 2777 74 |  |  |  | Windows & Doors | S Burgess | 2024-07-03 | 11am to 3pm |  |  | 19/6; AC text for survey for 3/7. CONFIRMED FOR 3/7. Tenant is epileptic, asthmatic, arthritis and blood cancer
11 |  | 62763 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 18 | Avro Way | Birmingham |  | B35 7NW |  | Mrs M Mackenzie | 01217485666 | 07955 882689 |  |  | Windows & Doors | S Burgess | 2024-07-03 | 8am to 12 noon |  |  | 19/6; AC text for survey for 3/7. CONFIRMED FOR 3/7.
11 |  | 61324 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 20 | Avro Way | Birmingham |  | B35 7NW |  | Mrs S Pearson |  | 07957991918 |  |  | Windows & Doors | S Burgess | 2024-07-03 | 11am to 3pm |  |  | 19/6; AC text for survey for 3/7. 21/6; RANG BUT WRONG NUMBER, SENT LETTER.
11 |  | 68996 |  | SURVEY BOOKED |  | FLAT 6 Block 16 | Bicester Square | Castle Vale |  | B35 6HR |  | Miss KG Walker | 7387314944 | 07557783791 |  |  | Windows & Doors | S Burgess | 2024-07-24 |  |  | 2 | TS-02/04/24 Text sent for 12/04/24. TS-04/04/24 Called tenant left vm, txt & ltr sent. TS-15/04/24 No access for 12/04/24 carded @ 12.26pm.04/06 SMS text sent for 18/06. 11/06 SMS called N/A. 13/06 SMS called N/A Lttr sent. 19/06 SMS 2nd no access survey on 18/06 at 11.03am, client emailed.19/6; AC text for survey for 3/7. 04/07 SMS emailed client & Dominie to arrange this 3rd access attempt directly with the tenant.
11 |  | 68516 |  | SURVEY BOOKED |  | 5 | Bond Drive | Birmingham |  | B35 7QQ |  | Mrs W Walsh |  | 07496 536972 | wendywalsh.cv@btinternet.com |  | Windows & Doors | S Burgess | 2024-07-24 | 11am to 3pm |  |  | 05/06 SMS text sent for 19/06. 11/06 SMS called N/A. 13/06 SMS called N/A lttr sent. 18/06 SMS tenant called to cancel, re-scheduled to 09/07 tenant CONFIRMED. 04/07 SMS tenant cancelled.05/07 SMS emailed tenant for 24/07. 10/07 SMS left voicemail. 11/07 SMS called N/A lttr sent
11 |  | 69724 |  | SURVEY BOOKED |  | 16 | Bovingdon Road | Birmingham |  | B35 6QD |  | Miss J-J Mckean | 7512032487 | 07547322202 | pwrincessjay@outlook.com |  | Windows & Doors | P Beahan | 2024-07-11 | 11am to 3pm |  |  | 29/05 SMS text sent for 12/06. 31/05 SMS called & no. NIS lttr sent. 14/06 SMS tenant called to advise she missed her survey on 12/06 and to give us a new contact number. CONFIRMED for 11/07
11 |  | 69709 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 18 | Bovingdon Road | Birmingham |  | B35 6QD |  | Miss C Chambers |  | 07779 003 594 | corrine.chambers@btinternet.com |  | Windows & Doors | P Beahan | 2024-07-10 | 8am to 2pm |  |  | 29/05 SMS text sent for 12/06. CONFIRMED for 12/06. CONFIRMED for 10/07.
11 |  | 68517 |  | SURVEY BOOKED |  | 15 | Chigwell Close | Birmingham |  | B35 7HG |  | Ms G Metcalfe | 07854 614 241 |  | Georginahumphries@icloud.com |  | Windows & Doors | P Beahan | 2024-07-17 | 8am to 12 noon |  | 1 | 19/06 SMS text sent for 28/06. 19/6; AC emailed. 19/6; tenant emailed to confirm. 28.06.24 SF Tenant called, he missed the surveyor, NO ACCESS, he said he wasn't advised, but we sent an email to Georgina and she replied confirming they would be home, this never happened so we've re-booked this for 17.07.24, sent another email to Georgina to confirm this.
11 |  | 68369 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 55 | Chigwell Close | Birmingham |  | B35 7HG |  | Mr M Hughes |  | 07368627234 |  |  | Windows & Doors | P Beahan | 2024-07-05 | 8am to 12 noon |  |  | 19/6; AC sent text for survey. CONFIRMED FOR 5/7. 7/7; PB advised he has surveyed via sending in his sheet.
11 |  | 55582 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 61 | Chigwell Close | Birmingham |  | B35 7HG |  | Mrs D Machin | 07860 112 206 |  |  |  | Windows & Doors | P Beahan | 2024-07-05 | 11am to 3pm |  |  | 19/6; AC sent text for survey. CONFIRMED FOR 5/7. 7/7; PB advised he has surveyed via sending in his sheet.
11 |  | 55583 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 63 | Chigwell Close | Birmingham |  | B35 7HG |  | Mrs D V Heath |  |  |  |  | Windows & Doors | P Beahan | 2024-07-05 | 11am to 3pm |  |  | 19/6; AC sent letter for survey. 7/7; PB advised he has surveyed via sending in his sheet.
11 |  | 69332 |  | SURVEY BOOKED |  | 4 | Chigwell Close | Birmingham |  | B35 7HH |  | Mr S Doyle |  | 07735495850 | stevendoyle1984@hotmail.co.uk |  | Windows & Doors | P Beahan | 2024-07-17 | 8am to 12 noon |  |  | 14/06 SMS text sent for 27/06. 19/6; AC rang but cannot leave message, emailed and sent letter. Tenant rang Sharnel changing her date to 1/7 however PB is not surveying then and Sharnel had not asked Martin to do it either. Tenant not happy but rearranged for 17/7, confirmed.
11 |  | 69433 |  | SURVEY BOOKED |  | 10 | Chigwell Close | Birmingham |  | B35 7HH |  | Miss A Delaney |  | 07492 970 639 | angeldelaney96@outlook.com |  | Windows & Doors | P Beahan | 2024-07-17 | 8am to 12 noon |  | 1 | 19/06 SMS lttr sent. 19/6; AC emailed. 28/6; NO ACCESS, CARDED. 1/7; tenant rang as missed surveyeor on 28/6. CP advised anoter date will be offered soon. 28.06.24 SF Called tenant, CONFIRMED for 05.07.24 for the survey. 02.07.24 SF Tenant called, cancelled, re-booked and CONFIRMED for 17.07.24.
11 |  | 65764 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 20 | Chigwell Close | Birmingham |  | B35 7HH |  | Mrs S Webb |  | 0121 649 3211 |  |  | Windows & Doors | P Beahan | 2024-07-05 | 8am to 12 noon |  |  | 19/6; AC sent letter for survey. 21/6; AC rang NA. 7/7; PB advised he has surveyed via sending in his sheet.
11 |  | 61363 |  | SURVEY BOOKED |  | 21 | Concorde Drive | Birmingham |  | B35 7EE |  | Miss J Weston |  | 07429922484 |  |  | Windows & Doors | M Turpin | 2024-07-25 | 8am to 2pm |  | 1 | 04/06 SMS text sent for 18/06. 11/06 SMS called N/A. 13/06 SMS called N/A lttr sent. 20.06.24 SF Received top sheet from Martin, nothing filled out, assuming this was NO ACCESS 18/6, need to re-book. 02/07 SMS 1st no access on 18/06, emailed client & Dominie to advise.08/07 SMS text sent for 25/07
11 |  | 65877 |  | SURVEY BOOKED |  | FLAT 1 Block 33 | Concorde Drive | Castle Vale |  | B35 7EE |  | Miss SL Murphy |  | 07759039463 | mia-roseclarke11@outlook.com |  | Windows & Doors | M Turpin | 2024-07-16 | 8am to 2pm |  | 1 | 05/06 SMS text sent for 19/06. 11/06 SMS left voicemail. 13/06 SMS called N/A lttr sent. 21.06.24 SF Received top sheet from Martin, NO ACCESS 19/6, need to re-book. 02/07 SMS no access photo for 19/06 @ 8.55am sent to client & Dominie. 04.07.24 SF Sent text message. 10/07 SMS left voicemail. 11/07 SMS called N/A lttr sent
11 |  | 70481 |  | SURVEY BOOKED |  | FLAT 3 Block 33 | Concorde Drive | Castle Vale |  | B35 7EE |  | Miss S Minhas |  | 07856434055 | minhasshahida@gmail.com |  | Windows & Doors | M Turpin | 2024-07-16 | 8am to 2pm |  | 1 | 05/06 SMS text sent for 19/06. 11/06 SMS called N/A. 13/06 SMS called N/A lttr sent. 21.06.24 SF Received top sheet from Martin, NO ACCESS 19/6, need to re-book. 02/07 SMS emailed client and Dominie no access photos on 19/06. 04.07.24 SF Sent text message. 10/07 SMS N/A lttr sent
11 |  | 69485 |  | SURVEY BOOKED |  | FLAT 10 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss JM Lydon | 01217302262 | 07732885362 | jacquelinelydon@gmail.com |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm |  |  | (Access via 8 Cosford & 2 Abingdon) 20/05 SMS text sent for 06/06. Tenant text back to decline with no details. 19/06 SMS text sent for 27/06. 24/06 SMS tenant text back to decline appointment on 27/06. 11/07 SMS spoke to tenant on phone so 27/07 is CONFIRMED | [28 empty] | Acess via 8 Cosford & 2 Abingdon | [11 empty] | (Access via 8 Cosford & 2 Abingdon)
11 |  | 59708 |  | SURVEY BOOKED |  | 3 | Cranwell Way | Birmingham |  | B35 6QH |  | Miss Z Carr |  | 07856402181 |  |  | Windows & Doors | M Turpin | 2024-07-30 | 8am to 2pm |  | 1 | 14/06 SMS text sent for 25/06. 18/6; AC rang and LM. 19/6; letter sent. 26/6/2024; NO ACCESS, CARDED.
11 |  | 66186 |  | SURVEY RECEIVED | Survey Rec'd, awaiting photos | FLAT 133A | Farnborough Road | Birmingham |  | B35 7LQ |  | Rita Mponzo |  | 07388 645 206 | ritamponzo@yahoo.com |  | Windows & Doors | M Turpin | 2024-07-11 | 8am to 2pm |  |  | 24/06 SMS text sent for 11/07. 25/06 SMS left voicemail. At survey was different tenant in property. |  |  | 5 | [14 empty] | 1
11 |  | 56974 |  | SURVEY BOOKED |  | 1 | Hawker Drive | Birmingham |  | B35 7DX |  | Miss K Hinett | 0790 197 5798 | 0121 749 5278 |  |  | Windows & Doors | P Beahan | 2024-07-31 | 11am to 3pm |  | 1 | 24/06 SMS text sent for 10/07. 25/06 SMS called and tenant cut off call. 11/07 SMS surveyor reported 1st no access on 10/07, await no access card photo. 12/7; photo received. 15/7; AC SENT SURVEY TEXT FOR 31/7.
11 |  | 68514 |  | SURVEY BOOKED |  | 35 | Hawker Drive | Birmingham |  | B35 7DY |  | Mrs G Brown-Robinson | 01216784443 |  | georgiabrown240@gmail.com |  | Windows & Doors | P Beahan | 2024-07-18 | 8am to 12 noon |  |  | 05/07 SMS called no. NIS lttr sent for 18/07
12 |  | 55816 |  | COMMENCEMENT PENDING | SEE COMMENTS | 37 | Hawker Drive | Birmingham |  | B35 7DY |  | Mr D Cooney | 0121 747 0410 | 07565 600 342 |  |  | Windows & Doors | P Beahan | DO NOT BOOK |  |  |  | 08/07 SMS text sent for 24/07. CONFIRMED for 24/07 after 12pm pls. 17/07 SMS tenant called to advise is under paliative care so not upto any works being done, emailed TLO and Client to advise put on hold.
11 |  | 61931 |  | SURVEY BOOKED |  | 39 | Hawker Drive | Birmingham |  | B35 7DY |  | Ms P C Moran | 01217477076 | 07455 201 844 | pippa30uk@yahoo.co.uk |  | Windows & Doors | P Beahan | 2024-07-24 | 8am to 12 noon |  |  | 08/07 SMS text sent for 24/07. 10/07 SMS called NIS. 11/07 SMS lttr sent
11 |  | 55820 |  | SURVEY BOOKED |  | 43 | Hawker Drive | Birmingham |  | B35 7DY |  | Mrs Y Taylor | 01217487193 |  |  |  | Windows & Doors | P Beahan | 2024-07-24 | 11am to 3pm |  |  | 08/07 SMS lttr sent for 24/07
11 |  | 69098 |  | SURVEY BOOKED |  | 45 | Hawker Drive | Birmingham |  | B35 7DY |  | Miss L Jones |  | 07312253894 | lindseylocket@hotmail.co.uk |  | Windows & Doors | P Beahan | 2024-07-24 | 11am to 3pm |  |  | 08/07 SMS text sent for 24/07. 11/07 SMS called no. NIS, lttr sent
12 |  | 63343 |  | COMMENCEMENT PENDING |  | 10 | Hawker Drive | Birmingham |  | B35 7EG |  | Miss S Kelly | 01217482006 | 07564 366 180 |  |  | Windows & Doors | P Beahan | Must be school Hols |  |  |  | 05/07 SMS text sent for 18/07. 08/07 SMS left voicemail. 10/07 SMS called N/A Lttr sent. 16/07 SMS tenant called to cancel. Must be in school hols
11 |  | 58465 |  | SURVEY BOOKED |  | 38 | Hawker Drive | Birmingham |  | B35 7EG |  | Mrs S L Burke |  | 07470280658 |  |  | Windows & Doors | P Beahan | 2024-07-24 | 8am to 12 noon |  |  | 08/07 SMS text sent for 24/07. 10/07 SMS left voicemail. 10.07.24 SF Tenant called to CONFIRM the 24.07.24 for us to attend.
11 |  | 61380 |  | SURVEY BOOKED |  | 10A | Hawker Drive | Birmingham |  | B35 7EG |  | Mrs K Moore | 07857 457916 |  |  |  | Windows & Doors | P Beahan | 2024-07-18 | 11am to 3pm |  |  | 05/07 SMS text sent for 18/07. CONFIRMED for 18/07.
11 |  | 61374 |  | SURVEY BOOKED |  | 4B | Hawker Drive | Birmingham |  | B35 7EG |  | Miss K Hanson |  |  |  |  | Windows & Doors | P Beahan | 2024-07-18 | 8am to 12 noon |  |  | 05/07 SMS lttr sent for 18/07
11 |  | 65208 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 6 | Hawker Drive | Birmingham |  | B35 7EG |  | Mrs T Hobbis |  | 07823471922 |  |  | Windows & Doors | P Beahan | 2024-07-05 | 11am to 3pm |  |  | 24/06 SMS text sent for 05/07. CONFIRMED FOR 5/7. 7/7; PB advised he has surveyed via sending in his sheet.
11 |  | 65265 |  | SURVEY BOOKED |  | 6A | Hawker Drive | Birmingham |  | B35 7EG |  | Mrs E Venard | 0121 749 1523 | 07486 522672 |  |  | Windows & Doors | P Beahan | 2024-07-18 | 8am to 12 noon |  |  | 05/07 SMS text sent for 18/07. 08/07 SMS called N/A. 10/07 SMS called N/A Lttr sent.
11 |  | 69677 |  | SURVEY BOOKED |  | 8 | Hawker Drive | Birmingham |  | B35 7EG |  | Mrs V Hassall |  | 07552733533 |  |  | Windows & Doors | P Beahan | 2024-07-17 | 11am to 3pm |  |  | 03.07.24 SF Sent text message. 03.07.24 SF Tenant text back CONFIRMED for 17.07.24
11 |  | 70185 |  | SURVEY BOOKED |  | 8A | Hawker Drive | Birmingham |  | B35 7EG |  | Miss D Meah |  |  | meahdonna58@gmail.com |  | Windows & Doors | P Beahan | 2024-07-17 | 11am to 3pm |  |  | 08/07 SMS lttr sent for 17/07
11 |  | 61378 |  | SURVEY BOOKED |  | 8B | Hawker Drive | Birmingham |  | B35 7EG |  | Miss C Wallace |  |  |  |  | Windows & Doors | P Beahan | 2024-07-17 | 11am to 3pm
11 |  | 69971 |  | SURVEY RECEIVED | Photos rec'd, await survey. | FLAT 2A | Hawker Drive | Birmingham |  | B35 7EG |  | Mr C Moran |  | 07867922078 | conormoran93@putlook.com |  | Windows & Doors | P Beahan | 2024-07-10 | 8am to 12 noon |  |  | 24/06 SMS text sent for 10/07. CONFIRMED for 10/07 after 10am
11 |  | 61979 |  | SURVEY RECEIVED | Photos rec'd, await survey. | FLAT 2B | Hawker Drive | Birmingham |  | B35 7EG |  | Mrs J Wheeler | 01217470368 | 07828 664416 | joanbw@yahoo.com |  | Windows & Doors | P Beahan | 2024-07-10 | 8am to 12 noon |  |  | 24/06 SMS text sent for 10/07. 25/06 SMS called N/A
11 |  | 69536 |  | SURVEY BOOKED |  | FLAT 4 | Hawker Drive | Birmingham |  | B35 7EG |  | Mrs C Langford | 01217491866 | 07949372749 | carollangford@hotmail.co.uk |  | Windows & Doors | P Beahan | 2024-07-11 | 8am to 12 noon
11 |  | 59776 |  | SURVEY BOOKED |  | 76 | Heyford Way | Birmingham |  | B35 6HU |  | Mrs P Brown | 079254 14 091 |  |  |  | Windows & Doors | P Beahan | 2024-07-25 | 8am to 12 noon |  | 2 | TS-02/04/24 Text sent for 10/04/24. TS-03/04/24 Called tenant number NIS ltr sent. TS-15/04/24 NO access for 10/04/24 carded @ 11.05am. TS-15/04/24 Text sent offering 25/04/24. TS-18/04/24 Sent text cancelling 25/04/24 and offering 14/05/24. 08/05 SMS no. NIS. 17/6; AC chased survey. 1/7/2024; AC NOTED PB NO access for 14/05/24 carded @ 10.20am. 03/07 SMS emailed client & Dominie to advised scheduled in for 25/07/2024 but as 3rd access attempt they need to arrange access directly with the tenant
11 |  | 69782 |  | SURVEY BOOKED |  | 34 | Javelin Avenue | Birmingham |  | B35 7LW |  | Miss T Gordon |  | 07583 234 987 | TionnaGordon@hotmail.com |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm |  | 2 | TS-15/04/24 Text sent for 24/04/24. tS-15/04/24 Tenant txt back no replied asking what days are better. TS-19/04/24 Text sent for 29/04/24. TS-22/04/24 Survey CONFIRMED for 29/04/24.14/05 SMS 1st survey no access on 29.04 email sent to client to advise. 14/06 SMS text sent for 27/06. CONFIRMED for 27/06.03/07 SMS 2nd no access on 27/06 carded, emailed client & Dominie with photos, advised new date so they can arrange 3rd attempt, emailed client & Dom to arrange access directly with the tenant for 29/07
11 |  | 67507 |  | SURVEY BOOKED |  | 11 | Javelin Avenue | Birmingham |  | B35 7LH |  | Miss KL Macken |  | 07538863242 | katemacken@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm |  | 2 | TS-12/04/24 Text sent for 22/04/24. TS-15/04/24 Survey CONFIRMED for 22/04/24. TS-30/04/24 No access for 22/04/24 carded @ 1.30pm emailed client. 14/06 SMS text sent for 27/06. 1/7 No access for 27/06/24 carded @ email sent to client and Dominie with photos. 03/07 SMS 3rd attempt, emailed client & Dom to arrange access directly with the tenant for this date. 29/07/2024
11 |  | 61868 |  | SURVEY BOOKED |  | 48 | Javelin Avenue | Birmingham |  | B35 7LW |  | Ms S Jones |  | 07389811707 | sarahjanejones1575@gmail.com |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm |  | 2 | TS-15/04/24 Text sent for 24/04/24. TS-17/04/24 Called phone was switched off - text & ltr sent. Ts-30/04/24 No access for 24/04/24 carded @ 1.10pm emailed client.14/06 SMS text sent for 27/06. 19/6; AC rang but phone switched off. Emailed and sent letter. 27/62024; Tenant advised Martin they have covid so cannot be measured. they did not advise office though so classed as no access. 03/07 SMS 3rd attempt, emailed client & Dom to arrange access directly with the tenant for 29/07
11 |  | 69627 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 22 | Mere Avenue | Birmingham |  | B35 6QT |  | Mrs F Dainty |  | 07947 56 59 58 incorrect number | Francescaleigh2010@hotmail.co.uk |  | Windows & Doors | P Beahan | 2024-07-11 | 8am to 12 noon |  |  | TS-12/04/24 Text sent for 23/04/24. TS-18/04/24 Text sent cancelling the survey of 23/04/24 and offering 13/05/24. TS-03/05/24 Sent text offering 13/05/24. 08/05 SMS called tenant ended call. 10/05 SMS tenant cancelled 13/05. 14/06 SMS text sent for 27/06. 19/6; AC rang and LM, emailed and sent letter. Cancelled as working all day. Can be home 26/6? Ac advised cannot offer thst date but can attend 11/7?
11 |  | 64700 |  | SURVEY BOOKED |  | FLAT 60 | Mere Avenue | Birmingham |  | B35 6QT |  | Mr P J McCallion |  | 7751066503 | patrickmccallion8@gmail.com |  | Windows & Doors | P Beahan | 2024-07-25 | 8am to 12 noon |  | 1 | TS-25/04/24 Text sent for 07/05/24. TS-01/05/24 Called left vm, text & ltr sent. 08/05 SMS tenant called to give a new contact number 07751 066 503 and advise had a missed appointment. 03/06 SMS text sent for 14/06. 04/06 SMS called left voicemail. 05/06 SMS called N/A Lttr sent. 17/06 SMS 1st survey no access on 14/06, will email Dominieonce photo recvd from surveyor.24/06 SMS text sent for 11/07. CONFIRMED for 11/07. 11.07.24 SF Tenant called, cancelled survey for today, no-one to be in the house for him, re-booked for 25.07.24, tenant CONFIRMED, either him or a friend will be in the property. | [28 empty] | Access via 58 Mere & 37 Shawberry
11 |  | 69875 |  | SURVEY BOOKED |  | FLAT 62 | Mere Avenue | Birmingham |  | B35 6QT |  | Miss C Timberlake | 07543445769 | 07543445769 | charleyanne5@aol.com |  | Windows & Doors | P Beahan | 2024-05-07 | 11am to 3pm |  |  | TS-25/04/24 Text sent for 07/05/24. TS-01/05/24 Called survey CONFIRMED for 07/05/24 but tenant has a nursery run 12.50pm for about 30 mins. 17/6; AC chased survey. 1/7; AC chased survey. | [28 empty] | Access via 58 Mere & 37 Shawberry
11 |  | 68165 |  | SURVEY BOOKED |  | FLAT 68 | Mere Avenue | Birmingham |  | B35 6QT |  | Mr S Gardiner | 7305947116 | 07873894184 | mya1997@live.co.uk |  | Windows & Doors | P Beahan | 2024-07-25 | 11am to 3pm |  | 2 | TS-26/04/24 Text sent for 08/05/24. TS-01/05/24 Called left vm, text & ltr sent. TS-01/05/24 Survey CONFIRMED for 08/05/24. 03/06 SMS text sent for 14/06. 04/06 SMS called N/A. 17/06 SMS 1st survey no access on 14/06, will email Dominie once photo recvd from surveyor.CONFIRMED for 14/06. 24/06 SMS text sent for 11/07. CONFIRMED for 11/07. 11/7; 2ND NO ACCESS SURVEY, CARDED. PHOTO IN FILE. Sent to client. AC chased PB for first card photo too. 15/7; AC asked client and TLO to confirm the final attempt appointment on 25/7.
11 |  | 69648 |  | SURVEY BOOKED |  | FLAT 5 Block 1 | Montrose Drive | Castle Vale |  | B35 6DH |  | Mr K Palmer | 07399584441 |  | kanepalmer@gmail.com |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm |  | 1 | 11/06 SMS text sent for 20/06. CONFIRMED for 20/06. 24.06.24 SF Received top sheet from Martin, NO ACCESS, carded, need to re-book. 02/07 SMS emailed client & Dominie no access photos from 20/06
11 |  | 67331 |  | SURVEY BOOKED |  | 9 | Montrose Drive | Birmingham |  | B35 6DH |  | Miss R Garrington |  | 07397 384 556 |  |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm |  | 2 | 10/06 SMS text sent for 12/06. 17/06 SMS 1st survey no access on 12/06, emailed client to advise. 19/06 SMS text sent for 27/06 and AC rang and left message and sent letter. 03/07 SMS No access for 27/06/24 3rd attempt, emailed client & Dom to arrange access directly with the tenant for 29/07
11 |  | 65909 |  | SURVEY BOOKED |  | 17 | Montrose Drive | Birmingham |  | B35 6DH |  | Mr N Proffitt | 07874 328 741 |  |  |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm |  | 1 | 11/06 text sent for 20/06. 13/06 SMS called no. NIS lttr sent. 24.06.24 SF Received top sheet from Martin, NO ACCESS, carded, need to re-book. 02/07 SMS emailed client & Dominie no access photos
11 |  | 66146 |  | SURVEY BOOKED |  | 19 | Montrose Drive | Birmingham |  | B35 6DH |  | Mr MA Smith | 07908293857 |  |  |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm |  | 1 | 11/06 text sent for 20/06. 13/06 SMS called N/A. 14/06 SMS called N/A Lttr sent. 24.06.24 SF Received top sheet from Martin, NO ACCESS, carded, need to re-book. 02/07 SMS emailed client & Dominie no access 20/06 photos
11 |  | 60269 |  | SURVEY BOOKED |  | 30 | Northolt Drive | Birmingham |  | B35 6QX |  | Mrs N Parry | 07707478425 |  | nickki250@live.co.uk |  | Windows & Doors | S Burgess | 2024-07-24 | 8am to 12 noon |  |  | TS-12/04/24 Text sent for 23/04/24. ts-15/04/24 Tenant called she is away on the 23/04/24 back early May. 23.05.24 SF Sent text for 07.07 to survey. 29/05 SMS left voicemail. 30/05 SMS tenant declined 07/06.13/06 SMS text sent for 27/06. CONFIRMED for 27/06. 26/6; TENANT CANCELLED SURVEY. 08/07 SMS text sent for 24/07. CONFIRMED
11 |  | 70035 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 3 | Pioneer Way | Birmingham |  | B35 7LA |  | Mrs E Sturdy | 07985 494 722 | 07985 494 722 |  |  | Windows & Doors | S Burgess | 2024-07-09 | 8am to 12 noon |  |  | 24/06 SMS text sent for 09/07. CONFIRMED for 09/07
11 |  | 68410 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 5 | Pioneer Way | Birmingham |  | B35 7LA |  | Ms H F Day |  | 07375 064068 | feathers0201@live.co.uk |  | Windows & Doors | S Burgess | 2024-07-09 | 8am to 12 noon |  |  | 24/06 SMS text sent for 09/07. CONFIRMED for 09/07
11 |  | 70275 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 7 | Pioneer Way | Birmingham |  | B35 7LA |  | Miss L Swann |  | 07902696139 | leanneswann@hotmail.co.uk |  | Windows & Doors | S Burgess | 2024-07-09 | 11am to 3pm |  |  | 24/06 SMS text sent for 09/07. 25/06 SMS called N/A
11 |  | 65791 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 14 | Pioneer Way | Birmingham |  | B35 7LA |  | Miss K Caines |  | 07429788939 |  |  | Windows & Doors | S Burgess | 2024-07-10 | 11am to 3pm |  |  | 24/06 SMS text sent for 10/07. CONFIRMED for 10/07
11 |  | 65833 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 18 | Pioneer Way | Birmingham |  | B35 7LA |  | Miss C Proudfoot |  | 07923 963 048 | caronheath098@icloud.com |  | Windows & Doors | S Burgess | 2024-07-10 | 11am to 3pm |  |  | 24/06 SMS text sent for 10/07. CONFIRMED for 10/07
11 |  | 61890 |  | SURVEY RECEIVED | Photos rec'd, await survey. | FLAT 6 | Pioneer Way | Birmingham |  | B35 7LA |  | Mr J Barrett | 0121 748 7212 |  |  |  | Windows & Doors | S Burgess | 2024-07-09 | 11am to 3pm |  |  | CONFIRMED for 09/07
11 |  | 69077 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 4 | Sopwith Croft | Birmingham |  | B35 7QH |  | Mr AG Butler |  | 07545 965196 |  |  | Windows & Doors | S Burgess | 2024-07-11 | 8am to 12 noon |  |  | 24/06 SMS text sent for 11/07. CONFIRMED for 11/07
11 |  | 67469 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 6 | Sopwith Croft | Birmingham |  | B35 7QH |  | Miss C Turner |  | 07811587683 | chriscutler92@live.com |  | Windows & Doors | S Burgess | 2024-07-11 | 8am to 12 noon |  |  | 24/06 SMS text sent for 11/07. 25/06 SMS called N/A
11 |  | 56566 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 10 | Sopwith Croft | Birmingham |  | B35 7QH |  | Mrs J Pearce | 1217767619 | 07861451530 | leaaubreyjack@aol.com |  | Windows & Doors | S Burgess | 2024-07-11 | 11am to 3pm |  |  | 24/06 SMS text sent for 11/07. CONFIRMED for 11/07
11 |  | 65276 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 14 | Sopwith Croft | Birmingham |  | B35 7QH |  | Mrs I Rigby | 7380369666 |  |  |  | Windows & Doors | S Burgess | 2024-07-11 | 11am to 3pm |  |  | 24/06 SMS text sent for 11/07. CONFIRMED for 11/07
11 |  | 66900 |  | SURVEY RECEIVED | Photos rec'd, await survey. | 7 | Trident Boulevard | Birmingham |  | B35 7LZ |  | Mrs K L Baker |  | 07943729362 | Kelly.Sinclair1@btinternet.com INCORRECT EMAIL |  | Windows & Doors | M Turpin | 2024-07-11 | 8am to 2pm |  |  | 19/06 SMS text sent for 01/07. 19/6 AC emailed. EMAIL BOUNCED BACK INCORRECT. 19/06 SMS tenant declined, offered 11/07. 24/06 SMS text sent for 11/07. CONFIRMED for 11/07
11 |  | 65876 |  | SURVEY RECEIVED | DOOR CHOICE | 27 | Trident Boulevard | Birmingham |  | B35 7LZ |  | Miss M O'Coy | 07947 378488 |  | Mazwaz2010@yahoo.com |  | Windows & Doors | M Turpin | 2024-07-09 | 8am to 2pm |  |  | 24/06 SMS text sent for 09/07. 17/07 SMS emailed TLO to ask to get a door choice from tenant.
11 |  | 68890 |  | SURVEY RECEIVED |  | 29 | Trident Boulevard | Birmingham |  | B35 7LZ |  | Mr D Jones |  |  |  |  | Windows & Doors | M Turpin | 2024-07-09 | 8am to 2pm |  |  | 24/06 SMS lttr sent for 09/07
11 |  | 68434 |  | SURVEY BOOKED |  | 30 | Trident Boulevard | Birmingham |  | B35 7LZ |  | Miss R Douglas |  | 07778035265 |  |  | Windows & Doors | M Turpin | 2024-07-30 | 8am to 2pm |  | 1 | 24/06 SMS text sent for 09/07. 25/06 SMS called N/A. 09/07 SMS tenant cancelled on the day of survey.11/07 SMS spoke to tenant CONFIRMED 30/07
11 |  | 68589 |  | SURVEY BOOKED | SEE COMMENTS | FLAT 129D | Farnborough Road | Birmingham |  | B35 7LQ |  | Miss C Morris | 01217767045 |  | cat_and_corey23@outlook.com |  | Windows & Doors | M Turpin | 2024-07-24 | 8am to 2pm |  |  | 24/06 SMS called no. NIS, lttr sent. 05/07 SMS tenant emailed to cancel this offered date advising not available until after 4.30pm week days, I have replied offering to schedule an 8am appointment or would need to ref back to Pioneer, awaiting reply. 09.07.24 SF Replied to the tenants email offering Wednesday 24.07.24 at 8am, this is not guaranteed to be dead on 8am, awaiting reply. Tenant replied and CONFIRMED the 24.07.24 for the survey.
12 |  | 69094 |  | COMMENCEMENT PENDING |  | 2 | Abingdon Way | Birmingham |  | B35 6QF |  | Miss A Goode | 07715 470 787 | 07715 470 787 | amanda.goode87@hotmail.co.uk |  | Windows & Doors | P Beahan |  |  |  | 1 | TS-26/04/24 Text sent offering 10/05/24. TS-26/04/24 Tenant text back no replyed asking what days are better for them. 08/05 SMS left voicemail offering 14/05 (19th or 27th free in June). 17/6; AC chased survey. 1/7/2024; AC NOTED PB NO access for 14/05/24 carded @ 11.45am.08/07 SMS text sent for 25/07. 15/7; AC SENT LETTER FOR SURVEY 25/7. 18/07 SMS tenant text back declining 25/07
11 |  | 68431 |  | SURVEY BOOKED |  | 35 | Abingdon Way | Birmingham |  | B35 6QF |  | Mr L Willetts | 07496159464 | 07564057802 | Lrwilletts@outlook.com |  | Windows & Doors | P Beahan | 2024-07-25 | 8am to 12 noon |  |  | 08/07 SMS text sent for 25/07. CONFIRMED for 25/07 | [28 empty] | Access via 11 Cranwell
11 |  | 61705 |  | SURVEY BOOKED |  | 3 | Avro Way | Birmingham |  | B35 7NW |  | Mr M Riddell |  | 07980833904 |  |  | Windows & Doors | S Burgess | 2024-07-24 | 8am to 12 noon |  |  | 19/6; AC text for 2/7. CANCELLED TENANT CANNOT BE HOME 2/7. 08/07 SMS text sent for 24/07. CONFIRMED for 24/07
11 |  | 68459 |  | SURVEY BOOKED |  | 4 | Avro Way | Birmingham |  | B35 7NW |  | Miss T Watson | 07748 332296 |  | tessakwatson@yahoo.co.uk |  | Windows & Doors | S Burgess | 2024-07-24 | 8am to 12 noon |  |  | 19/6; AC text for 2/7 and emailed. 21/6; AC sent letter. 21/6; Tenant rang - cannot be home 2/7 as she works. Can only do Weds or Thursday. 08/07 SMS text sent for 24/07. CONFIRMED
11 |  | 61347 |  | SURVEY BOOKED |  | 10 | Coltishall Close | Birmingham |  | B35 7EF |  | Mr S Marles | 0121 574 5664 | 07870635271 |  |  | Windows & Doors | M Turpin | 25/27/24 | 8am to 2pm |  |  | 03/06 SMS text sent for 17/06. 06/06 SMS called N/A. 11/06 SMS called N/A Lttr sent. 14/06 SMS tenant called to cancel.04/07 SMS text sent for 17/07. 08/07 SMS left voicemail. 09.07.24 SF Tenant called to cancel the survey on the 17.07.24 and re-booked CONFIRMED the 25.07.24 for the survey to take place.
11 |  | 61742 |  | SURVEY BOOKED |  | FLAT 139A | Farnborough Road | Birmingham |  | B35 7LQ |  | Mr W Draper | 07901 702 357 |  |  |  | Windows & Doors | M Turpin | 2024-07-24 | 8am to 2pm |  |  | 08/07 SMS text sent for 24/07
11 |  | 61535 |  | SURVEY BOOKED |  | FLAT 139B | Farnborough Road | Birmingham |  | B35 7LQ |  | Mr M Lawerence | 07543 036 936 | 07543746836 | chicogrimes@gmail.com |  | Windows & Doors | M Turpin | 2024-07-24 | 8am to 2pm |  |  | 08/07 SMS text sent for 24/07
11 |  | 63288 |  | SURVEY BOOKED |  | FLAT 139C | Farnborough Road | Birmingham |  | B35 7LQ |  | Mr AJ Mcmahon |  | 07986980943 |  |  | Windows & Doors | M Turpin | 2024-07-24 | 8am to 2pm |  |  | 08/07 SMS text sent for 24/07
11 |  | 61537 |  | SURVEY BOOKED |  | FLAT 139D | Farnborough Road | Birmingham |  | B35 7LQ |  | Mr S B Howell |  | 07707 806198 |  |  | Windows & Doors | M Turpin | 2024-07-24 | 8am to 2pm |  |  | 08/07 SMS text sent for 24/07. CONFIRMED for 24/07
11 |  | 62089 |  | SURVEY BOOKED |  | FLAT 139E | Farnborough Road | Birmingham |  | B35 7LQ |  | Mr J Sullivan |  | 07507382658 |  |  | Windows & Doors | M Turpin | 2024-07-24 | 8am to 2pm |  |  | 08/07 SMS text sent for 24/07
11 |  | 61539 |  | SURVEY BOOKED |  | FLAT 139F | Farnborough Road | Birmingham |  | B35 7LQ |  | Mr V Smith |  | 07506312689 |  |  | Windows & Doors | M Turpin | 2024-07-24 | 8am to 2pm |  |  | 08/07 SMS text sent for 24/07
11 |  | 64393 |  | SURVEY BOOKED |  | FLAT 145A | Farnborough Road | Birmingham |  | B35 7LQ |  | Mr A Shakespeare | 07428 715 334 |  |  |  | Windows & Doors | M Turpin | 2024-07-24 | 8am to 2pm |  |  | 08/07 SMS text sent for 24/07
11 |  | 61554 |  | SURVEY BOOKED |  | FLAT 145B | Farnborough Road | Birmingham |  | B35 7LQ |  | Mr J Cassidy | 07800850130 |  |  |  | Windows & Doors | M Turpin | 2024-07-24 | 8am to 2pm |  |  | 08/07 SMS text sent for 24/07
11 |  | 61555 |  | SURVEY BOOKED |  | FLAT 145C | Farnborough Road | Birmingham |  | B35 7LQ |  | Mrs M Corcoran | 0121 748 2849 |  |  |  | Windows & Doors | M Turpin | 2024-07-24 | 8am to 2pm |  |  | 08/07 SMS called line engaged
11 |  | 64158 |  | SURVEY BOOKED |  | FLAT 145E | Farnborough Road | Birmingham |  | B35 7LQ |  | Mr PJ Guest | 07718 613 519 |  | Paul-Guest1985@Hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-07-24 | 8am to 2pm |  |  | 08/07 SMS text sent for 24/07. CONFIRMED for 24/07
11 |  | 70270 |  | SURVEY BOOKED |  | FLAT 145F | Farnborough Road | Birmingham |  | B35 7LQ |  | Miss S L Whitehouse |  | 07762123269 | sharna161120@gmail.com |  | Windows & Doors | M Turpin | 2024-07-24 | 8am to 2pm |  |  | 08/07 SMS text sent for 24/07. CONFIRMED for 24/07
11 |  | 68994 |  | SURVEY BOOKED |  | FLAT 145G | Farnborough Road | Birmingham |  | B35 7LQ |  | Miss R Mcmahon | 07473126803 |  |  |  | Windows & Doors | M Turpin | 2024-07-24 | 8am to 2pm |  |  | 08/07 SMS text sent for 24/07
11 |  | 69411 |  | SURVEY BOOKED |  | FLAT 147A | Farnborough Road | Birmingham |  | B35 7LQ |  | Miss S Al-Muhimin |  | 07860377737 | sammara.93@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-07-25 | 8am to 2pm |  |  | 08/07 SMS text sent for 25/07. CONFIRMED for 25/07
11 |  | 61838 |  | SURVEY BOOKED |  | FLAT 147B | Farnborough Road | Birmingham |  | B35 7LQ |  | Mr M Larkin | 01217477887 |  |  |  | Windows & Doors | M Turpin | 2024-07-25 | 8am to 2pm |  |  | 08/07 SMS lttr sent
11 |  | 69831 |  | SURVEY BOOKED |  | FLAT 147C | Farnborough Road | Birmingham |  | B35 7LQ |  | Mr D Doe |  | 07712405839 |  |  | Windows & Doors | M Turpin | 2024-07-25 | 8am to 2pm |  |  | 08/07 SMS text sent for 25/07
11 |  | 69123 |  | SURVEY BOOKED |  | FLAT 147D | Farnborough Road | Birmingham |  | B35 7LQ |  | Miss A Gray |  | 07944199293 | grayantoinette79@gmail.com |  | Windows & Doors | M Turpin | 2024-07-25 | 8am to 2pm |  |  | 08/07 SMS text sent for 25/07. CONFIRMED for 25/07
11 |  | 69434 |  | SURVEY BOOKED |  | FLAT 147E | Farnborough Road | Birmingham |  | B35 7LQ |  | Miss E Krause | 0121 574 1978 |  | epakrause@gmail.com |  | Windows & Doors | M Turpin | 2024-07-25 | 8am to 2pm |  |  | 08/07 SMS lttr sent
11 |  | 61837 |  | SURVEY BOOKED |  | FLAT 147F | Farnborough Road | Birmingham |  | B35 7LQ |  | Miss J Morgan | 07738 388 182 |  |  |  | Windows & Doors | M Turpin | 2024-07-25 | 8am to 2pm |  |  | 08/07 SMS text sent for 25/07
11 |  | 68855 |  | SURVEY BOOKED |  | FLAT 4 Block 214 | Farnborough Road | Castle Vale |  | B35 7NH |  | Miss M Khalid | 07587324064 | 07401887702 | maneeba.khalid@hotmail.com |  | Windows & Doors | M Turpin | 2024-07-25 | 8am to 2pm |  |  | 08/07 SMS text sent for 25/07
11 |  | 70408 |  | SURVEY BOOKED |  | FLAT 1 Flats 214 1-6 Farnborough Road | Farnborough Road | Castle Vale |  | B35 7NH |  | Miss C Wilson |  | 07581576078 | chelseawilson1997@yahoo.co.uk |  | Windows & Doors | M Turpin | 2024-07-25 | 8am to 2pm |  |  | 08/07 SMS text sent for 25/07. CONFIRMED for 25/07
11 |  | 70049 |  | SURVEY BOOKED |  | FLAT 3 Flats 214 1-6 Farnborough Road | Farnborough Road | Castle Vale |  | B35 7NH |  | Miss K Savage |  | 07950913901 | savagekeyleigh@gmail.com |  | Windows & Doors | M Turpin | 2024-07-25 | 8am to 2pm |  |  | 08/07 SMS text sent for 25/07
11 |  | 62862 |  | SURVEY BOOKED |  | FLAT 5 Flats 214 1-6 Farnborough Road | Farnborough Road | Castle Vale |  | B35 7NH |  | Miss G Simmonds |  |  |  |  | Windows & Doors | M Turpin | 2024-07-25 | 8am to 2pm |  |  | 08/07 SMS lttr sent
11 |  | 55754 |  | SURVEY BOOKED |  | FLAT 6 Flats 214 1-6 Farnborough Road | Farnborough Road | Castle Vale |  | B35 7NH |  | Mrs L Moss | 01217478044 |  |  |  | Windows & Doors | M Turpin | 2024-07-25 | 8am to 2pm |  |  | 08/07 SMS lttr sent
11 |  | 63712 |  | SURVEY BOOKED |  | 97 | Hawker Drive | Birmingham |  | B35 7EA |  | Miss J Campbell |  | 07543350787 |  |  | Windows & Doors | P Beahan | 2024-08-01 | 11am to 3pm |  |  | 15/7; AC SENT SURVEY TEXT FOR 31/7.
11 |  | 70001 |  | SURVEY BOOKED |  | 101 | Hawker Drive | Birmingham |  | B35 7EA |  | Miss J Marston |  | 07379359151 |  |  | Windows & Doors | P Beahan | 2024-08-01 | 11am to 3pm |  |  | 15/7; AC SENT SURVEY TEXT FOR 31/7. 15/7; TENANT TEXT TO CONFIRM.
11 |  | 69574 |  | SURVEY BOOKED |  | 60 | Hawker Drive | Birmingham |  | B35 7EG |  | Miss T Doherty | 0121 240 0267 | 07502225839 | Tammy.1987@hotmail.co.uk |  | Windows & Doors | P Beahan | 2024-07-24 | 11am to 3pm |  |  | 08/07 SMS text sent for 24/07. CONFIRMED
11 |  | 56197 |  | SURVEY BOOKED |  | 8 | Montrose Drive | Birmingham |  | B35 6DH |  | Mr D Loveridge | 7761915204 | 07761915204 |  |  | Windows & Doors | M Turpin | 2024-07-16 | 8am to 2pm |  | 1 | 17/06 SMS 1st survey no access on 12/06, client emailed.
11 |  | 65516 |  | SURVEY BOOKED |  | 4 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Mrs B Brough | 07884 141 491 |  | sarahrutter1@live.co.uk |  | Windows & Doors | S Burgess | 2024-07-25 | 11am to 3pm |  |  | 08/07 SMS text sent for 25/07. 15/7; AC sent letter for survey 25/7.
11 |  | 69920 |  | SURVEY BOOKED |  | 1 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Miss L Ginn | 07305092651 |  | Lucymginn@hotmail.co.uk |  | Windows & Doors | S Burgess | 2024-07-24 | 11am to 3pm |  |  | 08/07 SMS text sent for 24/07. CONFIRMED for 24/07
11 |  | 65362 |  | SURVEY BOOKED |  | 2 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Miss S McGuire | 07517 408 879 |  |  |  | Windows & Doors | S Burgess | 2024-07-24 | 11am to 3pm |  |  | 08/07 SMS text sent for 24/07. CONFIRMED for 24/07
11 |  | 59990 |  | SURVEY BOOKED |  | 3 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Miss L Cross |  | 07301529422 | lucymarie2015@gmail.com |  | Windows & Doors | S Burgess | 2024-07-25 | 11am to 3pm |  |  | 08/07 SMS text sent for 25/07. CONFIRMED for 25/07
11 |  | 60366 |  | SURVEY BOOKED |  | 18 | Sopwith Croft | Birmingham |  | B35 7QH |  | Mr B Pike | 07760994271 | 07760994271 | B2R2UK@YAHOO.CO.UK |  | Windows & Doors | S Burgess | 2024-07-25 | 8am to 12 noon |  |  | 08/07 SMS text sent for 25/07. CONFIRMED for 25/07
11 |  | 60346 |  | SURVEY BOOKED |  | 20 | Sopwith Croft | Birmingham |  | B35 7QH |  | Mr C Molloy |  | 07400705148 | c-molloy@hotmail.co.uk |  | Windows & Doors | S Burgess | 2024-07-25 | 8am to 12 noon |  |  | 08/07 SMS text sent for 25/07. CONFIRMED for 25/07
11 |  | 60756 |  | SURVEY BOOKED |  | 26 | Sopwith Croft | Birmingham |  | B35 7QH |  | Mr PD Littler | 07861770066 |  | pabsandbabs@aol.co.uk |  | Windows & Doors | S Burgess | 2024-07-25 | 11am to 3pm |  |  | 08/07 SMS text sent for 25/07. 15/7; AC sent letter for survey 25/7.
12 |  | 65204 |  | COMMENCEMENT PENDING |  | 10 | Trident Boulevard | Birmingham |  | B35 7LZ |  | Mrs G Poole |  | 07535 608 915 |  |  | Windows & Doors | M Turpin |  |  |  | 1 | 19/06 SMS text sent for 01/07. 21/6; AC letter sent. 09.07.24 SF no access Photos received. 15/07 1st survey No access photo sent to TLO
12 |  | 64327 |  | COMMENCEMENT PENDING |  | 26 | Hawker Drive | Birmingham |  | B35 7EG |  | Mrs L Cutler | 07742 842 219 |  |  |  | Windows & Doors | P Beahan |  |  |  |  | 05/07 SMS lttr sent for 18/07. 15/07 SMS tenant called to cancel.
12 |  | 56564 |  | COMMENCEMENT PENDING | CLUTTERED HOUSE | 8 | Sopwith Croft | Birmingham |  | B35 7QH |  | Mrs J O'Hare | 1217475102 | 07411 914 261 |  |  | Windows & Doors | S Burgess |  |  |  | 1 | 24/06 SMS text sent for 11/07. 25/06 SMS left voicemail. 11/7/2024; NO ACCESS DUE TO SEVERE CLUTTER.
12 |  | 60135 |  | COMMENCEMENT PENDING |  | FLAT 331 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Mr W Hall |  | 07399591051 |  |  | Windows & Doors | M Turpin |  | 8am to 2pm |  | 2 | (Access via 327 Yatesbury & 1 Cosford Crescent)29/05 SMS text sent for 10/06. 31/05 SMS called N/A. 03/06 SMS called N/A Lttr sent. 12/06/2024 SMS reported as no access 10/6/2024, awaiting photo before can email client to advise. 17/06 SMS no access photos received, emailed client. 24/06 SMS text sent for 11/07. 25/06 SMS called N/A. 11/7/2024 NO ACCESS, CARDED. | [40 empty] | (Access via 327 Yatesbury & 1 Cosford Crescent)
12 |  | 67710 |  | COMMENCEMENT PENDING |  | FLAT 335 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Mr RJ Sharpe |  | 07572975677 |  |  | Windows & Doors | M Turpin |  | 8am to 2pm |  | 2 | (Access via 327 Yatesbury & 1 Cosford Crescent) 29/05 SMS text sent for 10/06. 31/05 SMS called N/A. 03/06 SMS called N/A Lttr sent. 12/06 SMS reported as no access on 10/06/2024, awaiting photo before can report to client as a no access. 17/06 SMS photos received, email sent to client.Tenant confirmed this date direct with Dominie for 11/07. 11/7/2024 NO ACCESS, CARDED. | [40 empty] | (Access via 327 Yatesbury & 1 Cosford Crescent)
12 |  | 60138 |  | COMMENCEMENT PENDING |  | FLAT 337 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Mr G Kinsella | 7984479727 |  |  |  | Windows & Doors | M Turpin |  | 8am to 2pm |  | 2 | (Access via 349 Yatesbury & 2 Cosford Crescent)29/05 SMS text sent for 11/06. 31/05 SMS left voicemail. 03/06 SMS called N/A Lttr sent. 12/06 SMS survey reported no access on 10/06/2024, photo sent to Dominie in the first instance. Re-scheduled for 10/07. 20/06 SMS Dominie CONFIRMED this date directly with the tenant. 10/7/2024; NO ACCESS, CARDED. 18/07 SMS email sent to TLO & client with 2nd no access photos. | [28 empty] | Access via 349 Yatesbury & 2 Cosford | [11 empty] | (Access via 349 Yatesbury & 2 Cosford Crescent)
12 |  | 64632 |  | COMMENCEMENT PENDING |  | FLAT 127C | Farnborough Road | Birmingham |  | B35 7LQ |  | Mr DM Hughes | 07376064601 | 07932903425 |  |  | Windows & Doors | M Turpin |  | 8am to 2pm |  | 1 | 24/06 SMS text sent for 09/07. 25/06 SMS called N/A. 9/7/2024;1st survey no access, carded. Email sent to TLO
12 |  | 70227 |  | COMMENCEMENT PENDING |  | FLAT 129C | Farnborough Road | Birmingham |  | B35 7LQ |  | Miss D Brown |  | 07990486128 | dinneka901@outlook.com |  | Windows & Doors | M Turpin |  | 8am to 2pm |  | 1 | 24/06 SMS text sent for 10/07. 25/06 SMS called N/A. 10/7/2024; NO ACCESS, CARDED. 18/07 SMS 1st survey no access photos emailed to TLO
12 |  | 68862 |  | COMMENCEMENT PENDING |  | FLAT 129E | Farnborough Road | Birmingham |  | B35 7LQ |  | Mr R Edwards | 01217491989 | 07376092266 |  |  | Windows & Doors | M Turpin |  | 8am to 2pm |  | 1 | 24/06 SMS text sent for 10/07. 25/06 SMS called N/A. 10/7/2024; NO ACCESS, CARDED. 18/07 SMS emailed 1st no access photos to TLO
12 |  | 67532 |  | COMMENCEMENT PENDING |  | 7 | Bond Drive | Birmingham |  | B35 7QQ |  | Mr R H Nezad-Asl |  | 07383558099 | Majid.asll@yahoo.com |  | Windows & Doors | S Burgess |  |  |  | 2 | 05/06 SMS text sent for 19/06. CONFIRMED for 19/06. 20/06 SMS 1st survey no access on 19/06 @ 12.50pm, emailed Dominie to advise.24/06 SMS text sent for 11/07. CONFIRMED for 11/07. 11/7/2024; NO ACCESS, CARDED 13.05PM.
12 |  | 59528 |  | COMMENCEMENT PENDING |  | 14 | Bovingdon Road | Birmingham |  | B35 6QD |  | Miss T Grinham |  | 07368828517 |  |  | Windows & Doors | P Beahan |  |  |  | 1 | 29/05 SMS text sent for 12/06. CONFIRMED for 12/06. 24/06 SMS text sent for 11/07. CONFIRMED for 11/07. 11/7/2024; NO ACCESS, CARDED. PHOTO IN FILE.
12 |  | 67734 |  | COMMENCEMENT PENDING |  | FLAT 24 | Bovingdon Road | Birmingham |  | B35 6QD |  | Mr S Abhar |  | 07462086448 | sarooshabhar1@gmail.com |  | Windows & Doors | P Beahan |  |  |  | 1 | 29/05 SMS text sent for 13/06. 31/05 SMS left voicemail. 03/06 SMS called N/A Lttr sent. 24/06 SMS text sent for 11/07. 24/06 SMS text sent for 11/07. 25/06 SMS called N/A. 11/7/2024; NO ACCESS, CARDED. PHOTO IN FILE.
12 |  | 59656 |  | COMMENCEMENT PENDING |  | FLAT 42 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mr W Doyle | 07858206323 |  |  |  | Windows & Doors | M Turpin |  | 8am to 2pm |  | 1 | (Access via 30 & 46 Cosford Crescent).13.06.24 SF sent text for survey on the 24.06.24, waiting confirmation. 18.06.24 SF Tenant not available, call back with an alternative date.24/06 SMS text sent for 11/07. 25/06 SMS called N/A. 11/7/2024 NO ACCESS, CARDED. 15.07.24 SF Tenant called, he's actually in hospital, having an operation on the 18.07.24, he'll need 1/2 weeks recovery, we can call beginning of August to give him a new survey date. | [28 empty] | Access via 30 & 46 Cosford Crescent
12 |  | 63878 |  | COMMENCEMENT PENDING |  | FLAT 131F | Farnborough Road | Birmingham |  | B35 7LQ |  | Mr I Rolland |  |  |  |  | Windows & Doors | M Turpin |  | 8am to 2pm |  | 1 | 24/06 SMS lttr sent. 11/7/2024 NO ACCESS, CARDED.
12 |  | 68474 |  | COMMENCEMENT PENDING |  | FLAT 141C | Farnborough Road | Birmingham |  | B35 7LQ |  | Miss J Neave | 07583019842 |  | j.neave0987@googlemail.com |  | Windows & Doors | M Turpin | 2024-07-31 | 8am to 2pm |  |  | 04.07.24 SF Sent text message. 08/07 SMS tenant text back and declined 16/07
12 |  | 59621 |  | COMMENCEMENT PENDING |  | 57 | Chigwell Close | Birmingham |  | B35 7HG |  | Miss D Taylor |  | 07508 198 215 |  |  | Windows & Doors | P Beahan |  |  |  |  | 19/6; AC sent text for survey 5/7. CANCELLED CAN ONLY DO WEDNESDAYS. 24/06 SMS text sent for 10/07. CONFIRMED for 10/07. Tenant declined.
12 |  | 63487 |  | COMMENCEMENT PENDING |  | 4A | Hawker Drive | Birmingham |  | B35 7EG |  | Miss C Davis |  | 07794540365 | claire_davis3@hotmail.co.uk |  | Windows & Doors | P Beahan |  |  |  | 1 | 24/06 SMS text sent for 10/07. CONFIRMED for 10/07. 11/07 SMS surveyor reported 1st no access on 10/07, awaiting photo of no access. 12/7; photo received.
12 |  | 67238 |  | COMMENCEMENT PENDING |  | 12 | Pioneer Way | Birmingham |  | B35 7LA |  | Mrs J M Whitehouse | 01214082382 |  |  |  | Windows & Doors | S Burgess | 3Wks notice req |  |  | 1 | 24/06 SMS called no NIS, lttr sent for 10/07. 11/07 SMS surveyor advised 1st no access on 10/07 tenant advised needs 3 weeks notice for an appointment
12 |  | 61878 |  | COMMENCEMENT PENDING |  | 16 | Pioneer Way | Birmingham |  | B35 7LA |  | Miss C Griffiths |  | 07940 330004 |  |  | Windows & Doors | S Burgess |  |  |  |  | 24/06 SMS text sent for 10/07. 25/06 SMS called N/A. 09/07 SMS tenant cancelled.
12 |  | 65529 |  | COMMENCEMENT PENDING |  | FLAT 10 | Pioneer Way | Birmingham |  | B35 7LA |  | Mr S Walker |  | 7543841494 |  |  | Windows & Doors | S Burgess |  |  |  | 1 | 24/06 SMS text sent for 10/07. 25/06 SMS called N/A. 11/07 SMS 1st survey no access on 10/07, emailed TLO
12 |  | 61892 |  | COMMENCEMENT PENDING |  | FLAT 4 | Pioneer Way | Birmingham |  | B35 7LA |  | Mrs S Weller | 07859 419 990 |  |  |  | Windows & Doors | S Burgess |  |  |  | 1 | 24/06 SMS text sent for 09/07. 25/06 SMS left voicemail. 10/07 SMS surveyor reported 1st survey no access on 09/07, emailed TLO
12 |  | 68794 |  | COMMENCEMENT PENDING |  | FLAT 8 | Pioneer Way | Birmingham |  | B35 7LA |  | Miss B Tregillies |  | 07759302013 | biancatregillies1993@gmail.com |  | Windows & Doors | S Burgess |  |  |  | 1 | 24/06 SMS text sent for 10/07. 25/06 SMS called N/A. 11/07 SMS surveyor advised 1st no access on 10/07 as tenant had no clear rooms to enable survey, emailed TLO to advise.
12 |  | 63193 |  | COMMENCEMENT PENDING |  | 16 | Sopwith Croft | Birmingham |  | B35 7QH |  | Mr D Kingston | 07523 375509 |  |  |  | Windows & Doors | S Burgess |  |  |  |  | 24/06 SMS text sent for 02/07. CONFIRMED for 2/7. 02/07 SMS surveyor advised not have time to attend this address today, called and advised the tenant. 08/07 SMS text sent for 24/07. 08/07 SMS tenant text back to decline date of 24/07
12 |  | 68935 |  | COMMENCEMENT PENDING |  | 29 | A St Athan Croft | Birmingham |  | B35 7LR |  | Mrs S Stibbs |  | 07922758849 |  |  | Windows & Doors
12 |  | 70154 |  | COMMENCEMENT PENDING |  | 65 | Abbey Road | Birmingham |  | B23 7QQ |  | Miss N Chauhan |  | 07935031896 | njc_1991@hotmail.co.uk |  | Windows & Doors
12 |  | 67447 |  | COMMENCEMENT PENDING |  | 67 | Abbey Road | Birmingham |  | B23 7QQ |  | Miss B Sheridan |  | 07432 002720 | bmsheridan89@gmail.com |  | Windows & Doors
12 |  | 68756 |  | COMMENCEMENT PENDING |  | 81 | Abbey Road | Birmingham |  | B23 7QQ |  | Miss M Doyle | 01212508480 | 07783639265 | sjohns1606@gmail.com |  | Windows & Doors
12 |  | 67848 |  | COMMENCEMENT PENDING |  | FLAT 133C | Farnborough Road | Birmingham |  | B35 7LQ |  | Mr S Webb | 01212389607 | 07402935863 | swebb1965.sw@google.com |  | Windows & Doors | M Turpin |  |  |  |  | 24/06 SMS text sent for 11/07. Tenant declined date. 03.07.24 SF Sent text message with new date 17.07.24 for the survey. 04.07.24 SF Tenant called back, he can only do after 3pm because he works. 11.07.24 SF Tenant called and CONFIRMED for 17.07.24 - Please call 1 HOUR before arriving, he'll be home at 2pm. Missed from advising surveyer added on will need re-scheduling.
12 |  | 55490 |  | COMMENCEMENT PENDING | SEE COMMENTS | 42 | Brabazon Grove | Birmingham |  | B35 6DT |  | Mrs D Carr |  | 07376 809845 |  |  | Windows & Doors | M Turpin |  |  |  |  | TS-03/05/24 Text sent for 13/05/24. TS-07/05/24 Ltr sent. 08/05 SMS called N/A.Awaiting info from surveyor to see if was a no access or not
12 |  | 68430 |  | COMMENCEMENT PENDING |  | 58 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mr M Lambert |  | 07368 848 378 | lamb262001@yahoo.com |  | Windows & Doors | M Turpin | 2024-07-30 | 8am to 2pm
12 |  | 67662 |  | COMMENCEMENT PENDING |  | FLAT 78 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mr D Gayle | 01212412287 | 07858 988830 | darrengayle@ymail.com |  | Windows & Doors | M Turpin | 2024-07-30 | 8am to 2pm |  |  | 14/06 SMS text sent for 25/06. 18/6; AC rang and LM and emailed. 19/6; letter sent. 24.06.24 SF Tenant called this morning to cancel the survey as he won't be home, he was a very rude man. 3/7/2024; AC sent letter for survey 30/7. | [28 empty] | Access via 64 Cosford & 21 Cranwell Way
12 |  | 62635 |  | COMMENCEMENT PENDING |  | 1 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss F C Morris | 07926757397 |  | morrisfiona020@gmail.com |  | Windows & Doors | M Turpin | 2024-07-30 | 8am to 2pm |  |  | 29/05 SMS text sent for 10/06. Tenant declined. 19.06.24 SF LM, sent text & letter. 21.06.24 SF Tenant sent a text saying NO to the survey on the 24.06.24, need to re-book.
12 |  | 64169 |  | COMMENCEMENT PENDING |  | 24 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss S N Smith |  | 07307377916 |  |  | Windows & Doors | M Turpin | 2024-07-30 | 8am to 2pm
12 |  | 59650 |  | COMMENCEMENT PENDING |  | 28 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss S Meenan |  | 07753 676 037 | STACEY-MEENAN@HOTMAIL.CO.UK |  | Windows & Doors | M Turpin | 2024-07-30 | 8am to 2pm
12 |  | 70434 |  | COMMENCEMENT PENDING |  | 50 | Hermitage Road | Birmingham |  | B23 6AS |  | Miss J Chadneymills |  |  | jadechad17@hotmail.co.uk |  | Windows & Doors
12 |  | 68922 |  | COMMENCEMENT PENDING |  | 29 | Lysander Way | Birmingham |  | B35 7JY |  | Mr M Younis | 07378866549 | 07378866549 | muhammadyoung.my@gmail.com |  | Windows & Doors | M Turpin | 2024-07-30 | 8am to 2pm |  | 2 | TS-19/04/24 Text sent for 01/05/24. TS-19/04/24 Tenant called survey CONFIRMED for 01/05/24. 14/05 SMS no access survey on 01/05 email sent to client to advise. 21.06.24 SF Received top sheet from Martin, NO ACCESS, need to re-book. 3/7; AC advised client and reallocated to 30/7 requesting their assistance.
12 |  | 66843 |  | COMMENCEMENT PENDING |  | FLAT 4 Block 1 | Montrose Drive | Castle Vale |  | B35 6DH |  | Mrs A J Preston | 07845185767 |  |  |  | Windows & Doors | M Turpin |  |  |  |  | 11/06 text sent for 20/06. 13/06 SMS called N/A. 14/06 SMS called N/A Lttr sent.19/06 SMS tenant text back on 19/06 to cancel.
12 |  | 69072 |  | COMMENCEMENT PENDING |  | FLAT 1 | Reservoir Road | Stockland Green |  | B23 6DJ |  | Mr P Duffy |  |  | philduffy74@icloud.com |  | Windows & Doors
12 |  | 68700 |  | COMMENCEMENT PENDING |  | FLAT 2 | Reservoir Road | Stockland Green |  | B23 6DJ |  | Mr I Singh |  | 07392423782 | rebeccafletcher@live.co.uk |  | Windows & Doors
12 |  | 56830 |  | COMMENCEMENT PENDING |  | 50 | Watton Green | Birmingham |  | B35 7JP |  | Miss T Arlow | 07453 414 148 |  |  |  | Windows & Doors | M Turpin |  |  |  | 2 | TS-25/04/24 Text sent for 07/05/24. TS-26/04/24 Survey CONFIRMED for 07/05/24.No Access on 07/05, emailed info to client on 16/05. 29/05 SMS text sent for 10/06. 31/05 SMS left voicemail. 03/06 SMS called N/A Lttr sent. 07/06 TS tenant cancelled. 13.06.24 SF sent text for survey on the 24.06.24, waiting confirmation. 18.06.24 SF LM again & sent letter. 21.06.24 SF Tenant received the letter, she can't do Mondays, re-booked & CONFIRMED for the 02.07.024 for the survey. 2/7/2024; tenant decided "not today", classed as no access therefore.
12 |  | 59454 |  | COMMENCEMENT PENDING | SEE COMMENTS | 22 | Abingdon Way | Birmingham |  | B35 6QF |  | Miss C Spencer |  | 07840 521 365 |  |  | Windows & Doors | P Beahan |  |  |  |  | 16/05 SMS text sent for 30/05. 17/05 SMS no. NIS lttr sent. 17/6; AC chased survey.
12 |  | 67094 |  | COMMENCEMENT PENDING |  | 43 | Abingdon Way | Birmingham |  | B35 6QF |  | Mrs OM Oghogho | 07852506045 |  |  |  | Windows & Doors | P Beahan |  |  |  |  | 20/05 SMS text sent for 05/06. 20/05 tenant text to decline 05/06. 08/07 SMS text sent for 25/07. 08/07 SMS tenant text back to decline 25/07
12 |  | 59468 |  | COMMENCEMENT PENDING | SEE COMMENTS | FLAT 15 | Abingdon Way | Birmingham |  | B35 6QF |  | Mr N Sheldon | 01217476769 |  |  |  | Windows & Doors | P Beahan |  |  |  |  | 17/05 SMS req Dominie do a home visit to check accessibility to measure & fit any windows prior to scheduled survey visit on 24/05. 23/05 SMS survey cancelled as Dominie did home visit and will need some work doing before we can re-schedule a survey. | [28 empty] | Acess via 17 Abingdon Way & 24 Cosford
12 |  | 69418 |  | COMMENCEMENT PENDING |  | 560 | Auckland Drive | Birmingham |  | B36 0DB |  | Miss T Eales |  |  | traceyeales@msn.com |  | Windows & Doors
12 |  | 65966 |  | COMMENCEMENT PENDING |  | 25 | Avery Croft | Birmingham |  | B35 7DG |  | Miss N E Campbell |  | 07413 402266 |  |  | Windows & Doors
12 |  | 66790 |  | COMMENCEMENT PENDING |  | 31 | Avery Croft | Birmingham |  | B35 7DG | [6 empty] | Windows & Doors
12 |  | 69185 |  | COMMENCEMENT PENDING |  | 16 | Avery Croft | Birmingham |  | B35 7DH |  | Miss T A Hyatt |  | 07510727097 |  |  | Windows & Doors
12 |  | 62173 |  | COMMENCEMENT PENDING |  | 18 | Avery Croft | Birmingham |  | B35 7DH |  | Mr G Byard |  | 07818601517 |  |  | Windows & Doors
12 |  | 65626 |  | COMMENCEMENT PENDING |  | FLAT 12 | Avery Croft | Birmingham |  | B35 7DH |  | Miss B McMahon |  | 07400967481 |  |  | Windows & Doors
12 |  | 62479 |  | COMMENCEMENT PENDING |  | FLAT 14 | Avery Croft | Birmingham |  | B35 7DH |  | Mr JA Southcombe | 07490181912 |  | jjaybham@sky.com |  | Windows & Doors | [5 empty] | *tenant will need lots of notice for any appointments, may have to be over 2 days, speak to Dominie when booking any appointments with this tenant | [28 empty] | *tenant will need lots of notice for any appointments, may have to be over 2 days, speak to Dominie when booking any appointments with this tenant | [11 empty] | *tenant will need lots of notice for any appointments, may have to be over 2 days, speak to Dominie when booking any appointments with this tenant
12 |  | 61991 |  | COMMENCEMENT PENDING |  | FLAT 8 | Avery Croft | Birmingham |  | B35 7DH |  | Mr M Wainwright | 0121 748 4399 | 07944281947 |  |  | Windows & Doors
12 |  | 68532 |  | COMMENCEMENT PENDING |  | 52 | Avery Croft | Birmingham |  | B35 7DQ |  | Miss D A Kiely |  | 07809384970 |  |  | Windows & Doors
12 |  | 69003 |  | COMMENCEMENT PENDING |  | 29 | B St Athan Croft | Birmingham |  | B35 7LR |  | Mrs D Rochefort | 01217491757 | 07842 052 996 |  |  | Windows & Doors
12 |  | 61278 |  | COMMENCEMENT PENDING |  | 15 | Bader Walk | Birmingham |  | B35 7HA |  | Mrs P Dale-Williams |  | 07737085123 | nicwill50@outlook.com |  | Windows & Doors
12 |  | 55419 |  | COMMENCEMENT PENDING |  | 17 | Bader Walk | Birmingham |  | B35 7HA |  | Miss V Hodson |  | 07402 043814 |  |  | Windows & Doors
12 |  | 69908 |  | COMMENCEMENT PENDING |  | 19 | Bader Walk | Birmingham |  | B35 7HA |  | Miss R Shaw |  | 07710031268 | robynshaw216@gmail.com |  | Windows & Doors
12 |  | 55421 |  | COMMENCEMENT PENDING |  | 21 | Bader Walk | Birmingham |  | B35 7HA |  | Mrs D L Wardle |  | 07950 478 453 |  |  | Windows & Doors
12 |  | 65517 |  | COMMENCEMENT PENDING |  | 23 | Bader Walk | Birmingham |  | B35 7HA |  | Miss F Rowe |  | 07983 458363 |  |  | Windows & Doors
12 |  | 64886 |  | COMMENCEMENT PENDING |  | 25 | Bader Walk | Birmingham |  | B35 7HA |  | Mrs A Tickner- Vickers | 0121 748 4521 | 07850 864175 |  |  | Windows & Doors
12 |  | 64818 |  | COMMENCEMENT PENDING |  | 31 | Bader Walk | Birmingham |  | B35 7HA |  | Miss C Billiard |  | 07710644020 | clairebilliard@gmail.co |  | Windows & Doors
12 |  | 55425 |  | COMMENCEMENT PENDING |  | 33 | Bader Walk | Birmingham |  | B35 7HA |  | Mrs J Rooney | 07745842558 |  | joyrooney33@gmail.com |  | Windows & Doors
12 |  | 70510 |  | COMMENCEMENT PENDING |  | FLAT 20 | Barra Croft | Birmingham |  | B35 6NF |  | Miss S Madden |  |  | susanmadden1967@icloud.com |  | Windows & Doors
12 |  | 67089 |  | COMMENCEMENT PENDING |  | 14 | Beale Close | Birmingham |  | B35 7DA |  | Mrs CC Milligan | 07479517482 | 07479517482 |  |  | Windows & Doors
12 |  | 58189 |  | COMMENCEMENT PENDING |  | 15 | Beale Close | Birmingham |  | B35 7DA |  | Miss D Bent |  | 07811 214 758 |  |  | Windows & Doors
12 |  | 69135 |  | COMMENCEMENT PENDING |  | 22 | Beale Close | Birmingham |  | B35 7DA |  | Miss S Harding |  |  | sophia.harding@hotmail.co.uk |  | Windows & Doors
12 |  | 55450 |  | COMMENCEMENT PENDING |  | 31 | Beale Close | Birmingham |  | B35 7DA |  | Miss A Lunn |  | 07972 414 842 | lunn2875@gmail.com |  | Windows & Doors
12 |  | 63929 |  | COMMENCEMENT PENDING |  | FLAT 5 | Beale Close | Birmingham |  | B35 7DA |  | Mr M Spicer | 07946035120 | 07946035120 | spicermartin5@gmail.com |  | Windows & Doors
12 |  | 61827 |  | COMMENCEMENT PENDING |  | FLAT 7 | Beale Close | Birmingham |  | B35 7DA |  | Mrs S Tresigne |  | 073766 06143 |  |  | Windows & Doors
12 |  | 66250 |  | COMMENCEMENT PENDING |  | FLAT 9 | Beale Close | Birmingham |  | B35 7DA |  | Miss A White | 07875 328599 | 07875 328599 | titchamy17@msn.com |  | Windows & Doors
12 |  | 68075 |  | COMMENCEMENT PENDING |  | 35 | Blenheim Way | Birmingham |  | B35 7JF |  | Miss N Smith | 0121 448 0114 | 07565376163 |  |  | Windows & Doors
12 |  | 69897 |  | COMMENCEMENT PENDING |  | 37 | Blenheim Way | Birmingham |  | B35 7JF |  | Mrs C Morgan |  | 07518 040458 |  |  | Windows & Doors
12 |  | 59486 |  | COMMENCEMENT PENDING |  | 39 | Blenheim Way | Birmingham |  | B35 7JF |  | Mrs J Day | 7497742 | 07864198853 |  |  | Windows & Doors
12 |  | 64131 |  | COMMENCEMENT PENDING |  | 45 | Blenheim Way | Birmingham |  | B35 7JF |  | Mrs GM Shaw | 0121 749 6436 | 07591 471342 |  |  | Windows & Doors
12 |  | 69759 |  | COMMENCEMENT PENDING |  | 47 | Blenheim Way | Birmingham |  | B35 7JF |  | Miss L Rigby |  |  |  |  | Windows & Doors
12 |  | 68475 |  | COMMENCEMENT PENDING |  | 49 | Blenheim Way | Birmingham |  | B35 7JF |  | Mrs J McKenzie |  | 07729 899803 |  |  | Windows & Doors
12 |  | 69959 |  | COMMENCEMENT PENDING |  | 50 | Blenheim Way | Birmingham |  | B35 7JF |  | Miss T Phillips | 07548280872 |  | tammymello20@outlook.com |  | Windows & Doors | [5 empty] | 14/06 SMS text sent for 25/06
12 |  | 59491 |  | COMMENCEMENT PENDING |  | 51 | Blenheim Way | Birmingham |  | B35 7JF |  | Mrs C Challenor |  | 07782189030 | carol.challenor@ppdg.co.uk |  | Windows & Doors
12 |  | 69083 |  | COMMENCEMENT PENDING |  | 53 | Blenheim Way | Birmingham |  | B35 7JF |  | Mr D Macfarlane |  | 07817771374 | dazmac1@sky.com |  | Windows & Doors
12 |  | 65504 |  | COMMENCEMENT PENDING |  | 55 | Blenheim Way | Birmingham |  | B35 7JF |  | Miss A Wilson | 07908 227 606 |  |  |  | Windows & Doors
12 |  | 59495 |  | COMMENCEMENT PENDING |  | 56 | Blenheim Way | Birmingham |  | B35 7JF |  | Miss T Timms | 01217767138 |  |  |  | Windows & Doors
12 |  | 61568 |  | COMMENCEMENT PENDING |  | 58 | Blenheim Way | Birmingham |  | B35 7JF |  | Mr M Brookes |  | 07832 066088 |  |  | Windows & Doors
12 |  | 67658 |  | COMMENCEMENT PENDING |  | 59 | Blenheim Way | Birmingham |  | B35 7JF |  | Miss S Anderson-Green | 07460 027 949 |  | stephanie1991x@hotmail.com |  | Windows & Doors
12 |  | 68085 |  | COMMENCEMENT PENDING |  | 60 | Blenheim Way | Birmingham |  | B35 7JF |  | Miss L Price |  | 07847 359 117 |  |  | Windows & Doors | [5 empty] | 14/06 SMS text sent for 25/06
12 |  | 59500 |  | COMMENCEMENT PENDING |  | 61 | Blenheim Way | Birmingham |  | B35 7JF |  | Mr D Mabbett |  | 07340003231 |  |  | Windows & Doors
12 |  | 65416 |  | COMMENCEMENT PENDING |  | 62 | Blenheim Way | Birmingham |  | B35 7JF |  | Miss G L Shaw |  | 07471455624 |  |  | Windows & Doors
12 |  | 70686 |  | COMMENCEMENT PENDING |  | 63 | Blenheim Way | Birmingham |  | B35 7JF |  | Miss S McHugh |  | 07368623032 | slmxx@live.co.uk |  | Windows & Doors
12 |  | 59502 |  | COMMENCEMENT PENDING |  | 64 | Blenheim Way | Birmingham |  | B35 7JF |  | Miss M Greenan | 07780719250 |  |  |  | Windows & Doors
12 |  | 65967 |  | COMMENCEMENT PENDING |  | 65 | Blenheim Way | Birmingham |  | B35 7JF |  | Miss R Mundenda | 0121 241 5967 | 07456 206457 | rosemundenda07@hotmail.co.uk |  | Windows & Doors
12 |  | 63988 |  | COMMENCEMENT PENDING |  | 66 | Blenheim Way | Birmingham |  | B35 7JF |  | Miss J Ford | 01217482970 | 07805854171 |  |  | Windows & Doors
12 |  | 59505 |  | COMMENCEMENT PENDING |  | 67 | Blenheim Way | Birmingham |  | B35 7JF |  | Miss C Smith |  | 07495386265 |  |  | Windows & Doors
12 |  | 59506 |  | COMMENCEMENT PENDING |  | 68 | Blenheim Way | Birmingham |  | B35 7JF |  | Mrs J Mcvey | 07484114934 |  |  |  | Windows & Doors
12 |  | 68057 |  | COMMENCEMENT PENDING |  | 70 | Blenheim Way | Birmingham |  | B35 7JF |  | Mr C Sharpe |  | 07707518125 |  |  | Windows & Doors
12 |  | 68442 |  | COMMENCEMENT PENDING |  | 73 | Blenheim Way | Birmingham |  | B35 7JF |  | Miss C Scarff |  | 0744 3438178 |  |  | Windows & Doors
12 |  | 67821 |  | COMMENCEMENT PENDING |  | 79 | Blenheim Way | Birmingham |  | B35 7JF |  | Miss G Costa | 07341261841 |  | vida_@hotmail.co.uk |  | Windows & Doors
12 |  | 68397 |  | COMMENCEMENT PENDING |  | 81 | Blenheim Way | Birmingham |  | B35 7JF |  | Miss S Edwards | 07865 674 674 |  | susansalon@yahoo.co.uk |  | Windows & Doors
12 |  | 65024 |  | COMMENCEMENT PENDING |  | 85 | Blenheim Way | Birmingham |  | B35 7JF |  | Mrs R Morgan |  | 07969552282 |  |  | Windows & Doors
12 |  | 60419 |  | COMMENCEMENT PENDING |  | 87 | Blenheim Way | Birmingham |  | B35 7JF |  | Miss T Doyle |  | 07756 347 988 | theresadoyle509@gmail.co.uk |  | Windows & Doors
12 |  | 59518 |  | COMMENCEMENT PENDING |  | 89 | Blenheim Way | Birmingham |  | B35 7JF |  | Mr K O'Brien | 01217473769 | 07736953117 | bellashazza@hotmail.com |  | Windows & Doors
12 |  | 61569 |  | COMMENCEMENT PENDING |  | 91 | Blenheim Way | Birmingham |  | B35 7JF |  | Mrs H Murrell |  | 07908414144 |  |  | Windows & Doors
12 |  | 69078 |  | COMMENCEMENT PENDING |  | 93 | Blenheim Way | Birmingham |  | B35 7JF |  | Miss K J Daniels | 07393 607 135 |  | kayleigh.daniels@hotmail.co.uk |  | Windows & Doors
12 |  | 62318 |  | COMMENCEMENT PENDING |  | 95 | Blenheim Way | Birmingham |  | B35 7JF |  | Miss L Joynson | 07865062563 |  | l.joynson@hotmail.co.uk |  | Windows & Doors
12 |  | 68963 |  | COMMENCEMENT PENDING |  | 97 | Blenheim Way | Birmingham |  | B35 7JF |  | Miss J Smart |  | 07542114903 |  |  | Windows & Doors
12 |  | 59496 |  | COMMENCEMENT PENDING |  | 57 | Blenheim Way | Birmingham |  | B35 7JF |  | Ms S Rivers |  | 07383 567 864 |  |  | Windows & Doors
12 |  | 66949 |  | COMMENCEMENT PENDING |  | 69 | Blenheim Way | Birmingham |  | B35 7JF |  | Miss J Wilson | 07392848569 | 07858 380 770 |  |  | Windows & Doors
12 |  | 59509 |  | COMMENCEMENT PENDING |  | 71 | Blenheim Way | Birmingham |  | B35 7JF |  | Miss T Fielding | 07478 653586 |  |  |  | Windows & Doors
12 |  | 64438 |  | COMMENCEMENT PENDING |  | 75 | Blenheim Way | Birmingham |  | B35 7JF |  | Mrs L C Williams |  | 07496383413 | laura_cath@yahoo.co.uk |  | Windows & Doors
12 |  | 65331 |  | COMMENCEMENT PENDING |  | 18 | Bond Drive | Birmingham |  | B35 7QQ |  | Miss N Price | 0121 748 8664 | 07706 568103 |  |  | Windows & Doors | S Burgess |  |  |  | 1 | 20/6; AC text for 2/7. 21/6; CONFIRMED. 2/7; NO ACCESS SURVEY, TOO CLUTTERED.
12 |  | 65444 |  | COMMENCEMENT PENDING |  | FLAT 32 | Bovingdon Road | Birmingham |  | B35 6QD |  | Mr M Abdalla | 07932 660 609 |  | mohamed0905@hotmail.co.uk |  | Windows & Doors | P Beahan | August |  |  |  | 08/07 SMS text sent for 25/07. 10/07 SMS tenant declined and advised away unit August
12 |  | 70784 |  | COMMENCEMENT PENDING |  | 70 | Brabazon Grove | Birmingham |  | B35 6DT |  | Mrs K Marshall | 01217493482 | 07943 129723 | kayleighmarshall24@outlook.com |  | Windows & Doors | [5 empty] | TS-03/05/24 Text sent for 14/05/24. TS-07/05/24 Tenant text back no she needs Fridays only.13/05 SMS text sent for 24/05. CONFIRMED for 24/05. 24.05.24 SF CANCELLED via phone. 24.05.24 SF Martin Turpin did actually attend, he van probably got fixed quicker than he thought, he attended the proper and NO ACCESS, need to re-book,
12 |  | 69821 |  | COMMENCEMENT PENDING |  | 20 | Brookpiece Walk | Birmingham |  | B35 7LG |  | Mr G Clark |  |  |  |  | Windows & Doors
12 |  | 66046 |  | COMMENCEMENT PENDING |  | 3 | Brookpiece Walk | Birmingham |  | B35 7LG |  | Mrs A L Proudfoot |  | 07897579340 |  |  | Windows & Doors
12 |  | 69747 |  | COMMENCEMENT PENDING |  | 5 | Brookpiece Walk | Birmingham |  | B35 7LG |  | Miss P Majidnejadi |  | 07478505959 |  |  | Windows & Doors
12 |  | 66157 |  | COMMENCEMENT PENDING |  | 9 | Brookpiece Walk | Birmingham |  | B35 7LG |  | Miss V Stokes | 0792 721 7009 | 07549912080 |  |  | Windows & Doors
12 |  | 55520 |  | COMMENCEMENT PENDING |  | 24 | Brookpiece Walk | Birmingham |  | B35 7LJ |  | Mrs H Alders |  |  | hildamytton@talktalk.net |  | Windows & Doors
12 |  | 55526 |  | COMMENCEMENT PENDING |  | 38 | Brookpiece Walk | Birmingham |  | B35 7LJ |  | Mr R J Taylor |  | 07967 840 978 | rayjeandawn@talktalk.net |  | Windows & Doors
12 |  | 64290 |  | COMMENCEMENT PENDING |  | 40 | Brookpiece Walk | Birmingham |  | B35 7LJ |  | Miss S Wolfe |  | 07980 197165 | wolfies@live.co.uk |  | Windows & Doors
12 |  | 66995 |  | COMMENCEMENT PENDING |  | 44 | Brookpiece Walk | Birmingham |  | B35 7LJ |  | Mrs T Noreen |  |  |  |  | Windows & Doors
12 |  | 69720 |  | COMMENCEMENT PENDING |  | 46 | Brookpiece Walk | Birmingham |  | B35 7LJ |  | Mrs Y Wilson | 0121 240 9929 | 07940902140 |  |  | Windows & Doors
12 |  | 64479 |  | COMMENCEMENT PENDING |  | 48 | Brookpiece Walk | Birmingham |  | B35 7LJ |  | Miss A Wardell | 0121 730 3220 | 07880310342 |  |  | Windows & Doors
12 |  | 70785 |  | COMMENCEMENT PENDING |  | 50 | Brookpiece Walk | Birmingham |  | B35 7LJ |  | Mrs M Hadley |  | 07385 196 840 |  |  | Windows & Doors
12 |  | 62594 |  | COMMENCEMENT PENDING |  | 50A | Brookpiece Walk | Birmingham |  | B35 7LS |  | Mr J F Kirby | 07977116320 | 07977116320 |  |  | Windows & Doors
12 |  | 70440 |  | COMMENCEMENT PENDING |  | 22 | Brooks Croft | Birmingham |  | B35 7BX |  | Miss S O'Hagan |  | 07940752871 | sohagan123@outlook.com |  | Windows & Doors
12 |  | 55519 |  | COMMENCEMENT PENDING |  | 19 | Brooks Croft | Birmingham |  | B35 7BY |  | Mrs J T Wright | 01217492800 |  |  |  | Windows & Doors
12 |  | 63655 |  | COMMENCEMENT PENDING |  | 31 | Brooks Croft | Birmingham |  | B35 7BY |  | Mrs T Soniyi | 07474826698 | 07735519402 |  |  | Windows & Doors
12 |  | 64524 |  | COMMENCEMENT PENDING |  | 33 | Brooks Croft | Birmingham |  | B35 7BY |  | Mr B Crowley |  | 07598235197 |  |  | Windows & Doors
12 |  | 58108 |  | COMMENCEMENT PENDING |  | 63 | Brooks Croft | Birmingham |  | B35 7BY |  | Mrs E Matthews |  | 07476275666 | esthermathers87@gmail.com |  | Windows & Doors
12 |  | 68005 |  | COMMENCEMENT PENDING |  | 67 | Brooks Croft | Birmingham |  | B35 7BY |  | Miss V Shread | 07415401907 | 07415401907 | shread446@gmail.com |  | Windows & Doors
12 |  | 67659 |  | COMMENCEMENT PENDING |  | 35A | Brooks Croft | Castle Vale |  | B35 7BY |  | Ms A Clarke |  | 07814822242 | alison63@life.co.uk |  | Windows & Doors
12 |  | 58151 |  | COMMENCEMENT PENDING |  | FLAT 11 | Brooks Croft | Birmingham |  | B35 7BY |  | Mr S Thorneywork |  | 07779 089842 | sthorneywork@yahoo.co.uk |  | Windows & Doors
12 |  | 67741 |  | COMMENCEMENT PENDING |  | FLAT 15 | Brooks Croft | Birmingham |  | B35 7BY |  | Miss K Maxfield | 07863453058 |  | kirstiemaxfield@hotmail.co.uk |  | Windows & Doors
12 |  | 65559 |  | COMMENCEMENT PENDING |  | FLAT 35 | Brooks Croft | Birmingham |  | B35 7BY |  | Miss C Ashfield | 07542626176 |  |  |  | Windows & Doors
12 |  | 69011 |  | COMMENCEMENT PENDING |  | FLAT 37 | Brooks Croft | Birmingham |  | B35 7BY |  | Ms T Black |  | 07902537904 |  |  | Windows & Doors
12 |  | 68541 |  | COMMENCEMENT PENDING |  | FLAT 39 | Brooks Croft | Birmingham |  | B35 7BY |  | Miss N Hagi Mohamed |  | 07310161724 |  |  | Windows & Doors
12 |  | 70764 |  | COMMENCEMENT PENDING |  | FLAT 43 | Brooks Croft | Birmingham |  | B35 7BY |  | Miss G Johns |  |  |  |  | Windows & Doors
12 |  | 55511 |  | COMMENCEMENT PENDING |  | FLAT 45 | Brooks Croft | Birmingham |  | B35 7BY |  | Mrs P Reid | 07910314679 | 07910314679 | regreid52@gmail.com |  | Windows & Doors
12 |  | 66189 |  | COMMENCEMENT PENDING |  | FLAT 47 | Brooks Croft | Birmingham |  | B35 7BY |  | Ms JE Panton |  | 07949067712 | pantonjoy22@gmail.com |  | Windows & Doors
12 |  | 69932 |  | COMMENCEMENT PENDING |  | FLAT 49 | Brooks Croft | Birmingham |  | B35 7BY |  | Miss S Wale |  |  |  |  | Windows & Doors
12 |  | 63717 |  | COMMENCEMENT PENDING |  | FLAT 51 | Brooks Croft | Birmingham |  | B35 7BY |  | Miss J Francis | 0121 406 9751 | 07727291618 | hedgehogitaly@gmail.com |  | Windows & Doors
12 |  | 60486 |  | COMMENCEMENT PENDING |  | FLAT 7 | Brooks Croft | Birmingham |  | B35 7BY |  | Mrs G M Stock |  |  | GWENPET33@YAHOO.CO.UK |  | Windows & Doors
12 |  | 65508 |  | COMMENCEMENT PENDING |  | FLAT 9 | Brooks Croft | Birmingham |  | B35 7BY |  | Mr I Wright | 07791187889 |  |  |  | Windows & Doors
12 |  | 68554 |  | COMMENCEMENT PENDING |  | FLAT 11 | Cadbury Drive | Birmingham |  | B35 7EJ |  | Mrs N Chowdhury |  | 07491367417 |  |  | Windows & Doors
12 |  | 58106 |  | COMMENCEMENT PENDING |  | FLAT 15 | Cadbury Drive | Birmingham |  | B35 7EJ |  | Mrs S Radigan |  |  |  |  | Windows & Doors
12 |  | 64490 |  | COMMENCEMENT PENDING |  | FLAT 17 | Cadbury Drive | Birmingham |  | B35 7EJ |  | Mrs R Boyd | 07865 705397 |  | boydbex@hotmail.co.uk |  | Windows & Doors
12 |  | 66782 |  | COMMENCEMENT PENDING |  | FLAT 19 | Cadbury Drive | Birmingham |  | B35 7EJ |  | Miss L C Brotherson |  | 07887 427 211 | pineapple.lb46@gmail.com |  | Windows & Doors
12 |  | 65001 |  | COMMENCEMENT PENDING |  | FLAT 21 | Cadbury Drive | Birmingham |  | B35 7EJ |  | Miss J Boyce | 01212813649 |  |  |  | Windows & Doors
12 |  | 55541 |  | COMMENCEMENT PENDING |  | FLAT 23 | Cadbury Drive | Birmingham |  | B35 7EJ |  | Mrs B Bagby | 01217302880 |  |  |  | Windows & Doors
12 |  | 67768 |  | COMMENCEMENT PENDING |  | FLAT 29 | Cadbury Drive | Birmingham |  | B35 7EJ |  | Miss R Townsend | 07846906974 | 07846906974 |  |  | Windows & Doors
12 |  | 62853 |  | COMMENCEMENT PENDING |  | FLAT 31 | Cadbury Drive | Birmingham |  | B35 7EJ |  | Miss L Rickards | 07595 943 413 | 07595943413 | laurarickards@hotmail.com |  | Windows & Doors
12 |  | 68079 |  | COMMENCEMENT PENDING |  | FLAT 33 | Cadbury Drive | Birmingham |  | B35 7EJ |  | Mrs W Rogers | 0121 493 4364 | 07359553892 | rjsimons2003@yahoo.com |  | Windows & Doors
12 |  | 55545 |  | COMMENCEMENT PENDING |  | FLAT 35 | Cadbury Drive | Birmingham |  | B35 7EJ |  | Miss A Kirk | 0121 749 1257 |  | amanda.kirk@heartofengland.nhs.uk |  | Windows & Doors
12 |  | 68384 |  | COMMENCEMENT PENDING |  | FLAT 37 | Cadbury Drive | Birmingham |  | B35 7EJ |  | Mrs S Coffman | 07391115267 | 07500158793 | sarah.coffman@hotmal.co.uk |  | Windows & Doors
12 |  | 69058 |  | COMMENCEMENT PENDING |  | FLAT 41 | Cadbury Drive | Birmingham |  | B35 7EJ |  | Miss S Crossley |  |  |  |  | Windows & Doors
12 |  | 69624 |  | COMMENCEMENT PENDING |  | FLAT 9 | Cadbury Drive | Birmingham |  | B35 7EJ |  | Miss T Johnson |  | 07544998974 |  |  | Windows & Doors
12 |  | 63391 |  | COMMENCEMENT PENDING |  | 63 | Cadbury Drive | Birmingham |  | B35 7EP |  | Miss J I Whitehead |  | 07802479212 | juliewhitehead128@yahoo.com |  | Windows & Doors
12 |  | 68087 |  | COMMENCEMENT PENDING |  | 65 | Cadbury Drive | Birmingham |  | B35 7EP |  | Mrs N Ibrahim |  | 07889209750 |  |  | Windows & Doors
12 |  | 55555 |  | COMMENCEMENT PENDING |  | 73 | Cadbury Drive | Birmingham |  | B35 7EP |  | Miss D Kennedy |  | 07702 802 300 |  |  | Windows & Doors
12 |  | 55556 |  | COMMENCEMENT PENDING |  | 77 | Cadbury Drive | Birmingham |  | B35 7EP |  | Mrs J Sleigh | 0121 294 5555 |  |  |  | Windows & Doors
12 |  | 55557 |  | COMMENCEMENT PENDING |  | 89 | Cadbury Drive | Birmingham |  | B35 7EP |  | Mrs J Thompson | 07977 761 958 |  |  |  | Windows & Doors
12 |  | 67576 |  | COMMENCEMENT PENDING |  | 93 | Cadbury Drive | Birmingham |  | B35 7EP |  | Miss N Harris | 07879672959 | 07879672959 |  |  | Windows & Doors
12 |  | 68611 |  | COMMENCEMENT PENDING |  | 51 | Cadbury Drive | Birmingham |  | B35 7EP |  | Mr C Hackett | 07732939616 |  | buffaloackit@live.co.uk |  | Windows & Doors
12 |  | 68338 |  | COMMENCEMENT PENDING |  | FLAT 55 | Cadbury Drive | Birmingham |  | B35 7EP |  | Mr R Collin |  |  |  |  | Windows & Doors
12 |  | 66776 |  | COMMENCEMENT PENDING |  | FLAT 57 | Cadbury Drive | Birmingham |  | B35 7EP |  | Mrs L Claxton |  | 07715927167 | terrytlc@hotmail.co.uk |  | Windows & Doors
12 |  | 58385 |  | COMMENCEMENT PENDING |  | FLAT 61 | Cadbury Drive | Birmingham |  | B35 7EP |  | Mr G Coates | 07759939077 | 07759939077 |  |  | Windows & Doors
12 |  | 59596 |  | COMMENCEMENT PENDING |  | 24 | Cadbury Drive | Birmingham |  | B35 7EW |  | Mr M Flynn | 07956086795 |  |  |  | Windows & Doors
12 |  | 64284 |  | COMMENCEMENT PENDING |  | 26 | Cadbury Drive | Birmingham |  | B35 7EW |  | Miss JL Meredith | 07871 214221 |  |  |  | Windows & Doors
12 |  | 69797 |  | COMMENCEMENT PENDING |  | 28 | Cadbury Drive | Birmingham |  | B35 7EW |  | Miss K Parry |  | 07576 405 155 |  |  | Windows & Doors
12 |  | 59601 |  | COMMENCEMENT PENDING |  | 30 | Cadbury Drive | Birmingham |  | B35 7EW |  | Miss C Williams | 07920404807 |  | clair1974@live-co.uk |  | Windows & Doors
12 |  | 59595 |  | COMMENCEMENT PENDING |  | 22 | Cadbury Drive | Birmingham |  | B35 7EW |  | Miss K Radigan |  |  |  |  | Windows & Doors
12 |  | 55559 |  | COMMENCEMENT PENDING |  | 121 | Cadbury Drive | Birmingham |  | B35 7EX |  | Mr P Hill | 07388 731386 |  |  |  | Windows & Doors
12 |  | 65776 |  | COMMENCEMENT PENDING |  | 127 | Cadbury Drive | Birmingham |  | B35 7EX |  | Miss E Clarke |  | 07342139484 |  |  | Windows & Doors
12 |  | 55562 |  | COMMENCEMENT PENDING |  | 131 | Cadbury Drive | Birmingham |  | B35 7EX |  | Mrs M Doyle | 07729645633 |  |  |  | Windows & Doors
12 |  | 65749 |  | COMMENCEMENT PENDING |  | 133 | Cadbury Drive | Birmingham |  | B35 7EX |  | Miss K Taylor | 0121 748 3540 | 07907382938 | kimmy_taylor@hotmail.co.uk |  | Windows & Doors
12 |  | 68365 |  | COMMENCEMENT PENDING |  | 135 | Cadbury Drive | Birmingham |  | B35 7EX |  | Mr A Johnson | 077 807 571 30 |  | AJ.BIZ@OUTLOOK.COM |  | Windows & Doors
12 |  | 70531 |  | COMMENCEMENT PENDING |  | 137 | Cadbury Drive | Birmingham |  | B35 7EX |  | Miss TA Munn |  | 07543150704 | tanishamunn@gmail.com |  | Windows & Doors
12 |  | 68678 |  | COMMENCEMENT PENDING |  | 147 | Cadbury Drive | Birmingham |  | B35 7EY |  | Miss JMM Fitzgerald |  | 07516321312 | mixy-jd@hotmail.com.co.uk |  | Windows & Doors
12 |  | 67332 |  | COMMENCEMENT PENDING |  | 157 | Cadbury Drive | Birmingham |  | B35 7EY |  | Mr Z Saleh |  | 07922730482 | zakabro@hotmail.com |  | Windows & Doors
12 |  | 69416 |  | COMMENCEMENT PENDING |  | 165 | Cadbury Drive | Birmingham |  | B35 7EY |  | Mr G Lowe |  |  | grahamlowe748@hotmail.com |  | Windows & Doors
12 |  | 55572 |  | COMMENCEMENT PENDING |  | 169 | Cadbury Drive | Birmingham |  | B35 7EY |  | Mrs B Jackson | 07369224629 |  |  |  | Windows & Doors
12 |  | 65914 |  | COMMENCEMENT PENDING |  | 171 | Cadbury Drive | Birmingham |  | B35 7EY |  | Miss S Edwards | 07833775799 |  |  |  | Windows & Doors
12 |  | 59602 |  | COMMENCEMENT PENDING |  | 145 | Cadbury Drive | Birmingham |  | B35 7EY |  | Mrs N Blenkiron | 07400330594 | 07400330594 |  |  | Windows & Doors
12 |  | 61247 |  | COMMENCEMENT PENDING |  | FLAT 149 | Cadbury Drive | Birmingham |  | B35 7EY |  | Mr G Pearson |  | 07973953526 | grahamtheman13@yahoo.co.uk |  | Windows & Doors
12 |  | 64858 |  | COMMENCEMENT PENDING |  | FLAT 151 | Cadbury Drive | Birmingham |  | B35 7EY |  | Mrs C Bryan |  | 07580931284 | jamestomnina@icloud.com |  | Windows & Doors
12 |  | 58462 |  | COMMENCEMENT PENDING |  | FLAT 153 | Cadbury Drive | Birmingham |  | B35 7EY |  | Mr I Bingham |  | 07484 896 502 | ianb15357@outlook.com |  | Windows & Doors
12 |  | 69391 |  | COMMENCEMENT PENDING |  | 34 | Canterbury Close | Birmingham |  | B23 7QL |  | Mr R Sanders |  |  | rickyg22@hotmail.co.uk |  | Windows & Doors
12 |  | 69792 |  | COMMENCEMENT PENDING |  | No.3, Air Ministry Houses | Chester Road | Castle Vale |  | B35 7AA |  | Mr J Bradley | 07449184815 |  | joebrad07@hotmail.co.uk |  | Windows & Doors
12 |  | 67261 |  | COMMENCEMENT PENDING |  | No.5, Air Ministry Houses | Chester Road | Castle Vale |  | B35 7AA |  | Miss K E Eggleton |  | 07361793204 | kevin118@live.co.uk |  | Windows & Doors
12 |  | 61343 |  | COMMENCEMENT PENDING |  | 1301 | Chester Road | Birmingham |  | B35 7ED |  | Miss S Locke |  | 07541960052 |  |  | Windows & Doors
12 |  | 68300 |  | COMMENCEMENT PENDING |  | 1303 | Chester Road | Birmingham |  | B35 7ED |  | Miss B Wadrup |  | 07530 909586 |  |  | Windows & Doors
12 |  | 61345 |  | COMMENCEMENT PENDING |  | 1305 | Chester Road | Birmingham |  | B35 7ED |  | Miss S Walsh |  | 07762991286 |  |  | Windows & Doors
12 |  | 61346 |  | COMMENCEMENT PENDING |  | 1307 | Chester Road | Birmingham |  | B35 7ED |  | Miss A Hinton | 07983419426 |  |  |  | Windows & Doors
11 |  | 65963 |  | SURVEY BOOKED |  | 17 | Chigwell Close | Birmingham |  | B35 7HG |  | Ms P Vincent | 01217492601 | 07796805324 | pennyroger2@yahoo.co.uk |  | Windows & Doors | P Beahan | 2024-08-01 | 8am to 12 noon |  |  | 15/7; AC SENT SURVEY TEXT FOR 31/7. 15/7; TENANT TEXT TO CONFIRM.
11 |  | 62497 |  | SURVEY BOOKED |  | 19 | Chigwell Close | Birmingham |  | B35 7HG |  | Mrs J Dunston | 07754 213858 |  | jdunston35@googlemail.com |  | Windows & Doors | P Beahan | 2024-08-01 | 8am to 12 noon |  |  | 15/7; AC SENT SURVEY TEXT FOR 31/7.
11 |  | 61800 |  | SURVEY BOOKED |  | 21 | Chigwell Close | Birmingham |  | B35 7HG |  | Miss J Cooney |  | 07876191419 | janecooney@hotmail.co.uk |  | Windows & Doors | P Beahan | 2024-08-01 | 8am to 12 noon |  |  | 15/7; AC SENT SURVEY TEXT FOR 31/7.
12 |  | 67601 |  | COMMENCEMENT PENDING |  | 27 | Chigwell Close | Birmingham |  | B35 7HG |  | Miss K Finney | 07812996853 |  |  |  | Windows & Doors | P Beahan | SEPTEMBER only |  |  |  | 20/6; AC sent text for survey. CONFIRMED FOR 5/7. 1/7/2024; CANCELLED REQUIRED IN SEPTEMBER - Tenant is a carer and her client has had a major stroke.
12 |  | 55581 |  | COMMENCEMENT PENDING |  | 59 | Chigwell Close | Birmingham |  | B35 7HG |  | Miss M Delaney | 07809 144646 |  |  |  | Windows & Doors | P Beahan |  |  |  |  | 19/6; AC sent text for survey. Tenant text back cannot be home 5/7.
12 |  | 66818 |  | COMMENCEMENT PENDING |  | 23 | Chigwell Close | Birmingham |  | B35 7HG |  | Mrs S Maqbool | 07825731348 |  | syedall@hotmail.co.uk |  | Windows & Doors | P Beahan
12 |  | 55576 |  | COMMENCEMENT PENDING |  | 8 | Chigwell Close | Birmingham |  | B35 7HH |  | Mr N Kendall |  | 07539 309 821 |  |  | Windows & Doors | P Beahan |  | 8am to 12 noon |  | 1 | 19/06 SMS text sent for 28/06. 01/07 SMS surveyor reported no access on 28/06, awating photos before can report to the client.
11 |  | 69545 |  | SURVEY BOOKED |  | 25 | Chigwell Close | Birmingham |  | B35 7HH |  | Miss K Haughton |  | 07312 421 916 |  |  | Windows & Doors | P Beahan | 2024-08-01 | 11am to 3pm |  |  | 15/7; AC SENT SURVEY TEXT FOR 31/7.
12 |  | 70321 |  | COMMENCEMENT PENDING |  | 1 | Clayton Walk | Birmingham |  | B35 7DB |  | Miss C-A Davies | 07537985180 | 07537985180 | carly_davies1990@outlook.com |  | Windows & Doors
12 |  | 70739 |  | COMMENCEMENT PENDING |  | 3 | Clayton Walk | Birmingham |  | B35 7DB |  | Ms M Ford |  | 07341003087 | madzons@yahoo.co.uk |  | Windows & Doors
12 |  | 55625 |  | COMMENCEMENT PENDING |  | 7 | Clayton Walk | Birmingham |  | B35 7DB |  | Mrs R Griffin |  | 07456998099 |  |  | Windows & Doors
12 |  | 65777 |  | COMMENCEMENT PENDING |  | 11 | Clayton Walk | Birmingham |  | B35 7DB |  | Miss G Humpage |  | 07354 294 129 |  |  | Windows & Doors | [5 empty] | 20/05 SMS Dominie forwarded new tenant contact name & telelphone number, info updated.
12 |  | 65268 |  | COMMENCEMENT PENDING |  | 25 | Clayton Walk | Birmingham |  | B35 7DB |  | Miss G Delaney | 0121 748 4848 | 07581 126165 | missgdelaney@gmail.com |  | Windows & Doors
12 |  | 62178 |  | COMMENCEMENT PENDING |  | 27 | Clayton Walk | Castle Vale |  | B35 7DB |  | Miss S Burke |  | 07594828214 |  |  | Windows & Doors
12 |  | 70574 |  | COMMENCEMENT PENDING |  | 29 | Clayton Walk | Castle Vale |  | B35 7DB |  | Mr C Mohammadi |  |  | chimoh123456@gmail.com |  | Windows & Doors
12 |  | 70239 |  | COMMENCEMENT PENDING |  | 31 | Clayton Walk | Castle Vale |  | B35 7DB |  | Mr LR Canham |  | 07780 060 894 |  |  | Windows & Doors
12 |  | 62181 |  | COMMENCEMENT PENDING |  | 33 | Clayton Walk | Birmingham |  | B35 7DB |  | Mr A Maycock |  | 07960018895 |  |  | Windows & Doors
12 |  | 68389 |  | COMMENCEMENT PENDING |  | 35 | Clayton Walk | Birmingham |  | B35 7DB |  | Miss K Toole |  | 07718939863 | miss-toole@hotmail.co.uk |  | Windows & Doors
12 |  | 66922 |  | COMMENCEMENT PENDING |  | 40 | Clayton Walk | Birmingham |  | B35 7DD |  | Mrs S Reeves | 07719 475202 | 07719475202 |  |  | Windows & Doors
12 |  | 66162 |  | COMMENCEMENT PENDING |  | 42 | Clayton Walk | Birmingham |  | B35 7DD |  | Mrs M Hill |  | 07469203370 |  |  | Windows & Doors
12 |  | 67866 |  | COMMENCEMENT PENDING |  | 44 | Clayton Walk | Birmingham |  | B35 7DD |  | Miss A Lyons |  |  |  |  | Windows & Doors
12 |  | 62194 |  | COMMENCEMENT PENDING |  | 46 | Clayton Walk | Birmingham |  | B35 7DD |  | Mr K Slaney |  | 07471874335 |  |  | Windows & Doors
12 |  | 69070 |  | COMMENCEMENT PENDING |  | 28 | Clayton Walk | Birmingham |  | B35 7DD |  | Miss J Byrne |  | 07394159303 |  |  | Windows & Doors
12 |  | 65544 |  | COMMENCEMENT PENDING |  | 30 | Clayton Walk | Birmingham |  | B35 7DD |  | Miss C Clarson | 07581472664 | 07581472664 | none@usable.com |  | Windows & Doors
12 |  | 68930 |  | COMMENCEMENT PENDING |  | 48 | Clayton Walk | Birmingham |  | B35 7DD |  | Miss K Higgins |  | 07399114534 |  |  | Windows & Doors
12 |  | 62196 |  | COMMENCEMENT PENDING |  | 50 | Clayton Walk | Birmingham |  | B35 7DD |  | Miss K Joynson |  | 077855 31292 |  |  | Windows & Doors
12 |  | 70430 |  | COMMENCEMENT PENDING |  | FLAT 18 | Clayton Walk | Birmingham |  | B35 7DD |  | Mr A Painter |  |  | anthonypainter450@gmail.com |  | Windows & Doors
12 |  | 69653 |  | COMMENCEMENT PENDING |  | FLAT 24 | Clayton Walk | Birmingham |  | B35 7DD |  | Miss K Knott |  | 07935327310 | Kirsten2491@icloud.com |  | Windows & Doors
12 |  | 69484 |  | COMMENCEMENT PENDING |  | FLAT 32 | Clayton Walk | Birmingham |  | B35 7DD |  | Mr L Hitchman |  | 07958 757 596 | lee-hitchman@hotmail.co.uk |  | Windows & Doors
12 |  | 66745 |  | COMMENCEMENT PENDING |  | FLAT 34 | Clayton Walk | Birmingham |  | B35 7DD |  | Miss KL Eyles |  |  | kellyEyles@hotmail.co.uk |  | Windows & Doors
12 |  | 61903 |  | COMMENCEMENT PENDING |  | FLAT 36 | Clayton Walk | Birmingham |  | B35 7DD |  | Mr R Mottram |  | 07762073293 | mottramr28@gmail.com |  | Windows & Doors
12 |  | 67752 |  | COMMENCEMENT PENDING |  | FLAT 38 | Clayton Walk | Birmingham |  | B35 7DD |  | Mr D Hitchman | 07562806064 | 07940753670 | hitchmandale95@gmail.com |  | Windows & Doors
12 |  | 70409 |  | COMMENCEMENT PENDING |  | FLAT 47 | Clayton Walk | Birmingham |  | B35 7DE |  | Mr S Beet |  | 07532812383 | stevenbeetx@gmail.com |  | Windows & Doors
12 |  | 69990 |  | COMMENCEMENT PENDING |  | FLAT 49 | Clayton Walk | Birmingham |  | B35 7DE |  | Mr J Burke |  | 07425989450 | burke21@live.co.uk |  | Windows & Doors
12 |  | 55641 |  | COMMENCEMENT PENDING |  | FLAT 51 | Clayton Walk | Birmingham |  | B35 7DE |  | Miss M Rock | 07985 282730 |  |  |  | Windows & Doors
12 |  | 70656 |  | COMMENCEMENT PENDING |  | FLAT 52 | Clayton Walk | Birmingham |  | B35 7DF |  | Miss C Harrison |  | 07305017582 | courtneyleighharrison02@gmail.com |  | Windows & Doors
12 |  | 70013 |  | COMMENCEMENT PENDING |  | FLAT 54 | Clayton Walk | Birmingham |  | B35 7DF |  | Miss J Olner | 0121 5378208 | 07412 75 20 61 |  |  | Windows & Doors
12 |  | 69818 |  | COMMENCEMENT PENDING |  | FLAT 56 | Clayton Walk | Birmingham |  | B35 7DF |  | Miss L McCann | 07375932198 |  | leahandpreston@outlook.com |  | Windows & Doors
12 |  | 58686 |  | COMMENCEMENT PENDING |  | FLAT 58 | Clayton Walk | Birmingham |  | B35 7DF |  | Miss D Simner |  | 07443908598 | debsimner@talktalk.net |  | Windows & Doors
12 |  | 55647 |  | COMMENCEMENT PENDING |  | 20 | Cobham Close | Birmingham |  | B35 6EA |  | Miss K Williams |  | 07799 037537 | karen_williams3@sky.com |  | Windows & Doors
12 |  | 55648 |  | COMMENCEMENT PENDING |  | 22 | Cobham Close | Birmingham |  | B35 6EA |  | Mrs S Chapman | 07957310022 |  |  |  | Windows & Doors
12 |  | 55649 |  | COMMENCEMENT PENDING |  | 24 | Cobham Close | Birmingham |  | B35 6EA |  | Mrs J Forknall | 01217484532 |  |  |  | Windows & Doors
12 |  | 61351 |  | COMMENCEMENT PENDING |  | 16 | Coltishall Close | Birmingham |  | B35 7EF |  | Mrs M Duffy |  | 07900 652 579 |  |  | Windows & Doors | M Turpin | 2024-07-31 | 8am to 2pm
12 |  | 61352 |  | COMMENCEMENT PENDING |  | 17 | Coltishall Close | Birmingham |  | B35 7EF |  | Mrs T Cottrell | 01217481461 | 07445676678 |  |  | Windows & Doors | M Turpin | 2024-07-31 | 8am to 2pm
12 |  | 68873 |  | COMMENCEMENT PENDING |  | 19 | Coltishall Close | Birmingham |  | B35 7EF |  | Miss H Condron |  |  | hollycondronhc@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-07-31 | 8am to 2pm
12 |  | 67600 |  | COMMENCEMENT PENDING |  | 15A | Coltishall Close | Birmingham |  | B35 7EF |  | Miss T A Edwards | 0121 408 9836 | 07305 595 250 | na_edwards@hotmail.com |  | Windows & Doors | M Turpin | 2024-07-31 | 8am to 2pm
12 |  | 68527 |  | COMMENCEMENT PENDING |  | 25 | Concorde Drive | Birmingham |  | B35 7EE |  | Miss J Cowan | 01217486221 | 07788230297 |  |  | Windows & Doors | M Turpin | 2024-07-31 | 8am to 2pm |  |  | 04/06 SMS text sent for 18/06. 11/06 SMS called N/A. Tenant declined this date
12 |  | 70036 |  | COMMENCEMENT PENDING |  | 29 | Concorde Drive | Birmingham |  | B35 7EE |  | Miss DL Carter |  | 07342016962 |  |  | Windows & Doors | M Turpin | 2024-07-31 | 8am to 2pm |  |  | 05/06 SMS text sent for 19/06. Tenant declined.
12 |  | 61360 |  | COMMENCEMENT PENDING |  | 15 | Concorde Drive | Birmingham |  | B35 7EE |  | Ms J Mulligan |  | 07496108763 |  |  | Windows & Doors | M Turpin |  |  |  |  | 04/06 SMS text sent for 18/06. Tenant declined
12 |  | 63932 |  | COMMENCEMENT PENDING |  | 3 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mrs B E Peach |  | 07518755167 | brenda.liss@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-08-01 | 8am to 2pm
12 |  | 64710 |  | COMMENCEMENT PENDING |  | 4 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss K Kehoe | 0121 218 3025 | 07562272502 |  |  | Windows & Doors | M Turpin | 2024-08-01 | 8am to 2pm
12 |  | 66905 |  | COMMENCEMENT PENDING |  | 5 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss A Roe | 07951676470 |  | angieroe01@gmail.com |  | Windows & Doors | M Turpin | 2024-08-01 | 8am to 2pm
12 |  | 61597 |  | COMMENCEMENT PENDING |  | 6 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss E Johnson |  | 07769596226 | jhns330@hotmail.co.uk |  | Windows & Doors | M Turpin | 2024-08-01 | 8am to 2pm
12 |  | 59632 |  | COMMENCEMENT PENDING |  | 7 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss A O'regan | 07495993808 |  |  |  | Windows & Doors | M Turpin | 2024-08-01 | 8am to 2pm
12 |  | 63486 |  | COMMENCEMENT PENDING |  | 9 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mrs J Baker | 07983 746 872 |  | julieanne001@hotmail.com |  | Windows & Doors | M Turpin | 2024-08-01 | 8am to 2pm
12 |  | 69822 |  | COMMENCEMENT PENDING |  | 11 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mr A Connolly | 07432316830 |  | starlord0032@icloud.com |  | Windows & Doors | M Turpin | 2024-08-01 | 8am to 2pm
12 |  | 69957 |  | COMMENCEMENT PENDING |  | 26 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mrs M Doherty |  | 07713826954 | MAZDOHERTY@HOTMAIL.CO.UK |  | Windows & Doors | M Turpin | 2024-08-01 | 8am to 2pm
12 |  | 59659 |  | COMMENCEMENT PENDING |  | 48 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss J Caesar | 01217482042 | 07837320565 |  |  | Windows & Doors | M Turpin | 2024-08-01 | 8am to 2pm
12 |  | 64386 |  | COMMENCEMENT PENDING |  | 50 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss T L Colbourne | 0121 776 7154 | 07769179506 | tcolbourne71@gmail.com |  | Windows & Doors
12 |  | 61601 |  | COMMENCEMENT PENDING |  | 52 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss N Chambers |  | 07877481007 |  |  | Windows & Doors | M Turpin | 2024-08-01 | 8am to 2pm
12 |  | 67831 |  | COMMENCEMENT PENDING |  | 54 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss S Rollason |  | 07742309599 |  |  | Windows & Doors | M Turpin | 2024-08-01 | 8am to 2pm
12 |  | 70251 |  | COMMENCEMENT PENDING |  | 56 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss A Crowley |  | 07592 464 037 |  |  | Windows & Doors | M Turpin | 2024-07-31 | 8am to 2pm
12 |  | 67829 |  | COMMENCEMENT PENDING |  | 60 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss L Sharpe |  | 07731618505 | lisaamu18@gmail.com |  | Windows & Doors | M Turpin | 2024-07-31 | 8am to 2pm
12 |  | 70373 |  | COMMENCEMENT PENDING |  | 62 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mr C Liwolweki |  | 07802293624 | csliwo_0878@hotmail.com |  | Windows & Doors | M Turpin | 2024-07-31 | 8am to 2pm
12 |  | 68710 |  | COMMENCEMENT PENDING |  | 88 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss H Ybrah | 07931 29 51 69 |  |  |  | Windows & Doors | M Turpin
12 |  | 64746 |  | COMMENCEMENT PENDING |  | 90 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mrs F Rangel | 0121 748 2765 | 07826241872 | olavoabreu98@hotmail.com |  | Windows & Doors | M Turpin
12 |  | 64086 |  | COMMENCEMENT PENDING |  | 94 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss A Bahourm |  | 07359626091 |  |  | Windows & Doors | M Turpin
12 |  | 63314 |  | COMMENCEMENT PENDING |  | 96 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss L Regan |  | 07380806878 |  |  | Windows & Doors | M Turpin
12 |  | 65473 |  | COMMENCEMENT PENDING |  | 98 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss T Dainter | 01217473720 | 07817317983 | munch90@hotmail.co.uk |  | Windows & Doors | M Turpin
12 |  | 68280 |  | COMMENCEMENT PENDING |  | 106 | Cosford Crescent | Birmingham |  | B35 6QE |  | Ms S Jacques | 07951936060 |  |  |  | Windows & Doors | M Turpin
12 |  | 59693 |  | COMMENCEMENT PENDING |  | 118 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss T Harvey |  | 07846226558 |  |  | Windows & Doors | M Turpin
12 |  | 64629 |  | COMMENCEMENT PENDING |  | 120 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss K D Delaney | 01217483367 | 07472685190 | kirbyddelaney@gmail.com |  | Windows & Doors | M Turpin
12 |  | 62931 |  | COMMENCEMENT PENDING |  | 122 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mrs J Stanley | 0121 730 1471 | 07740957404 | jackie-stanley@sky.com |  | Windows & Doors | M Turpin
12 |  | 67011 |  | COMMENCEMENT PENDING |  | 124 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss M A Jones |  | 07834 503 546 | xsh3ll82x@gmail.com |  | Windows & Doors | M Turpin
12 |  | 59698 |  | COMMENCEMENT PENDING |  | 126 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mrs T Broadmore |  | 07949 944 463 |  |  | Windows & Doors | M Turpin
12 |  | 59701 |  | COMMENCEMENT PENDING |  | 130 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mr D Lane | 0121 238 5580 | 07528 852 893 |  |  | Windows & Doors | M Turpin
12 |  | 65520 |  | COMMENCEMENT PENDING |  | 132 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mr J Burdett |  | 07855250469 |  |  | Windows & Doors | M Turpin
12 |  | 59703 |  | COMMENCEMENT PENDING |  | 134 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mr V Toole | 0121 749 7562 |  | vic.toole@eriks.co.uk |  | Windows & Doors | M Turpin
12 |  | 68531 |  | COMMENCEMENT PENDING |  | 138 | Cosford Crescent | Birmingham |  | B35 6QE |  | Ms J Hall | 0121 776 6281 | 07801413252 |  |  | Windows & Doors | M Turpin
12 |  | 65899 |  | COMMENCEMENT PENDING |  | 100 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss L Millar |  | 07758 923 106 | Leanne0385@gmail.com |  | Windows & Doors | M Turpin
12 |  | 68271 |  | COMMENCEMENT PENDING |  | 102 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss J Donnelly |  | 07498 808 943 | jodiemichelle22@mail.com |  | Windows & Doors | M Turpin
12 |  | 59692 |  | COMMENCEMENT PENDING |  | 116 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss J Barrett-Brown | 01217767753 |  | jbarrettbrown@hotmail.com |  | Windows & Doors | M Turpin
12 |  | 68144 |  | COMMENCEMENT PENDING |  | 128 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss D Hagans |  | 07852828303 | debz.h@icloud.com |  | Windows & Doors | M Turpin
12 |  | 66097 |  | COMMENCEMENT PENDING |  | FLAT 108 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss J Fitzwilliam-Carrington | 07565 831544 |  | nubjet_34@icloud.com |  | Windows & Doors | M Turpin | [33 empty] | Access via 116 & 106 Cosford Crescent
12 |  | 68128 |  | COMMENCEMENT PENDING |  | FLAT 110 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mr S Campbell |  | 07927318896 | simeoncampbell93@live.co.uk |  | Windows & Doors | M Turpin | [33 empty] | Access via 116 & 106 Cosford Crescent
12 |  | 59689 |  | COMMENCEMENT PENDING |  | FLAT 112 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mr G Newstead |  | 07969131722 | geoffreynewstead@gmail.com |  | Windows & Doors | M Turpin | [33 empty] | Access via 116 & 106 Cosford Crescent
12 |  | 59690 |  | COMMENCEMENT PENDING |  | FLAT 114 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mr B Hewings | 07507 395 230 | 07508 781 941 |  |  | Windows & Doors | M Turpin | [33 empty] | Access via 116 & 106 Cosford Crescent
12 |  | 69186 |  | COMMENCEMENT PENDING |  | FLAT 15 | Cosford Crescent | Birmingham |  | B35 6QE |  | Revd E Miller |  | 07387286011 | elsiemiller6@gmail.com |  | Windows & Doors | M Turpin | [33 empty] | Access via 17 Cosford
12 |  | 67873 |  | COMMENCEMENT PENDING |  | FLAT 17 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss S Cardoza | 0737 895 3156 | 0737 895 3156 |  |  | Windows & Doors | M Turpin | [33 empty] | Access gained through grd floor flat
12 |  | 69463 |  | COMMENCEMENT PENDING |  | FLAT 19 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mr N Morgan |  | 07397395060 | morgan.1990@live.co.uk |  | Windows & Doors | M Turpin | [33 empty] | Access gained through grd floor flat
12 |  | 68106 |  | COMMENCEMENT PENDING |  | FLAT 2 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss MAL Edwards | 0781036262638 | 07392631023 | carolbabygirl@hotmail.co.uk |  | Windows & Doors | M Turpin
12 |  | 69441 |  | COMMENCEMENT PENDING |  | FLAT 20 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss D Blake |  | 07496463152 | daynamorales@hotmail.co.uk |  | Windows & Doors | M Turpin | [33 empty] | Acess via 8 Cosford & 2 Abingdon
12 |  | 70307 |  | COMMENCEMENT PENDING |  | FLAT 21 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss S Shaheen |  | 07482372023 | sidrashaheen1992@hotmail.com |  | Windows & Doors | M Turpin | [33 empty] | Access gained through grd floor flat
12 |  | 64261 |  | COMMENCEMENT PENDING |  | FLAT 22 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mr SA Lester | 07988 071 562 | 07988071562 | stuartlester2008@hotmail.co.uk |  | Windows & Doors | M Turpin | [33 empty] | Acess via 8 Cosford & 2 Abingdon
12 |  | 59645 |  | COMMENCEMENT PENDING |  | FLAT 23 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mr T Harris | 07533669879 | 07533669879 | thomasharris346@rocketmail.com |  | Windows & Doors | M Turpin | [33 empty] | Access gained through grd floor flat
12 |  | 59649 |  | COMMENCEMENT PENDING |  | FLAT 27 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mr J Cullen | 07790737302 |  |  |  | Windows & Doors | M Turpin | [33 empty] | Access gained through grd floor flat
12 |  | 67841 |  | COMMENCEMENT PENDING |  | FLAT 38 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mr C A Layton | 07784729094 |  |  |  | Windows & Doors | M Turpin | 2024-07-30 | 8am to 2pm |  | 1 | (Access via 30 & 46 Cosford Crescent). 13.06.24 SF sent text for survey on the 24.06.24, waiting confirmation. 18.06.24 SF NIS sent letter. 24/6; NO ACCESS SURVEY, CARDED. 3/7/2024; AC sent letter for survey 30/7. | [28 empty] | Access via 30 & 46 Cosford Crescent
12 |  | 64754 |  | COMMENCEMENT PENDING |  | FLAT 40 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mr C L Jones | 0121 7481010 | 07894708299 | c.jones99965@yahoo.com |  | Windows & Doors | M Turpin | 2024-07-30 | 8am to 2pm |  | 1 | 14/06 SMS text sent for 25/06. 13.06.24 SF sent text for survey on the 24.06.24, waiting confirmation. 18.06.24 SF NIS & NA sent letter. 24/6; NO ACCESS SURVEY, CARDED. 3/7/2024; AC sent letter for survey 30/7. | [28 empty] | Access via 30 & 46 Cosford Crescent
12 |  | 68360 |  | COMMENCEMENT PENDING |  | FLAT 72 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mr MB Hatton |  | 07469170364 |  |  | Windows & Doors | M Turpin | 2024-07-30 | 8am to 2pm |  | 1 | 14/06 SMS text sent for 25/06. 18/6; AC rang and tenant works very day. He said he will try to find someone to houses it if we ring back in 2 days alternatively he will need 2 weeks to find a house sitter. 21.06.24 SF Called tenant, he can't do 24.06.24, said to call back on Monday 24.06.24 and maybe he has found someone to sit in the house, re-booked provisionally for the 01.07.24 for the survey. 1/7; NO ONE HOME FOR SURVEY, CARDED. 15/07 SMS email sent for 1st no access to TLO. 3/7/2024; AC sent letter for survey 30/7. | [28 empty] | Access via 64 Cosford & 21 Cranwell Way
12 |  | 69532 |  | COMMENCEMENT PENDING |  | FLAT 80 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mr K Smith | 07932081002 | 07932081002 |  |  | Windows & Doors | M Turpin | [33 empty] | Access via 88 Cosford & 16 Cranwell
12 |  | 66076 |  | COMMENCEMENT PENDING |  | FLAT 82 | Cosford Crescent | Birmingham |  | B35 6QE |  | Miss AL Cormell |  | 07516 224 654 | amy_cormell@live.co.uk |  | Windows & Doors | M Turpin | [33 empty] | Access via 88 Cosford & 16 Cranwell
12 |  | 64196 |  | COMMENCEMENT PENDING |  | FLAT 84 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mr S Guest |  | 07391 647 381 |  |  | Windows & Doors | M Turpin | [33 empty] | Access via 88 Cosford & 16 Cranwell
12 |  | 63357 |  | COMMENCEMENT PENDING |  | FLAT 86 | Cosford Crescent | Birmingham |  | B35 6QE |  | Mr T Coleman |  | 07771 915 390 |  |  | Windows & Doors | M Turpin | [33 empty] | Access via 88 Cosford & 16 Cranwell
12 |  | 59711 |  | COMMENCEMENT PENDING |  | 6 | Cranwell Way | Birmingham |  | B35 6QH |  | Mrs J Lawson | 0121 250 9010 | 07944 128 821 |  |  | Windows & Doors | M Turpin
12 |  | 59715 |  | COMMENCEMENT PENDING |  | 10 | Cranwell Way | Birmingham |  | B35 6QH |  | Mrs N Cuffe | 07486108166 | 07794343766 |  |  | Windows & Doors | M Turpin
12 |  | 59717 |  | COMMENCEMENT PENDING |  | 12 | Cranwell Way | Birmingham |  | B35 6QH |  | Miss S Cleal |  | 07908530582 |  |  | Windows & Doors | M Turpin
12 |  | 64265 |  | COMMENCEMENT PENDING |  | 14 | Cranwell Way | Birmingham |  | B35 6QH |  | Mrs H Harvey | 07802 846 703 |  |  |  | Windows & Doors | M Turpin
12 |  | 68126 |  | COMMENCEMENT PENDING |  | 16 | Cranwell Way | Birmingham |  | B35 6QH |  | Miss S Hamilton |  | 07340 37 89 00 | Symone_hamilton20@yahoo.co.uk |  | Windows & Doors | M Turpin
12 |  | 61616 |  | COMMENCEMENT PENDING |  | 17 | Cranwell Way | Birmingham |  | B35 6QH |  | Mr M Musson |  |  | tinacrowton@btinternet.com |  | Windows & Doors | M Turpin
12 |  | 59728 |  | COMMENCEMENT PENDING |  | 19 | Cranwell Way | Birmingham |  | B35 6QH |  | Mrs D Hanson |  | 07843771505 | deborahhanson37@yahoo.co.uk |  | Windows & Doors | M Turpin
12 |  | 64972 |  | COMMENCEMENT PENDING |  | 7 | Cranwell Way | Birmingham |  | B35 6QH |  | Miss J Ball | 07539192748 | 07539 192 748 |  |  | Windows & Doors | M Turpin | [33 empty] | Access via 5 Cranwell Way
12 |  | 63031 |  | COMMENCEMENT PENDING |  | 9 | Cranwell Way | Birmingham |  | B35 6QH |  | Miss Y Bouzidi |  | 07452899804 |  |  | Windows & Doors | M Turpin
12 |  | 66896 |  | COMMENCEMENT PENDING |  | FLAT 11 | Cranwell Way | Birmingham |  | B35 6QH |  | Mrs J Sherrington | 07587205593 |  |  |  | Windows & Doors | M Turpin
12 |  | 55659 |  | COMMENCEMENT PENDING |  | 3 | Davenport Drive | Birmingham |  | B35 7NT |  | Miss T Graham |  | 07368945792 | traceygraham@yahoo.co.uk |  | Windows & Doors
12 |  | 55660 |  | COMMENCEMENT PENDING |  | 4 | Davenport Drive | Birmingham |  | B35 7NT |  | Mrs G Thorne |  |  |  |  | Windows & Doors
12 |  | 55661 |  | COMMENCEMENT PENDING |  | 5 | Davenport Drive | Birmingham |  | B35 7NT |  | Mrs Bowron | 0121 730 2726 | 07904 806 262 |  |  | Windows & Doors
12 |  | 69855 |  | COMMENCEMENT PENDING |  | 7 | Davenport Drive | Birmingham |  | B35 7NT |  | Miss K Williams |  | 07543 642 145 | kayliew831@gmail.com |  | Windows & Doors
12 |  | 65429 |  | COMMENCEMENT PENDING |  | 11 | Davenport Drive | Birmingham |  | B35 7NT |  | Miss R Robinson |  | 07462913180 | rachelrobinson1005@iloud.com |  | Windows & Doors
12 |  | 63702 |  | COMMENCEMENT PENDING |  | 12 | Davenport Drive | Birmingham |  | B35 7NT |  | Miss N J Cattell |  | 07415885959 |  |  | Windows & Doors
12 |  | 55665 |  | COMMENCEMENT PENDING |  | 14 | Davenport Drive | Birmingham |  | B35 7NT |  | Miss M Hines | 07429590109 |  |  |  | Windows & Doors
12 |  | 70571 |  | COMMENCEMENT PENDING |  | 17 | Davenport Drive | Birmingham |  | B35 7NT |  | Mrs G Nazir |  | 07542871119 |  |  | Windows & Doors
12 |  | 55668 |  | COMMENCEMENT PENDING |  | 18 | Davenport Drive | Birmingham |  | B35 7NT |  | Miss T Witherington | 07730330381 |  | bobb63@hotmail.co.uk |  | Windows & Doors
12 |  | 55669 |  | COMMENCEMENT PENDING |  | 19 | Davenport Drive | Birmingham |  | B35 7NT |  | Mr R M Deeming | 07403 171 529 |  | raydeeming@gmail.com |  | Windows & Doors
12 |  | 55670 |  | COMMENCEMENT PENDING |  | 20 | Davenport Drive | Birmingham |  | B35 7NT |  | Mrs D Mitchell | 01217302316 |  |  |  | Windows & Doors
12 |  | 58738 |  | COMMENCEMENT PENDING |  | 21 | Davenport Drive | Birmingham |  | B35 7NT |  | Miss H Davies | 07503879185 | 07503 879 185 |  |  | Windows & Doors
12 |  | 55674 |  | COMMENCEMENT PENDING |  | 25 | Davenport Drive | Birmingham |  | B35 7NT |  | Miss M Creedon | 0121 730 1347 |  |  |  | Windows & Doors
12 |  | 55676 |  | COMMENCEMENT PENDING |  | 29 | Davenport Drive | Birmingham |  | B35 7NT |  | Mrs V Doras | 01217477944 | 07452 972 940 |  |  | Windows & Doors
12 |  | 70547 |  | COMMENCEMENT PENDING |  | 31 | Davenport Drive | Birmingham |  | B35 7NT |  | Mr K Boyd |  | 07548162722 |  |  | Windows & Doors
12 |  | 69064 |  | COMMENCEMENT PENDING |  | 33 | Davenport Drive | Birmingham |  | B35 7NT |  | Ms A Clarke |  | 07581 042010 |  |  | Windows & Doors
12 |  | 55679 |  | COMMENCEMENT PENDING |  | 37 | Davenport Drive | Birmingham |  | B35 7NT |  | Miss S Smith | 01213017410 | 07565868375 |  |  | Windows & Doors
12 |  | 63124 |  | COMMENCEMENT PENDING |  | 43 | Davenport Drive | Birmingham |  | B35 7NT |  | Mrs S M Purton |  | 07535086052 | smpurton@gmail.com |  | Windows & Doors
12 |  | 55683 |  | COMMENCEMENT PENDING |  | 12 | Dixon Close | Birmingham |  | B35 7EN |  | Mrs R Hopkins | 07482758721 | 07713445871 |  |  | Windows & Doors
12 |  | 67624 |  | COMMENCEMENT PENDING |  | 22 | Dixon Close | Birmingham |  | B35 7EN |  | Miss B Leigh |  | 07908131308 | binzlee@live.com |  | Windows & Doors
12 |  | 62197 |  | COMMENCEMENT PENDING |  | 26 | Dixon Close | Birmingham |  | B35 7EN |  | Mr C Tyrell |  | 07949 136 124 |  |  | Windows & Doors
12 |  | 68343 |  | COMMENCEMENT PENDING |  | 28 | Dixon Close | Birmingham |  | B35 7EN |  | Mr W Anderson |  |  |  |  | Windows & Doors
12 |  | 69856 |  | COMMENCEMENT PENDING |  | 30 | Dixon Close | Birmingham |  | B35 7EN |  | Miss N Harris |  | 07563385106 | harrinikki40@gmail.com |  | Windows & Doors
12 |  | 62200 |  | COMMENCEMENT PENDING |  | 32 | Dixon Close | Birmingham |  | B35 7EN |  | Mr D Conroy |  | 07981825847 | dconroy1928@btinternet.com |  | Windows & Doors
12 |  | 68395 |  | COMMENCEMENT PENDING |  | 34 | Dixon Close | Birmingham |  | B35 7EN |  | Mr C Teager |  | 07948 618 545 | colinteager62@gmail.com |  | Windows & Doors
12 |  | 62202 |  | COMMENCEMENT PENDING |  | 36 | Dixon Close | Birmingham |  | B35 7EN |  | Mr B A Beards |  | 07305531168 | babeards@outlook.com |  | Windows & Doors
12 |  | 63713 |  | COMMENCEMENT PENDING |  | 38 | Dixon Close | Birmingham |  | B35 7EN |  | Miss C E Pritchatt |  | 07508493698 | clairepritchatt@googlemail.com |  | Windows & Doors
12 |  | 67683 |  | COMMENCEMENT PENDING |  | 40 | Dixon Close | Birmingham |  | B35 7EN |  | Miss E L Oldham |  | 07904330493 | oldhamellen@yahoo.co.uk |  | Windows & Doors
12 |  | 66204 |  | COMMENCEMENT PENDING |  | 42 | Dixon Close | Birmingham |  | B35 7EN |  | Miss P Cruise | 01214391563 |  | patricacruise123456@gmail.com |  | Windows & Doors
12 |  | 64695 |  | COMMENCEMENT PENDING |  | 44 | Dixon Close | Birmingham |  | B35 7EN |  | Miss J Whitby |  | 07507018405 |  |  | Windows & Doors
12 |  | 62207 |  | COMMENCEMENT PENDING |  | 46 | Dixon Close | Birmingham |  | B35 7EN |  | Mr J P Carthy | 07792 030913 |  | jamescarthy43@gmail.com |  | Windows & Doors
12 |  | 62239 |  | COMMENCEMENT PENDING |  | 48 | Dixon Close | Birmingham |  | B35 7EN |  | Ms T A Lembariti | 07473494441 |  |  |  | Windows & Doors
12 |  | 69670 |  | COMMENCEMENT PENDING |  | 89 | Doidge Road | Birmingham |  | B23 7SQ |  | Miss N Westwood |  | 07776206133 | Nicola_Westwood@hotmail.com |  | Windows & Doors
12 |  | 69414 |  | COMMENCEMENT PENDING |  | 40 | Doncaster Way | Birmingham |  | B36 8UD |  | Miss J Fowler |  | 07716499730 | jessicafowler123@icloud.com |  | Windows & Doors
12 |  | 65624 |  | COMMENCEMENT PENDING |  | 16 | Donibristle Croft | Birmingham |  | B35 6BL |  | Miss K Fearn |  | 07885459131 | Fearn64@sky.com |  | Windows & Doors | M Turpin | School Hols |  |  |  | TS-03/05/24 Text sent for 16/05/24. TS-08/05/24 Tenant text back no, replied asking what days are better. 08/05 SMS tenant advised cant do that week but is available on the 30th or 31st May, advised we would come back once we have more dates available. 20/05 SMS text sent for 05/06. 23/05 SMS tenant declined 05/06. 03/06 SMS text sent for 17/06. 06/06 SMS tenant declined 17/06 needs in scholl hols
12 |  | 62974 |  | COMMENCEMENT PENDING | SEE COMMENTS | 21 | Donibristle Croft | Birmingham |  | B35 6BL |  | Mrs T A Robinson | 01217487692 |  | robrobinson@live.co.uk |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm |  |  | TS-07/05/24 Ltr sent for 15/05. 08/05 SMS called but no. NIS. MT reported tenant refused. Tenant changed his mind will need a survey re-booking once a new date becomes available. 06/06 SMS called no. NIS lttr sent for 17/06. 20.06.24 SF Received top sheet from Martin, NO ACCESS, CARDED, need to re-book another date. 02/07 SMS no access card has '21 Colishill on it so under query with surveyor as to what address was attended. 05/07 surveyor emailed to say he thinks he must of put the wrong address on the no access card so will need re-scheduling so as not clear will not log as a no access.
12 |  | 59741 |  | COMMENCEMENT PENDING | SEE COMMENTS | 20 | Donibristle Croft | Birmingham |  | B35 6BL |  | Mrs F Chantler | (Daughter) 07779 339 025 | 01217767481 |  |  | Windows & Doors | M Turpin |  |  |  |  | TS-07/05/24 Ltr sent for 15/05. No Access on 15/05 awaiting photo b4 sending info to client
12 |  | 65025 |  | COMMENCEMENT PENDING |  | 1 | Farnborough Road | Birmingham |  | B35 7EH |  | Miss L Elliot |  | 07950 519021 |  |  | Windows & Doors | M Turpin
12 |  | 68845 |  | COMMENCEMENT PENDING |  | 3 | Farnborough Road | Birmingham |  | B35 7EH |  | Mrs J Fearne | 07871854000 | 07871854000 | juniefearn1238@gmail.com |  | Windows & Doors | M Turpin
12 |  | 55711 |  | COMMENCEMENT PENDING |  | 5 | Farnborough Road | Birmingham |  | B35 7EH |  | Miss J Kane | 0121 730 3202 | 07858 403038 |  |  | Windows & Doors | M Turpin
12 |  | 59752 |  | COMMENCEMENT PENDING |  | 9 | Farnborough Road | Birmingham |  | B35 7EH |  | Miss S Derry | 0121 749 1276 | 07586 300775 |  |  | Windows & Doors | M Turpin
12 |  | 70053 |  | COMMENCEMENT PENDING |  | 11 | Farnborough Road | Birmingham |  | B35 7EH |  | Miss D Jeffrey |  | 07983 756792 |  |  | Windows & Doors | M Turpin
12 |  | 65179 |  | COMMENCEMENT PENDING |  | 15 | Farnborough Road | Birmingham |  | B35 7EH |  | Miss E Weetman |  | 07545267737 | ellieweetman@icloud.com |  | Windows & Doors | M Turpin
12 |  | 69615 |  | COMMENCEMENT PENDING |  | 17 | Farnborough Road | Birmingham |  | B35 7EH |  | Miss C O'Sullivan |  | 07944 126 501 | carly04_5@hotmail.com |  | Windows & Doors | M Turpin
12 |  | 68744 |  | COMMENCEMENT PENDING |  | 27 | Farnborough Road | Birmingham |  | B35 7EH |  | Mr K Quigley | 01212910049 | 07368 278 424 | kennyquigley837@gmail.com |  | Windows & Doors | M Turpin
12 |  | 68995 |  | COMMENCEMENT PENDING |  | FLAT 101 | Farnborough Road | Birmingham |  | B35 7EH |  | Mr TL Palmer-Bentley |  | 07473681990 |  |  | Windows & Doors | M Turpin
12 |  | 69273 |  | COMMENCEMENT PENDING |  | FLAT 103 | Farnborough Road | Birmingham |  | B35 7EH |  | Miss V Wilson |  | 07555730013 | vikki.wilson@outlook.com |  | Windows & Doors | M Turpin
12 |  | 63754 |  | COMMENCEMENT PENDING |  | FLAT 105 | Farnborough Road | Birmingham |  | B35 7EH |  | Mr L J Faloona | 0121 218 1073 | 07918820133 |  |  | Windows & Doors | M Turpin
12 |  | 69889 |  | COMMENCEMENT PENDING |  | FLAT 107 | Farnborough Road | Birmingham |  | B35 7EH |  | Mr C Smith |  | 07548 921 386 | copelandsmith8@hotmail.com |  | Windows & Doors | M Turpin
12 |  | 70237 |  | COMMENCEMENT PENDING |  | FLAT 109 | Farnborough Road | Birmingham |  | B35 7EH |  | Mr S Collins |  | 0737692837 | steven-0121@outlook.com |  | Windows & Doors | M Turpin
12 |  | 68452 |  | COMMENCEMENT PENDING |  | FLAT 111 | Farnborough Road | Birmingham |  | B35 7EH |  | Miss S Hughes |  | 07544 948464 | louisesades1985@gmail.com |  | Windows & Doors | M Turpin
12 |  | 62883 |  | COMMENCEMENT PENDING |  | FLAT 113 | Farnborough Road | Birmingham |  | B35 7EH |  | Mr P Kiely |  | 07429314294 | jasper896@googlemail.com |  | Windows & Doors | M Turpin
12 |  | 67435 |  | COMMENCEMENT PENDING |  | FLAT 115 | Farnborough Road | Birmingham |  | B35 7EH |  | Mr J Pettitt |  | 07305796295 |  |  | Windows & Doors | M Turpin
12 |  | 69550 |  | COMMENCEMENT PENDING |  | FLAT 117 | Farnborough Road | Birmingham |  | B35 7EH |  | Mr M Zelek |  | 07951447820 | mikolajzelek@hotmail.com |  | Windows & Doors | M Turpin
12 |  | 67322 |  | COMMENCEMENT PENDING |  | FLAT 119 | Farnborough Road | Birmingham |  | B35 7EH |  | Mr P Hogan | 07894999082 | 07894999082 |  |  | Windows & Doors | M Turpin
12 |  | 69495 |  | COMMENCEMENT PENDING |  | FLAT 121 | Farnborough Road | Birmingham |  | B35 7EH |  | Mr C Bond | 07717107372 |  |  |  | Windows & Doors | M Turpin
12 |  | 69020 |  | COMMENCEMENT PENDING |  | FLAT 123 | Farnborough Road | Birmingham |  | B35 7EH |  | Mr N Hughes | 07773227141 | 07773227141 | nathanhughes82@yahoo.co.uk |  | Windows & Doors | M Turpin
12 |  | 67584 |  | COMMENCEMENT PENDING |  | FLAT 31 | Farnborough Road | Birmingham |  | B35 7EH |  | Mrs R Deneke | 07380 172 236 | 07472914841 |  |  | Windows & Doors | M Turpin
12 |  | 69668 |  | COMMENCEMENT PENDING |  | 100 | Farnborough Road | Birmingham |  | B35 7JG |  | Mrs K Shepherd |  | 07494855249 |  |  | Windows & Doors | M Turpin
12 |  | 64595 |  | COMMENCEMENT PENDING |  | 98 | Farnborough Road | Birmingham |  | B35 7JG |  | Miss Y Edwards |  | 07850444154 |  |  | Windows & Doors | M Turpin
12 |  | 69399 |  | COMMENCEMENT PENDING |  | FLAT 145D | Farnborough Road | Birmingham |  | B35 7LQ |  | Mrs H Ali | 0121 748 2796 | 07985 393 342 | hasinaali@hotmail.com |  | Windows & Doors | M Turpin |  |  |  |  | 08/07 SMS text sent for 24/07. 08/07 SMS tenant text to decline
12 |  | 61834 |  | COMMENCEMENT PENDING |  | FLAT 147G | Farnborough Road | Birmingham |  | B35 7LQ |  | Mr D Wood | 0121 730 1945 | 07906726339 | don.wood1@hotmail.co.uk |  | Windows & Doors | M Turpin |  |  |  |  | 08/07 SMS text sent for 25/07. 08/07 SMS tenant text back to decline 25/07
12 |  | 55731 |  | COMMENCEMENT PENDING |  | 172 | Farnborough Road | Birmingham |  | B35 7NE |  | Mrs J M Cooksey |  | 07950 475165 |  |  | Windows & Doors | M Turpin
12 |  | 65573 |  | COMMENCEMENT PENDING |  | FLAT 1 Flats 216 1-6 Farnborough Road | Farnborough Road | Castle Vale |  | B35 7NH |  | Mrs J L Hislop |  |  |  |  | Windows & Doors | M Turpin
12 |  | 70400 |  | COMMENCEMENT PENDING |  | FLAT 2 Flats 216 1-6 Farnborough Road | Farnborough Road | Castle Vale |  | B35 7NH |  | Miss E Powell |  | 07830241088 | ellishapowell@hotmail.com |  | Windows & Doors | M Turpin
12 |  | 69252 |  | COMMENCEMENT PENDING |  | FLAT 3 Flats 216 1-6 Farnborough Road | Farnborough Road | Castle Vale |  | B35 7NH |  | Miss S Malone |  | 07515116920 | malones447@gmail.com |  | Windows & Doors | M Turpin
12 |  | 55758 |  | COMMENCEMENT PENDING |  | FLAT 4 Flats 216 1-6 Farnborough Road | Farnborough Road | Castle Vale |  | B35 7NH |  | Miss J Rogers |  |  |  |  | Windows & Doors | M Turpin
12 |  | 67125 |  | COMMENCEMENT PENDING |  | FLAT 5 Flats 216 1-6 Farnborough Road | Farnborough Road | Castle Vale |  | B35 7NH |  | Miss T Davis |  | 07938 849 668 |  |  | Windows & Doors | M Turpin
12 |  | 70383 |  | COMMENCEMENT PENDING |  | FLAT 6 Flats 216 1-6 Farnborough Road | Farnborough Road | Castle Vale |  | B35 7NH |  | Miss H Maloney |  | 07737449075 | hannahmoloneyxx18@gamil.com |  | Windows & Doors | M Turpin
12 |  | 55737 |  | COMMENCEMENT PENDING |  | 230 | Farnborough Road | Birmingham |  | B35 7NL |  | Mr KM Stanley |  |  |  |  | Windows & Doors | M Turpin
12 |  | 55738 |  | COMMENCEMENT PENDING |  | 238 | Farnborough Road | Birmingham |  | B35 7NL |  | Mr B E Bessey | 0121 748 5581 |  |  |  | Windows & Doors | M Turpin
12 |  | 61852 |  | COMMENCEMENT PENDING |  | 328 | Farnborough Road | Birmingham |  | B35 7NL |  | Miss A Histon |  | 07860811258 |  |  | Windows & Doors | M Turpin
12 |  | 63837 |  | COMMENCEMENT PENDING |  | 330 | Farnborough Road | Birmingham |  | B35 7NL |  | Mr A Russell |  | 07946 310 835 | adamrussell2@mail.co.uk |  | Windows & Doors | M Turpin
12 |  | 67589 |  | COMMENCEMENT PENDING |  | 258 | Farnborough Road | Birmingham |  | B35 7NR |  | Miss J Wheeler | 07888788307 |  | wheelerjodie693@gmail.com |  | Windows & Doors | M Turpin
12 |  | 55741 |  | COMMENCEMENT PENDING |  | 266 | Farnborough Road | Birmingham |  | B35 7NR |  | Mrs A Price | 0121 244 7626 | 077866 79766 |  |  | Windows & Doors | M Turpin
12 |  | 67362 |  | COMMENCEMENT PENDING |  | 268 | Farnborough Road | Birmingham |  | B35 7NR |  | Mr M Plant | 07944 058 064 | 07944 058496 |  |  | Windows & Doors | M Turpin
12 |  | 55745 |  | COMMENCEMENT PENDING |  | 284 | Farnborough Road | Birmingham |  | B35 7NR |  | Mr K C Bayliss | 0121 730 1503 |  |  |  | Windows & Doors | M Turpin
12 |  | 61578 |  | COMMENCEMENT PENDING |  | 359 | Farnborough Road | Birmingham |  | B35 7PA |  | Mrs M M Ryder | 0121 749 2753 | 07838 028 267 |  |  | Windows & Doors | M Turpin
12 |  | 61581 |  | COMMENCEMENT PENDING |  | 365 | Farnborough Road | Birmingham |  | B35 7PA |  | Mrs M Edmunds | 01217481175 | 07427923178 |  |  | Windows & Doors | M Turpin
12 |  | 61579 |  | COMMENCEMENT PENDING |  | 361 | Farnborough Road | Birmingham |  | B35 7PA |  | Miss J Smith | 0121 218 8333 | 07805 596348 |  |  | Windows & Doors | M Turpin
12 |  | 61582 |  | COMMENCEMENT PENDING |  | 367 | Farnborough Road | Birmingham |  | B35 7PA |  | Mrs L Skeffington | 0121 749 1568 | 07964 651965 |  |  | Windows & Doors | M Turpin
12 |  | 61948 |  | COMMENCEMENT PENDING |  | 369 | Farnborough Road | Birmingham |  | B35 7PA |  | Miss J McGregor |  | 07939 432616 | Howardbrandy53@gmail.com |  | Windows & Doors | M Turpin
12 |  | 69443 |  | COMMENCEMENT PENDING |  | 371 | Farnborough Road | Birmingham |  | B35 7PA |  | Miss B Mitchell | 07476959707 |  | brittneymitchell89@hotmail.com |  | Windows & Doors | M Turpin
12 |  | 68683 |  | COMMENCEMENT PENDING |  | 375 | Farnborough Road | Birmingham |  | B35 7PA |  | Miss C M Wellard-Taylor | 07736846250 | 07736846250 |  |  | Windows & Doors | M Turpin |  |  |  |  | *tenant will need lots of notice for any appointments | [28 empty] | *tenant will need lots of notice for any appointments | [11 empty] | *tenant will need lots of notice for any appointments
12 |  | 66045 |  | COMMENCEMENT PENDING |  | 377 | Farnborough Road | Birmingham |  | B35 7PA |  | Mr A E Swann |  | 07802366961 |  |  | Windows & Doors | M Turpin
12 |  | 61588 |  | COMMENCEMENT PENDING |  | 379 | Farnborough Road | Birmingham |  | B35 7PA |  | Miss I Loveridge |  | 07752028855 | ireneloveridge@btinternet.com |  | Windows & Doors | M Turpin
12 |  | 55747 |  | COMMENCEMENT PENDING |  | 332 | Farnborough Road | Birmingham |  | B35 7PD |  | Mrs M Cunningham |  | 07842480164 |  |  | Windows & Doors | M Turpin
12 |  | 68762 |  | COMMENCEMENT PENDING |  | 334 | Farnborough Road | Birmingham |  | B35 7PD |  | Mrs T Engamba | 07897530915 | 07897530915 | thmimboe@gmail.com |  | Windows & Doors | M Turpin
12 |  | 69762 |  | COMMENCEMENT PENDING |  | 340 | Farnborough Road | Birmingham |  | B35 7PD |  | Miss C Shirley | 01217485660 |  | charlotte.c.s@hotmail.co.uk |  | Windows & Doors | M Turpin
12 |  | 67884 |  | COMMENCEMENT PENDING |  | 1 | Filton Croft | Birmingham |  | B35 6JR |  | Mrs A Proffitt | 1217303071 |  | DONP46@live.co.uk |  | Windows & Doors
12 |  | 61590 |  | COMMENCEMENT PENDING |  | 14A | Filton Croft | Birmingham |  | B35 6JR |  | Miss A Loveridge | 0121 748 5657 | 07507721393 | angel-love1712@hotmail.com |  | Windows & Doors
12 |  | 69439 |  | COMMENCEMENT PENDING |  | 14B | Filton Croft | Birmingham |  | B35 6JR |  | Miss A Morris | 07714 242351 | 07714242351 |  |  | Windows & Doors
12 |  | 59768 |  | COMMENCEMENT PENDING |  | 1A | Filton Croft | Birmingham |  | B35 6JR |  | Mrs B Baggott |  |  |  |  | Windows & Doors
12 |  | 69552 |  | COMMENCEMENT PENDING |  | FLAT 29 Geeson Close | Geeson Close | Birmingham |  | B35 6NU |  | Miss C Dorrell |  | 07467494029 | courtneylouise28@outlook.com |  | Windows & Doors
12 |  | 63243 |  | COMMENCEMENT PENDING |  | 15 | Halfpennyfield Walk | Birmingham |  | B35 7HT |  | Miss R A Barnsley |  | 07377078828 | barnsleyrebecca@yahoo.com |  | Windows & Doors
12 |  | 55791 |  | COMMENCEMENT PENDING |  | 10 | Halfpennyfield Walk | Birmingham |  | B35 7HX |  | Mrs A Edwards | 0121 749 4333 |  | anniebubble@ymail.com |  | Windows & Doors
12 |  | 68035 |  | COMMENCEMENT PENDING |  | 12 | Halfpennyfield Walk | Birmingham |  | B35 7HX |  | Mrs K Teece |  | 01217495129 | kelzminx88@gmail.com |  | Windows & Doors
12 |  | 65804 |  | COMMENCEMENT PENDING |  | 14 | Halfpennyfield Walk | Birmingham |  | B35 7HX |  | Miss C Jones | 07394004942 |  | lil_miss_cj_2013@hotmail.co.uk |  | Windows & Doors
12 |  | 67423 |  | COMMENCEMENT PENDING |  | 8 | Halfpennyfield Walk | Birmingham |  | B35 7HX |  | Mr N J Goldie | 07740 984 556 |  | sorrellet@yahoo.co.uk |  | Windows & Doors
12 |  | 70267 |  | COMMENCEMENT PENDING |  | 48 | Hampton Road | Birmingham |  | B23 7JJ |  | VOID |  |  |  |  | Windows & Doors
12 |  | 55822 |  | ON HOLD | CLIENT ISSUE | 47 | Hawker Drive | Birmingham |  | B35 7DY |  | Mrs S Bradshaw |  | 07943 175389 | suebradshaw04@hotmail.co.uk |  | Windows & Doors | P Beahan | Read Notes |  |  |  | 08/07 SMS text sent for 25/07. 08/07 SMS tenant replied advising is currently undergoing Cancer treatment so want to be put on hold for any survey etc, ref back to CLIENT & Dominie.
11 |  | 70308 |  | SURVEY BOOKED |  | 49 | Hawker Drive | Birmingham |  | B35 7DY |  | Mrs M Franks | 07828956007 |  | michellefranks52@yahoo.co.uk |  | Windows & Doors | P Beahan | 2024-07-31 |  |  |  | 15/7; AC SENT SURVEY TEXT FOR 31/7. 15/7; TENANT TEXT BACK TO CONFIRM.
11 |  | 55825 |  | SURVEY BOOKED |  | 53 | Hawker Drive | Birmingham |  | B35 7DY |  | Mrs G Wilkins | 01217486754 | 07941037147 |  |  | Windows & Doors | P Beahan | 2024-07-31 |  |  |  | 15/7; AC SENT SURVEY TEXT FOR 31/7.
11 |  | 55827 |  | SURVEY BOOKED |  | 55 | Hawker Drive | Birmingham |  | B35 7DY |  | Mr T Greenfield | 0121 681 5011 | 07545381214 | t.greenfield@sky.com |  | Windows & Doors | P Beahan | 2024-07-31 |  |  |  | 15/7; AC SENT SURVEY TEXT FOR 31/7. 15/7; TENANT TEXT BACK TO CONFIRM.
11 |  | 55830 |  | SURVEY BOOKED |  | 63 | Hawker Drive | Birmingham |  | B35 7DY |  | Mr M Eaton | 01217491552 | 07717307605 |  |  | Windows & Doors | P Beahan | 2024-07-31 |  |  |  | 15/7; AC SENT SURVEY TEXT FOR 31/7. 17/7; tenant confirmed by text.
11 |  | 55832 |  | SURVEY BOOKED |  | 65 | Hawker Drive | Birmingham |  | B35 7DY |  | Mr K Griffiths |  |  |  |  | Windows & Doors | P Beahan | 2024-07-31 |  |  |  | 15/7; AC SENT SURVEY TEXT FOR 31/7.
12 |  | 69459 |  | COMMENCEMENT PENDING |  | 109 | Hawker Drive | Birmingham |  | B35 7EB |  | Mr D Adeniran | 07500 53 03 83 | 07983 600720 |  |  | Windows & Doors | P Beahan
12 |  | 65861 |  | COMMENCEMENT PENDING |  | 111 | Hawker Drive | Birmingham |  | B35 7EB |  | Mr TA Cadby |  | 07399557509 | t.cadby@live.com |  | Windows & Doors | P Beahan
12 |  | 55852 |  | COMMENCEMENT PENDING |  | 115 | Hawker Drive | Birmingham |  | B35 7EB |  | Miss D Basnett |  |  |  |  | Windows & Doors | P Beahan
12 |  | 67840 |  | COMMENCEMENT PENDING |  | 123 | Hawker Drive | Birmingham |  | B35 7EB |  | Miss A Cross |  | 07957 149919 |  |  | Windows & Doors | P Beahan
12 |  | 58597 |  | COMMENCEMENT PENDING |  | 52 | Hawker Drive | Birmingham |  | B35 7EG |  | Mrs K Smith | 07790865747 |  |  |  | Windows & Doors | P Beahan
12 |  | 55826 |  | COMMENCEMENT PENDING |  | 54 | Hawker Drive | Birmingham |  | B35 7EG |  | Mr A Stanton |  | 07846 850384 | tony.stanton54@hotmail.co.uk |  | Windows & Doors | P Beahan
12 |  | 55833 |  | COMMENCEMENT PENDING | SEE COMMENTS | 68 | Hawker Drive | Birmingham |  | B35 7EG |  | Mrs M White |  | 07890 188 074 (Rosemary-Neice) |  |  | Windows & Doors | P Beahan |  |  |  |  | Tenant bed bound, contact is neice Rosemary who all arrangements will be made through as tenant not able to answer door.Will need to be liasing with Dominie also regarding any visits to property as she will need to attend also. | [28 empty] | Tenant bed bound, contact is neice Rosemary who all arrangements will be made through as tenant not able to answer door.Will need to be liasing with Dominie also regarding any visits to property as she will need to attend also. | [11 empty] | Tenant bed bound, contact is neice Rosemary who all arrangements will be made through as tenant not able to answer door.Will need to be liasing with Dominie also regarding any visits to property as she will need to attend also.
12 |  | 57808 |  | COMMENCEMENT PENDING |  | 70 | Hawker Drive | Birmingham |  | B35 7EG |  | Mr S Ashe |  |  | simonashe1@hotmail.com |  | Windows & Doors | P Beahan
12 |  | 62856 |  | COMMENCEMENT PENDING |  | FLAT 2 | Hawker Drive | Birmingham |  | B35 7EG |  | Miss D S Newton | 07460 759 433 | 0772 983 2129 |  |  | Windows & Doors | P Beahan | SEPTEMBER only |  |  |  | 24/06 SMS text sent for 10/07. 24/06 SMS tenant text back to decline appointment
12 |  | 65986 |  | COMMENCEMENT PENDING |  | 4 | Hawkinge Drive | Birmingham |  | B35 6BP |  | Mrs S M Fahy | 0121 748 7608 | 07855586905 | THEWORLDCUP1966@HOTMAIL.COM |  | Windows & Doors
12 |  | 60199 |  | COMMENCEMENT PENDING |  | 6 | Hawkinge Drive | Birmingham |  | B35 6BP |  | Mrs S Swingler |  | 07793848746 | sarahswingler.1@btinternet.com |  | Windows & Doors
12 |  | 68515 |  | COMMENCEMENT PENDING |  | 26 | Hawkinge Drive | Birmingham |  | B35 6BP |  | Miss A Williams Francis |  |  | tenneshia85@sky.com |  | Windows & Doors
12 |  | 69914 |  | COMMENCEMENT PENDING |  | 28 | Hawkinge Drive | Birmingham |  | B35 6BP |  | Miss A Dodwell |  |  | aimeedod89@hotmail.co.uk |  | Windows & Doors
12 |  | 62731 |  | COMMENCEMENT PENDING |  | 30 | Hawkinge Drive | Birmingham |  | B35 6BP |  | Ms C L Wighton |  | 07790 752892 | clarewighton@nhs.net |  | Windows & Doors
12 |  | 70669 |  | COMMENCEMENT PENDING |  | 32 | Hawkinge Drive | Birmingham |  | B35 6BP |  | Mr J Renshaw |  | 07896266724 | mildredrenshaw@yahoo.co.uk |  | Windows & Doors
12 |  | 64578 |  | COMMENCEMENT PENDING |  | 34 | Hawkinge Drive | Birmingham |  | B35 6BP |  | Mr L Hall | 0121 439 6992 | 07858 127 904 | lance-hall@hotmail.co.uk |  | Windows & Doors
12 |  | 68774 |  | COMMENCEMENT PENDING |  | 36 | Hawkinge Drive | Birmingham |  | B35 6BP |  | Miss L Hunt | 0796 131 0677 |  | laurahunt2009@hotmail.co.uk |  | Windows & Doors
12 |  | 64162 |  | COMMENCEMENT PENDING |  | 38 | Hawkinge Drive | Birmingham |  | B35 6BP |  | Miss D Robertson |  | 07813 505 471 |  |  | Windows & Doors
12 |  | 58147 |  | COMMENCEMENT PENDING |  | 48 | Hawkinge Drive | Birmingham |  | B35 6BP |  | Miss J Murray | 01217470702 |  |  |  | Windows & Doors
12 |  | 68921 |  | COMMENCEMENT PENDING |  | 50 | Hawkinge Drive | Birmingham |  | B35 6BP |  | Mr T Currivan | 07854571718 |  |  |  | Windows & Doors
12 |  | 55946 |  | COMMENCEMENT PENDING |  | 52 | Hawkinge Drive | Birmingham |  | B35 6BP |  | Mrs M A Crumpton | 01217491957 |  |  |  | Windows & Doors
12 |  | 65411 |  | COMMENCEMENT PENDING |  | 56 | Hawkinge Drive | Birmingham |  | B35 6BP |  | Miss C P Rice |  | 07858514098 |  |  | Windows & Doors
12 |  | 67733 |  | COMMENCEMENT PENDING |  | FLAT 40 | Hedley Croft | Birmingham |  | B35 6PB |  | Miss F Franks |  |  | f.franks@hotmail.co.uk |  | Windows & Doors
12 |  | 55905 |  | COMMENCEMENT PENDING | SEE COMMENTS | 32 | Heyford Way | Birmingham |  | B35 6HU |  | Miss L Wood |  | 07903 305463 | lisa_1970@iphone.com |  | Windows & Doors | P Beahan |  |  |  |  | TS-02/04/24 Text sent for 11/04/24. TS-04/04/24 Called tenant left vm, txt & ltr sent. TS-15/04/24 PB left a card with the tenant's brother to contact Housing Association.
12 |  | 67818 |  | COMMENCEMENT PENDING | SEE COMMENTS | 33 | Heyford Way | Birmingham |  | B35 6HY |  | Miss D Banner |  | 07714469572 | dannioliver@me.com |  | Windows & Doors | P Beahan |  |  |  |  | TS-02/04/24 Text sent for 11/04/24. TS-02/04/24 Tenant CONFIRMED for the 11/04/24. TS-15/04/24 PB marked on the diary sheet "Scope of works to be determined" email to follow.
12 |  | 57085 |  | COMMENCEMENT PENDING |  | 2 | Howes Croft | Birmingham |  | B35 7EL |  | Mrs S A Tipper |  |  |  |  | Windows & Doors
12 |  | 70445 |  | COMMENCEMENT PENDING |  | 5 | Howes Croft | Birmingham |  | B35 7EL |  | Miss A Pulfer |  | 07895085772 |  |  | Windows & Doors
12 |  | 64687 |  | COMMENCEMENT PENDING |  | 8 | Howes Croft | Birmingham |  | B35 7EL |  | Mr S Messaoudi |  | 07830 027 516 |  |  | Windows & Doors
12 |  | 60726 |  | COMMENCEMENT PENDING |  | 10 | Howes Croft | Birmingham |  | B35 7EL |  | Mrs P Edwards |  |  |  |  | Windows & Doors
12 |  | 55935 |  | COMMENCEMENT PENDING |  | 12 | Howes Croft | Birmingham |  | B35 7EL |  | Miss C Reilly |  | 07784715748 | sarahrutter1@live.co.uk |  | Windows & Doors
12 |  | 65702 |  | COMMENCEMENT PENDING |  | 14 | Howes Croft | Birmingham |  | B35 7EL |  | Mr D Friend |  | 07981776899 |  |  | Windows & Doors
12 |  | 55937 |  | COMMENCEMENT PENDING |  | 15 | Howes Croft | Birmingham |  | B35 7EL |  | Ms S Powell | 0121 628 6799 |  | s.powell841@btinternet.com |  | Windows & Doors
12 |  | 63361 |  | COMMENCEMENT PENDING |  | 19 | Howes Croft | Birmingham |  | B35 7EL |  | Mrs P Marles | 0121 748 2704 |  |  |  | Windows & Doors
12 |  | 57155 |  | COMMENCEMENT PENDING |  | 21 | Howes Croft | Birmingham |  | B35 7EL |  | Mrs J Roberts |  | 07467 454 619 |  |  | Windows & Doors
12 |  | 55938 |  | COMMENCEMENT PENDING |  | 22 | Howes Croft | Birmingham |  | B35 7EL |  | Mrs B Ray | 748 2840 |  |  |  | Windows & Doors
12 |  | 55939 |  | COMMENCEMENT PENDING |  | 27 | Howes Croft | Birmingham |  | B35 7EL |  | Mr S Lavin | 07973897510 |  | sblhorse@hotmail.co.uk |  | Windows & Doors
12 |  | 55940 |  | COMMENCEMENT PENDING |  | 31 | Howes Croft | Birmingham |  | B35 7EL |  | Mr R Clinton |  | 07875144434 |  |  | Windows & Doors
12 |  | 65468 |  | COMMENCEMENT PENDING |  | 21 | Innsworth Drive | Birmingham |  | B35 6AU |  | Mr M J Colburn |  | 07971 382040 | mcolburn77@yahoo.co.uk |  | Windows & Doors
12 |  | 65505 |  | COMMENCEMENT PENDING |  | 34 | Innsworth Drive | Birmingham |  | B35 6BB |  | Miss L O'Neill | 01217496078 | 07936748273 |  |  | Windows & Doors
12 |  | 65784 |  | COMMENCEMENT PENDING |  | 60 | Innsworth Drive | Birmingham |  | B35 6BD |  | Mrs M Harvey | 07735 342 672 | 07956561044 | johnharveyb35@gmail.com |  | Windows & Doors
12 |  | 61399 |  | COMMENCEMENT PENDING |  | 62 | Innsworth Drive | Birmingham |  | B35 6BD |  | Mr B McElwee |  | 07756466125 |  |  | Windows & Doors
12 |  | 62609 |  | COMMENCEMENT PENDING |  | 64 | Innsworth Drive | Birmingham |  | B35 6BD |  | Mr P Langston |  | 079844 695 60 |  |  | Windows & Doors
12 |  | 61909 |  | COMMENCEMENT PENDING |  | 66 | Innsworth Drive | Birmingham |  | B35 6BD |  | Mr W Burton | 07578366064 |  |  |  | Windows & Doors
12 |  | 69395 |  | COMMENCEMENT PENDING |  | 68 | Innsworth Drive | Birmingham |  | B35 6BD |  | Mr I Nahar |  | 07460542955 | ibrahimnayar143@gmail.com |  | Windows & Doors
12 |  | 62167 |  | COMMENCEMENT PENDING |  | 70 | Innsworth Drive | Birmingham |  | B35 6BD |  | Mr E Koppenhoffer | 01217486387 | 077739 49728 | koppenhof@aol.com |  | Windows & Doors
12 |  | 68661 |  | COMMENCEMENT PENDING |  | 72 | Innsworth Drive | Birmingham |  | B35 6BD |  | Mr S V Mccracken | 01217497448 | 07561034505 | seanmac2009@hotmail.co.uk |  | Windows & Doors
12 |  | 61403 |  | COMMENCEMENT PENDING |  | 74 | Innsworth Drive | Birmingham |  | B35 6BD |  | Mrs M Burke |  | 07531 135 647 |  |  | Windows & Doors
12 |  | 69090 |  | COMMENCEMENT PENDING |  | 76 | Innsworth Drive | Birmingham |  | B35 6BD |  | Ms V Stockton | 07883742021 |  | ruddvicky@gmail.com |  | Windows & Doors
12 |  | 70362 |  | COMMENCEMENT PENDING |  | 78 | Innsworth Drive | Birmingham |  | B35 6BD |  | Miss C Frost |  | 07376050597 | chelsealouisefrost@hotmail.com |  | Windows & Doors
12 |  | 67574 |  | COMMENCEMENT PENDING |  | 17 | Jackson Walk | Birmingham |  | B35 7ER |  | Miss S Wade |  | 07931 801890 | sarahwade54@yahoo.com |  | Windows & Doors
12 |  | 57812 |  | COMMENCEMENT PENDING |  | 19 | Jackson Walk | Birmingham |  | B35 7ER |  | Miss S Hobbs |  |  |  |  | Windows & Doors
12 |  | 59784 |  | COMMENCEMENT PENDING |  | 25 | Jackson Walk | Birmingham |  | B35 7ER |  | Mrs V Hill |  |  |  |  | Windows & Doors
12 |  | 63028 |  | COMMENCEMENT PENDING |  | 29 | Jackson Walk | Birmingham |  | B35 7ER |  | Mrs E M Fogg |  | 07734 324 637 |  |  | Windows & Doors
12 |  | 56025 |  | COMMENCEMENT PENDING |  | 71 | Jackson Walk | Birmingham |  | B35 7ER |  | Mr M Ellis |  | 07398027805 |  |  | Windows & Doors
12 |  | 69408 |  | COMMENCEMENT PENDING |  | FLAT 11 | Jackson Walk | Birmingham |  | B35 7ER |  | Mr P Chancellor |  | 07392933824 | phillipchancellor@hotmail.com |  | Windows & Doors
12 |  | 64980 |  | COMMENCEMENT PENDING |  | FLAT 5 | Jackson Walk | Birmingham |  | B35 7ER |  | Mr C Loach | 0121 747 3836 | 07486539691 | vaughtons@yahoo.co.uk |  | Windows & Doors
12 |  | 65923 |  | COMMENCEMENT PENDING |  | FLAT 61 | Jackson Walk | Birmingham |  | B35 7ER |  | Mrs G A Foster |  |  | gillRobertson2008@hotmail.co.uk |  | Windows & Doors
12 |  | 68875 |  | COMMENCEMENT PENDING |  | FLAT 63 | Jackson Walk | Birmingham |  | B35 7ER |  | Miss N Napper | 0121 220 3449 | 07842388408 |  |  | Windows & Doors
12 |  | 56023 |  | COMMENCEMENT PENDING |  | FLAT 65 | Jackson Walk | Birmingham |  | B35 7ER |  | Mr S Brittain |  | 07816 627 372 |  |  | Windows & Doors
12 |  | 56024 |  | COMMENCEMENT PENDING |  | FLAT 67 | Jackson Walk | Birmingham |  | B35 7ER |  | Mr P Edwards |  |  |  |  | Windows & Doors
12 |  | 68493 |  | COMMENCEMENT PENDING |  | FLAT 7 | Jackson Walk | Birmingham |  | B35 7ER |  | Miss L Fryer |  |  | laurafryer93@outlook.com |  | Windows & Doors
12 |  | 69458 |  | COMMENCEMENT PENDING |  | FLAT 73 | Jackson Walk | Birmingham |  | B35 7ER |  | Mrs Z Begum |  | 07542596516 | azizur8076@gmail.com |  | Windows & Doors
12 |  | 70771 |  | COMMENCEMENT PENDING |  | FLAT 75 | Jackson Walk | Birmingham |  | B35 7ER |  | VOID |  |  |  |  | Windows & Doors
12 |  | 56028 |  | COMMENCEMENT PENDING |  | FLAT 77 | Jackson Walk | Birmingham |  | B35 7ER |  | Mr G Halling |  | 07970301352 | geoffrey.halling@googlemail.com |  | Windows & Doors
12 |  | 69884 |  | COMMENCEMENT PENDING |  | FLAT 79 | Jackson Walk | Birmingham |  | B35 7ER |  | Miss J Blythe |  | 07508173658 |  |  | Windows & Doors
12 |  | 63237 |  | COMMENCEMENT PENDING |  | FLAT 9 | Jackson Walk | Birmingham |  | B35 7ER |  | Mr S J Clarke |  | 07852 937 671 |  |  | Windows & Doors
12 |  | 62424 |  | COMMENCEMENT PENDING |  | FLAT 10 | Jackson Walk | Birmingham |  | B35 7ES |  | Ms B Namayanja | 0121 238 5068 | 07368 146087 |  |  | Windows & Doors
12 |  | 69562 |  | COMMENCEMENT PENDING |  | FLAT 12 | Jackson Walk | Birmingham |  | B35 7ES |  | Mr A Douglas |  | 07804281427 | ad52erd@hotmail.com |  | Windows & Doors
12 |  | 67634 |  | COMMENCEMENT PENDING |  | FLAT 14 | Jackson Walk | Birmingham |  | B35 7ES |  | Miss I Walker |  |  | isobelwalks@gmail.com |  | Windows & Doors
12 |  | 68377 |  | COMMENCEMENT PENDING |  | FLAT 8 | Jackson Walk | Birmingham |  | B35 7ES |  | Mrs B Tekle | 07588624303 | 07588624303 | naeley2015@gmail.com |  | Windows & Doors
12 |  | 63785 |  | COMMENCEMENT PENDING |  | 26 | Jackson Walk | Birmingham |  | B35 7ET |  | Mr P Kendrick | 07809439188 | 07502042729 |  |  | Windows & Doors
12 |  | 56003 |  | COMMENCEMENT PENDING |  | 28 | Jackson Walk | Birmingham |  | B35 7ET |  | Mrs B Wilson |  | 07377 376 485 |  |  | Windows & Doors
12 |  | 65110 |  | COMMENCEMENT PENDING |  | 30 | Jackson Walk | Birmingham |  | B35 7ET |  | Mr D Jones |  | 07731932821 |  |  | Windows & Doors
12 |  | 56008 |  | COMMENCEMENT PENDING |  | 34 | Jackson Walk | Birmingham |  | B35 7ET |  | Mr M Cooksey |  | 07763 964 307 | mark.cooksey@o2.co.uk |  | Windows & Doors
12 |  | 56013 |  | COMMENCEMENT PENDING |  | 44 | Jackson Walk | Birmingham |  | B35 7ET |  | Mrs P Jones | 0121 748 1209 | 07928257661 | patj19521952@gmail.com |  | Windows & Doors
12 |  | 70338 |  | COMMENCEMENT PENDING |  | FLAT 46 | Jackson Walk | Birmingham |  | B35 7ET |  | Ms D Raven |  |  |  |  | Windows & Doors
12 |  | 69732 |  | COMMENCEMENT PENDING |  | FLAT 48 | Jackson Walk | Birmingham |  | B35 7ET |  | Miss D Boylan |  | 07377902763 | daniwilf@gmail.com |  | Windows & Doors
12 |  | 68679 |  | COMMENCEMENT PENDING |  | FLAT 50 | Jackson Walk | Birmingham |  | B35 7ET |  | Mr F Abbas | 07474169278 | 07474169278 | firfir86@gmail.com |  | Windows & Doors
12 |  | 68644 |  | COMMENCEMENT PENDING |  | FLAT 52 | Jackson Walk | Birmingham |  | B35 7ET |  | Mr C Duke |  | 07796668916 |  |  | Windows & Doors
12 |  | 61938 |  | COMMENCEMENT PENDING |  | 78 | Javelin Avenue | Birmingham |  | B35 7LW |  | Miss C Belle |  | 07985555420 | carlabelle@ymail.com |  | Windows & Doors | M Turpin | Fridays |  |  |  | TS-19/04/24 Text sent for 29/04/24. TS-23/04/24 Called tenant and she can't make the 29/04/24 child has a doctors appointment and they can't change it - child has autism. 14/06 SMS text sent for 27/06. 19/6; AC rang tenant, she cannot be home for survey 27/6 as she works. Fridays are better - she does want her replacements and acknowledged thast she could not do the other date we offered too in April.
12 |  | 65215 |  | COMMENCEMENT PENDING |  | 14 | Johnson Drive | Birmingham |  | B35 6DS |  | Ms C Gordon |  | 07859334888 | chezzyg34@hotmail.com |  | Windows & Doors
12 |  | 65295 |  | COMMENCEMENT PENDING |  | 15 | Johnson Drive | Birmingham |  | B35 6DS |  | Miss N Ricketts | 0121 748 6204 | 07711933578 | nat14_73@hotmail.com |  | Windows & Doors
12 |  | 56059 |  | COMMENCEMENT PENDING |  | 20 | Johnson Drive | Birmingham |  | B35 6DS |  | Mrs D Edmunds |  |  |  |  | Windows & Doors
12 |  | 56060 |  | COMMENCEMENT PENDING |  | 26 | Johnson Drive | Birmingham |  | B35 6DS |  | Mrs S Pointon |  |  |  |  | Windows & Doors
12 |  | 69728 |  | COMMENCEMENT PENDING |  | 42 | Johnson Drive | Birmingham |  | B35 6DS |  | Ms L M Light |  | 07938 684 384 | lisalight63@gmail.com |  | Windows & Doors
12 |  | 66759 |  | COMMENCEMENT PENDING |  | FLAT 1 | Johnson Drive | Birmingham |  | B35 6DS |  | Mrs J Johnson |  |  | jaynejohnson1@hotmail.co.uk |  | Windows & Doors
12 |  | 69423 |  | COMMENCEMENT PENDING |  | FLAT 10 | Johnson Drive | Birmingham |  | B35 6DS |  | Miss S Hickman |  | 07910741525 | sarahhickman1234@gmail.com |  | Windows & Doors
12 |  | 63770 |  | COMMENCEMENT PENDING |  | FLAT 12 | Johnson Drive | Birmingham |  | B35 6DS |  | Miss B Catwell |  | 078100 35 373 | sarahrutter1@live.co.uk |  | Windows & Doors
12 |  | 56049 |  | COMMENCEMENT PENDING |  | FLAT 3 | Johnson Drive | Birmingham |  | B35 6DS |  | Mrs Greasley | 07775164812 |  |  |  | Windows & Doors
12 |  | 69462 |  | COMMENCEMENT PENDING |  | FLAT 34 | Johnson Drive | Birmingham |  | B35 6DS |  | Miss Z Ashiq | 07850960005 | 07879775097 | zarina123@hotmail.com |  | Windows & Doors
12 |  | 56063 |  | COMMENCEMENT PENDING |  | FLAT 38 | Johnson Drive | Birmingham |  | B35 6DS |  | Mr K Hunter | 0121 749 7514 |  | klhunter1952@gmail.com |  | Windows & Doors
12 |  | 67425 |  | COMMENCEMENT PENDING |  | FLAT 44 | Johnson Drive | Birmingham |  | B35 6DS |  | Mr P Craythorne | 07305 046 601 | 07975602634 |  |  | Windows & Doors
12 |  | 63624 |  | COMMENCEMENT PENDING |  | FLAT 46 | Johnson Drive | Birmingham |  | B35 6DS |  | Miss L Roberts |  |  | lisatot@hotmail.co.uk |  | Windows & Doors
12 |  | 64508 |  | COMMENCEMENT PENDING |  | FLAT 48 | Johnson Drive | Birmingham |  | B35 6DS |  | Mr PA Patrick | 0795 791 2074 | 07932546499 | papatrick2012@hotmail.co.uk |  | Windows & Doors
12 |  | 70511 |  | COMMENCEMENT PENDING |  | FLAT 5 | Johnson Drive | Birmingham |  | B35 6DS |  | Miss A Pinney-Smith |  |  | Anneikasmith@hotmail.co.uk |  | Windows & Doors
12 |  | 57081 |  | COMMENCEMENT PENDING |  | FLAT 50 | Johnson Drive | Birmingham |  | B35 6DS |  | Mr D Haden | 0121 749 2197 |  |  |  | Windows & Doors
12 |  | 67776 |  | COMMENCEMENT PENDING |  | FLAT 52 | Johnson Drive | Birmingham |  | B35 6DS |  | Miss Z Burke |  | 07493539091 |  |  | Windows & Doors
12 |  | 56070 |  | COMMENCEMENT PENDING |  | FLAT 54 | Johnson Drive | Birmingham |  | B35 6DS |  | Mr A Callender | 0121 748 1457 |  |  |  | Windows & Doors
12 |  | 69721 |  | COMMENCEMENT PENDING |  | FLAT 56 | Johnson Drive | Birmingham |  | B35 6DS |  | Miss A Kousar |  | 07563005972 |  |  | Windows & Doors
12 |  | 70710 |  | COMMENCEMENT PENDING |  | FLAT 58 | Johnson Drive | Birmingham |  | B35 6DS |  | Miss C Boocock | 07936475190 |  | julierosina@yahoo.co.uk |  | Windows & Doors
12 |  | 56051 |  | COMMENCEMENT PENDING |  | FLAT 6 | Johnson Drive | Birmingham |  | B35 6DS |  | Mr A Micklewright |  | 07549317365 |  |  | Windows & Doors
12 |  | 56052 |  | COMMENCEMENT PENDING |  | FLAT 7 | Johnson Drive | Birmingham |  | B35 6DS |  | Mr P Strong |  | 01217476147 | paulstrong.cv1@outlook.com |  | Windows & Doors
12 |  | 62054 |  | COMMENCEMENT PENDING |  | FLAT 8 | Johnson Drive | Birmingham |  | B35 6DS |  | Ms M L Beattie | 01217471610 | 07387202122 |  |  | Windows & Doors
12 |  | 70288 |  | COMMENCEMENT PENDING | SEE COMMENTS | FLAT 30 | Kemble Drive | Birmingham |  | B35 6QS |  | Mr L Stokes | 07554843963 NIS | 07359680237 NIS |  |  | Windows & Doors | P Beahan |  |  |  | 2 | TS-04/04/24 Text sent for 18/04/24. TS-09/04/24 Called both numbers are NIS - ltr sent. TS-19/04/24 No access for 18/04/24 carded @ 11.05am. TS-03/05/24 Text sent for 14/05/24. TS-07/05/24 Ltr sent for 14/05/24. 08/05 SMS called neither mobile number is in service.17/6; AC chased survey. 1/7; PB sent through his survey lidt and this is no access on 14/5/2024, 9.35am. Paul advises trade access button no working. Both numbers are incorrect and no access therefore to leave a card. | [28 empty] | Access Via 28 Kemble & 2 Mere Avenue
12 |  | 68869 |  | COMMENCEMENT PENDING |  | FLAT 34 | Kenrick Croft | Birmingham |  | B35 7DF |  | Ms J Strain |  | 07913914744 | juju642000@hotmail.com |  | Windows & Doors
12 |  | 68814 |  | COMMENCEMENT PENDING |  | 57 | Kenrick Croft | Birmingham |  | B35 7DJ |  | Miss K J Weaver | 07460116000 |  | katyweaver17@hotmail.com |  | Windows & Doors
12 |  | 70687 |  | COMMENCEMENT PENDING |  | 65 | Kenrick Croft | Birmingham |  | B35 7DJ |  | Miss E Hewes |  | 07368 914 686 | erinhewes02@gmail.com |  | Windows & Doors
12 |  | 65618 |  | COMMENCEMENT PENDING |  | 44 | Kenrick Croft | Birmingham |  | B35 7DL |  | Mrs W Ling |  | 07835541918 |  |  | Windows & Doors
12 |  | 63334 |  | COMMENCEMENT PENDING |  | 50 | Kenrick Croft | Birmingham |  | B35 7DL |  | Miss D M Cridge |  | 07856653106 |  |  | Windows & Doors
12 |  | 56099 |  | COMMENCEMENT PENDING |  | 54 | Kenrick Croft | Birmingham |  | B35 7DL |  | Mrs V Kennedy | 0121 748 3892 | 07870369496 |  |  | Windows & Doors
12 |  | 56102 |  | COMMENCEMENT PENDING |  | 58 | Kenrick Croft | Birmingham |  | B35 7DL |  | Miss S Walker |  | 07870528259 |  |  | Windows & Doors
12 |  | 56087 |  | COMMENCEMENT PENDING |  | 27 | Kenrick Croft | Birmingham |  | B35 7DN |  | Mrs I A Clynch |  | 07765072781 |  |  | Windows & Doors
12 |  | 68540 |  | COMMENCEMENT PENDING |  | FLAT 11 | Kenrick Croft | Birmingham |  | B35 7DN |  | Miss N Owens |  | 07394459568 |  |  | Windows & Doors
12 |  | 68846 |  | COMMENCEMENT PENDING |  | FLAT 15 | Kenrick Croft | Birmingham |  | B35 7DN |  | Miss D Bartlam | 07776822064 |  | demmiie32@gmail.com |  | Windows & Doors
12 |  | 70194 |  | COMMENCEMENT PENDING |  | FLAT 17 | Kenrick Croft | Birmingham |  | B35 7DN |  | Miss C Cleaver |  | 07340613024 |  |  | Windows & Doors
12 |  | 56081 |  | COMMENCEMENT PENDING |  | FLAT 19 | Kenrick Croft | Birmingham |  | B35 7DN |  | Mrs M Whitehouse | 01217470842 |  | holtham217@hotmail.co.uk |  | Windows & Doors
12 |  | 56082 |  | COMMENCEMENT PENDING |  | FLAT 21 | Kenrick Croft | Birmingham |  | B35 7DN |  | Miss E Forbes |  | 07950 282 707 |  |  | Windows & Doors
12 |  | 67073 |  | COMMENCEMENT PENDING |  | FLAT 23 | Kenrick Croft | Birmingham |  | B35 7DN |  | Miss E Wells | 01212944676 | 07843 988 959 | EmmaWells1988@gmail.com |  | Windows & Doors
12 |  | 65912 |  | COMMENCEMENT PENDING |  | FLAT 7 | Kenrick Croft | Birmingham |  | B35 7DN |  | Ms P W Avon |  | 077046 14259 |  |  | Windows & Doors
12 |  | 70751 |  | COMMENCEMENT PENDING |  | FLAT 9 | Kenrick Croft | Birmingham |  | B35 7DN |  | Mrs H Bell |  | 07808850639 | hmolyneux@rocketmail.com |  | Windows & Doors
12 |  | 56083 |  | COMMENCEMENT PENDING |  | 22 | Kenrick Croft | Birmingham |  | B35 7DP |  | Mrs M Kavanagh |  | 07980 488005 |  |  | Windows & Doors
12 |  | 69283 |  | COMMENCEMENT PENDING |  | FLAT 12 | Kenrick Croft | Birmingham |  | B35 7DP |  | Ms P Y Smith | 01216490446 | 07496176210 |  |  | Windows & Doors
12 |  | 56076 |  | COMMENCEMENT PENDING |  | FLAT 14 | Kenrick Croft | Birmingham |  | B35 7DP |  | Mr G Jesson | 01217495697 | 07771952042 |  |  | Windows & Doors
12 |  | 56078 |  | COMMENCEMENT PENDING |  | FLAT 16 | Kenrick Croft | Birmingham |  | B35 7DP |  | Mrs J Hayes |  | 07708467135 |  |  | Windows & Doors
12 |  | 56080 |  | COMMENCEMENT PENDING |  | FLAT 18 | Kenrick Croft | Birmingham |  | B35 7DP |  | Mr A Smith |  | 07496303386 |  |  | Windows & Doors
12 |  | 68716 |  | COMMENCEMENT PENDING |  | FLAT 26 | Kenrick Croft | Birmingham |  | B35 7DP |  | Miss R Palmer | 07462125061 | 07462125061 |  |  | Windows & Doors
12 |  | 67130 |  | COMMENCEMENT PENDING |  | FLAT 28 | Kenrick Croft | Birmingham |  | B35 7DP |  | Miss F Watson |  | 07796 484 108 |  |  | Windows & Doors
12 |  | 70496 |  | COMMENCEMENT PENDING |  | FLAT 30 | Kenrick Croft | Birmingham |  | B35 7DP |  | Miss L Fogg |  | 07935 545646 |  |  | Windows & Doors
12 |  | 68513 |  | COMMENCEMENT PENDING |  | FLAT 32 | Kenrick Croft | Birmingham |  | B35 7DP |  | Mrs S E Alexander |  | 07957294770 | sophie.Alexander@live.co.uk |  | Windows & Doors
12 |  | 66036 |  | COMMENCEMENT PENDING |  | FLAT 36 | Kenrick Croft | Birmingham |  | B35 7DP |  | Mrs E Berhane | 07944 590314 | 07944590314 |  |  | Windows & Doors
12 |  | 69425 |  | COMMENCEMENT PENDING |  | FLAT 38 | Kenrick Croft | Birmingham |  | B35 7DP |  | Mrs V Baynham-Eyles |  | 07710658017 | vix5@hotmail.co.uk |  | Windows & Doors
12 |  | 66208 |  | COMMENCEMENT PENDING |  | FLAT 40 | Kenrick Croft | Birmingham |  | B35 7DP |  | Mrs S Rana-Sommerville | 07813158454 |  | sonalrana@live.co.uk |  | Windows & Doors
12 |  | 64121 |  | COMMENCEMENT PENDING |  | FLAT 42 | Kenrick Croft | Birmingham |  | B35 7DP |  | Miss K Edwards |  | 07835156352 |  |  | Windows & Doors
12 |  | 68311 |  | COMMENCEMENT PENDING |  | 4 | Lambourn Road | Birmingham |  | B23 6HN |  | Mrs KG Vernalls |  | 07967 337952 | karenrava@hotmail.com |  | Windows & Doors
12 |  | 59803 |  | COMMENCEMENT PENDING |  | 1 | Lancaster Drive | Birmingham |  | B35 7JX |  | Miss S Davis | 0121 747 3699 | 07387566044 |  |  | Windows & Doors
12 |  | 59804 |  | COMMENCEMENT PENDING |  | 2 | Lancaster Drive | Birmingham |  | B35 7JX |  | Mrs J Keily | 0773 199 5170 | 07809 384 970 |  |  | Windows & Doors
12 |  | 64910 |  | COMMENCEMENT PENDING |  | 3 | Lancaster Drive | Birmingham |  | B35 7JX |  | Miss C L Woolgrove |  | 07530 798 977 | clairewoolgrove@hotmail.co.uk |  | Windows & Doors
12 |  | 59806 |  | COMMENCEMENT PENDING |  | 4 | Lancaster Drive | Birmingham |  | B35 7JX |  | Miss P O'neill | 07306 026 080 |  |  |  | Windows & Doors
12 |  | 59807 |  | COMMENCEMENT PENDING |  | 5 | Lancaster Drive | Birmingham |  | B35 7JX |  | Mrs J Roche |  | 07735 310229 | janerch17@googlemail.com |  | Windows & Doors
12 |  | 65361 |  | COMMENCEMENT PENDING |  | 6 | Lancaster Drive | Birmingham |  | B35 7JX |  | Mrs Y O'Reilly-Hewings |  | 07800 929 116 |  |  | Windows & Doors
12 |  | 59809 |  | COMMENCEMENT PENDING | DOOR CHOICE | 7 | Lancaster Drive | Birmingham |  | B35 7JX |  | Mrs T Cooper |  | 07712474770 |  |  | Windows & Doors | [5 empty] | TS-17/04/24 Door choice received THIRSK in BLACK.
12 |  | 59810 |  | COMMENCEMENT PENDING |  | 8 | Lancaster Drive | Birmingham |  | B35 7JX |  | Miss S Westwood | 07565878208 |  |  |  | Windows & Doors
12 |  | 61753 |  | COMMENCEMENT PENDING |  | 9 | Lancaster Drive | Birmingham |  | B35 7JX |  | Miss L A Wood |  | 07368534596 | lynne562015@outlook.com |  | Windows & Doors
12 |  | 68217 |  | COMMENCEMENT PENDING |  | 10 | Lancaster Drive | Birmingham |  | B35 7JX |  | Ms H McCormack |  | 07414167153 |  |  | Windows & Doors
12 |  | 64038 |  | COMMENCEMENT PENDING |  | 11 | Lancaster Drive | Birmingham |  | B35 7JX |  | Miss M Bibb |  | 07563902293 | shellbibb@gmail.com |  | Windows & Doors
12 |  | 68491 |  | COMMENCEMENT PENDING |  | 12 | Lancaster Drive | Birmingham |  | B35 7JX |  | Miss K Ravenhill |  | 07746228073 |  |  | Windows & Doors
12 |  | 59815 |  | COMMENCEMENT PENDING |  | 14 | Lancaster Drive | Birmingham |  | B35 7JX |  | Miss L Reilly | 01217497210 | 07511022992 | lall@fsmail.net |  | Windows & Doors
12 |  | 59816 |  | COMMENCEMENT PENDING |  | 15 | Lancaster Drive | Birmingham |  | B35 7JX |  | Mr P Williams | 07869467992 | 07869 467 992 |  |  | Windows & Doors
12 |  | 69427 |  | COMMENCEMENT PENDING |  | 16 | Lancaster Drive | Birmingham |  | B35 7JX |  | Miss R Woodcock | 07889611988 |  | rachelellious@gmail.com |  | Windows & Doors
12 |  | 64509 |  | COMMENCEMENT PENDING |  | 17 | Lancaster Drive | Birmingham |  | B35 7JX |  | Mr N J Booth | 0121 649 7982 | 07492364708 |  |  | Windows & Doors
12 |  | 59820 |  | COMMENCEMENT PENDING |  | 19 | Lancaster Drive | Birmingham |  | B35 7JX |  | Mrs T Wilson | 01217302599 | 07549 621 497 | traceywilson1964@hotmail.com |  | Windows & Doors
12 |  | 59821 |  | COMMENCEMENT PENDING |  | 20 | Lancaster Drive | Birmingham |  | B35 7JX |  | Miss T Thompson | 07925 818 399 |  |  |  | Windows & Doors
12 |  | 63396 |  | COMMENCEMENT PENDING |  | 22 | Lancaster Drive | Birmingham |  | B35 7JX |  | Miss M Olner | 07872351563 |  |  |  | Windows & Doors
12 |  | 64985 |  | COMMENCEMENT PENDING |  | 24 | Lancaster Drive | Birmingham |  | B35 7JX |  | Miss K Rees | 07484656058 |  |  |  | Windows & Doors
12 |  | 70652 |  | COMMENCEMENT PENDING |  | 25 | Lancaster Drive | Birmingham |  | B35 7JX |  | Mr RD Francis |  | 07852446954 | pololoco@live.co.uk |  | Windows & Doors
12 |  | 61626 |  | COMMENCEMENT PENDING |  | 26 | Lancaster Drive | Birmingham |  | B35 7JX |  | Mrs DAC Lanchester | 01217471383 |  | cluleydonna@gmail.com |  | Windows & Doors
12 |  | 68780 |  | COMMENCEMENT PENDING |  | 27 | Lancaster Drive | Birmingham |  | B35 7JX |  | Mrs T Hopkins |  | 07796 712 482 | seanleighoethan@gmail.com |  | Windows & Doors
12 |  | 69776 |  | COMMENCEMENT PENDING |  | 2 | Locking Croft | Birmingham |  | B35 7LB |  | Miss I Morris |  | 07534314829 |  |  | Windows & Doors
12 |  | 59830 |  | COMMENCEMENT PENDING |  | 4 | Locking Croft | Birmingham |  | B35 7LB |  | Miss V Taylor |  | 07876 073 756 |  |  | Windows & Doors
12 |  | 68523 |  | COMMENCEMENT PENDING |  | 6 | Locking Croft | Birmingham |  | B35 7LB |  | Miss G Haslam |  | 07824883009 |  |  | Windows & Doors
12 |  | 59832 |  | COMMENCEMENT PENDING |  | 8 | Locking Croft | Birmingham |  | B35 7LB |  | Miss L Bartlam |  | 07899279603 |  |  | Windows & Doors
12 |  | 59833 |  | COMMENCEMENT PENDING |  | 10 | Locking Croft | Birmingham |  | B35 7LB |  | Miss S Bartlam |  | 07534630058 |  |  | Windows & Doors
12 |  | 64854 |  | COMMENCEMENT PENDING |  | 12 | Locking Croft | Birmingham |  | B35 7LB |  | Mr EC Lemon |  | 07426 860001 | elemon2011@gmail.com |  | Windows & Doors
12 |  | 59835 |  | COMMENCEMENT PENDING |  | 14 | Locking Croft | Birmingham |  | B35 7LB |  | Miss L Taylor | 0121 218 9007 | 07368319015 |  |  | Windows & Doors
12 |  | 64068 |  | COMMENCEMENT PENDING |  | 16 | Locking Croft | Birmingham |  | B35 7LB |  | Miss S M Griffin | 07479635681 |  | soniagriffin06@gmail.com |  | Windows & Doors
12 |  | 63405 |  | COMMENCEMENT PENDING |  | 18 | Locking Croft | Birmingham |  | B35 7LB |  | Miss T Wilkes |  | 07763 051874 |  |  | Windows & Doors
12 |  | 59838 |  | COMMENCEMENT PENDING |  | 40 | Locking Croft | Birmingham |  | B35 7LB |  | Mrs K Woods |  | 07549956968 | kimbarmer@hotmail.com |  | Windows & Doors
12 |  | 56113 |  | COMMENCEMENT PENDING |  | 56 | Locking Croft | Birmingham |  | B35 7LB |  | Mrs D Stoddart | 0121 748 4672 | 07908848018 |  |  | Windows & Doors
12 |  | 69359 |  | COMMENCEMENT PENDING |  | 62 | Locking Croft | Birmingham |  | B35 7LB |  | Miss SA Barnes | 0121 748 2796 |  | sallyannbarnes86@live.co.uk |  | Windows & Doors
12 |  | 62416 |  | COMMENCEMENT PENDING |  | 66 | Locking Croft | Birmingham |  | B35 7LB |  | Ms N Mahmoodi |  | 07976 963150 | lilispring2001@yahoo.co.uk |  | Windows & Doors
12 |  | 70708 |  | COMMENCEMENT PENDING |  | 68 | Locking Croft | Birmingham |  | B35 7LB |  | Miss T Phillips |  | 07718613149 | xtoniiadelex@hotmail.co.uk |  | Windows & Doors
12 |  | 69854 |  | COMMENCEMENT PENDING |  | 84 | Locking Croft | Birmingham |  | B35 7LB |  | Mr D Butlin |  | 07711261115 |  |  | Windows & Doors
12 |  | 69997 |  | COMMENCEMENT PENDING |  | 86 | Locking Croft | Birmingham |  | B35 7LB |  | Miss Z Bickerstaff | 07510 757 069 |  | ZENA-B@HOTMAIL.CO.UK |  | Windows & Doors
12 |  | 62857 |  | COMMENCEMENT PENDING |  | 88 | Locking Croft | Birmingham |  | B35 7LB |  | Mrs J Pease |  | 07977 057 176 |  |  | Windows & Doors
12 |  | 70705 |  | COMMENCEMENT PENDING |  | 90 | Locking Croft | Birmingham |  | B35 7LB |  | Miss K Proctor |  | 07368990900 | kayleighproctor94@outlook.com |  | Windows & Doors
12 |  | 70061 |  | COMMENCEMENT PENDING |  | 92 | Locking Croft | Birmingham |  | B35 7LB |  | Miss C Kelly |  | 07377418746 |  |  | Windows & Doors
12 |  | 67994 |  | COMMENCEMENT PENDING |  | 94 | Locking Croft | Birmingham |  | B35 7LB |  | Miss L Semper |  | 07852 570 321 |  |  | Windows & Doors
12 |  | 69249 |  | COMMENCEMENT PENDING |  | 96 | Locking Croft | Birmingham |  | B35 7LB |  | Mrs S Alaloush |  | 07727 746655 | sosoalloush12@gmail.com |  | Windows & Doors
12 |  | 68778 |  | COMMENCEMENT PENDING |  | 98 | Locking Croft | Birmingham |  | B35 7LB |  | Mr W Doherty | 0775769962 |  |  |  | Windows & Doors
12 |  | 59843 |  | COMMENCEMENT PENDING |  | 120 | Locking Croft | Birmingham |  | B35 7LB |  | Mrs B Judd |  |  | BridgetJudd@hotmail.com |  | Windows & Doors
12 |  | 62988 |  | COMMENCEMENT PENDING |  | 1 | Locking Croft | Birmingham |  | B35 7LD |  | Mrs N Broderick | 07599936661 | 07527042268 |  |  | Windows & Doors
12 |  | 56105 |  | COMMENCEMENT PENDING |  | 3 | Locking Croft | Birmingham |  | B35 7LD |  | Miss J Hobbis | 07368289192 | 07368289192 | amccrea83@outlook.com |  | Windows & Doors
12 |  | 56106 |  | COMMENCEMENT PENDING |  | 9 | Locking Croft | Birmingham |  | B35 7LD |  | Mr R Key |  | 07392 625156 |  |  | Windows & Doors
12 |  | 68078 |  | COMMENCEMENT PENDING |  | 15 | Locking Croft | Birmingham |  | B35 7LD |  | Mr JP Brady |  | 07930 438582 |  |  | Windows & Doors
12 |  | 56108 |  | COMMENCEMENT PENDING |  | 17 | Locking Croft | Birmingham |  | B35 7LD |  | Mr J Newton | 01217481417 | 07951550515 | john.newton17@talktalk.net |  | Windows & Doors
12 |  | 67896 |  | COMMENCEMENT PENDING |  | 19 | Locking Croft | Birmingham |  | B35 7LD |  | Miss C McLeod |  | 07936492545 | mcleodcarlina4@gmail.com |  | Windows & Doors
12 |  | 70399 |  | COMMENCEMENT PENDING |  | 21 | Locking Croft | Birmingham |  | B35 7LD |  | Miss S Jackson |  | 07732408623 |  |  | Windows & Doors
12 |  | 62821 |  | COMMENCEMENT PENDING |  | 31 | Locking Croft | Birmingham |  | B35 7LD |  | Mr B Phillis |  | 07949277121 |  |  | Windows & Doors
12 |  | 56121 |  | COMMENCEMENT PENDING |  | 106 | Locking Croft | Birmingham |  | B35 7LE |  | Mrs J Liveley |  | 07702 214526 | enuj@talktalk.net |  | Windows & Doors
12 |  | 56123 |  | COMMENCEMENT PENDING |  | 114 | Locking Croft | Birmingham |  | B35 7LE |  | Mr J Bent |  |  |  |  | Windows & Doors
12 |  | 59842 |  | COMMENCEMENT PENDING |  | 118 | Locking Croft | Birmingham |  | B35 7LE |  | Mr B Bagshaw | 01217473926 |  | karenb118@btinternet.com |  | Windows & Doors
12 |  | 59844 |  | COMMENCEMENT PENDING |  | 122 | Locking Croft | Birmingham |  | B35 7LE |  | Mr K Woolgrove | 01217476727 |  |  |  | Windows & Doors
12 |  | 58159 |  | COMMENCEMENT PENDING |  | FLAT 1 Block 100 | Locking Croft | Castle Vale |  | B35 7LE |  | Mr B Taverner | 0121 748 3388 |  | briantaverner@talktalk.net |  | Windows & Doors
12 |  | 67907 |  | COMMENCEMENT PENDING |  | FLAT 1 Block 102 | Locking Croft | Castle Vale |  | B35 7LE |  | Mrs M Middleham |  | 0121 747 2932 |  |  | Windows & Doors
12 |  | 67868 |  | COMMENCEMENT PENDING |  | FLAT 1 Block 104 | Locking Croft | Castle Vale |  | B35 7LE |  | Miss C Walsh |  | 07706 754 485 | louisewalsh698@gmail.com |  | Windows & Doors
12 |  | 62921 |  | COMMENCEMENT PENDING |  | FLAT 2 Block 100 | Locking Croft | Castle Vale |  | B35 7LE |  | Mr I J Geddes |  | 07979774328 | IANGEDDES2@LIVE.COM |  | Windows & Doors
12 |  | 70495 |  | COMMENCEMENT PENDING |  | FLAT 2 Block 102 | Locking Croft | Castle Vale |  | B35 7LE |  | Miss DM Lynch |  | 07544102811 | danielelynchdandan1@hotmail.com |  | Windows & Doors
12 |  | 63210 |  | COMMENCEMENT PENDING |  | FLAT 2 Block 104 | Locking Croft | Castle Vale |  | B35 7LE |  | Mr W Cole |  | 07903 526123 | willhelmslack@hotmail.co.uk |  | Windows & Doors
12 |  | 70190 |  | COMMENCEMENT PENDING |  | FLAT 3 Block 100 | Locking Croft | Castle Vale |  | B35 7LE |  | Ms V Flaherty |  | 07738418031 | flahertyviv20@gmail.com |  | Windows & Doors
12 |  | 69126 |  | COMMENCEMENT PENDING |  | FLAT 3 Block 102 | Locking Croft | Castle Vale |  | B35 7LE |  | Miss A Edge |  | 07958 000 262 | alixdedge1234567@gmail.com |  | Windows & Doors
12 |  | 69972 |  | COMMENCEMENT PENDING |  | FLAT 3 Block 104 | Locking Croft | Castle Vale |  | B35 7LE |  | Mr K Hewings | 07970864544 | 07817181780 |  |  | Windows & Doors
12 |  | 56128 |  | COMMENCEMENT PENDING |  | FLAT 4 Block 100 | Locking Croft | Castle Vale |  | B35 7LE |  | Mrs P Moseley | 0121 748 4005 | (07981) 642 873 | Pauline.stan129@btinternet.com |  | Windows & Doors
12 |  | 64398 |  | COMMENCEMENT PENDING |  | FLAT 4 Block 102 | Locking Croft | Castle Vale |  | B35 7LE |  | Mr M Doherty | 07752719086 | 07563 194483 |  |  | Windows & Doors
12 |  | 56140 |  | COMMENCEMENT PENDING |  | FLAT 4 Block 104 | Locking Croft | Castle Vale |  | B35 7LE |  | Mr J Johnson |  | 07935 069 742 |  |  | Windows & Doors
12 |  | 69300 |  | COMMENCEMENT PENDING |  | FLAT 5 Block 100 | Locking Croft | Castle Vale |  | B35 7LE |  | Miss S Rudman |  | 07360174372 | scarlettrudman@gmail.com |  | Windows & Doors
12 |  | 64706 |  | COMMENCEMENT PENDING |  | FLAT 5 Block 102 | Locking Croft | Castle Vale |  | B35 7LE |  | Mrs GS Moopowe |  | (07488) 259 068 |  |  | Windows & Doors
12 |  | 66762 |  | COMMENCEMENT PENDING |  | FLAT 5 Block 104 | Locking Croft | Castle Vale |  | B35 7LE |  | Miss P Cooke | 07548 150895 |  |  |  | Windows & Doors
12 |  | 70197 |  | COMMENCEMENT PENDING |  | FLAT 6 Block 100 | Locking Croft | Castle Vale |  | B35 7LE |  | Miss L Patience |  | 07455667444 | leniece1@hotmail.co.uk |  | Windows & Doors
12 |  | 66262 |  | COMMENCEMENT PENDING |  | FLAT 6 Block 104 | Locking Croft | Castle Vale |  | B35 7LE |  | Miss S Bartlam | 07770 909 441 | 07826064848 | shanbart92@googlemail.com |  | Windows & Doors
12 |  | 70284 |  | COMMENCEMENT PENDING |  | 15 | Longclose Walk | Birmingham |  | B35 7LP |  | Mrs C Flatley |  |  | cutie31@live.co.uk |  | Windows & Doors
12 |  | 56143 |  | COMMENCEMENT PENDING |  | 2 | Longcroft Close | Birmingham |  | B35 7QS |  | Mr M Shwalbe |  | 07826 107 185 |  |  | Windows & Doors
12 |  | 56144 |  | COMMENCEMENT PENDING |  | 4 | Longcroft Close | Birmingham |  | B35 7QS |  | Miss T Hobbs | 0121 776 7494 | 07766392422 |  |  | Windows & Doors
12 |  | 68639 |  | COMMENCEMENT PENDING |  | FLAT 26 | Luce Close | Birmingham |  | B35 6PJ |  | Miss S Horsfall |  | 07739971248 | sianhorsfall@hotmail.co.uk |  | Windows & Doors
12 |  | 67996 |  | COMMENCEMENT PENDING |  | 1 | Lyneham Way | Birmingham |  | B35 6DJ |  | Miss N Clegg |  | 07526663425 | nyshaclegg@hotmail.com |  | Windows & Doors
12 |  | 68494 |  | COMMENCEMENT PENDING |  | 3 | Lyneham Way | Birmingham |  | B35 6DJ |  | Miss J Gameson | 07704525066 | 07704525066 |  |  | Windows & Doors
12 |  | 66791 |  | COMMENCEMENT PENDING |  | 8 | Lyneham Way | Birmingham |  | B35 6DJ |  | Mrs R Amani Dunia |  |  |  |  | Windows & Doors
12 |  | 65417 |  | COMMENCEMENT PENDING |  | 9 | Lyneham Way | Birmingham |  | B35 6DJ |  | Mrs S Ashton |  | 07753 408 066 | shaz1danks@hotmail.co.uk |  | Windows & Doors
12 |  | 56159 |  | COMMENCEMENT PENDING |  | 18 | Lyneham Way | Birmingham |  | B35 6DJ |  | Miss K Buttery |  | 07792168594 |  |  | Windows & Doors
12 |  | 56160 |  | COMMENCEMENT PENDING |  | 20 | Lyneham Way | Birmingham |  | B35 6DJ |  | Miss H Greenshields |  |  |  |  | Windows & Doors
12 |  | 62353 |  | COMMENCEMENT PENDING |  | 24 | Lyneham Way | Birmingham |  | B35 6DJ |  | Miss S Lavill | 01217471140 | 07967308841 |  |  | Windows & Doors
12 |  | 69404 |  | COMMENCEMENT PENDING |  | 3 | Lysander Way | Birmingham |  | B35 7JY |  | Ms C Brown |  | 07486047902 | 00clare@gmail.com |  | Windows & Doors | M Turpin | 2024-07-30 | 8am to 2pm |  | 2 | TS-19/04/24 Text sent for 30/04/24. TS-22/04/24 Survey CONFIRMED for 30/04/24. TS-30/04/24 Tenant text in they are no longer available today.13/06 SMS text sent for 26/06. 19/06 SMS called N/A Lttr sent. 26/6/2024; NO ACCESS, CARDED. 3/7; AC advised client and reallocated to 30/7 requesting their assistance.
12 |  | 70789 |  | COMMENCEMENT PENDING |  | 7 | Manby Road | Birmingham |  | B35 6HE |  | Miss L Robinson | 07496201987 | 07496201987 |  |  | Windows & Doors
12 |  | 56163 |  | COMMENCEMENT PENDING |  | 9 | Manby Road | Birmingham |  | B35 6HE |  | Mr J Fairgrieve |  | 747 8116 | jim@switchradio.co.uk |  | Windows & Doors
12 |  | 56164 |  | COMMENCEMENT PENDING |  | 11 | Manby Road | Birmingham |  | B35 6HE |  | Mr R Averill | 0121 747 6498 | 07947 597 126 |  |  | Windows & Doors
12 |  | 64697 |  | COMMENCEMENT PENDING |  | 17 | Manby Road | Birmingham |  | B35 6HG |  | Miss N Stone |  | 07719 835 834 |  |  | Windows & Doors
12 |  | 56165 |  | COMMENCEMENT PENDING |  | 31 | Manby Road | Birmingham |  | B35 6HG |  | Mrs J Ricketts |  |  |  |  | Windows & Doors
12 |  | 64857 |  | COMMENCEMENT PENDING |  | 45 | Manby Road | Birmingham |  | B35 6HH |  | Miss D McQueen |  | 07792 498733 |  |  | Windows & Doors
12 |  | 62995 |  | COMMENCEMENT PENDING |  | 51 | Manby Road | Birmingham |  | B35 6HH |  | Mr J Perry | 07729 628 717 | 07729 62 87 17 |  |  | Windows & Doors
12 |  | 64034 |  | COMMENCEMENT PENDING |  | 53 | Manby Road | Birmingham |  | B35 6HH |  | Miss K Nagra |  | 07496 421 523 |  |  | Windows & Doors
12 |  | 68549 |  | COMMENCEMENT PENDING |  | 55 | Manby Road | Birmingham |  | B35 6HH |  | Miss J Mccann |  | 07398468695 |  |  | Windows & Doors
12 |  | 63588 |  | COMMENCEMENT PENDING |  | 57 | Manby Road | Birmingham |  | B35 6HH |  | Miss D S Yap |  | 07861910388 |  |  | Windows & Doors
12 |  | 61434 |  | COMMENCEMENT PENDING |  | 51A | Manby Road | Birmingham |  | B35 6HH |  | Mr M Billingham |  | 07544 047 589 |  |  | Windows & Doors
12 |  | 65499 |  | COMMENCEMENT PENDING |  | 53A | Manby Road | Birmingham |  | B35 6HH |  | Mr KS Sullivan |  | 07429590109 |  |  | Windows & Doors
12 |  | 69331 |  | COMMENCEMENT PENDING |  | 59 | Manby Road | Birmingham |  | B35 6HJ |  | Mr L Bayo |  | 07404530679 | ibroadma63@gmail.com |  | Windows & Doors
12 |  | 56167 |  | COMMENCEMENT PENDING |  | 61 | Manby Road | Birmingham |  | B35 6HJ |  | Mrs C Hodson | 01217492922 | 07989 362 133 |  |  | Windows & Doors
12 |  | 56169 |  | COMMENCEMENT PENDING |  | 69 | Manby Road | Birmingham |  | B35 6HJ |  | Miss J Lawry | 0121 749 4295 |  |  |  | Windows & Doors
12 |  | 61833 |  | COMMENCEMENT PENDING |  | 73 | Manby Road | Birmingham |  | B35 6HJ |  | Mrs A Hicklin |  | 07929353858 |  |  | Windows & Doors
12 |  | 70017 |  | COMMENCEMENT PENDING |  | 115 | Manby Road | Birmingham |  | B35 6HP |  | Mrs JD Reid |  | 07528846789 |  |  | Windows & Doors
12 |  | 70263 |  | COMMENCEMENT PENDING |  | 15 | Martlesham Square | Birmingham |  | B35 6BE |  | Miss N Downey |  | 07944983489 | natalied91@hotmail.com |  | Windows & Doors
12 |  | 61763 |  | COMMENCEMENT PENDING |  | 17 | Martlesham Square | Birmingham |  | B35 6BE |  | Miss L Darby | 07788451408 | 0121 747 3111 |  |  | Windows & Doors
12 |  | 70012 |  | COMMENCEMENT PENDING |  | FLAT 5 | Martlesham Square | Birmingham |  | B35 6BE |  | Miss A Verikaite |  |  | arma971716814@gmail.com |  | Windows & Doors
12 |  | 56189 |  | COMMENCEMENT PENDING |  | 14 | Melksham Square | Birmingham |  | B35 6BY |  | Mrs I Thomas |  | 07859 00 65 85 |  |  | Windows & Doors
12 |  | 70508 |  | COMMENCEMENT PENDING |  | 15 | Melksham Square | Birmingham |  | B35 6BY |  | Miss S- Cramman |  | 07365622072 | salliejo96@gmail.com |  | Windows & Doors
12 |  | 58655 |  | COMMENCEMENT PENDING |  | 22 | Melksham Square | Birmingham |  | B35 6BY |  | Mr S Oldbury | 01217486044 |  |  |  | Windows & Doors
12 |  | 57943 |  | COMMENCEMENT PENDING |  | 26 | Melksham Square | Birmingham |  | B35 6BY |  | Ms J Stroud |  | 07749465197 |  |  | Windows & Doors
12 |  | 63514 |  | COMMENCEMENT PENDING |  | 32 | Melksham Square | Birmingham |  | B35 6BY |  | Miss R Wall | 0121 471 4004 | 07824676346 | beckywall123@hotmail.co.uk |  | Windows & Doors
12 |  | 62837 |  | COMMENCEMENT PENDING |  | 36 | Melksham Square | Birmingham |  | B35 6BY |  | Miss J Dookie |  | 07463 822 618 | jenevedookie@hotmail.com |  | Windows & Doors
12 |  | 63751 |  | COMMENCEMENT PENDING |  | 38 | Melksham Square | Birmingham |  | B35 6BY |  | Miss D Archer |  | 07375379357 |  |  | Windows & Doors
12 |  | 67968 |  | COMMENCEMENT PENDING |  | 7 | Montrose Drive | Birmingham |  | B35 6DH |  | Ms G Kavanagh | 07496163811 | 07432844536 | gemmakavanagh11@gmail.com |  | Windows & Doors | M Turpin | Wants summer hols |  |  |  | 10/06 SMS text sent for 12/06. Declined.
12 |  | 68701 |  | COMMENCEMENT PENDING |  | 11 | Montrose Drive | Birmingham |  | B35 6DH |  | Ms R Carter | 07481614010 | 07481614010 |  |  | Windows & Doors | M Turpin |  |  |  |  | 10/06 SMS text sent for 12/06. Declined. 11/06 SMS text sent for 18/06. 13/06 SMS called N/A lttr sent. Tenant declined again.17/06 SMS tenant called to cancel
12 |  | 64050 |  | COMMENCEMENT PENDING |  | 1 | Morar Close | Birmingham |  | B35 7PE |  | Mrs L J Cotterill |  | 07982029804 | desmon.cotterill@sky.com |  | Windows & Doors
12 |  | 67107 |  | COMMENCEMENT PENDING |  | 19 | Morar Close | Birmingham |  | B35 7PE |  | Mrs J A Doherty |  | 07477 541 734 | jadoherty@live.co.uk |  | Windows & Doors
12 |  | 65497 |  | COMMENCEMENT PENDING |  | 21 | Morar Close | Birmingham |  | B35 7PE |  | Miss K Williams | 07795202928 |  | kim.me@hotmail.co.uk |  | Windows & Doors
12 |  | 66811 |  | COMMENCEMENT PENDING |  | 27 | Morar Close | Birmingham |  | B35 7PE |  | Miss A Beet |  | 07853025248 | amynicolabeet@hotmail.co.uk |  | Windows & Doors
12 |  | 56219 |  | COMMENCEMENT PENDING |  | 29 | Morar Close | Birmingham |  | B35 7PE |  | Mrs J Holness-Lyons |  |  |  |  | Windows & Doors
12 |  | 56224 |  | COMMENCEMENT PENDING |  | 35 | Morar Close | Birmingham |  | B35 7PE |  | Mr J Martin | 0121 749 4944 |  |  |  | Windows & Doors
12 |  | 58457 |  | COMMENCEMENT PENDING |  | 37 | Morar Close | Birmingham |  | B35 7PE |  | Miss N J Preston |  | 07590904398 |  |  | Windows & Doors
12 |  | 58707 |  | COMMENCEMENT PENDING |  | 45 | Morar Close | Birmingham |  | B35 7PE |  | Mrs K L Coombs |  | 07512837150 | kellycollins07@btinternet.com |  | Windows & Doors
12 |  | 69177 |  | COMMENCEMENT PENDING |  | 53 | Morar Close | Birmingham |  | B35 7PE |  | Mr J Mirga |  | 07590 188 201 | jacekmirga@interia.pl |  | Windows & Doors
12 |  | 56210 |  | COMMENCEMENT PENDING |  | 4 | Morar Close | Birmingham |  | B35 7PG |  | Mr R Hewitt | 0121 748 6383 | 077 35050048 |  |  | Windows & Doors
12 |  | 68359 |  | COMMENCEMENT PENDING |  | 14 | Morar Close | Birmingham |  | B35 7PG |  | Miss C Hill | 0121 649 8086 | 07480 670 727 |  |  | Windows & Doors
12 |  | 56214 |  | COMMENCEMENT PENDING |  | 16 | Morar Close | Birmingham |  | B35 7PG |  | Mrs M O'Connor |  |  |  |  | Windows & Doors
12 |  | 65142 |  | COMMENCEMENT PENDING |  | 22 | Morar Close | Birmingham |  | B35 7PG |  | Miss CJ Ancill |  | 07930162646 |  |  | Windows & Doors
12 |  | 56984 |  | COMMENCEMENT PENDING |  | 26 | Morar Close | Birmingham |  | B35 7PG |  | Mrs J Spalding | 07972602127 |  | jeanetteplading@aol.co.uk |  | Windows & Doors
12 |  | 56220 |  | COMMENCEMENT PENDING |  | 30 | Morar Close | Birmingham |  | B35 7PG |  | Miss M Beckett |  |  | MichelleBeckett071@gmail.com |  | Windows & Doors
12 |  | 56223 |  | COMMENCEMENT PENDING |  | 34 | Morar Close | Birmingham |  | B35 7PG |  | Mrs M Edmonds |  |  |  |  | Windows & Doors
12 |  | 58554 |  | COMMENCEMENT PENDING |  | 38 | Morar Close | Birmingham |  | B35 7PG |  | Mr D Wattis | 01217471340 | 07525 786 124 | sharronwattis@hotmail.com |  | Windows & Doors
12 |  | 62891 |  | COMMENCEMENT PENDING |  | 40 | Morar Close | Birmingham |  | B35 7PG |  | Miss S Haughton |  | 07307 598 219 | yungting@live.co.uk |  | Windows & Doors
12 |  | 56228 |  | COMMENCEMENT PENDING |  | 48 | Morar Close | Birmingham |  | B35 7PG |  | Mrs N Beet | 01217484136 |  | nicolabeet@hotmail.co.uk |  | Windows & Doors
12 |  | 56232 |  | COMMENCEMENT PENDING |  | 54 | Morar Close | Birmingham |  | B35 7PG |  | Mrs E Feix |  |  |  |  | Windows & Doors
12 |  | 65518 |  | COMMENCEMENT PENDING |  | 58 | Morar Close | Birmingham |  | B35 7PG |  | Mrs SG Morris | 07554160472 |  |  |  | Windows & Doors
12 |  | 70253 |  | COMMENCEMENT PENDING |  | 62 | Morar Close | Birmingham |  | B35 7PG |  | Miss R Kelly |  | 07908 626 120 | riak6@icloud.com |  | Windows & Doors
12 |  | 56237 |  | COMMENCEMENT PENDING |  | 64 | Morar Close | Birmingham |  | B35 7PG |  | Mr A Donovan |  | 07505093186 |  |  | Windows & Doors
12 |  | 56238 |  | COMMENCEMENT PENDING |  | 66 | Morar Close | Birmingham |  | B35 7PG |  | Mrs J Eamonson |  | 07891234284 |  |  | Windows & Doors
12 |  | 69881 |  | COMMENCEMENT PENDING |  | 72 | Morar Close | Birmingham |  | B35 7PG |  | Mr C Leonard |  | 07597290885 | craiglfc15@gmail.com |  | Windows & Doors
12 |  | 56242 |  | COMMENCEMENT PENDING |  | 3 | Neville Walk | Birmingham |  | B35 7JH |  | Miss S Rogers | 0121 747 1023 | 07762 314082 |  |  | Windows & Doors
12 |  | 59913 |  | COMMENCEMENT PENDING |  | 4 | Neville Walk | Birmingham |  | B35 7JH |  | Miss L Tilsley |  | 07894 063101 |  |  | Windows & Doors
12 |  | 67977 |  | COMMENCEMENT PENDING |  | 9 | Neville Walk | Birmingham |  | B35 7JH |  | Miss Z Robins | 07513 865874 |  |  |  | Windows & Doors
12 |  | 66000 |  | COMMENCEMENT PENDING |  | 11 | Neville Walk | Birmingham |  | B35 7JH |  | Mr M Owen |  | 07413633858 | owen1983@outlook.com |  | Windows & Doors
12 |  | 67735 |  | COMMENCEMENT PENDING |  | 25 | Neville Walk | Birmingham |  | B35 7JH |  | Miss S Swords |  | 07961 909909 |  |  | Windows & Doors
12 |  | 65987 |  | COMMENCEMENT PENDING |  | 2 | Neville Walk | Birmingham |  | B35 7JJ |  | Mrs A Jabbi | 07903005056 |  | adamagabbi@yahoo.com |  | Windows & Doors
12 |  | 58173 |  | COMMENCEMENT PENDING |  | 6 | Neville Walk | Birmingham |  | B35 7JJ |  | Mrs J Lucas |  | 07950866298 |  |  | Windows & Doors
12 |  | 59914 |  | COMMENCEMENT PENDING |  | 7 | Neville Walk | Birmingham |  | B35 7JJ |  | Miss S Sturch |  | 07717 579 462 |  |  | Windows & Doors
12 |  | 62060 |  | COMMENCEMENT PENDING |  | 27 | Neville Walk | Birmingham |  | B35 7JJ |  | Miss F Marshall |  | 07535 603 707 |  |  | Windows & Doors
12 |  | 69801 |  | COMMENCEMENT PENDING |  | 29 | Neville Walk | Birmingham |  | B35 7JJ |  | Miss J Hemming | 07786634546 | 07786634546 | jane.hemming@yahoo.com |  | Windows & Doors
12 |  | 69405 |  | COMMENCEMENT PENDING |  | 31 | Neville Walk | Birmingham |  | B35 7JJ |  | Mrs L Bruton |  | 07850960005 | lesley2011x@hotmail.co.uk |  | Windows & Doors
12 |  | 67914 |  | COMMENCEMENT PENDING |  | 33 | Neville Walk | Birmingham |  | B35 7JJ |  | Mr B Merc | 01217301442 | 07563 745319 | borismerc@btinternet.com |  | Windows & Doors
12 |  | 69338 |  | COMMENCEMENT PENDING |  | 35 | Neville Walk | Birmingham |  | B35 7JJ |  | Mr W Carter |  | 07849224623 |  |  | Windows & Doors
12 |  | 67687 |  | COMMENCEMENT PENDING |  | 37 | Neville Walk | Birmingham |  | B35 7JJ |  | Mr T Watson | 01217766591 | 07881763079 | Tomw@jav7wanadoo.co.uk |  | Windows & Doors
12 |  | 69132 |  | COMMENCEMENT PENDING |  | 39 | Neville Walk | Birmingham |  | B35 7JJ |  | Mrs L Broughton | 0121 749 7881 | 07377 983706 |  |  | Windows & Doors
12 |  | 59922 |  | COMMENCEMENT PENDING |  | 41 | Neville Walk | Birmingham |  | B35 7JJ |  | Mr B Humphries | 01217494440 |  |  |  | Windows & Doors
12 |  | 59923 |  | COMMENCEMENT PENDING |  | 43 | Neville Walk | Birmingham |  | B35 7JJ |  | Miss K Basnett |  | 07414 230 156 |  |  | Windows & Doors
12 |  | 65977 |  | COMMENCEMENT PENDING |  | 45 | Neville Walk | Birmingham |  | B35 7JJ |  | Miss R Moseley |  | 07342797066 | rachelmoseley333@gmail.com |  | Windows & Doors
12 |  | 70282 |  | COMMENCEMENT PENDING |  | 47 | Neville Walk | Birmingham |  | B35 7JJ |  | Mr E Whyte | 07359663789 | 07359663789 | elijahwhyteew@gmail.com |  | Windows & Doors
12 |  | 59926 |  | COMMENCEMENT PENDING |  | 49 | Neville Walk | Birmingham |  | B35 7JJ |  | Miss D Henry |  | 07368 367156 | debshen82@hotmail.com |  | Windows & Doors
12 |  | 59928 |  | COMMENCEMENT PENDING |  | 53 | Neville Walk | Birmingham |  | B35 7JJ |  | Miss D McKenzie | 07534 479 670 |  |  |  | Windows & Doors
12 |  | 57862 |  | COMMENCEMENT PENDING |  | 1 | Newcastle Croft | Birmingham |  | B35 7NS |  | Mrs C Greenhill |  | 07902 032 092 |  |  | Windows & Doors
12 |  | 63383 |  | COMMENCEMENT PENDING |  | 3 | Newcastle Croft | Birmingham |  | B35 7NS |  | Mrs S Hopkins |  | 07481 833 226 | samevans56@gmail.com |  | Windows & Doors
12 |  | 68341 |  | COMMENCEMENT PENDING |  | 5 | Newcastle Croft | Birmingham |  | B35 7NS |  | Miss S Islam |  | 07713748296 |  |  | Windows & Doors
12 |  | 67854 |  | COMMENCEMENT PENDING |  | 9 | Newcastle Croft | Birmingham |  | B35 7NS |  | Miss P Hewitt |  | 07885499782 |  |  | Windows & Doors
12 |  | 56252 |  | COMMENCEMENT PENDING |  | 11 | Newcastle Croft | Birmingham |  | B35 7NS |  | Mrs S Chard | 0121 241 0685 | 07842 316019 |  |  | Windows & Doors
12 |  | 56253 |  | COMMENCEMENT PENDING |  | 15 | Newcastle Croft | Birmingham |  | B35 7NS |  | Mr K Mills |  |  |  |  | Windows & Doors
12 |  | 69134 |  | COMMENCEMENT PENDING |  | 19 | Newcastle Croft | Birmingham |  | B35 7NS |  | Miss D Kelly |  | 07940127027 | kelljadex@icloud.com |  | Windows & Doors
12 |  | 64830 |  | COMMENCEMENT PENDING |  | 21 | Newcastle Croft | Birmingham |  | B35 7NS |  | Miss AM Langford |  | 07851 669 060 |  |  | Windows & Doors
12 |  | 65994 |  | COMMENCEMENT PENDING |  | 33 | Newcastle Croft | Birmingham |  | B35 7NS |  | Miss K Nally |  | 07565 884 900 | katy.90nally@yaho.co.uk |  | Windows & Doors
12 |  | 62258 |  | COMMENCEMENT PENDING |  | FLAT 2 | Northolt Drive | Birmingham |  | B35 6QX |  | Mr P Sinclair |  | 078151 94683 | peter.sinclair2026@gmail.com |  | Windows & Doors | S Burgess |  |  |  |  | TS-04/04/24 Text sent for 16/04/24. TS-05/04/24 Tenant text back to decline they need a Wednesday after 1pm. 8/07 SMS text sent for 24/07 AFTER 1PM. Tenant declined 24/07 after 1pm, req 3 weeks notice | [28 empty] | Access via 10 Northolt & 471 Yatesbury Avenue
12 |  | 62379 |  | COMMENCEMENT PENDING |  | 4 | Oakington Drive | Birmingham |  | B35 7HQ |  | Mrs Jodie Hanley |  | 07969476176 |  |  | Windows & Doors
12 |  | 68613 |  | COMMENCEMENT PENDING |  | 6 | Oakington Drive | Birmingham |  | B35 7HQ |  | Mr T Phillips |  | 07479 543 398 |  |  | Windows & Doors
12 |  | 65715 |  | COMMENCEMENT PENDING |  | 8 | Oakington Drive | Birmingham |  | B35 7HQ |  | Miss LE Plumb |  |  |  |  | Windows & Doors
12 |  | 62386 |  | COMMENCEMENT PENDING |  | 12 | Oakington Drive | Birmingham |  | B35 7HQ |  | Mrs C E Bailey |  | 07878 947 765 | clairewhelan2007@hotmail.co.uk |  | Windows & Doors
12 |  | 56295 |  | COMMENCEMENT PENDING |  | 3 | Orchard Meadow Walk | Birmingham |  | B35 7LT |  | Miss K A Hennessy |  | 07480 247072 | kerri.hennessy@yahoo.co.uk |  | Windows & Doors
12 |  | 67579 |  | COMMENCEMENT PENDING |  | 5 | Orchard Meadow Walk | Birmingham |  | B35 7LT |  | Miss J Robinson |  | 07717471105 |  |  | Windows & Doors
12 |  | 68083 |  | COMMENCEMENT PENDING |  | 7 | Orchard Meadow Walk | Birmingham |  | B35 7LT |  | Miss N A McFarlane | 0121 747 7898 | 07874056322 | nicole_mcfarlane@hotmail.co.uk |  | Windows & Doors
12 |  | 64900 |  | COMMENCEMENT PENDING |  | 9 | Orchard Meadow Walk | Birmingham |  | B35 7LT |  | Miss N Lynch | 0121 240 8365 | 07806 703 291 | Lynchnicola17@gmail.com |  | Windows & Doors
12 |  | 66960 |  | COMMENCEMENT PENDING |  | 17 | Orchard Meadow Walk | Birmingham |  | B35 7LT |  | Miss K Blackwell |  |  | kimberleyb1990@hotmail.co.uk |  | Windows & Doors
12 |  | 64283 |  | COMMENCEMENT PENDING |  | 19 | Orchard Meadow Walk | Birmingham |  | B35 7LT |  | Miss R Sheppard |  | 07305 532 140 |  |  | Windows & Doors
12 |  | 67653 |  | COMMENCEMENT PENDING |  | 21 | Orchard Meadow Walk | Birmingham |  | B35 7LT |  | Miss J White |  | 07415463710 | Jennywhite2009@live.co.uk |  | Windows & Doors
12 |  | 63935 |  | COMMENCEMENT PENDING |  | 25 | Orchard Meadow Walk | Birmingham |  | B35 7LT |  | Miss L Reid | 0121 730 1311 | 07765033528 | reid.leah@yahoo.co.uk |  | Windows & Doors
12 |  | 70410 |  | COMMENCEMENT PENDING |  | 27 | Orchard Meadow Walk | Birmingham |  | B35 7LT |  | Miss C L O'Connor |  | 07883367045 | caraleigh18@icloud.com |  | Windows & Doors
12 |  | 56312 |  | COMMENCEMENT PENDING |  | 43 | Orchard Meadow Walk | Birmingham |  | B35 7LT |  | Ms S Roberts |  | 07495077761 |  |  | Windows & Doors
12 |  | 56313 |  | COMMENCEMENT PENDING |  | 47 | Orchard Meadow Walk | Birmingham |  | B35 7LT |  | Mrs M Gouldney |  |  |  |  | Windows & Doors
12 |  | 69010 |  | COMMENCEMENT PENDING |  | 4 | Orchard Meadow Walk | Birmingham |  | B35 7LU |  | Ms S Tolley |  | 07532335081 |  |  | Windows & Doors
12 |  | 67865 |  | COMMENCEMENT PENDING |  | 18 | Orchard Meadow Walk | Birmingham |  | B35 7LU |  | Mr M Field |  | 07971016941 | fieldrachel79@gmail.com |  | Windows & Doors
12 |  | 56305 |  | COMMENCEMENT PENDING |  | 24 | Orchard Meadow Walk | Birmingham |  | B35 7LU |  | Miss L Haden |  | 07507395230 | lisahayden20@gmail.com |  | Windows & Doors
12 |  | 57860 |  | COMMENCEMENT PENDING |  | 28 | Orchard Meadow Walk | Birmingham |  | B35 7LU |  | Mrs J Marsh |  |  |  |  | Windows & Doors
12 |  | 60369 |  | COMMENCEMENT PENDING |  | 34 | Orchard Meadow Walk | Birmingham |  | B35 7LU |  | Miss M Ford | 07928175749 | 07928175749 |  |  | Windows & Doors
12 |  | 66244 |  | COMMENCEMENT PENDING |  | 42 | Orchard Meadow Walk | Birmingham |  | B35 7LU |  | Mrs T McCalla | 0121 523 4608 |  |  |  | Windows & Doors
12 |  | 68844 |  | COMMENCEMENT PENDING |  | 4 | Padgate | Birmingham |  | B35 7LX |  | Mr M P Yates |  | 07368 392 617 | martinyates940@hotmail.com |  | Windows & Doors
12 |  | 63753 |  | COMMENCEMENT PENDING |  | 2 | Padgate Close | Birmingham |  | B35 7LX |  | Miss K Clayton |  | 07340 167 385 |  |  | Windows & Doors
12 |  | 62838 |  | COMMENCEMENT PENDING |  | 6 | Padgate Close | Birmingham |  | B35 7LX |  | Mrs J Jones |  | 07494296173 |  |  | Windows & Doors
12 |  | 56315 |  | COMMENCEMENT PENDING |  | 12 | Padgate Close | Birmingham |  | B35 7LX |  | Mr N Taylor |  | 07778 774 711 | ntaylor12@talktalk.net |  | Windows & Doors
12 |  | 56316 |  | COMMENCEMENT PENDING |  | 15 | Padgate Close | Birmingham |  | B35 7LX |  | Mr W Shepherd |  |  |  |  | Windows & Doors
12 |  | 56318 |  | COMMENCEMENT PENDING |  | 19 | Padgate Close | Birmingham |  | B35 7LX |  | Mr D Hagans |  |  |  |  | Windows & Doors
12 |  | 64608 |  | COMMENCEMENT PENDING |  | 27 | Padgate Close | Birmingham |  | B35 7LX |  | Mr RA Williams | 0121 747 2440 | 07940 238307 | krystyok@hotmail.co.uk |  | Windows & Doors
12 |  | 69726 |  | COMMENCEMENT PENDING |  | 29 | Padgate Close | Birmingham |  | B35 7LX |  | Miss K Clarke |  |  |  |  | Windows & Doors
12 |  | 56324 |  | COMMENCEMENT PENDING |  | 33 | Padgate Close | Birmingham |  | B35 7LX |  | Mrs J Asbury |  |  |  |  | Windows & Doors
12 |  | 62210 |  | COMMENCEMENT PENDING |  | 34 | Padgate Close | Birmingham |  | B35 7LX |  | Miss K A Hansard | 07583 964820 |  | khansard05@aol.com |  | Windows & Doors
12 |  | 69760 |  | COMMENCEMENT PENDING |  | 36 | Padgate Close | Birmingham |  | B35 7LX |  | Miss A McManus |  | 07379 632 123 | Lanna96_X@hotmail.co.uk |  | Windows & Doors
12 |  | 68393 |  | COMMENCEMENT PENDING |  | 38 | Padgate Close | Birmingham |  | B35 7LX |  | Mr M White | 07971 838163 | 07971838163 |  |  | Windows & Doors
12 |  | 62213 |  | COMMENCEMENT PENDING |  | 40 | Padgate Close | Birmingham |  | B35 7LX |  | Miss M Harris | 0121 749 4432 |  | maryannh644@gmail.com |  | Windows & Doors
12 |  | 62214 |  | COMMENCEMENT PENDING |  | 61 | Padgate Close | Birmingham |  | B35 7LX |  | Miss S Carter | 0121 240 8146 | 07449 650709 |  |  | Windows & Doors
12 |  | 66176 |  | COMMENCEMENT PENDING |  | 63 | Padgate Close | Birmingham |  | B35 7LX |  | Miss J Large |  | 07818005878 |  |  | Windows & Doors
12 |  | 62216 |  | COMMENCEMENT PENDING |  | 65 | Padgate Close | Birmingham |  | B35 7LX |  | Miss J Bennett | 0121 574 5315 | 07762471025 |  |  | Windows & Doors
12 |  | 64382 |  | COMMENCEMENT PENDING |  | 67 | Padgate Close | Birmingham |  | B35 7LX |  | Miss B J Whitehorne |  | 07931515433 |  |  | Windows & Doors
12 |  | 67406 |  | COMMENCEMENT PENDING |  | 69 | Padgate Close | Birmingham |  | B35 7LX |  | Mr W Stuart-Stephens | 0121 792 1608 | 07427013611 |  |  | Windows & Doors
12 |  | 68978 |  | COMMENCEMENT PENDING |  | 71 | Padgate Close | Birmingham |  | B35 7LX |  | Mr P A Wood |  | 07432136984 |  |  | Windows & Doors
12 |  | 69486 |  | COMMENCEMENT PENDING |  | 10 | Padgate Close | Birmingham |  | B35 7LX |  | Miss V Martin |  | 07738823890 | justveevee@icloud.com |  | Windows & Doors
12 |  | 69956 |  | COMMENCEMENT PENDING |  | 10A | Padgate Close | Birmingham |  | B35 7LX |  | Ms N Latif |  | 07723614959 | sofierehman2@gmail.com |  | Windows & Doors
12 |  | 63783 |  | COMMENCEMENT PENDING |  | 8 | Padgate Close | Birmingham |  | B35 7LX |  | Mrs D Latham |  | 07896101006 |  |  | Windows & Doors
12 |  | 69896 |  | COMMENCEMENT PENDING |  | 8A | Padgate Close | Birmingham |  | B35 7LX |  | Miss S Cotterill | 01212514370 | 07891835919 | sharonc123@hotmail.co.uk |  | Windows & Doors
12 |  | 56326 |  | COMMENCEMENT PENDING |  | FLAT 2 Block 361 | Park Lane | Castle Vale |  | B35 6LL |  | Mrs M R Hall | 07592537547 |  |  |  | Windows & Doors
12 |  | 70578 |  | COMMENCEMENT PENDING |  | FLAT 3 Block 361 | Park Lane | Castle Vale |  | B35 6LL |  | Miss J Gordon | 07772 293687 |  |  |  | Windows & Doors
12 |  | 70382 |  | COMMENCEMENT PENDING |  | FLAT 4 Block 361 | Park Lane | Castle Vale |  | B35 6LL |  | Miss K Preston |  | 07513789458 | mommy2430xx@icloiud.com |  | Windows & Doors
12 |  | 61571 |  | COMMENCEMENT PENDING |  | FLAT 5 Block 361 | Park Lane | Castle Vale |  | B35 6LL |  | Mrs S Hughes | 01215746538 |  | suehughes95@ymail.com |  | Windows & Doors
12 |  | 67720 |  | COMMENCEMENT PENDING |  | FLAT 6 Block 361 | Park Lane | Castle Vale |  | B35 6LL |  | Mr S Taylor | 01217494184 |  | steven_taylor10@hotmail.co.uk |  | Windows & Doors
12 |  | 61440 |  | COMMENCEMENT PENDING |  | 219 | Park Lane | Birmingham |  | B35 6LS |  | Mr N Taggart |  | 07956223641 |  |  | Windows & Doors
12 |  | 63240 |  | COMMENCEMENT PENDING |  | 221 | Park Lane | Birmingham |  | B35 6LS |  | Miss E Grant |  | 07814460219 | egrant1976@btinternet.com |  | Windows & Doors
12 |  | 61442 |  | COMMENCEMENT PENDING |  | 223 | Park Lane | Birmingham |  | B35 6LS |  | Mr C Blakemore |  | 07763982884 | Colinblakmore58@sky.com |  | Windows & Doors
12 |  | 61443 |  | COMMENCEMENT PENDING |  | 225 | Park Lane | Birmingham |  | B35 6LS |  | Mr D Penny |  | 07788760565 |  |  | Windows & Doors
12 |  | 61446 |  | COMMENCEMENT PENDING |  | 231 | Park Lane | Birmingham |  | B35 6LS |  | Mr M Day |  | 07760551180 |  |  | Windows & Doors
12 |  | 61447 |  | COMMENCEMENT PENDING |  | 233 | Park Lane | Birmingham |  | B35 6LS |  | Mr C Murtagh | 01217471786 | 07939977722 |  |  | Windows & Doors
12 |  | 61448 |  | COMMENCEMENT PENDING |  | 235 | Park Lane | Birmingham |  | B35 6LS |  | Mr S Asbury |  | 07787484673 |  |  | Windows & Doors
12 |  | 70454 |  | COMMENCEMENT PENDING |  | FLAT 1 Block 1 | Pixhall Walk | Castle Vale |  | B35 7NJ |  | Mrs T OKubaselasie | 07453442941 | 07453442941 | tirhasok@gmail.com |  | Windows & Doors
12 |  | 69045 |  | COMMENCEMENT PENDING |  | FLAT 1 Block 15 | Pixhall Walk | Castle Vale |  | B35 7NJ |  | Mr RW Hawthorn |  | 07359253186 |  |  | Windows & Doors
12 |  | 67580 |  | COMMENCEMENT PENDING |  | FLAT 1 Block 17 | Pixhall Walk | Castle Vale |  | B35 7NJ |  | Mrs J A Stokes |  | 07713960464 |  |  | Windows & Doors
12 |  | 65071 |  | COMMENCEMENT PENDING |  | FLAT 1 Block 2 | Pixhall Walk | Castle Vale |  | B35 7NJ |  | Mr N Pendrey | 0121 537 8708 | 07712 390 951 |  |  | Windows & Doors
12 |  | 56432 |  | COMMENCEMENT PENDING |  | FLAT 1 Block 3 | Pixhall Walk | Castle Vale |  | B35 7NJ |  | Mr R Parkes | 07866 308415 | 01902635683 |  |  | Windows & Doors
12 |  | 56414 |  | COMMENCEMENT PENDING |  | FLAT 1 Block 4 | Pixhall Walk | Castle Vale |  | B35 7NJ |  | Mrs CA Williams |  |  |  |  | Windows & Doors
12 |  | 56439 |  | COMMENCEMENT PENDING |  | FLAT 2 Block 1 | Pixhall Walk | Castle Vale |  | B35 7NJ |  | Mr T A O'Sullivan | 0121 749 3165 |  |  |  | Windows & Doors
12 |  | 64760 |  | COMMENCEMENT PENDING |  | FLAT 2 Block 15 | Pixhall Walk | Castle Vale |  | B35 7NJ |  | Mr R Williams | 0121 747 8967 |  |  |  | Windows & Doors
12 |  | 68492 |  | COMMENCEMENT PENDING |  | FLAT 2 Block 17 | Pixhall Walk | Castle Vale |  | B35 7NJ |  | Miss N Littleford |  | 07311265188 |  |  | Windows & Doors
12 |  | 70372 |  | COMMENCEMENT PENDING |  | FLAT 2 Block 2 | Pixhall Walk | Castle Vale |  | B35 7NJ |  | Mrs M Blenkiron | 01217483154 | 07508 091 994 | marieblenkiron@hotmail.com |  | Windows & Doors
12 |  | 67361 |  | COMMENCEMENT PENDING |  | FLAT 2 Block 3 | Pixhall Walk | Castle Vale |  | B35 7NJ |  | Mr S G Kavanagh |  | 07882540112 |  |  | Windows & Doors
12 |  | 66984 |  | COMMENCEMENT PENDING |  | FLAT 2 Block 4 | Pixhall Walk | Castle Vale |  | B35 7NJ |  | Ms E M Lewandowska | 07545 253924 | 07850653535 | darson1970@gmail.com |  | Windows & Doors
12 |  | 69891 |  | COMMENCEMENT PENDING |  | FLAT 3 Block 1 | Pixhall Walk | Castle Vale |  | B35 7NJ |  | Mr A Fleming |  | 07868344312 |  |  | Windows & Doors
12 |  | 70152 |  | COMMENCEMENT PENDING |  | FLAT 3 Block 15 | Pixhall Walk | Castle Vale |  | B35 7NJ |  | Miss K Rainbird |  | 07525 181 451 |  |  | Windows & Doors
12 |  | 66888 |  | COMMENCEMENT PENDING |  | FLAT 3 Block 17 | Pixhall Walk | Castle Vale |  | B35 7NJ |  | Mr D H Lewis |  | 07999840705 | echos1@hotmail.co.uk |  | Windows & Doors
12 |  | 62480 |  | COMMENCEMENT PENDING |  | FLAT 3 Block 3 | Pixhall Walk | Castle Vale |  | B35 7NJ |  | Mr L Donovon |  |  |  |  | Windows & Doors
12 |  | 66213 |  | COMMENCEMENT PENDING |  | FLAT 4 Block 1 | Pixhall Walk | Castle Vale |  | B35 7NJ |  | Miss M L Nicholls |  | 07735 704 995 |  |  | Windows & Doors
12 |  | 69898 |  | COMMENCEMENT PENDING |  | FLAT 4 Block 15 | Pixhall Walk | Castle Vale |  | B35 7NJ |  | Miss C Wakefield |  | 07391635754 | chelseyellen@live.co.uk |  | Windows & Doors
12 |  | 68779 |  | COMMENCEMENT PENDING |  | FLAT 4 Block 17 | Pixhall Walk | Castle Vale |  | B35 7NJ |  | Miss K Whitehouse |  | 07488309580 | kimberleywhitehouse2@gmail.com |  | Windows & Doors
12 |  | 58549 |  | COMMENCEMENT PENDING |  | FLAT 4 Block 3 | Pixhall Walk | Castle Vale |  | B35 7NJ |  | Mr P Loveridge |  |  |  |  | Windows & Doors
12 |  | 56442 |  | COMMENCEMENT PENDING |  | FLAT 5 Block 1 | Pixhall Walk | Castle Vale |  | B35 7NJ |  | Mrs P Spence |  |  |  |  | Windows & Doors
12 |  | 65551 |  | COMMENCEMENT PENDING |  | FLAT 5 Block 15 | Pixhall Walk | Castle Vale |  | B35 7NJ |  | Mr G Feld |  | 07547736336 |  |  | Windows & Doors
12 |  | 56424 |  | COMMENCEMENT PENDING |  | FLAT 5 Block 17 | Pixhall Walk | Castle Vale |  | B35 7NJ |  | Ms L McBride | 07495050438 |  | lynling@gmail.com |  | Windows & Doors
12 |  | 68804 |  | COMMENCEMENT PENDING |  | FLAT 5 Block 3 | Pixhall Walk | Castle Vale |  | B35 7NJ |  | Ms L Pountney | 07454969300 | 07454969300 | lisa071269@gmail.com |  | Windows & Doors
12 |  | 61197 |  | COMMENCEMENT PENDING |  | FLAT 5 Block 4 | Pixhall Walk | Castle Vale |  | B35 7NJ |  | Mr D Brooks | 0121 288 6000 | 07488700958 | donbrookes9@gmail.com |  | Windows & Doors
12 |  | 70644 |  | COMMENCEMENT PENDING |  | FLAT 6 Block 1 | Pixhall Walk | Castle Vale |  | B35 7NJ |  | Miss C Dobb |  | 07481970055 | clairemdobb@icloud.com |  | Windows & Doors
12 |  | 63728 |  | COMMENCEMENT PENDING |  | FLAT 6 Block 15 | Pixhall Walk | Castle Vale |  | B35 7NJ |  | Miss K Walsh |  |  |  |  | Windows & Doors
12 |  | 67791 |  | COMMENCEMENT PENDING |  | FLAT 6 Block 17 | Pixhall Walk | Castle Vale |  | B35 7NJ |  | Miss A K Taylor | 01217488220 |  | lishataylor86@icloud.com |  | Windows & Doors
12 |  | 67857 |  | COMMENCEMENT PENDING |  | FLAT 6 Block 2 | Pixhall Walk | Castle Vale |  | B35 7NJ |  | Miss P Hanson | 07804 586 846 | 07804586846 |  |  | Windows & Doors
12 |  | 64859 |  | COMMENCEMENT PENDING |  | FLAT 6 Block 3 | Pixhall Walk | Castle Vale |  | B35 7NJ |  | Mr N E Jeffrey |  | 07407481895 |  |  | Windows & Doors
12 |  | 63123 |  | COMMENCEMENT PENDING |  | 39 | Prestwick Road | Birmingham |  | B35 6PG |  | Miss KHJ Evans | 0121 748 3577 | 07472187236 | kathrynevans1@sky.com |  | Windows & Doors
12 |  | 65665 |  | COMMENCEMENT PENDING |  | 55 | Prestwick Road | Birmingham |  | B35 6PG |  | Mr R Hinett |  | 0745868243 | ryanhinett87@gmail.com |  | Windows & Doors
12 |  | 69057 |  | COMMENCEMENT PENDING |  | FLAT 6 Block 47 | Prestwick Road | Castle Vale |  | B35 6PG |  | Mr J Harris |  |  | jackharris0809@hotmail.co.uk |  | Windows & Doors
12 |  | 65887 |  | COMMENCEMENT PENDING |  | 3 | Rawlins Croft | Birmingham |  | B35 7NN |  | Miss C Coley |  | 07407 551 156 |  |  | Windows & Doors
12 |  | 56445 |  | COMMENCEMENT PENDING |  | 5 | Rawlins Croft | Birmingham |  | B35 7NN |  | Mr K Bradbury |  | 07425144546 |  |  | Windows & Doors
12 |  | 67111 |  | COMMENCEMENT PENDING |  | 8 | Rawlins Croft | Birmingham |  | B35 7NN |  | Mrs D Shaw |  | 07549655288 | dawnfearby@live.co.uk |  | Windows & Doors
12 |  | 65046 |  | COMMENCEMENT PENDING |  | 12 | Rawlins Croft | Birmingham |  | B35 7NN |  | Mr W Hickin |  | 07770309493 |  |  | Windows & Doors
12 |  | 65138 |  | COMMENCEMENT PENDING |  | 14 | Rawlins Croft | Birmingham |  | B35 7NN |  | Miss M Ross |  |  |  |  | Windows & Doors
12 |  | 66851 |  | COMMENCEMENT PENDING |  | 6A | Rawlins Croft | Birmingham |  | B35 7NN |  | Mrs J Littler |  | 07412491871 | littlerjacqueline722@gmail.com |  | Windows & Doors
12 |  | 63293 |  | COMMENCEMENT PENDING |  | 6B | Rawlins Croft | Birmingham |  | B35 7NN |  | Miss T Hough |  | 07957 389 862 | traceyhough08@gmail.com |  | Windows & Doors
12 |  | 68838 |  | COMMENCEMENT PENDING |  | FLAT 1 Block 25 | Renfrew Square | Castle Vale |  | B35 6JT |  | Ms L Stanford |  | 07476 710 711 | lesley.stanford@live.co.uk |  | Windows & Doors
12 |  | 63956 |  | COMMENCEMENT PENDING |  | FLAT 1 Block 27 | Renfrew Square | Castle Vale |  | B35 6JT |  | Miss C Hill | 01217486965 | 07830 047 819 | carmelhill18@yahoo.com |  | Windows & Doors
12 |  | 70529 |  | COMMENCEMENT PENDING |  | FLAT 2 Block 25 | Renfrew Square | Castle Vale |  | B35 6JT |  | Miss S McFarlane |  | 07479451704 | missnaymcfarlane@gmail.com |  | Windows & Doors
12 |  | 68419 |  | COMMENCEMENT PENDING |  | FLAT 2 Block 27 | Renfrew Square | Castle Vale |  | B35 6JT |  | Miss B D Asbury | 07900819893 |  | brookly@hotmail.co.uk |  | Windows & Doors
12 |  | 68897 |  | COMMENCEMENT PENDING |  | FLAT 2 Block 29 | Renfrew Square | Castle Vale |  | B35 6JT |  | Miss O Roberts | 07989 638 770 |  |  |  | Windows & Doors
12 |  | 67790 |  | COMMENCEMENT PENDING |  | FLAT 4 Block 25 | Renfrew Square | Castle Vale |  | B35 6JT |  | Miss S Grant |  | 07984632063 |  |  | Windows & Doors
12 |  | 68191 |  | COMMENCEMENT PENDING |  | FLAT 5 Block 25 | Renfrew Square | Castle Vale |  | B35 6JT |  | Miss D Banner | 07708 251 056 | 07708 251056 | denise.banner@hotmail.co.uk |  | Windows & Doors
12 |  | 56466 |  | COMMENCEMENT PENDING |  | FLAT 6 Block 25 | Renfrew Square | Castle Vale |  | B35 6JT |  | Ms L Lynch | 07792 178190 |  |  |  | Windows & Doors
12 |  | 69491 |  | COMMENCEMENT PENDING |  | FLAT 3 | Reservoir Road | Stockland Green |  | B23 6DJ |  | Mr C Bibby |  | 07983 592909 | chrismcg47@outlook.com |  | Windows & Doors
12 |  | 69786 |  | COMMENCEMENT PENDING |  | FLAT 4 | Reservoir Road | Stockland Green |  | B23 6DJ |  | Mr P Dutton |  | 07477037683 | duttzdhl@hotmail.com |  | Windows & Doors
12 |  | 70505 |  | COMMENCEMENT PENDING |  | FLAT 5 | Reservoir Road | Stockland Green |  | B23 6DJ |  | Miss J Martins-Etimbuk |  | 07399148604 | ennyjane005@gmail.com |  | Windows & Doors
12 |  | 70261 |  | COMMENCEMENT PENDING |  | 11 | Rhoose Croft | Birmingham |  | B35 7NB |  | Miss N Osman |  | 07871841385 | nadiareis2012@hotmail.com |  | Windows & Doors
12 |  | 62373 |  | COMMENCEMENT PENDING |  | 17 | Rhoose Croft | Birmingham |  | B35 7NB |  | Miss S N Clinton |  | 07487259939 | simone1983@hotmail.co.uk |  | Windows & Doors
12 |  | 59973 |  | COMMENCEMENT PENDING |  | 9 | Rhoose Croft | Birmingham |  | B35 7NB |  | Miss R Pritchard | 07891182297 | 07891 182297 | rachelpritchad30@gmail.com |  | Windows & Doors
12 |  | 68295 |  | COMMENCEMENT PENDING |  | 80 | Riddfield Road | Birmingham |  | B36 8PS |  | Mr M Bichescu |  |  | G7_GABU@YAHOO.COM |  | Windows & Doors
12 |  | 69019 |  | COMMENCEMENT PENDING |  | 65 | Rosary Road | Birmingham |  | B23 7RD |  | Miss M Begum |  |  | minab77@hotmail.com |  | Windows & Doors
12 |  | 65267 |  | COMMENCEMENT PENDING |  | 1 | Roughcoppice Walk | Birmingham |  | B35 7JB |  | Mrs K Abdi | 0121 572 3105 | 07956040336 | roodaabdi1@gmail.com |  | Windows & Doors
12 |  | 56495 |  | COMMENCEMENT PENDING |  | 51 | Roughcoppice Walk | Birmingham |  | B35 7JB |  | Mrs B Fletcher |  |  |  |  | Windows & Doors
12 |  | 56485 |  | COMMENCEMENT PENDING |  | 8 | Roundmoor Walk | Birmingham |  | B35 7HJ |  | Miss S Woodroffe |  |  | sarahwoodroffe@yahoo.co.uk |  | Windows & Doors
12 |  | 68801 |  | COMMENCEMENT PENDING |  | 14 | Roundmoor Walk | Birmingham |  | B35 7HJ |  | Miss G Roberts |  | 07860 959834 | gem.8308@hotmail.com |  | Windows & Doors
12 |  | 65779 |  | COMMENCEMENT PENDING |  | 16 | Roundmoor Walk | Birmingham |  | B35 7HJ |  | Miss A Bould |  | 07403297843 | amy.bould@live.co.uk |  | Windows & Doors
12 |  | 70135 |  | COMMENCEMENT PENDING |  | 18 | Roundmoor Walk | Birmingham |  | B35 7HJ |  | Miss L Taylor |  | 07553463731 |  |  | Windows & Doors
12 |  | 59982 |  | COMMENCEMENT PENDING |  | 20 | Roundmoor Walk | Birmingham |  | B35 7HJ |  | Miss S Smith | 01214399751 | 07516 226 814 |  |  | Windows & Doors
12 |  | 59979 |  | COMMENCEMENT PENDING |  | 16A | Roundmoor Walk | Birmingham |  | B35 7HJ |  | Mr J Boyce |  | 07766 881 939 | ajlboyce@hotmail.com |  | Windows & Doors
12 |  | 62314 |  | COMMENCEMENT PENDING |  | 18A | Roundmoor Walk | Birmingham |  | B35 7HJ |  | Miss M Kinsella | 07391657790 | 07391657 790 |  |  | Windows & Doors
12 |  | 59983 |  | COMMENCEMENT PENDING |  | 20A | Roundmoor Walk | Birmingham |  | B35 7HJ |  | Mrs J Smith |  |  |  |  | Windows & Doors
12 |  | 70245 |  | COMMENCEMENT PENDING |  | 11 | Roundmoor Walk | Birmingham |  | B35 7HL |  | Ms J Northcote |  | 07854017712 | minnieme91@hotmail.co.uk |  | Windows & Doors
12 |  | 56481 |  | COMMENCEMENT PENDING |  | 17 | Roundmoor Walk | Birmingham |  | B35 7HL |  | Mrs J Johnson | 07977 460911 |  |  |  | Windows & Doors
12 |  | 68954 |  | COMMENCEMENT PENDING |  | 19 | Roundmoor Walk | Birmingham |  | B35 7HL |  | Miss L Scully |  | 07380 798583 |  |  | Windows & Doors
12 |  | 59975 |  | COMMENCEMENT PENDING |  | 21 | Roundmoor Walk | Birmingham |  | B35 7HL |  | Mrs S Mytton | 01216825922 |  | smytton@yahoo.co.uk |  | Windows & Doors
12 |  | 68708 |  | COMMENCEMENT PENDING |  | 25 | Roundmoor Walk | Birmingham |  | B35 7HL |  | Mrs KF Khan |  | 07448264926 |  |  | Windows & Doors
12 |  | 59974 |  | COMMENCEMENT PENDING |  | 9 | Roundmoor Walk | Birmingham |  | B35 7HL |  | Mr J Hipkiss |  | 07540 588 685 |  |  | Windows & Doors
12 |  | 63386 |  | COMMENCEMENT PENDING |  | 22 | Roundmoor Walk | Birmingham |  | B35 7HN |  | Miss T Etheridge |  | 07516294336 | tetheridge274@gmail.com |  | Windows & Doors
12 |  | 68171 |  | COMMENCEMENT PENDING |  | 24 | Roundmoor Walk | Birmingham |  | B35 7HN |  | Miss D Moore | 07585 339 195 |  |  |  | Windows & Doors
12 |  | 68141 |  | COMMENCEMENT PENDING |  | 26 | Roundmoor Walk | Birmingham |  | B35 7HN |  | Miss S C Ansell | 07709698980 | 07988 028294 |  |  | Windows & Doors
12 |  | 56490 |  | COMMENCEMENT PENDING |  | 28 | Roundmoor Walk | Birmingham |  | B35 7HN |  | Mr M V Horrocks |  | 07974607480 |  |  | Windows & Doors
12 |  | 56491 |  | COMMENCEMENT PENDING |  | 32 | Roundmoor Walk | Birmingham |  | B35 7HN |  | Mr M Ward |  | 07891872697 |  |  | Windows & Doors
12 |  | 56493 |  | COMMENCEMENT PENDING |  | 36 | Roundmoor Walk | Birmingham |  | B35 7HN |  | Miss K Mcgivern | 01217470978 | 07903196943 | vourn_94@live.co.uk |  | Windows & Doors
12 |  | 56494 |  | COMMENCEMENT PENDING |  | 38 | Roundmoor Walk | Birmingham |  | B35 7HN |  | Mrs K Ashley |  |  | caronhscott@hotmail.com |  | Windows & Doors
12 |  | 59976 |  | COMMENCEMENT PENDING |  | 44 | Roundmoor Walk | Birmingham |  | B35 7HN |  | Mr A Abusubih |  | 07961 582605 |  |  | Windows & Doors
12 |  | 67529 |  | COMMENCEMENT PENDING |  | 58 | Roundmoor Walk | Birmingham |  | B35 7HP |  | Mrs S Edwards | 01212918835 |  |  |  | Windows & Doors
12 |  | 64056 |  | COMMENCEMENT PENDING |  | 60 | Roundmoor Walk | Birmingham |  | B35 7HP |  | Miss SL Willetts |  | 07939862809 |  |  | Windows & Doors
12 |  | 56502 |  | COMMENCEMENT PENDING |  | 66 | Roundmoor Walk | Birmingham |  | B35 7HP |  | Miss K Hobbs |  | 07779 858838 |  |  | Windows & Doors
12 |  | 56504 |  | COMMENCEMENT PENDING |  | 72 | Roundmoor Walk | Birmingham |  | B35 7HP |  | Miss S O Neill |  | 077337425300 |  |  | Windows & Doors
12 |  | 64257 |  | COMMENCEMENT PENDING |  | 74 | Roundmoor Walk | Birmingham |  | B35 7HP |  | Miss D E Wood | 07403 92 33 33 |  | D_wood08@live.co.uk |  | Windows & Doors
12 |  | 68747 |  | COMMENCEMENT PENDING |  | 55 | Roundmoor Walk | Birmingham |  | B35 7HR |  | Mr J Reynalds | 07469821821 | 07469821821 | reynaldsj9@gmail.com |  | Windows & Doors
12 |  | 59977 |  | COMMENCEMENT PENDING |  | 57 | Roundmoor Walk | Birmingham |  | B35 7HR |  | Mr W Brewer | 01217476996 | 07526505446 | billy.242@hotmail.co.uk |  | Windows & Doors
12 |  | 64365 |  | COMMENCEMENT PENDING |  | 63 | Roundmoor Walk | Birmingham |  | B35 7HR |  | Miss A Hunter |  |  | hunter404mars@gmail.com |  | Windows & Doors
12 |  | 70136 |  | COMMENCEMENT PENDING |  | 73 | Roundmoor Walk | Birmingham |  | B35 7HR |  | Miss S M Tuckey | 07393600505 | 07521728022 | taylorsarah526@yahoo.com |  | Windows & Doors
12 |  | 67045 |  | COMMENCEMENT PENDING |  | 59 | Roundmoor Walk | Birmingham |  | B35 7HR |  | Mrs A Fenwick |  | 07786 844 825 |  |  | Windows & Doors
12 |  | 65931 |  | COMMENCEMENT PENDING |  | 61A | Roundmoor Walk | Birmingham |  | B35 7HR |  | Mrs S Horsfall | 07542044542 |  |  |  | Windows & Doors
12 |  | 63351 |  | COMMENCEMENT PENDING |  | 7B | Ruislip Close | Birmingham |  | B35 6JN |  | Ms G Macenzie |  | 07770 898 971 |  |  | Windows & Doors
12 |  | 70339 |  | COMMENCEMENT PENDING |  | FLAT 1 Block 11 | Ruislip Close | Castle Vale |  | B35 6JN |  | Miss K Mullen |  | 07585047790 | k-lee-mullen@hotmail.co.uk |  | Windows & Doors
12 |  | 57000 |  | COMMENCEMENT PENDING |  | FLAT 1 Block 9 | Ruislip Close | Castle Vale |  | B35 6JN |  | Mr T R Harvey | 0121 748 6326 |  |  |  | Windows & Doors
12 |  | 56515 |  | COMMENCEMENT PENDING |  | FLAT 2 Block 11 | Ruislip Close | Castle Vale |  | B35 6JN |  | Mr C Blunn | 0121 679 2507 | 07488372850 |  |  | Windows & Doors
12 |  | 70397 |  | COMMENCEMENT PENDING |  | FLAT 2 Block 9 | Ruislip Close | Castle Vale |  | B35 6JN |  | Mr S Sisay |  | 07764440919 | sisaysheika84@gmail.com |  | Windows & Doors
12 |  | 67108 |  | COMMENCEMENT PENDING |  | FLAT 3 Block 11 | Ruislip Close | Castle Vale |  | B35 6JN |  | Mr A E Barnes |  | 07444814573 |  |  | Windows & Doors
12 |  | 65482 |  | COMMENCEMENT PENDING |  | FLAT 3 Block 9 | Ruislip Close | Castle Vale |  | B35 6JN |  | Miss L Young | 0121 649 3996 | 07392309691 |  |  | Windows & Doors
12 |  | 56518 |  | COMMENCEMENT PENDING |  | FLAT 4 Block 11 | Ruislip Close | Castle Vale |  | B35 6JN |  | Mr G F Campbell | 07305052051 |  |  |  | Windows & Doors
12 |  | 64343 |  | COMMENCEMENT PENDING |  | FLAT 5 Block 11 | Ruislip Close | Castle Vale |  | B35 6JN |  | Miss N L Mullen |  | 07894343613 |  |  | Windows & Doors
12 |  | 67665 |  | COMMENCEMENT PENDING |  | FLAT 5 Block 9 | Ruislip Close | Castle Vale |  | B35 6JN |  | Ms R Dawood | 07460587444 |  |  |  | Windows & Doors
12 |  | 69955 |  | COMMENCEMENT PENDING |  | FLAT 6 Block 11 | Ruislip Close | Castle Vale |  | B35 6JN |  | Miss P Mazone |  | 07507229114 | paigemazone22@gmail.com |  | Windows & Doors
12 |  | 60408 |  | COMMENCEMENT PENDING |  | FLAT 6 Block 9 | Ruislip Close | Castle Vale |  | B35 6JN |  | Mr C Cleaver |  |  | COLIN.CLEAVER@hotmail.com |  | Windows & Doors
12 |  | 59987 |  | COMMENCEMENT PENDING |  | 16 | Ruislip Close | Birmingham |  | B35 6JW |  | Miss C O'Sullivan |  |  |  |  | Windows & Doors
12 |  | 69647 |  | COMMENCEMENT PENDING |  | 20 | Ruislip Close | Birmingham |  | B35 6JW |  | Mrs C Murphy | 07708337066 | 07708 337 066 |  |  | Windows & Doors
12 |  | 68506 |  | COMMENCEMENT PENDING |  | 7A | Ruislip Close | Birmingham |  | B35 7JN |  | Mr G Kisela |  | 07398965458 |  |  | Windows & Doors
12 |  | 64361 |  | COMMENCEMENT PENDING |  | 1 | Ryegrass Walk | Birmingham |  | B35 7LL |  | Mrs AM Lane |  | 07715587172 | SimonFlane@Gmail.com |  | Windows & Doors
12 |  | 56523 |  | COMMENCEMENT PENDING |  | 9 | Ryegrass Walk | Birmingham |  | B35 7LL |  | Miss D Walton |  | 07428756083 |  |  | Windows & Doors
12 |  | 70127 |  | COMMENCEMENT PENDING |  | 11 | Ryegrass Walk | Birmingham |  | B35 7LL |  | Mrs H Jones |  |  | helenjonesy78@gmail.com |  | Windows & Doors
12 |  | 56526 |  | COMMENCEMENT PENDING |  | 15 | Ryegrass Walk | Birmingham |  | B35 7LL |  | Mrs T Mcguire |  |  |  |  | Windows & Doors
12 |  | 56528 |  | COMMENCEMENT PENDING |  | 17 | Ryegrass Walk | Birmingham |  | B35 7LL |  | Mrs M Allen |  | 07436979620 |  |  | Windows & Doors
12 |  | 65647 |  | COMMENCEMENT PENDING |  | 21 | Ryegrass Walk | Birmingham |  | B35 7LL |  | Miss NJ Dalby | 0121 749 3521 | 07365016160 | nicoladalby@hotmail.com |  | Windows & Doors
12 |  | 68688 |  | COMMENCEMENT PENDING |  | 23 | Ryegrass Walk | Birmingham |  | B35 7LL |  | Miss J Heyes |  | 07947 159301 |  |  | Windows & Doors
12 |  | 68934 |  | COMMENCEMENT PENDING |  | 25 | Ryegrass Walk | Birmingham |  | B35 7LL |  | Miss L Robinson | 07496201987 | 07496201987 |  |  | Windows & Doors
12 |  | 56534 |  | COMMENCEMENT PENDING |  | 27 | Ryegrass Walk | Birmingham |  | B35 7LL |  | Mrs V Bricknell |  |  |  |  | Windows & Doors
12 |  | 64823 |  | COMMENCEMENT PENDING |  | 31 | Ryegrass Walk | Birmingham |  | B35 7LL |  | Miss L Lacey | 01217485788 | 07525071058 | lianne_lacey@yahoo.com |  | Windows & Doors
12 |  | 68433 |  | COMMENCEMENT PENDING |  | 33 | Ryegrass Walk | Birmingham |  | B35 7LL |  | Mr A Smith |  | 07888441583 | smith0121@hotmail.co.uk |  | Windows & Doors
12 |  | 63688 |  | COMMENCEMENT PENDING |  | 37 | Ryegrass Walk | Birmingham |  | B35 7LL |  | Miss K Tims | 0121 749 3554 | 07752 055 658 |  |  | Windows & Doors
12 |  | 56539 |  | COMMENCEMENT PENDING |  | 39 | Ryegrass Walk | Birmingham |  | B35 7LL |  | Miss M Walsh | 07855041669 |  |  |  | Windows & Doors
12 |  | 69939 |  | COMMENCEMENT PENDING |  | 47 | Ryegrass Walk | Birmingham |  | B35 7LL |  | Miss J L Cusack | 07429431220 | 07429431220 |  |  | Windows & Doors
12 |  | 63231 |  | COMMENCEMENT PENDING |  | 49 | Ryegrass Walk | Birmingham |  | B35 7LL |  | Miss L Hewitt | 01217302111 | 07712 061 264 |  |  | Windows & Doors
12 |  | 56543 |  | COMMENCEMENT PENDING |  | 51 | Ryegrass Walk | Birmingham |  | B35 7LL |  | Mr J P O'Brien |  | 07933148097 | John.165.job@gmail.com |  | Windows & Doors
12 |  | 65305 |  | COMMENCEMENT PENDING |  | 55 | Ryegrass Walk | Birmingham |  | B35 7LL |  | Miss M Murtagh | 07540 383848 | 07540 383848 |  |  | Windows & Doors
12 |  | 56522 |  | COMMENCEMENT PENDING |  | 2 | Ryegrass Walk | Birmingham |  | B35 7LN |  | Mr R Forknall |  | 07455731431 |  |  | Windows & Doors
12 |  | 69561 |  | COMMENCEMENT PENDING |  | 10 | Ryegrass Walk | Birmingham |  | B35 7LN |  | Miss L Berrow |  |  | Lisa_b_@live.co.uk |  | Windows & Doors
12 |  | 59988 |  | COMMENCEMENT PENDING |  | 12 | Ryegrass Walk | Birmingham |  | B35 7LN |  | Mrs T Demetrius | 07949 235315 |  |  |  | Windows & Doors
12 |  | 67534 |  | COMMENCEMENT PENDING |  | 14 | Ryegrass Walk | Birmingham |  | B35 7LN |  | Miss C Cadby |  | 07757311448 | clairecadby@hotmail.com |  | Windows & Doors
12 |  | 67134 |  | COMMENCEMENT PENDING |  | 16 | Ryegrass Walk | Birmingham |  | B35 7LN |  | Mr J R Hayes |  |  |  |  | Windows & Doors
12 |  | 60655 |  | COMMENCEMENT PENDING |  | 18 | Ryegrass Walk | Birmingham |  | B35 7LN |  | Miss A L Wilson | 07402 915899 | 07568736388 |  |  | Windows & Doors
12 |  | 56530 |  | COMMENCEMENT PENDING |  | 20 | Ryegrass Walk | Birmingham |  | B35 7LN |  | Mr R Murrell |  | 07849866032 |  |  | Windows & Doors
12 |  | 62220 |  | COMMENCEMENT PENDING |  | 26 | Ryegrass Walk | Birmingham |  | B35 7LN |  | Miss K Gibson | 07856511213 |  | keeliegibson@icloud.com |  | Windows & Doors
12 |  | 65251 |  | COMMENCEMENT PENDING |  | 28 | Ryegrass Walk | Birmingham |  | B35 7LN |  | Miss B E Pearce |  |  |  |  | Windows & Doors
12 |  | 67679 |  | COMMENCEMENT PENDING |  | 30 | Ryegrass Walk | Birmingham |  | B35 7LN |  | Miss C Rider | 0121 257 1925 | 07403 864 292 | charlotte.2004@hotmail.co.uk |  | Windows & Doors
12 |  | 65645 |  | COMMENCEMENT PENDING |  | 32 | Ryegrass Walk | Birmingham |  | B35 7LN |  | Miss AS Weaver |  | 07718190558 | amy.weaver07@googlemail.com |  | Windows & Doors
12 |  | 62224 |  | COMMENCEMENT PENDING |  | 34 | Ryegrass Walk | Birmingham |  | B35 7LN |  | Miss S Pearce |  | 07944808304 |  |  | Windows & Doors
12 |  | 62225 |  | COMMENCEMENT PENDING |  | 36 | Ryegrass Walk | Birmingham |  | B35 7LN |  | Miss C Purcell |  | 07857935554 |  |  | Windows & Doors
12 |  | 62226 |  | COMMENCEMENT PENDING |  | 38 | Ryegrass Walk | Birmingham |  | B35 7LN |  | Miss S Jevons | 01217485485 | 07732344434 | sandrajevons@aol.com |  | Windows & Doors
12 |  | 64421 |  | COMMENCEMENT PENDING |  | 40 | Ryegrass Walk | Birmingham |  | B35 7LN |  | Mrs A Kolecka | 07878 373 536 | 07878373536 | a.kolecka@yahoo.co.uk |  | Windows & Doors
12 |  | 69924 |  | COMMENCEMENT PENDING |  | 42 | Ryegrass Walk | Birmingham |  | B35 7LN |  | Miss C Asmah |  | 07455014894 | aanc@live.co.uk |  | Windows & Doors
12 |  | 62229 |  | COMMENCEMENT PENDING |  | 44 | Ryegrass Walk | Birmingham |  | B35 7LN |  | Miss S Wall |  | 07584 326035 |  |  | Windows & Doors
12 |  | 62230 |  | COMMENCEMENT PENDING |  | 50 | Ryegrass Walk | Birmingham |  | B35 7LN |  | Miss A Allen | 07922649612 |  | antallen1@hotmail.com |  | Windows & Doors
12 |  | 70532 |  | COMMENCEMENT PENDING |  | 52 | Ryegrass Walk | Birmingham |  | B35 7LN |  | Miss A Hinsley |  | 07780845622 | alexandrajames2016@gmail.com |  | Windows & Doors
12 |  | 62232 |  | COMMENCEMENT PENDING |  | 54 | Ryegrass Walk | Birmingham |  | B35 7LN |  | Mrs B Hennessy | 01217487001 | 07400399949 |  |  | Windows & Doors
12 |  | 65328 |  | COMMENCEMENT PENDING |  | 56 | Ryegrass Walk | Birmingham |  | B35 7LN |  | Ms A L Hazell | 07592 972 138 | 07796 496175 |  |  | Windows & Doors
12 |  | 62234 |  | COMMENCEMENT PENDING |  | 58 | Ryegrass Walk | Birmingham |  | B35 7LN |  | Miss C Lawrence |  | 07467 398 699 |  |  | Windows & Doors
12 |  | 65459 |  | COMMENCEMENT PENDING |  | 60 | Ryegrass Walk | Birmingham |  | B35 7LN |  | Miss M D Diallo | 07596848329 | 07596 848 329 | mariamadiallo30@googlemail.com |  | Windows & Doors
12 |  | 62236 |  | COMMENCEMENT PENDING |  | 62 | Ryegrass Walk | Birmingham |  | B35 7LN |  | Miss J Hopkins |  | 07544667594 | j.hopkins65@icloud.com |  | Windows & Doors
12 |  | 65306 |  | COMMENCEMENT PENDING |  | 4 | School Close | Birmingham |  | B35 7NU |  | Miss J Hughes | 0121 748 6530 | 0121 351 2190 |  |  | Windows & Doors | M Turpin |  |  |  |  | 14/06 SMS text sent for 25/06
12 |  | 66861 |  | COMMENCEMENT PENDING |  | 5 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Miss L Wilde | 07445 285 596 |  | lisawilde68@gmail.com |  | Windows & Doors | S Burgess
12 |  | 66069 |  | COMMENCEMENT PENDING |  | 6 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Mr D Haines |  | 07926 260 411 | DARRENHAINES71@outlook.com |  | Windows & Doors | S Burgess
12 |  | 67917 |  | COMMENCEMENT PENDING |  | 7 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Miss S Jones |  | 07950912235 | shanjonesy20@yahoo.co.uk |  | Windows & Doors | S Burgess
12 |  | 59995 |  | COMMENCEMENT PENDING |  | 8 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Miss N Leach | 07592810170 |  |  |  | Windows & Doors | S Burgess
12 |  | 69642 |  | COMMENCEMENT PENDING |  | 10 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Miss V L Cleaver | 07946410090 | 07399897736 |  |  | Windows & Doors | S Burgess
12 |  | 68192 |  | COMMENCEMENT PENDING |  | 11 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Miss L Welburn |  | 07464639085 | leeann87@tislali.co.uk |  | Windows & Doors | S Burgess
12 |  | 64444 |  | COMMENCEMENT PENDING |  | 12 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Miss K Austin |  | 07341924764 |  |  | Windows & Doors | S Burgess
12 |  | 69350 |  | COMMENCEMENT PENDING |  | 14 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Miss J Unitt |  | 07936008324 | xxjessxxchloexx@live.co.uk |  | Windows & Doors | S Burgess
12 |  | 64805 |  | COMMENCEMENT PENDING |  | 15 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Mr PM Thomas | 07931 215 343 | 07931 215 343 | plthom321@hotmail.co.uk |  | Windows & Doors | S Burgess
12 |  | 65301 |  | COMMENCEMENT PENDING |  | 16 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Mr D Harper |  | 07914 637773 |  |  | Windows & Doors | S Burgess
12 |  | 70038 |  | COMMENCEMENT PENDING |  | 17 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Ms T Eales |  | 07368201443 | taileebrown@hotmail.com |  | Windows & Doors | S Burgess
12 |  | 67872 |  | COMMENCEMENT PENDING |  | 18 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Mrs I Davies |  | 07342567842 |  |  | Windows & Doors | S Burgess
12 |  | 67397 |  | COMMENCEMENT PENDING |  | 19 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Miss T Allen | 07969255887 | 07903650774 |  |  | Windows & Doors | S Burgess
12 |  | 70322 |  | COMMENCEMENT PENDING |  | 20 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Mr J Taylor |  | 07599545790 | j.taylor12@live.co.uk |  | Windows & Doors | S Burgess
12 |  | 64784 |  | COMMENCEMENT PENDING |  | 21 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Miss A Sims | 01214484672 | 07597363000 |  |  | Windows & Doors | S Burgess
12 |  | 60460 |  | COMMENCEMENT PENDING |  | 22 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Mr M Meehan | 07403207547 |  | mdmeehan@hotmail.co.uk |  | Windows & Doors | S Burgess
12 |  | 69259 |  | COMMENCEMENT PENDING |  | 23 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Mr DJ Shakespeare |  | 07790 154 774 |  |  | Windows & Doors | S Burgess
12 |  | 63554 |  | COMMENCEMENT PENDING |  | 24 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Mrs S Murdock |  | 07411 019 263 | s_murdock@sky.com |  | Windows & Doors | S Burgess
12 |  | 60451 |  | COMMENCEMENT PENDING |  | 25 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Mr R Thomas |  | 07817 483 550 |  |  | Windows & Doors | S Burgess
12 |  | 68277 |  | COMMENCEMENT PENDING |  | 26 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Mr A Phillips |  | 07729 243172 |  |  | Windows & Doors | S Burgess
12 |  | 60011 |  | COMMENCEMENT PENDING |  | 27 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Miss F McElwee |  | 07577 623 362 |  |  | Windows & Doors | S Burgess
12 |  | 66260 |  | COMMENCEMENT PENDING |  | 28 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Miss RL Armstrong | 0121 218 7101 |  | Beckysmallz87@gmail.com |  | Windows & Doors | S Burgess
12 |  | 60013 |  | COMMENCEMENT PENDING |  | 29 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Miss T McGarrity | 07948 482 450 |  | tracey.mcgarrity@allianz.co.uk |  | Windows & Doors | S Burgess
12 |  | 60014 |  | COMMENCEMENT PENDING |  | 30 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Mr A Gibson | 07522 48 06 00 |  |  |  | Windows & Doors | S Burgess
12 |  | 64944 |  | COMMENCEMENT PENDING |  | 31 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Miss N Martin |  | 07599 233 123 | nataliemartin1984@hotmail.co.uk |  | Windows & Doors | S Burgess
12 |  | 65915 |  | COMMENCEMENT PENDING |  | 32 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Mrs T Cluer | 07821039223 |  |  |  | Windows & Doors | S Burgess
12 |  | 68429 |  | COMMENCEMENT PENDING |  | 33 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Mrs S Welburn |  | 07460 704 857 | flanders2008@hotmail.com |  | Windows & Doors | S Burgess
12 |  | 68044 |  | COMMENCEMENT PENDING |  | 34 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Miss S Mayers |  | 07305460146 |  |  | Windows & Doors | S Burgess
12 |  | 60019 |  | COMMENCEMENT PENDING |  | 35 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Mr D Foster |  |  |  |  | Windows & Doors | S Burgess
12 |  | 68115 |  | COMMENCEMENT PENDING |  | 36 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Miss M McCalla |  | 07928478255 | michaelammccalla@gmail.com |  | Windows & Doors | S Burgess
12 |  | 65848 |  | COMMENCEMENT PENDING |  | 37 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Miss J Hopkins | 01212507715 |  | janethop@hotmail.co.uk |  | Windows & Doors | S Burgess
12 |  | 68201 |  | COMMENCEMENT PENDING |  | 38 | Shawberry Avenue | Birmingham |  | B35 6QU |  | Miss L L Savage |  | 07874 182 822 |  |  | Windows & Doors | S Burgess
12 |  | 65471 |  | COMMENCEMENT PENDING |  | 3 | Sheridan Walk | Birmingham |  | B35 7HE |  | Miss N Carnihan |  | 07917 104 729 | nic-carni@hotmail.co.uk |  | Windows & Doors
12 |  | 63992 |  | COMMENCEMENT PENDING |  | 9 | Sheridan Walk | Birmingham |  | B35 7HE |  | Miss N McGuire | 07426526698 | 07426526698 | nicholamcguire47@gmail.com |  | Windows & Doors
12 |  | 56547 |  | COMMENCEMENT PENDING |  | 15 | Sheridan Walk | Birmingham |  | B35 7HE |  | Mrs M D Kearney |  | 07581 718897 |  |  | Windows & Doors
12 |  | 60023 |  | COMMENCEMENT PENDING |  | 21 | Sheridan Walk | Birmingham |  | B35 7HE |  | Mrs L Hughes |  | 07413 177987 |  |  | Windows & Doors
12 |  | 56553 |  | COMMENCEMENT PENDING |  | 35 | Sheridan Walk | Birmingham |  | B35 7HE |  | Miss K Barmer |  | 07851 061 161 |  |  | Windows & Doors
12 |  | 68567 |  | COMMENCEMENT PENDING |  | 39 | Sheridan Walk | Birmingham |  | B35 7HE |  | Miss C Gonzales |  |  |  |  | Windows & Doors
12 |  | 66001 |  | COMMENCEMENT PENDING |  | 41 | Sheridan Walk | Birmingham |  | B35 7HE |  | Mrs N Mebrahtom | 01216792405 | 07951586418 |  |  | Windows & Doors
12 |  | 56548 |  | COMMENCEMENT PENDING |  | 22 | Sheridan Walk | Birmingham |  | B35 7HF |  | Mrs S Linden | 07306030439 |  |  |  | Windows & Doors
12 |  | 56549 |  | COMMENCEMENT PENDING |  | 26 | Sheridan Walk | Birmingham |  | B35 7HF |  | Mrs J A Houghton | 01217494706 | 07855536866 |  |  | Windows & Doors
12 |  | 63687 |  | COMMENCEMENT PENDING |  | 28 | Sheridan Walk | Birmingham |  | B35 7HF |  | Miss L Day | 07821012332 |  | countrygirl20@hotmail.com |  | Windows & Doors
12 |  | 61993 |  | COMMENCEMENT PENDING |  | 32 | Sheridan Walk | Birmingham |  | B35 7HF |  | Miss A Jeffs |  | 07593802838 | antoinettejeffs@gmail.com |  | Windows & Doors
12 |  | 68612 |  | COMMENCEMENT PENDING |  | 40 | Sheridan Walk | Birmingham |  | B35 7HF |  | Miss O Barraclough | 07412 546921 |  | liv.2788@googlemail.com |  | Windows & Doors
12 |  | 56557 |  | COMMENCEMENT PENDING |  | 50 | Sheridan Walk | Birmingham |  | B35 7HF |  | Mrs V Hill | 747 - 6474 |  |  |  | Windows & Doors
12 |  | 69520 |  | COMMENCEMENT PENDING |  | 26 | Shetland Walk | Birmingham |  | B36 0PH |  | Miss R Moss |  | 07841502019 | rebeccamoss1994@hotmail.co.uk |  | Windows & Doors
12 |  | 68564 |  | COMMENCEMENT PENDING |  | FLAT 1 | Slade Road | Stockland Green |  | B23 7JX |  | Mr A Williams |  | 07912641005 |  |  | Windows & Doors
12 |  | 68773 |  | COMMENCEMENT PENDING |  | FLAT 2 | Slade Road | Stockland Green |  | B23 7JX |  | Mr T Henry |  |  | henrytrevor128@gmail.com |  | Windows & Doors
12 |  | 70707 |  | COMMENCEMENT PENDING |  | FLAT 3 | Slade Road | Stockland Green |  | B23 7JX |  | Mr E Adesina |  | 07405784028 | eriadesina@gmail.com |  | Windows & Doors
12 |  | 68825 |  | COMMENCEMENT PENDING |  | FLAT 4 | Slade Road | Stockland Green |  | B23 7JX |  | Miss S Tariq |  | 07503015530 | sophina123@outlook.com |  | Windows & Doors
12 |  | 68470 |  | COMMENCEMENT PENDING |  | FLAT 5 | Slade Road | Stockland Green |  | B23 7JX |  | Mr D Singh |  | 07910421213 | didars303@gmail.com |  | Windows & Doors
12 |  | 70543 |  | COMMENCEMENT PENDING |  | FLAT 6 | Slade Road | Stockland Green |  | B23 7JX |  | Miss M Onigbinde |  |  | onigbindemonsurat@gmail.com |  | Windows & Doors
12 |  | 70629 |  | COMMENCEMENT PENDING |  | 151 | Slade Road | Birmingham |  | B23 7QU |  | Miss S Gormley-Bird |  | 07926729448 | sgormleybird@gmail.com |  | Windows & Doors
12 |  | 63692 |  | COMMENCEMENT PENDING |  | 27 | Sopwith Croft | Birmingham |  | B35 7QG |  | Miss S Amos | 0121 7767185 | 07565262978 | sheryll123@hotmail.co.uk |  | Windows & Doors | S Burgess
12 |  | 70572 |  | COMMENCEMENT PENDING |  | 29 | Sopwith Croft | Birmingham |  | B35 7QG |  | Miss L S Amos |  |  | louiseamos13@yahoo.com |  | Windows & Doors | S Burgess
12 |  | 60024 |  | COMMENCEMENT PENDING |  | 31 | Sopwith Croft | Birmingham |  | B35 7QG |  | Mrs T Weaver | 0121 747 6453 |  |  |  | Windows & Doors | S Burgess
12 |  | 67652 |  | COMMENCEMENT PENDING |  | 37 | Sopwith Croft | Birmingham |  | B35 7QG |  | Mr C Wood | 07766191349 |  | cwood2866@gmail.com |  | Windows & Doors | S Burgess
12 |  | 70319 |  | COMMENCEMENT PENDING |  | 39 | Sopwith Croft | Birmingham |  | B35 7QG |  | Miss H Ellis |  | 07514 040955 |  |  | Windows & Doors | S Burgess
12 |  | 60025 |  | COMMENCEMENT PENDING |  | 53 | Sopwith Croft | Birmingham |  | B35 7QG |  | Miss L Cooksey | 0121 748 4750 |  |  |  | Windows & Doors | S Burgess
12 |  | 64647 |  | COMMENCEMENT PENDING |  | 57 | Sopwith Croft | Birmingham |  | B35 7QG |  | Miss P Hollis |  | 07958515346 |  |  | Windows & Doors | S Burgess
12 |  | 56586 |  | COMMENCEMENT PENDING |  | 61 | Sopwith Croft | Birmingham |  | B35 7QG |  | Mrs B Higgs |  |  |  |  | Windows & Doors | S Burgess
12 |  | 60817 |  | COMMENCEMENT PENDING |  | 65 | Sopwith Croft | Birmingham |  | B35 7QG |  | Mrs S Lloyd | 01217492988 | 07969945108 | lottyone@hotmail.co.uk |  | Windows & Doors | S Burgess
12 |  | 68906 |  | COMMENCEMENT PENDING |  | 81 | Sopwith Croft | Birmingham |  | B35 7QG |  | Mrs M J Elliker | 07519 199439 |  | melissa.elliker@yahoo.co.uk |  | Windows & Doors | S Burgess
12 |  | 61457 |  | COMMENCEMENT PENDING |  | 83 | Sopwith Croft | Birmingham |  | B35 7QG |  | Mrs J Newall |  |  |  |  | Windows & Doors | S Burgess
12 |  | 62407 |  | COMMENCEMENT PENDING |  | 85 | Sopwith Croft | Birmingham |  | B35 7QG |  | Mr D Gee |  | 07488237065 | donald1@sky.com |  | Windows & Doors | S Burgess
12 |  | 64594 |  | COMMENCEMENT PENDING |  | 87 | Sopwith Croft | Birmingham |  | B35 7QG |  | Mr A Dunn | 0121 748 6208 |  |  |  | Windows & Doors | S Burgess
12 |  | 68315 |  | COMMENCEMENT PENDING |  | 89 | Sopwith Croft | Birmingham |  | B35 7QG |  | Mr S Hughes | 07968931400 | 07968931400 |  |  | Windows & Doors | S Burgess
12 |  | 65838 |  | COMMENCEMENT PENDING |  | 22 | Sopwith Croft | Birmingham |  | B35 7QH |  | Ms L Kelly |  | 07495 596 337 | lisakelly739@gmail.com |  | Windows & Doors | S Burgess |  |  |  |  | 08/07 SMS text sent for 25/07. 08/07 SMS tenant declined 25/07
12 |  | 56949 |  | COMMENCEMENT PENDING |  | 28 | Sopwith Croft | Birmingham |  | B35 7QH |  | Mrs J Line | 01217492634 | 07858769574 | janet.line11@gmail.com |  | Windows & Doors | S Burgess
12 |  | 63305 |  | COMMENCEMENT PENDING |  | 32 | Sopwith Croft | Birmingham |  | B35 7QH |  | Miss J Bazyluk |  | 07808070518 | joanna.bazyluk1@googlamail.com |  | Windows & Doors | S Burgess
12 |  | 56958 |  | COMMENCEMENT PENDING |  | 34 | Sopwith Croft | Birmingham |  | B35 7QH |  | Miss J Dean |  | 07833114938 | joannedean@live.co.uk |  | Windows & Doors | S Burgess
12 |  | 56960 |  | COMMENCEMENT PENDING |  | 36 | Sopwith Croft | Birmingham |  | B35 7QH |  | Mr D Robertson | 01217493959 | 07553 058 845 |  |  | Windows & Doors | S Burgess
12 |  | 69789 |  | COMMENCEMENT PENDING |  | 40 | Sopwith Croft | Birmingham |  | B35 7QH |  | Miss C Anderson | 07415808906 | 07415 808906 | carla9069@gmail.com |  | Windows & Doors | S Burgess
12 |  | 61461 |  | COMMENCEMENT PENDING |  | 1 | Squadron Close | Birmingham |  | B35 7PF |  | Miss T Lamb | 0121 749 2750 |  | thereselamb@hotmail.com |  | Windows & Doors
12 |  | 69748 |  | COMMENCEMENT PENDING |  | 3 | Squadron Close | Birmingham |  | B35 7PF |  | Ms K Wolfe |  | 07724557156 | thyone@02.pl |  | Windows & Doors
12 |  | 66306 |  | COMMENCEMENT PENDING |  | 5 | Squadron Close | Birmingham |  | B35 7PF |  | Miss S O'Donnell |  | 07957 597109 | callum1rio2010@gmail.com |  | Windows & Doors
12 |  | 61463 |  | COMMENCEMENT PENDING |  | 6 | Squadron Close | Birmingham |  | B35 7PF |  | Mr P MacDonald | 07909808711 |  |  |  | Windows & Doors
12 |  | 62567 |  | COMMENCEMENT PENDING |  | 7 | Squadron Close | Birmingham |  | B35 7PF |  | Ms D Charles |  | 07852882252 | carless7@tiscali.co.uk |  | Windows & Doors
12 |  | 69756 |  | COMMENCEMENT PENDING |  | 8 | Squadron Close | Birmingham |  | B35 7PF |  | Miss S J Hayes | 07852 534405 |  | shortyhayes@hotmail.co.uk |  | Windows & Doors
12 |  | 63177 |  | COMMENCEMENT PENDING |  | 9 | Squadron Close | Birmingham |  | B35 7PF |  | Miss C Kingston | 07542132244 | 07951 925 293 |  |  | Windows & Doors
12 |  | 61466 |  | COMMENCEMENT PENDING |  | 10 | Squadron Close | Birmingham |  | B35 7PF |  | Mr C Matthews | 01214936545 | 07572624601 |  |  | Windows & Doors
12 |  | 68777 |  | COMMENCEMENT PENDING |  | 11 | Squadron Close | Birmingham |  | B35 7PF |  | Miss C Dunleavy |  | 07985461189 |  |  | Windows & Doors
12 |  | 63632 |  | COMMENCEMENT PENDING |  | 12 | Squadron Close | Birmingham |  | B35 7PF |  | Mr S Sergeant | 01217486243 | 07984152025 | seamuss@btinternet.com |  | Windows & Doors
12 |  | 64337 |  | COMMENCEMENT PENDING |  | 15 | Squadron Close | Birmingham |  | B35 7PF |  | Miss L J Henry | 01217493767 | 07927332946 | laura-henry486@hotmail.com |  | Windows & Doors
12 |  | 61473 |  | COMMENCEMENT PENDING |  | 17 | Squadron Close | Birmingham |  | B35 7PF |  | Miss S Harding |  | 07435381839 | stuar7466@gmail.com |  | Windows & Doors
12 |  | 61474 |  | COMMENCEMENT PENDING |  | 19 | Squadron Close | Birmingham |  | B35 7PF |  | Mr S Robinson |  |  |  |  | Windows & Doors
12 |  | 61475 |  | COMMENCEMENT PENDING |  | 21 | Squadron Close | Birmingham |  | B35 7PF |  | Miss J Wragg | 07751755597 | 07984689510 |  |  | Windows & Doors
12 |  | 61476 |  | COMMENCEMENT PENDING |  | 23 | Squadron Close | Birmingham |  | B35 7PF |  | Mrs M Green |  | 07572780238 | mandygee1967@yahoo.co.uk |  | Windows & Doors
12 |  | 66887 |  | COMMENCEMENT PENDING |  | 6 | Squiresgate Walk | Birmingham |  | B35 7JL |  | Miss K McGuire | 07734340133 | 07734340133 | KMcGUIRE556@gmail.com |  | Windows & Doors
12 |  | 64297 |  | COMMENCEMENT PENDING |  | 10 | Squiresgate Walk | Birmingham |  | B35 7JL |  | Miss SD Morley |  | 07855 869 675 | sdm74@hotmail.co.uk |  | Windows & Doors
12 |  | 65506 |  | COMMENCEMENT PENDING |  | 12 | Squiresgate Walk | Birmingham |  | B35 7JL |  | Mrs J Thompson |  | 07429679548 | jeni_thompson@live.com |  | Windows & Doors
12 |  | 67691 |  | COMMENCEMENT PENDING |  | 3 | Squiresgate Walk | Birmingham |  | B35 7JN |  | Miss J Morris | 07932004187 |  |  |  | Windows & Doors
12 |  | 56592 |  | COMMENCEMENT PENDING |  | 5 | Squiresgate Walk | Birmingham |  | B35 7JN |  | Miss L O Malley |  | 07555036816 |  |  | Windows & Doors
12 |  | 62728 |  | COMMENCEMENT PENDING |  | 9 | Squiresgate Walk | Birmingham |  | B35 7JN |  | Miss M Turnbull |  |  | mech123@hotmail.co.uk |  | Windows & Doors
12 |  | 70769 |  | COMMENCEMENT PENDING |  | 17 | Squiresgate Walk | Birmingham |  | B35 7JN |  | Mr A Wilson |  | 07711 847 153 | wilson_aaron@live.co.uk |  | Windows & Doors
12 |  | 68279 |  | COMMENCEMENT PENDING |  | 19 | Squiresgate Walk | Birmingham |  | B35 7JN |  | Miss C Purcell | 01216496416 | 07972 566970 |  |  | Windows & Doors
12 |  | 68495 |  | COMMENCEMENT PENDING |  | 35 | St Athan Croft | Birmingham |  | B35 7 LR |  | Mr SD Brady | 07572011095 |  |  |  | Windows & Doors | M Turpin |  |  |  |  | 20/05 SMS sent email for 06/06 / 23.05.24 SF Sent another text. 29/05 SMS called N/A Lttr sent. 06/06 SMs tenant called to cancel.
12 |  | 63547 |  | COMMENCEMENT PENDING |  | 1 | St Athan Croft | Birmingham |  | B35 7LR |  | Mr K L Lee |  | 07951016499 | Kool1kieran@hotmail.com |  | Windows & Doors | M Turpin
12 |  | 65644 |  | COMMENCEMENT PENDING |  | 3 | St Athan Croft | Birmingham |  | B35 7LR |  | Mrs L O'Neill |  | 07879336841 |  |  | Windows & Doors | M Turpin
12 |  | 68893 |  | COMMENCEMENT PENDING |  | 5 | St Athan Croft | Birmingham |  | B35 7LR |  | Ms M Donovan | 07880 616472 |  |  |  | Windows & Doors | M Turpin
12 |  | 67326 |  | COMMENCEMENT PENDING |  | 7 | St Athan Croft | Birmingham |  | B35 7LR |  | Miss T Freeman | 01214066208 | 07883808287 |  |  | Windows & Doors | M Turpin
12 |  | 67632 |  | COMMENCEMENT PENDING |  | 11 | St Athan Croft | Birmingham |  | B35 7LR |  | Mrs T Wilson | 07539 355 313 | 07873790939 | traceywilson120@gmail.com |  | Windows & Doors | M Turpin
12 |  | 65788 |  | COMMENCEMENT PENDING |  | 15 | St Athan Croft | Birmingham |  | B35 7LR |  | Mr S Wright |  | 07388249505 | swright2000@hotmail.co.uk |  | Windows & Doors | M Turpin
12 |  | 68991 |  | COMMENCEMENT PENDING |  | 19 | St Athan Croft | Birmingham |  | B35 7LR |  | Miss S Abazari | 07428 762210 |  | abbazari@gmail.com |  | Windows & Doors | M Turpin
12 |  | 70166 |  | COMMENCEMENT PENDING |  | 21 | St Athan Croft | Birmingham |  | B35 7LR |  | Miss D Ledgister |  | 07729705587 |  |  | Windows & Doors | M Turpin
12 |  | 68473 |  | COMMENCEMENT PENDING |  | 25 | St Athan Croft | Birmingham |  | B35 7LR |  | Miss D Keogh | 07553 201 102 | 07879271002 | keogh77@live.co.uk |  | Windows & Doors | M Turpin
12 |  | 63696 |  | COMMENCEMENT PENDING |  | 27 | St Athan Croft | Birmingham |  | B35 7LR |  | Miss J L Bennett | 07476276911 | 07476 276911 |  |  | Windows & Doors | M Turpin
12 |  | 68626 |  | COMMENCEMENT PENDING |  | 29 | St Athan Croft | Birmingham |  | B35 7LR |  | Miss G Watson | 07840166322 |  |  |  | Windows & Doors | M Turpin
12 |  | 65710 |  | COMMENCEMENT PENDING |  | 31 | St Athan Croft | Birmingham |  | B35 7LR |  | Miss N Tiriboyi | 07460025981 | 07460445512 | ntiriboyi@gmail.com |  | Windows & Doors | M Turpin
12 |  | 66821 |  | COMMENCEMENT PENDING |  | 33 | St Athan Croft | Birmingham |  | B35 7LR |  | Miss A Clarke |  | 07927531878 | ethanclarke@hotmail.com |  | Windows & Doors | M Turpin
12 |  | 60030 |  | COMMENCEMENT PENDING |  | 37 | St Athan Croft | Birmingham |  | B35 7LR |  | Miss R Seeney | 07305871102 |  | BeckiSeeney1@gmail.com |  | Windows & Doors | M Turpin
12 |  | 60032 |  | COMMENCEMENT PENDING |  | 39 | St Athan Croft | Birmingham |  | B35 7LR |  | Miss S Phillips | 07783 554 907 | 07525844749 | devbaylilee@hotmail.com |  | Windows & Doors | M Turpin
12 |  | 69472 |  | COMMENCEMENT PENDING |  | 34 | St Athan Croft | Birmingham |  | B35 7LR |  | Miss C Tafrey |  |  | cynthiatsfrey@hotmail.com |  | Windows & Doors | M Turpin
12 |  | 62638 |  | COMMENCEMENT PENDING |  | 9 | St Athan Croft | Birmingham |  | B35 7LR |  | Ms A L Smith | 01217921072 | 07743301235 | msamanda@hotmail.co.uk |  | Windows & Doors | M Turpin
12 |  | 65970 |  | COMMENCEMENT PENDING |  | FLAT 1 Block 17 | St Athan Croft | Castle Vale |  | B35 7LR |  | Ms A Brake |  | 07591 773 728 | brakeangieo@gmail.com |  | Windows & Doors | M Turpin
12 |  | 64515 |  | COMMENCEMENT PENDING |  | FLAT 2 Block 17 | St Athan Croft | Castle Vale |  | B35 7LR |  | Mr D Brown | 0121 749 5405 | 07935437993 |  |  | Windows & Doors | M Turpin
12 |  | 68863 |  | COMMENCEMENT PENDING |  | FLAT 23 | St Athan Croft | Birmingham |  | B35 7LR |  | Miss KL Carty | 07460 112 729 |  | kl-carty@hotmail.com |  | Windows & Doors | M Turpin
12 |  | 56621 |  | COMMENCEMENT PENDING |  | FLAT 3 Block 17 | St Athan Croft | Castle Vale |  | B35 7LR |  | Mrs R Sullivan | 07773 272 126 |  |  |  | Windows & Doors | M Turpin
12 |  | 56622 |  | COMMENCEMENT PENDING |  | FLAT 4 Block 17 | St Athan Croft | Castle Vale |  | B35 7LR |  | Ms S Simner | 07960115837 | 07780691423 |  |  | Windows & Doors | M Turpin
12 |  | 58153 |  | COMMENCEMENT PENDING |  | FLAT 5 Block 17 | St Athan Croft | Castle Vale |  | B35 7LR |  | Mr R Trimmer |  | 07484787780 |  |  | Windows & Doors | M Turpin
12 |  | 70311 |  | COMMENCEMENT PENDING |  | FLAT 6 Block 17 | St Athan Croft | Castle Vale |  | B35 7LR |  | Mr R King |  | 07851766861 | ryan.king86@hotmail.com |  | Windows & Doors | M Turpin
12 |  | 69260 |  | COMMENCEMENT PENDING |  | 18 | St Athan Croft | Birmingham |  | B35 7LS |  | Miss L Guest |  |  | Leanne.Guest@yahoo.com |  | Windows & Doors | M Turpin
12 |  | 66119 |  | COMMENCEMENT PENDING |  | 20 | St Athan Croft | Birmingham |  | B35 7LS |  | Mr J Pearce | 07465 444 934 | 07923924355 | beccys@hotmail.co.uk |  | Windows & Doors | M Turpin
12 |  | 64728 |  | COMMENCEMENT PENDING |  | 24 | St Athan Croft | Birmingham |  | B35 7LS |  | Mrs J Shambley | 07717322396 | 07485 157654 |  |  | Windows & Doors | M Turpin
12 |  | 56615 |  | COMMENCEMENT PENDING |  | 26 | St Athan Croft | Birmingham |  | B35 7LS |  | Mrs J Byrne |  | 07383004689 |  |  | Windows & Doors | M Turpin
12 |  | 56617 |  | COMMENCEMENT PENDING |  | 28 | St Athan Croft | Birmingham |  | B35 7LS |  | Mr A Davis | 07385694122 |  |  |  | Windows & Doors | M Turpin
12 |  | 68998 |  | COMMENCEMENT PENDING |  | 36 | St Athan Croft | Birmingham |  | B35 7LS |  | Miss D Wright |  | 07821750 700 | demilei13@outlook.com |  | Windows & Doors | M Turpin
12 |  | 66746 |  | COMMENCEMENT PENDING |  | 38 | St Athan Croft | Birmingham |  | B35 7LS |  | Miss S Hamilton |  | 07591359936 | Shantelle_Hamilton@yahoo.co.uk |  | Windows & Doors | M Turpin
12 |  | 69757 |  | COMMENCEMENT PENDING |  | 40 | St Athan Croft | Birmingham |  | B35 7LS |  | Mr F Amin |  | 07479404184 | amintelefonia@yahoo.com |  | Windows & Doors | M Turpin
12 |  | 62895 |  | COMMENCEMENT PENDING |  | 42 | St Athan Croft | Birmingham |  | B35 7LS |  | Miss L Braddish |  | 07798921854 | lesleybraddish@yahoo.com |  | Windows & Doors | M Turpin
12 |  | 65763 |  | COMMENCEMENT PENDING |  | 44 | St Athan Croft | Birmingham |  | B35 7LS |  | Miss L Robinson |  | 07868 609 384 | l.taroni@hotmail.com |  | Windows & Doors | M Turpin
12 |  | 65643 |  | COMMENCEMENT PENDING |  | 46 | St Athan Croft | Birmingham |  | B35 7LS |  | Mrs ZC Mason | 07841350244 |  |  |  | Windows & Doors | M Turpin
12 |  | 67952 |  | COMMENCEMENT PENDING |  | 48 | St Athan Croft | Birmingham |  | B35 7LS |  | Miss A Daniels | 07747467491 |  |  |  | Windows & Doors | M Turpin
12 |  | 62588 |  | COMMENCEMENT PENDING |  | 34A | St Athan Croft | Birmingham |  | B35 7LS |  | Mr B Wallace |  | 07877018921 |  |  | Windows & Doors | M Turpin
12 |  | 66948 |  | COMMENCEMENT PENDING |  | 4 | St Athan Croft | Birmingham |  | B35 7LS |  | Miss M Gee | 07306825568 | 07392 848569 |  |  | Windows & Doors | M Turpin
12 |  | 68609 |  | COMMENCEMENT PENDING |  | FLAT 5 Block 18 | St Mawgan Close | Castle Vale |  | B35 6NR |  | Miss N Hall | 07590406140 |  | naomihall_1993@hotmail.co.uk |  | Windows & Doors
12 |  | 68392 |  | COMMENCEMENT PENDING |  | 68 | St Thomas Road | Birmingham |  | B23 7RG |  | Mr W Jablonski |  | 07466 790707 | wojciechjablonski@gmail.com |  | Windows & Doors
12 |  | 70189 |  | COMMENCEMENT PENDING |  | 72 | St Thomas Road | Birmingham |  | B23 7RG |  | Miss D Kelly |  | 07961548666 | donnaredhill@yahoo.co.uk |  | Windows & Doors
12 |  | 65519 |  | COMMENCEMENT PENDING |  | 91 | Stornoway Road | Birmingham |  | B35 6NJ |  | Miss AM Morgan | 0121 218 1880 | 07595875120 | princessanni@hotmail.co.uk |  | Windows & Doors
12 |  | 69363 |  | COMMENCEMENT PENDING |  | FLAT 52 | Stornoway Road | Birmingham |  | B35 6NS |  | Miss J Lunn | 07504680074 | 07504680074 | jessica_l_1993@hotmail.co.uk |  | Windows & Doors
12 |  | 65925 |  | COMMENCEMENT PENDING |  | 7 | Stornoway Road | Birmingham |  | B35 6PA |  | Mrs K Creighton |  |  |  |  | Windows & Doors
12 |  | 61781 |  | COMMENCEMENT PENDING |  | 12 | Sumburgh Croft | Birmingham |  | B35 6BD |  | Mrs A O'Hara |  | 07817449248 |  |  | Windows & Doors
12 |  | 67894 |  | COMMENCEMENT PENDING |  | 14 | Sumburgh Croft | Birmingham |  | B35 6BD |  | Miss C Jefferies | 077 572 29501 |  |  |  | Windows & Doors
12 |  | 68959 |  | COMMENCEMENT PENDING |  | 65 | Sumburgh Croft | Birmingham |  | B35 6BD |  | Miss C Matthews | 07522583019 | 07539 88 68 74 | charlottematthews@hotmail.com |  | Windows & Doors
12 |  | 56633 |  | COMMENCEMENT PENDING |  | 24 | Sumburgh Croft | Birmingham |  | B35 6DB |  | Mrs C Haycock | 01217471198 | 07858477516 | whiteball_wba@hotmail.com |  | Windows & Doors
12 |  | 56635 |  | COMMENCEMENT PENDING |  | 28 | Sumburgh Croft | Birmingham |  | B35 6DB |  | Mr E Russell | 07874 133 124 |  | linda1980russell@gmail.com |  | Windows & Doors
12 |  | 63637 |  | COMMENCEMENT PENDING |  | 32 | Sumburgh Croft | Birmingham |  | B35 6DB |  | Miss E McGee | 07984311937 |  |  |  | Windows & Doors
12 |  | 62959 |  | COMMENCEMENT PENDING |  | 42 | Sumburgh Croft | Birmingham |  | B35 6DB |  | Miss KA Southcombe |  |  |  |  | Windows & Doors
12 |  | 56657 |  | COMMENCEMENT PENDING |  | FLAT 1 Block 2 | Sumburgh Croft | Castle Vale |  | B35 6DB |  | Mrs M Ludlow | 01217483206 |  |  |  | Windows & Doors
12 |  | 70266 |  | COMMENCEMENT PENDING |  | FLAT 1 Block 48 | Sumburgh Croft | Castle Vale |  | B35 6DB |  | Miss I Richards |  | 07795522420 | richardsina8@gmail.com |  | Windows & Doors
12 |  | 62093 |  | COMMENCEMENT PENDING |  | FLAT 2 Block 2 | Sumburgh Croft | Castle Vale |  | B35 6DB |  | Miss S M Purcell |  | 07884939342 |  |  | Windows & Doors
12 |  | 67919 |  | COMMENCEMENT PENDING |  | FLAT 2 Block 48 | Sumburgh Croft | Castle Vale |  | B35 6DB |  | Mr C Vann | 07904058292 | 07904058292 |  |  | Windows & Doors
12 |  | 60812 |  | COMMENCEMENT PENDING |  | FLAT 3 Block 2 | Sumburgh Croft | Castle Vale |  | B35 6DB |  | Ms SL Wiggett |  | 07835 926 500 | cater_sharon@yahoo.co.uk |  | Windows & Doors
12 |  | 60837 |  | COMMENCEMENT PENDING |  | FLAT 3 Block 48 | Sumburgh Croft | Castle Vale |  | B35 6DB |  | Mr J Arundel | 01217497356 |  | johnarundel003@gmail.com |  | Windows & Doors
12 |  | 56660 |  | COMMENCEMENT PENDING |  | FLAT 4 Block 2 | Sumburgh Croft | Castle Vale |  | B35 6DB |  | Mr P Coope | 0121 574 2835 |  |  |  | Windows & Doors
12 |  | 70006 |  | COMMENCEMENT PENDING |  | FLAT 5 Block 2 | Sumburgh Croft | Castle Vale |  | B35 6DB |  | Miss C Woodhall |  | 07723635378 | chantellelouisew93@icloud.com |  | Windows & Doors
12 |  | 67976 |  | COMMENCEMENT PENDING |  | FLAT 5 Block 48 | Sumburgh Croft | Castle Vale |  | B35 6DB |  | Mr S Doherty | 07841377911 | 07841377911 | seandoherty1969@yahoo.co.uk |  | Windows & Doors
12 |  | 68956 |  | COMMENCEMENT PENDING |  | FLAT 6 Block 2 | Sumburgh Croft | Castle Vale |  | B35 6DB |  | Miss J Walsh |  | 07565 441 823 |  |  | Windows & Doors
12 |  | 69424 |  | COMMENCEMENT PENDING |  | FLAT 6 Block 48 | Sumburgh Croft | Castle Vale |  | B35 6DB |  | Miss B Jones | 01217486740 | 07734972188 | beverleym.j1210@yahoo.com |  | Windows & Doors
12 |  | 65537 |  | COMMENCEMENT PENDING |  | 23 | Sumburgh Croft | Birmingham |  | B35 6DD |  | Miss A Brooks | 07719572822 |  |  |  | Windows & Doors
12 |  | 57373 |  | COMMENCEMENT PENDING |  | 25 | Sumburgh Croft | Birmingham |  | B35 6DD |  | Mrs V Bate | 07546256116 |  | vanessabate@hotmail.co.uk |  | Windows & Doors
12 |  | 68122 |  | COMMENCEMENT PENDING |  | 29 | Sumburgh Croft | Birmingham |  | B35 6DE |  | Miss A Muhamed | 07599972720 | 07365989014 |  |  | Windows & Doors
12 |  | 56637 |  | COMMENCEMENT PENDING |  | 31 | Sumburgh Croft | Birmingham |  | B35 6DE |  | Mrs T Harvey | 01217479524 |  | tiddy1966@aol.com |  | Windows & Doors
12 |  | 56639 |  | COMMENCEMENT PENDING |  | 33 | Sumburgh Croft | Birmingham |  | B35 6DE |  | Mr S McDonald | 07867565269 |  |  |  | Windows & Doors
12 |  | 56640 |  | COMMENCEMENT PENDING |  | 35 | Sumburgh Croft | Birmingham |  | B35 6DE |  | Mr B Brown |  | 07939027605 |  |  | Windows & Doors
12 |  | 68979 |  | COMMENCEMENT PENDING |  | 41 | Sumburgh Croft | Birmingham |  | B35 6DE |  | Miss S Edmunds |  | 07510711608 |  |  | Windows & Doors
12 |  | 64847 |  | COMMENCEMENT PENDING |  | 47 | Sumburgh Croft | Birmingham |  | B35 6DE |  | Miss M P Norman |  | 0784 664 3158 | malibu22@sky.com |  | Windows & Doors
12 |  | 56646 |  | COMMENCEMENT PENDING |  | 49 | Sumburgh Croft | Birmingham |  | B35 6DE |  | Miss M Anderson |  | 07824 154 651 |  |  | Windows & Doors
12 |  | 68387 |  | COMMENCEMENT PENDING |  | 51 | Sumburgh Croft | Birmingham |  | B35 6DE |  | Miss J Roberts |  | 07873 592 968 | jade16374@gmail.com |  | Windows & Doors
12 |  | 56649 |  | COMMENCEMENT PENDING |  | 59 | Sumburgh Croft | Birmingham |  | B35 6DE |  | Mr S Austin |  | 07711998579 |  |  | Windows & Doors
12 |  | 69890 |  | COMMENCEMENT PENDING |  | 63 | Sumburgh Croft | Birmingham |  | B35 6DE |  | Miss S Kelly |  | 07774044702 | sharinakelly@yahoo.com |  | Windows & Doors
12 |  | 70155 |  | COMMENCEMENT PENDING |  | 71 | Sumburgh Croft | Birmingham |  | B35 6DE |  | Miss J Simpson | 01213580355 | 07886016973 | jessica.simpson18@hotmail.co.uk |  | Windows & Doors
12 |  | 70032 |  | COMMENCEMENT PENDING |  | 79 | Sumburgh Croft | Birmingham |  | B35 6DE |  | Miss K Jacobson | 0121 537 0237 | 07793116111 | karenlj3@sky.com |  | Windows & Doors
12 |  | 65088 |  | COMMENCEMENT PENDING |  | 81 | Sumburgh Croft | Birmingham |  | B35 6DE |  | Miss Z Smart |  | 07454104183 |  |  | Windows & Doors
12 |  | 68204 |  | COMMENCEMENT PENDING |  | 83 | Sumburgh Croft | Birmingham |  | B35 6DE |  | Ms S Akhtar |  | 07577 848557 | Angel_sam543@hotmail.co.uk |  | Windows & Doors
12 |  | 70491 |  | COMMENCEMENT PENDING |  | 85 | Sumburgh Croft | Birmingham |  | B35 6DE |  | Ms A Johnson |  | 07747759919 | leshy1006@gmail.com |  | Windows & Doors
12 |  | 65177 |  | COMMENCEMENT PENDING |  | 87 | Sumburgh Croft | Birmingham |  | B35 6DE |  | Miss W Lamey | 07961786181 | 07961786181 | wendy1004@hotmail.co.uk |  | Windows & Doors
12 |  | 63805 |  | COMMENCEMENT PENDING |  | 357 | Tangmere Drive | Birmingham |  | B35 7PU |  | Mrs R Humpage |  | 07951421886 |  |  | Windows & Doors
12 |  | 64450 |  | COMMENCEMENT PENDING |  | 359 | Tangmere Drive | Birmingham |  | B35 7PU |  | Miss K Stone |  | 07908 606 266 | kimmysto2@yahoo.co.uk |  | Windows & Doors
12 |  | 56693 |  | COMMENCEMENT PENDING |  | 363 | Tangmere Drive | Birmingham |  | B35 7PU |  | Mr R Gumbley |  | 07833130989 | redronvilla@hotmail.co.uk |  | Windows & Doors
12 |  | 64690 |  | COMMENCEMENT PENDING |  | 365 | Tangmere Drive | Birmingham |  | B35 7PU |  | Mrs A Rock |  | 07845892405 | amandarock1979@live.co.uk |  | Windows & Doors
12 |  | 61643 |  | COMMENCEMENT PENDING |  | 277 | Tangmere Drive | Birmingham |  | B35 7PX |  | Mrs N L Fox | 01212573938 | 07960146732 | nattydred277@hotmail.co.uk |  | Windows & Doors
12 |  | 56681 |  | COMMENCEMENT PENDING |  | 281 | Tangmere Drive | Birmingham |  | B35 7PX |  | Miss C A McCracken | 07528 821 444 |  | cath3@live.co.uk |  | Windows & Doors
12 |  | 70109 |  | COMMENCEMENT PENDING |  | 283 | Tangmere Drive | Birmingham |  | B35 7PX |  | Miss K Edwards |  | 07972778800 | kelly.e1@live.co.uk |  | Windows & Doors
12 |  | 69146 |  | COMMENCEMENT PENDING |  | 287 | Tangmere Drive | Birmingham |  | B35 7PX |  | Mr A Arosh | 07741318496 |  | aboudarosh@hotmail.com |  | Windows & Doors
12 |  | 69916 |  | COMMENCEMENT PENDING |  | 313 | Tangmere Drive | Birmingham |  | B35 7PX |  | Miss S Cherry |  | 07818216292 | sharmanecherry88@gmail.com |  | Windows & Doors
12 |  | 70512 |  | COMMENCEMENT PENDING |  | 315 | Tangmere Drive | Birmingham |  | B35 7PX |  | Mrs K Afrin |  |  | k.afrin125@gmail.com |  | Windows & Doors
12 |  | 57289 |  | COMMENCEMENT PENDING |  | 319 | Tangmere Drive | Birmingham |  | B35 7PX |  | Miss L J Rickus | 0121 747 0597 |  | lynrickus@yahoo.com |  | Windows & Doors
12 |  | 67608 |  | COMMENCEMENT PENDING |  | 321 | Tangmere Drive | Birmingham |  | B35 7PX |  | Miss M Baggott | 07754283296 | 07754283296 |  |  | Windows & Doors
12 |  | 57454 |  | COMMENCEMENT PENDING |  | 327 | Tangmere Drive | Birmingham |  | B35 7PX |  | Mr M Grenham |  | 07986 315048 |  |  | Windows & Doors
12 |  | 70668 |  | COMMENCEMENT PENDING |  | 329 | Tangmere Drive | Birmingham |  | B35 7PX |  | Mrs S Dean | 07745682685 | 07754 139337 | S.DEAN222328@GMAIL.COM |  | Windows & Doors
12 |  | 56690 |  | COMMENCEMENT PENDING |  | 331 | Tangmere Drive | Birmingham |  | B35 7PX |  | Mrs A Manley | 01217301255 |  |  |  | Windows & Doors
12 |  | 66876 |  | COMMENCEMENT PENDING |  | 333 | Tangmere Drive | Birmingham |  | B35 7PX |  | Mr M Arifi |  | 074505 66075 | basir1343@hotmail.com |  | Windows & Doors
12 |  | 60047 |  | COMMENCEMENT PENDING |  | 335 | Tangmere Drive | Birmingham |  | B35 7PX |  | Miss J Wood |  | 07425310252 |  |  | Windows & Doors
12 |  | 60045 |  | COMMENCEMENT PENDING |  | 309 | Tangmere Drive | Birmingham |  | B35 7PX |  | Miss Y Morton | 01217473620 | 07597515472 | yasmin_morton@yahoo.co.uk |  | Windows & Doors
12 |  | 60046 |  | COMMENCEMENT PENDING |  | 311 | Tangmere Drive | Birmingham |  | B35 7PX |  | Mr T Harvey |  | 07398227052 |  |  | Windows & Doors
12 |  | 59437 |  | COMMENCEMENT PENDING |  | 263 | Tangmere Drive | Birmingham |  | B35 7PY |  | Mrs B Richardson | 0121 478 4287 | 07814711293 | usintheuk@usintheuk.co.uk |  | Windows & Doors
12 |  | 56679 |  | COMMENCEMENT PENDING |  | 267 | Tangmere Drive | Birmingham |  | B35 7PY |  | Mr J Simms | 0121 776 7634 |  | bob22nab@aol.com |  | Windows & Doors
12 |  | 64493 |  | COMMENCEMENT PENDING |  | 217 | Tangmere Drive | Birmingham |  | B35 7QA |  | Ms J Nikiforova | 01214487105 | 07760896247 | jane.niki@hotmail.co.uk |  | Windows & Doors
12 |  | 63787 |  | COMMENCEMENT PENDING |  | 219 | Tangmere Drive | Birmingham |  | B35 7QA |  | Miss AJ Williams | 01212406498 | 07446 903 292 |  |  | Windows & Doors
12 |  | 70265 |  | COMMENCEMENT PENDING |  | 223 | Tangmere Drive | Birmingham |  | B35 7QA |  | Mr R Goodall | 01217492456 | 07876 224 376 |  |  | Windows & Doors
12 |  | 61483 |  | COMMENCEMENT PENDING |  | 225 | Tangmere Drive | Birmingham |  | B35 7QA |  | Mr D Joseph |  | 07869 393636 | jenrow@hotmail.co.uk |  | Windows & Doors
12 |  | 60038 |  | COMMENCEMENT PENDING |  | 227 | Tangmere Drive | Birmingham |  | B35 7QA |  | Miss K Duffy |  |  |  |  | Windows & Doors
12 |  | 70060 |  | COMMENCEMENT PENDING |  | 229 | Tangmere Drive | Birmingham |  | B35 7QA |  | Mrs K Joyce |  | 07702076756 |  |  | Windows & Doors
12 |  | 60040 |  | COMMENCEMENT PENDING |  | 231 | Tangmere Drive | Birmingham |  | B35 7QA |  | Mr A Gough |  |  |  |  | Windows & Doors
12 |  | 69563 |  | COMMENCEMENT PENDING |  | 233 | Tangmere Drive | Birmingham |  | B35 7QA |  | Miss E Hemming |  | 07938 880 752 | keltagph@outlook.com |  | Windows & Doors
12 |  | 67673 |  | COMMENCEMENT PENDING |  | 235 | Tangmere Drive | Birmingham |  | B35 7QA |  | Miss L Machin |  | 07496341192 |  |  | Windows & Doors
12 |  | 64066 |  | COMMENCEMENT PENDING |  | 237 | Tangmere Drive | Birmingham |  | B35 7QA |  | Miss E Flynn |  | 07814790594 |  |  | Windows & Doors
12 |  | 60044 |  | COMMENCEMENT PENDING |  | 239 | Tangmere Drive | Birmingham |  | B35 7QA |  | Miss S Pearce | 07508 463058 |  | suzette239@hotmail.com |  | Windows & Doors
12 |  | 61479 |  | COMMENCEMENT PENDING |  | 215 | Tangmere Drive | Birmingham |  | B35 7QA |  | Mr L Barrett | 01217484899 |  |  |  | Windows & Doors
12 |  | 65513 |  | COMMENCEMENT PENDING |  | 93 | Tangmere Drive | Birmingham |  | B35 7QD |  | Miss G Weare |  | 07958396451 |  |  | Windows & Doors
12 |  | 63350 |  | COMMENCEMENT PENDING |  | 105 | Tangmere Drive | Birmingham |  | B35 7QD |  | Miss R Hetherington | 07933200381 | 0121 748 5301 | raychelhetherington@googlemail.com |  | Windows & Doors
12 |  | 63542 |  | COMMENCEMENT PENDING |  | 103 | Tangmere Drive | Birmingham |  | B35 7QD |  | Miss D Jarrett |  | 07958 164 995 | dfjarrett7@gmail.com |  | Windows & Doors
12 |  | 69031 |  | COMMENCEMENT PENDING |  | 73 | Tangmere Drive | Birmingham |  | B35 7QE |  | Miss R Williams | 07728 548 096 | 07462922273 |  |  | Windows & Doors
12 |  | 64466 |  | COMMENCEMENT PENDING |  | 51 | Tangmere Drive | Birmingham |  | B35 7QJ |  | Mrs D Moore | 07872478206 |  | donna_moore1972@hotmail.co.uk |  | Windows & Doors
12 |  | 64943 |  | COMMENCEMENT PENDING |  | 53 | Tangmere Drive | Birmingham |  | B35 7QJ |  | Miss N Rose |  | 07702215493 | nadz_rose@hotmail.co.uk |  | Windows & Doors
12 |  | 56674 |  | COMMENCEMENT PENDING |  | 57 | Tangmere Drive | Birmingham |  | B35 7QJ |  | Miss K Whale | 07548 802 796 | 0121 493 9694 | karenwhale01@live.co.uk |  | Windows & Doors
12 |  | 58293 |  | COMMENCEMENT PENDING |  | FLAT 43 | Tangmere Drive | Birmingham |  | B35 7QJ |  | Mrs R Perkins |  |  |  |  | Windows & Doors
12 |  | 70444 |  | COMMENCEMENT PENDING |  | FLAT 47 | Tangmere Drive | Birmingham |  | B35 7QJ |  | Miss S Maddah |  | 07988453349 | smaddah@hotmail.co.uk |  | Windows & Doors
12 |  | 64874 |  | COMMENCEMENT PENDING |  | FLAT 49 | Tangmere Drive | Birmingham |  | B35 7QJ |  | Mr L Johnson | 07738825436 |  |  |  | Windows & Doors
12 |  | 65070 |  | COMMENCEMENT PENDING |  | 135 | Tangmere Drive | Birmingham |  | B35 7QW |  | Mrs I J Jackson | 0121 572 0556 | 07535 412 256 |  |  | Windows & Doors
12 |  | 63377 |  | COMMENCEMENT PENDING |  | 137 | Tangmere Drive | Birmingham |  | B35 7QW |  | Mr J T James |  | 07932 607 988 |  |  | Windows & Doors
12 |  | 67674 |  | COMMENCEMENT PENDING |  | 139 | Tangmere Drive | Birmingham |  | B35 7QW |  | Mr P Carter |  | 07495993866 |  |  | Windows & Doors
12 |  | 68865 |  | COMMENCEMENT PENDING |  | 141 | Tangmere Drive | Birmingham |  | B35 7QW |  | Mr I Knights |  | 07756749571 | ian.knight2k16@gmail.com |  | Windows & Doors
12 |  | 68990 |  | COMMENCEMENT PENDING |  | 143 | Tangmere Drive | Birmingham |  | B35 7QW |  | Mrs M Sheridan | 07599 613 890 | 07599 613 890 |  |  | Windows & Doors
12 |  | 66148 |  | COMMENCEMENT PENDING |  | 145 | Tangmere Drive | Birmingham |  | B35 7QW |  | Mrs L Ross-Jinks |  | 07485 117 510 | lesleyjinks@hotmail.com |  | Windows & Doors
12 |  | 69422 |  | COMMENCEMENT PENDING |  | 147 | Tangmere Drive | Birmingham |  | B35 7QW |  | Mrs C Daley |  | 07512618019 | christinedaley12@hotmail.co.uk |  | Windows & Doors
12 |  | 70432 |  | COMMENCEMENT PENDING |  | 149 | Tangmere Drive | Birmingham |  | B35 7QW |  | Mr M Proctor |  | 07377 614 294 |  |  | Windows & Doors
12 |  | 63931 |  | COMMENCEMENT PENDING |  | 151 | Tangmere Drive | Birmingham |  | B35 7QW |  | Mrs C Mitchell |  | 0774 908 5932 |  |  | Windows & Doors
12 |  | 70466 |  | COMMENCEMENT PENDING |  | FLAT 3 | The Hennalls | Birmingham |  | B36 8NJ |  | Miss G Asher |  |  | gemasher3@gmail.com |  | Windows & Doors
12 |  | 64282 |  | COMMENCEMENT PENDING |  | 17 | Trident Boulevard | Birmingham |  | B35 7LZ |  | Mrs J Sheppard | 07754238957 |  | janet.1959@hotmail.com |  | Windows & Doors | M Turpin |  | 8am to 2pm |  |  | 19/6; AC text for 2/7 and emailed. TENANT CANCELLED AS NOT HOME THIS DATE.
12 |  | 66810 |  | COMMENCEMENT PENDING |  | 20 | Trident Boulevard | Birmingham |  | B35 7LZ |  | Miss M G Bourne | 07725346049 | 07897582846 | moniquebourne321@gmail.com |  | Windows & Doors | M Turpin |  | 8am to 2pm |  | 1 | 19/6; AC text for 2/7 and emailed. 21/6; AC rang LM AND SENT LETTER. 2/7; tenant would not allow survey, maybe next week.
12 |  | 61709 |  | COMMENCEMENT PENDING |  | 26 | Trident Boulevard | Birmingham |  | B35 7LZ |  | Mrs D M Conlan | 0121 748 6786 | 07906 580 909 | dawn-mark@tiscali.co.uk |  | Windows & Doors | M Turpin | Not Tuesdays |  |  |  | 24/06 SMS text sent for 09/07. Tenant declined this date.
12 |  | 61196 |  | COMMENCEMENT PENDING |  | 161 | Turnhouse Road | Birmingham |  | B35 6LT |  | Mrs M Franks |  |  |  |  | Windows & Doors
12 |  | 56782 |  | COMMENCEMENT PENDING |  | 153 | Turnhouse Road | Birmingham |  | B35 6LY |  | Mrs S Carr |  | 0785 0 886 957 | noneavailable@cvch.co.uk |  | Windows & Doors
12 |  | 56780 |  | COMMENCEMENT PENDING |  | 29 | Turnhouse Road | Birmingham |  | B35 6PT |  | Mrs J Protheroe |  | 07986 011 534 |  |  | Windows & Doors
12 |  | 56781 |  | COMMENCEMENT PENDING |  | 33 | Turnhouse Road | Birmingham |  | B35 6PT |  | Mr B Scott | 01215724012 | 07739455174 | lessnesscott@live.co.uk |  | Windows & Doors
12 |  | 64019 |  | COMMENCEMENT PENDING |  | 19 | Upavon Close | Birmingham |  | B35 6BH |  | Miss K Jackson |  | 07977 749 945 |  |  | Windows & Doors
12 |  | 68640 |  | COMMENCEMENT PENDING |  | 21 | Upavon Close | Birmingham |  | B35 6BH |  | Miss S J Heath | 0121 749 4321 | 07712205961 |  |  | Windows & Doors
12 |  | 66079 |  | COMMENCEMENT PENDING |  | 23 | Upavon Close | Birmingham |  | B35 6BH |  | Miss C Jones |  | 07341251240 |  |  | Windows & Doors
12 |  | 56786 |  | COMMENCEMENT PENDING |  | 4 | Upavon Close | Birmingham |  | B35 6BJ |  | Mrs S Kinghorn |  |  |  |  | Windows & Doors
12 |  | 69410 |  | COMMENCEMENT PENDING |  | 6 | Upavon Close | Birmingham |  | B35 6BJ |  | Miss S Edmunds | 07908233619 |  |  |  | Windows & Doors
12 |  | 56791 |  | COMMENCEMENT PENDING |  | 14 | Upavon Close | Birmingham |  | B35 6BJ |  | Miss A Brennan |  | 07890 795 986 |  |  | Windows & Doors
12 |  | 66990 |  | COMMENCEMENT PENDING |  | 20 | Upavon Close | Birmingham |  | B35 6BJ |  | Mrs C Payne |  | 07874142269 | leopardprintmomma@gmail.com |  | Windows & Doors
12 |  | 65250 |  | COMMENCEMENT PENDING |  | 26 | Upavon Close | Birmingham |  | B35 6BJ |  | Miss S Smith |  | 07598166151 |  |  | Windows & Doors
12 |  | 56795 |  | COMMENCEMENT PENDING |  | 2 | Valencia Croft | Birmingham |  | B35 7PH |  | Miss L Johnson | 07928 615 785 |  |  |  | Windows & Doors
12 |  | 69022 |  | COMMENCEMENT PENDING |  | 3 | Valencia Croft | Birmingham |  | B35 7PH |  | Miss S Dale |  |  |  |  | Windows & Doors
12 |  | 56797 |  | COMMENCEMENT PENDING |  | 5 | Valencia Croft | Birmingham |  | B35 7PH |  | Mrs A V Jeffrey | 07775589878 |  |  |  | Windows & Doors
12 |  | 56798 |  | COMMENCEMENT PENDING |  | 7 | Valencia Croft | Birmingham |  | B35 7PH |  | Miss C Meah | 01217496185 | 07518693196 | natalieMeahMorgan@Live.Com |  | Windows & Doors
12 |  | 69243 |  | COMMENCEMENT PENDING |  | 8 | Valencia Croft | Birmingham |  | B35 7PH |  | Miss K M McCormack |  | 07599955030 | macca1382@icloud.com |  | Windows & Doors
12 |  | 56800 |  | COMMENCEMENT PENDING |  | 9 | Valencia Croft | Birmingham |  | B35 7PH |  | Mr M Yates |  | 07935308546 |  |  | Windows & Doors
12 |  | 69242 |  | COMMENCEMENT PENDING |  | 10 | Valencia Croft | Birmingham |  | B35 7PH |  | Mr T Walsh |  | 07300906811 | tomwalsh240487@gmail.com |  | Windows & Doors
12 |  | 60050 |  | COMMENCEMENT PENDING |  | 11 | Valencia Croft | Birmingham |  | B35 7PH |  | Miss M Mitchell |  | 07864268879 |  |  | Windows & Doors
12 |  | 69432 |  | COMMENCEMENT PENDING |  | 15 | Valencia Croft | Birmingham |  | B35 7PH |  | Miss M Waite | 01212474356 | 07470 670 356 |  |  | Windows & Doors
12 |  | 62184 |  | COMMENCEMENT PENDING |  | 16 | Valencia Croft | Birmingham |  | B35 7PH |  | Miss T Coombs | 07498 705657 |  |  |  | Windows & Doors
12 |  | 69522 |  | COMMENCEMENT PENDING |  | 22 | Valencia Croft | Birmingham |  | B35 7PH |  | Miss R L Perks |  | 07916637477 |  |  | Windows & Doors
12 |  | 56807 |  | COMMENCEMENT PENDING |  | 23 | Valencia Croft | Birmingham |  | B35 7PH |  | Miss C Webb | 07725 125 512 |  |  |  | Windows & Doors
12 |  | 63716 |  | COMMENCEMENT PENDING |  | 25 | Valencia Croft | Birmingham |  | B35 7PH |  | Miss R Woolgrove |  | 07484860147 |  |  | Windows & Doors
12 |  | 66812 |  | COMMENCEMENT PENDING |  | 26 | Valencia Croft | Birmingham |  | B35 7PH |  | Miss A Forknall | 07375514086 | 07960665981 | alex.forknall@hotmail.co.uk |  | Windows & Doors
12 |  | 67465 |  | COMMENCEMENT PENDING |  | 27 | Valencia Croft | Birmingham |  | B35 7PH |  | Miss R Western | 01212407439 | 07792018428 | rwestern18@blueyonder.co.uk |  | Windows & Doors
12 |  | 56810 |  | COMMENCEMENT PENDING |  | 28 | Valencia Croft | Birmingham |  | B35 7PH |  | Miss S Cooney |  | 07724 308 477 |  |  | Windows & Doors
12 |  | 61493 |  | COMMENCEMENT PENDING |  | 30 | Valencia Croft | Birmingham |  | B35 7PH |  | Miss P Lambert | 07889 267 872 |  | valenciakola@yahoo.co.uk |  | Windows & Doors
12 |  | 68355 |  | COMMENCEMENT PENDING |  | 32 | Valencia Croft | Birmingham |  | B35 7PH |  | Mrs B Taylor | 07449 353 058 | 07449 353 058 | 3dimondgirl2015@gmail.com |  | Windows & Doors
12 |  | 70151 |  | COMMENCEMENT PENDING |  | 35 | Valencia Croft | Birmingham |  | B35 7PH |  | Miss A Willetts | 07570363184 |  | amywilletts20@hotmail.co.uk |  | Windows & Doors
12 |  | 56812 |  | COMMENCEMENT PENDING |  | 37 | Valencia Croft | Birmingham |  | B35 7PH |  | Mrs K Harding |  | 07773552899 |  |  | Windows & Doors
12 |  | 64256 |  | COMMENCEMENT PENDING |  | 4 | Viscount | Birmingham |  | B35 7JQ |  | Mr E Key | 01217497124 |  |  |  | Windows & Doors
12 |  | 70711 |  | COMMENCEMENT PENDING |  | 1 | Viscount Close | Birmingham |  | B35 7JQ |  | Mr K Costello | 07899822438 |  | kevincostek24@gmail.com |  | Windows & Doors
12 |  | 70546 |  | COMMENCEMENT PENDING |  | 2 | Viscount Close | Birmingham |  | B35 7JQ |  | Mr M Murphy | 07957414697 |  | 'murphy.martin41@gmail.com' |  | Windows & Doors
12 |  | 70577 |  | COMMENCEMENT PENDING |  | 3 | Viscount Close | Birmingham |  | B35 7JQ |  | Miss E Meadows | 07900204364 |  | elizabethm8452@gmail.com |  | Windows & Doors
12 |  | 65562 |  | COMMENCEMENT PENDING |  | 5 | Viscount Close | Birmingham |  | B35 7JQ |  | Miss N H Nakawooya |  | 07852 105573 | anniekay92@yahoo.com |  | Windows & Doors
12 |  | 66954 |  | COMMENCEMENT PENDING |  | 6 | Viscount Close | Birmingham |  | B35 7JQ |  | Miss A Speed |  | 07940 209869 | alspeed@hotmail.co.uk |  | Windows & Doors
12 |  | 60083 |  | COMMENCEMENT PENDING |  | 8 | Viscount Close | Birmingham |  | B35 7JQ |  | Miss T Pittaway | 0121 4391542 | 07729 954 455 | trudynude@hotmail.com |  | Windows & Doors
12 |  | 67568 |  | COMMENCEMENT PENDING |  | 10 | Viscount Close | Birmingham |  | B35 7JQ |  | Miss S Ford | 0121 241 2775 | 07399394432 | trei679@gmail.com |  | Windows & Doors
12 |  | 70446 |  | COMMENCEMENT PENDING |  | 12 | Viscount Close | Birmingham |  | B35 7JQ |  | Miss S Murtagh |  | 07542990489 | steph_steve91@hotmail.com |  | Windows & Doors
12 |  | 68344 |  | COMMENCEMENT PENDING |  | 14 | Viscount Close | Birmingham |  | B35 7JQ |  | Ms T Ahmed |  | 07966910315 | tia-27@hotmail.co.uk |  | Windows & Doors
12 |  | 66989 |  | COMMENCEMENT PENDING |  | 16 | Viscount Close | Birmingham |  | B35 7JQ |  | Mrs S J Prichard |  | 07510690091 | staceyprichard@hotmail.co.uk |  | Windows & Doors
12 |  | 67543 |  | COMMENCEMENT PENDING |  | 17 | Viscount Close | Birmingham |  | B35 7JQ |  | Mr Z Timar | 07395 466 669 | 07886864381 |  |  | Windows & Doors
12 |  | 60453 |  | COMMENCEMENT PENDING |  | 18 | Viscount Close | Birmingham |  | B35 7JQ |  | Miss D Reilly | 0121 250 7071 | 07858 166 994 | ladydonna416@gmail.com |  | Windows & Doors
12 |  | 64051 |  | COMMENCEMENT PENDING |  | 19 | Viscount Close | Birmingham |  | B35 7JQ |  | Mrs M Oliver |  | 07584 991270 | marieo75@outlook.com |  | Windows & Doors
12 |  | 63627 |  | COMMENCEMENT PENDING |  | 20 | Viscount Close | Birmingham |  | B35 7JQ |  | Miss G Haughton |  | 07933643017 |  |  | Windows & Doors
12 |  | 60455 |  | COMMENCEMENT PENDING |  | 22 | Viscount Close | Birmingham |  | B35 7JQ |  | Miss D Dodd |  | 07925 939011 |  |  | Windows & Doors
12 |  | 70647 |  | COMMENCEMENT PENDING |  | 24 | Viscount Close | Birmingham |  | B35 7JQ |  | Miss S Wainwright | 07961 738077 | 07961 738 077 | stacey83may@gmail.com |  | Windows & Doors
12 |  | 62947 |  | COMMENCEMENT PENDING |  | 26 | Viscount Close | Birmingham |  | B35 7JQ |  | Mrs L Alexander | 01217481339 | 07940 353 767 | ladyloza73@yahoo.co.uk |  | Windows & Doors
12 |  | 60095 |  | COMMENCEMENT PENDING |  | 28 | Viscount Close | Birmingham |  | B35 7JQ |  | Mr C Walton |  | 07709 261 225 |  |  | Windows & Doors
12 |  | 60096 |  | COMMENCEMENT PENDING |  | 30 | Viscount Close | Birmingham |  | B35 7JQ |  | Mrs H Egan |  | 07513 921 048 |  |  | Windows & Doors
12 |  | 68591 |  | COMMENCEMENT PENDING |  | 32 | Viscount Close | Birmingham |  | B35 7JQ |  | Miss R M Simmons | 07946548399 | 07946548399 | raelene.simmons@yahoo.co.uk |  | Windows & Doors
12 |  | 68872 |  | COMMENCEMENT PENDING |  | 34 | Viscount Close | Birmingham |  | B35 7JQ |  | Mr RJ Phillips |  | 07456578597 | ryanjamesphillips@hotmail.co.uk |  | Windows & Doors
12 |  | 68155 |  | COMMENCEMENT PENDING |  | FLAT 1 Block 11 | Viscount Close | Castle Vale |  | B35 7JQ |  | Miss M Brown |  | 07532800109 | m.brown23@live.co.uk |  | Windows & Doors
12 |  | 66033 |  | COMMENCEMENT PENDING |  | FLAT 1 Block 15 | Viscount Close | Castle Vale |  | B35 7JQ |  | Mr D Goode |  | 07977758715 |  |  | Windows & Doors
12 |  | 69730 |  | COMMENCEMENT PENDING |  | FLAT 1 Block 7 | Viscount Close | Castle Vale |  | B35 7JQ |  | Miss C Hoo |  | 07733079719 |  |  | Windows & Doors
12 |  | 60053 |  | COMMENCEMENT PENDING |  | FLAT 1 Block 9 | Viscount Close | Castle Vale |  | B35 7JQ |  | Miss B Heap | 0121 749 4595 |  |  |  | Windows & Doors
12 |  | 69464 |  | COMMENCEMENT PENDING |  | FLAT 2 Block 11 | Viscount Close | Castle Vale |  | B35 7JQ |  | Mr A Fowler |  | 07712164286 | iiadamfowlerii@gmail.com |  | Windows & Doors
12 |  | 65688 |  | COMMENCEMENT PENDING |  | FLAT 2 Block 15 | Viscount Close | Castle Vale |  | B35 7JQ |  | Mr A Bird | 0121 2913612 | 07885582189 |  |  | Windows & Doors
12 |  | 60057 |  | COMMENCEMENT PENDING |  | FLAT 2 Block 7 | Viscount Close | Castle Vale |  | B35 7JQ |  | Mr P Lloyd | 07748 443 362 |  |  |  | Windows & Doors
12 |  | 60058 |  | COMMENCEMENT PENDING |  | FLAT 2 Block 9 | Viscount Close | Castle Vale |  | B35 7JQ |  | Mr G Hill | 07542761917 |  |  |  | Windows & Doors
12 |  | 70378 |  | COMMENCEMENT PENDING |  | FLAT 3 Block 11 | Viscount Close | Castle Vale |  | B35 7JQ |  | Miss P Crozier |  | 07788692392 | paigecrozier01@icloud.com |  | Windows & Doors
12 |  | 63628 |  | COMMENCEMENT PENDING |  | FLAT 3 Block 15 | Viscount Close | Castle Vale |  | B35 7JQ |  | Mr T Corbett |  | 07462 908 670 |  |  | Windows & Doors
12 |  | 69227 |  | COMMENCEMENT PENDING |  | FLAT 3 Block 7 | Viscount Close | Castle Vale |  | B35 7JQ |  | Miss D A Smith | 07833460726 |  | Sally Clark,6 Peartree Rd, 748 1060 |  | Windows & Doors
12 |  | 63080 |  | COMMENCEMENT PENDING |  | FLAT 3 Block 9 | Viscount Close | Castle Vale |  | B35 7JQ |  | Miss V Taylor |  |  | vickyalfie71@googlemail.com |  | Windows & Doors
12 |  | 60069 |  | COMMENCEMENT PENDING |  | FLAT 4 Block 11 | Viscount Close | Castle Vale |  | B35 7JQ |  | Mr R Stephenson |  | 07943182112 |  |  | Windows & Doors
12 |  | 60070 |  | COMMENCEMENT PENDING |  | FLAT 4 Block 15 | Viscount Close | Castle Vale |  | B35 7JQ |  | Mr M Barnes |  |  |  |  | Windows & Doors
12 |  | 64500 |  | COMMENCEMENT PENDING |  | FLAT 4 Block 7 | Viscount Close | Castle Vale |  | B35 7JQ |  | Mr P Moore | 07484793994 | 07933301112 | paulmoore053@gmail.com |  | Windows & Doors
12 |  | 68427 |  | COMMENCEMENT PENDING |  | FLAT 4 Block 9 | Viscount Close | Castle Vale |  | B35 7JQ |  | Miss S M Marshall | 0121 749 2311 | 07488339555 |  |  | Windows & Doors
12 |  | 67789 |  | COMMENCEMENT PENDING |  | FLAT 5 Block 11 | Viscount Close | Castle Vale |  | B35 7JQ |  | Ms N Gooden |  |  |  |  | Windows & Doors
12 |  | 66966 |  | COMMENCEMENT PENDING |  | FLAT 5 Block 15 | Viscount Close | Castle Vale |  | B35 7JQ |  | Miss L Mullen |  | 07494143935 | lcmullen2011@hotmail.co.uk |  | Windows & Doors
12 |  | 63796 |  | COMMENCEMENT PENDING |  | FLAT 5 Block 7 | Viscount Close | Castle Vale |  | B35 7JQ |  | Miss D E Bowen |  |  | deborah.ebowen@btinternet.com |  | Windows & Doors
12 |  | 70684 |  | COMMENCEMENT PENDING |  | FLAT 5 Block 9 | Viscount Close | Castle Vale |  | B35 7JQ |  | Mr J Hussey Brown |  | 07438185137 | javforce45@gmail.com |  | Windows & Doors
12 |  | 67713 |  | COMMENCEMENT PENDING |  | FLAT 6 Block 11 | Viscount Close | Castle Vale |  | B35 7JQ |  | Mr P Knight |  | 07935043231 |  |  | Windows & Doors
12 |  | 69973 |  | COMMENCEMENT PENDING |  | FLAT 6 Block 15 | Viscount Close | Castle Vale |  | B35 7JQ |  | Mrs L Wojtas |  | 07738004387 | lidzia@interia.eu |  | Windows & Doors
12 |  | 69084 |  | COMMENCEMENT PENDING |  | FLAT 6 Block 7 | Viscount Close | Castle Vale |  | B35 7JQ |  | Mr J Walsh |  |  | xxjord_villa_09xx@hotmail.co.uk |  | Windows & Doors
12 |  | 65284 |  | COMMENCEMENT PENDING |  | FLAT 6 Block 9 | Viscount Close | Castle Vale |  | B35 7JQ |  | Mr SA Round |  | 07570074982 |  |  | Windows & Doors
12 |  | 61575 |  | COMMENCEMENT PENDING |  | FLAT 7 Block 15 | Viscount Close | Castle Vale |  | B35 7JQ |  | Mr R Bierd | 730 1467 | 07738 718791 |  |  | Windows & Doors
12 |  | 70145 |  | COMMENCEMENT PENDING |  | FLAT 8 Block 15 | Viscount Close | Castle Vale |  | B35 7JQ |  | Miss E Belle |  | 07555 121 649 |  |  | Windows & Doors
12 |  | 61718 |  | COMMENCEMENT PENDING |  | FLAT 9 Block 15 | Viscount Close | Castle Vale |  | B35 7JQ |  | Mr W Hayes |  |  | williamhayes9@aol.com |  | Windows & Doors
12 |  | 69133 |  | COMMENCEMENT PENDING |  | 3 | Viscount Drive | Birmingham |  | B35 7JZ |  | Mrs K D Moroney | 07518 416 841 |  | kelly3493@hotmail.com |  | Windows & Doors
12 |  | 69181 |  | COMMENCEMENT PENDING |  | 5 | Viscount Drive | Birmingham |  | B35 7JZ |  | Miss C Ward |  | 07445199903 | carleywww@hotmail.co.uk |  | Windows & Doors
12 |  | 69712 |  | COMMENCEMENT PENDING |  | 7 | Viscount Drive | Birmingham |  | B35 7JZ |  | Mr G Edwards |  | 079857 24785 |  |  | Windows & Doors
12 |  | 66169 |  | COMMENCEMENT PENDING |  | 11 | Viscount Drive | Birmingham |  | B35 7JZ |  | Miss R L Lawrence |  | 07970 635837 | rhondalawrence123@hotmail.com |  | Windows & Doors
12 |  | 61498 |  | COMMENCEMENT PENDING |  | 15 | Viscount Drive | Birmingham |  | B35 7JZ |  | Mrs C T Evans | 07513 550 260 |  |  |  | Windows & Doors
12 |  | 67092 |  | COMMENCEMENT PENDING |  | 17 | Viscount Drive | Birmingham |  | B35 7JZ |  | Mrs N Gaynor | 07476 332327 | 07825370827 | naomirhone@yahoo.co.uk |  | Windows & Doors
12 |  | 61500 |  | COMMENCEMENT PENDING |  | 19 | Viscount Drive | Birmingham |  | B35 7JZ |  | Mrs T Cespedes |  | 07491 668 199 |  |  | Windows & Doors
12 |  | 61501 |  | COMMENCEMENT PENDING |  | 21 | Viscount Drive | Birmingham |  | B35 7JZ |  | Miss K Raymond |  | 07824369156 |  |  | Windows & Doors
12 |  | 67933 |  | COMMENCEMENT PENDING |  | 52 | Waldon Walk | Birmingham |  | B36 0TL |  | Mr J Bobb |  |  | jeganbobb@hotmail.com |  | Windows & Doors
12 |  | 69517 |  | COMMENCEMENT PENDING |  | 15 | Wattisham Square | Birmingham |  | B35 6JJ |  | Mr S McGuire |  | 07379131645 | ste04_1@hotmail.com |  | Windows & Doors
12 |  | 62484 |  | COMMENCEMENT PENDING |  | 2 | Wattisham Square | Birmingham |  | B35 6JL |  | Mr D Barratt |  | 07867 487 741 | louiam5@yahoo.co.uk |  | Windows & Doors
12 |  | 70702 |  | COMMENCEMENT PENDING |  | FLAT 2 Block 22 | Wattisham Square | Castle Vale |  | B35 6JL |  | Mrs L Foster |  | 07772347561 |  |  | Windows & Doors
12 |  | 57816 |  | COMMENCEMENT PENDING | SEE COMMENTS | 54 | Watton Green | Birmingham |  | B35 7JP |  | Miss M-A Kells |  | (Contact not tenant) 07907 540 212 |  |  | Windows & Doors | M Turpin |  |  |  |  | TS-25/04/24 Text sent for 07/05/24. TS-01/05/24 Called tenant number nis letter sent offering 07/05/24. TS-07/05 Tenant called she can't make today and wants booking in last as she needs to move beds etc.13/05 SMS text sent for 23/05. 15/05 SMS no. NIS. 16/05 SMS lttr sent,. 22/05 SMS tenant called to advise cant have offered survey on 23/05 as her house needs clearing, shes said would need until January to clear. Emailed Dominie and client to advise of this issue before scheduling back in a survey date.
12 |  | 65831 |  | COMMENCEMENT PENDING |  | 26 | Watton Green | Birmingham |  | B35 7JS |  | Miss S Thomas | 7557154887 |  | thomas86@hotmail.co.uk |  | Windows & Doors | M Turpin |  |  |  | 1 | TS-19/04/24 Text sent for 02/05/24. TS-24/04/24 Called left vm, text & ltr sent. TS-29/04/24 Tenant called she can't make this date tracker updated with new number.13/05 SMS text sent for 23/05. 15/05 SMS left voicemail. 16/05 SMS letter sent. 11/06 SMS 1st no access on 23/05. 14/06 SMS text sent for 27/06. 14/06 SMS tenant declined 27/06
12 |  | 69041 |  | COMMENCEMENT PENDING |  | 1 | Wellington Way | Birmingham |  | B35 7JU |  | Mrs A Standen | 07735552112 |  |  |  | Windows & Doors
12 |  | 60275 |  | COMMENCEMENT PENDING |  | 3 | Wellington Way | Birmingham |  | B35 7JU |  | Mr D Cooper |  |  |  |  | Windows & Doors
12 |  | 65904 |  | COMMENCEMENT PENDING |  | 5 | Wellington Way | Birmingham |  | B35 7JU |  | Mr J Doyle | 07956674606 |  |  |  | Windows & Doors
12 |  | 69852 |  | COMMENCEMENT PENDING |  | 7 | Wellington Way | Birmingham |  | B35 7JU |  | Miss S Smith |  | 07743105132 | samaiden84@hotmail.co.uk |  | Windows & Doors
12 |  | 69787 |  | COMMENCEMENT PENDING |  | 9 | Wellington Way | Birmingham |  | B35 7JU |  | Miss S Aslam |  | 07999998521 | anila-x@hotmail.co.uk |  | Windows & Doors
12 |  | 60122 |  | COMMENCEMENT PENDING |  | 11 | Wellington Way | Birmingham |  | B35 7JU |  | Mr D Broth | 07547 926 973 |  |  |  | Windows & Doors
12 |  | 64845 |  | COMMENCEMENT PENDING |  | 15 | Wellington Way | Birmingham |  | B35 7JU |  | Mr L Perkins | 0121 747 9860 | 07579 775349 | urx@btinternet.com |  | Windows & Doors
12 |  | 64671 |  | COMMENCEMENT PENDING |  | 17 | Wellington Way | Birmingham |  | B35 7JU |  | Miss E Gordon |  | 07775 972985 | gordon.elaine17@yahoo.com |  | Windows & Doors
12 |  | 65451 |  | COMMENCEMENT PENDING |  | 19 | Wellington Way | Birmingham |  | B35 7JU |  | Miss M Wedderburn |  | 07470 954174 | mahaliawedda@hotmail.com |  | Windows & Doors
12 |  | 69669 |  | COMMENCEMENT PENDING |  | 21 | Wellington Way | Birmingham |  | B35 7JU |  | Miss J Wood |  |  |  |  | Windows & Doors
12 |  | 70304 |  | COMMENCEMENT PENDING |  | 23 | Wellington Way | Birmingham |  | B35 7JU |  | Miss C Buck |  | 07517924522 | miss-buck2019@outlook.com |  | Windows & Doors
12 |  | 66258 |  | COMMENCEMENT PENDING |  | 25 | Wellington Way | Birmingham |  | B35 7JU |  | Miss J Cooksey |  | 07880703023 | jadelouise9394@hotmail.co.uk |  | Windows & Doors
12 |  | 57573 |  | COMMENCEMENT PENDING |  | 1 | Westland Walk | Birmingham |  | B35 7QL |  | Miss SM Busby | 07387766794 |  |  |  | Windows & Doors
12 |  | 60130 |  | COMMENCEMENT PENDING |  | 7 | Westland Walk | Birmingham |  | B35 7QL |  | Mr P Flowers | 07593328150 |  |  |  | Windows & Doors
12 |  | 70180 |  | COMMENCEMENT PENDING |  | 6 | Westland Walk | Birmingham |  | B35 7QN |  | Miss D Allen |  | 07925766217 | dena6ltdmjit@gmail.com |  | Windows & Doors
12 |  | 65944 |  | COMMENCEMENT PENDING |  | 8 | Westland Walk | Birmingham |  | B35 7QN |  | Mrs L Jones |  | 07495280304 |  |  | Windows & Doors
12 |  | 56850 |  | COMMENCEMENT PENDING |  | 10 | Westland Walk | Birmingham |  | B35 7QN |  | Mr R Horne |  |  |  |  | Windows & Doors
12 |  | 56851 |  | COMMENCEMENT PENDING |  | 12 | Westland Walk | Birmingham |  | B35 7QN |  | Miss W Atterbury |  | 07572509717 | wendyatterbury@hotmail.co.uk |  | Windows & Doors
12 |  | 56852 |  | COMMENCEMENT PENDING |  | 21 | Westland Walk | Birmingham |  | B35 7QP |  | Mr R K Wills | 07799724161 |  |  |  | Windows & Doors
12 |  | 69417 |  | COMMENCEMENT PENDING |  | 25 | Westland Walk | Birmingham |  | B35 7QP |  | Miss J Barnett |  | 07593210111 | jenjenn123@icloud.com |  | Windows & Doors
12 |  | 69623 |  | COMMENCEMENT PENDING |  | 27 | Westland Walk | Birmingham |  | B35 7QP |  | Miss S Gill |  | 07398663132 | bonz19881@gmail.com |  | Windows & Doors
12 |  | 61957 |  | COMMENCEMENT PENDING |  | 49 | Westland Walk | Birmingham |  | B35 7QR |  | Miss F S Goodman |  | 07443 674 704 | faithtt24@hotmail.co.uk |  | Windows & Doors
12 |  | 56856 |  | COMMENCEMENT PENDING |  | 57 | Westland Walk | Birmingham |  | B35 7QR |  | Mr R Franks | 01217474644 | 07761981061 |  |  | Windows & Doors
12 |  | 70396 |  | COMMENCEMENT PENDING |  | 15 | Whittle Croft | Birmingham |  | B35 6DN |  | Miss Z Akbar |  | 07521196246 | zeenatakbar83@gmail.com |  | Windows & Doors
12 |  | 69790 |  | COMMENCEMENT PENDING |  | 21 | Whittle Croft | Birmingham |  | B35 6DN |  | Miss L Morgan | 07745797139 | 07745797139 | sophie.brookes2012@hotmail.co.uk |  | Windows & Doors
12 |  | 67718 |  | COMMENCEMENT PENDING |  | FLAT 10 | Whittle Croft | Birmingham |  | B35 6DN |  | Mr G Francis | 07940241833 | 07940 241833 |  |  | Windows & Doors
12 |  | 66377 |  | COMMENCEMENT PENDING |  | FLAT 12 | Whittle Croft | Birmingham |  | B35 6DN |  | Mr J Light | 07984124068 | 07984120468 |  |  | Windows & Doors
12 |  | 68751 |  | COMMENCEMENT PENDING |  | FLAT 14 | Whittle Croft | Birmingham |  | B35 6DN |  | Mr W Ind | 0121 748 1793 | 07557799481 |  |  | Windows & Doors
12 |  | 64652 |  | COMMENCEMENT PENDING |  | FLAT 16 | Whittle Croft | Birmingham |  | B35 6DN |  | Mrs C Johnson | 07721204244 | 07721204244 |  |  | Windows & Doors
12 |  | 68156 |  | COMMENCEMENT PENDING |  | FLAT 2 | Whittle Croft | Birmingham |  | B35 6DN |  | Mrs J Cabena |  | 07585 287 395 |  |  | Windows & Doors
12 |  | 70464 |  | COMMENCEMENT PENDING |  | FLAT 3 | Whittle Croft | Birmingham |  | B35 6DN |  | Mrs R McCann | 07766542809 | 07766542809 |  |  | Windows & Doors
12 |  | 69566 |  | COMMENCEMENT PENDING |  | FLAT 4 | Whittle Croft | Birmingham |  | B35 6DN |  | Miss S McIntosh |  |  | SMCINTOSH796@GMAIL.COM |  | Windows & Doors
12 |  | 69533 |  | COMMENCEMENT PENDING |  | FLAT 5 | Whittle Croft | Birmingham |  | B35 6DN |  | Miss Y Williams | 07308141324 | 07932 495317 |  |  | Windows & Doors
12 |  | 68142 |  | COMMENCEMENT PENDING |  | FLAT 6 | Whittle Croft | Birmingham |  | B35 6DN |  | Mr J Russell | 01217494859 | 07484 683 409 | jgrusell@icloud.com |  | Windows & Doors
12 |  | 69540 |  | COMMENCEMENT PENDING |  | FLAT 7 | Whittle Croft | Birmingham |  | B35 6DN |  | Mr D Johnson | 0121 439 8818 |  |  |  | Windows & Doors
12 |  | 61301 |  | COMMENCEMENT PENDING |  | FLAT 8 | Whittle Croft | Birmingham |  | B35 6DN |  | Mr J Cole |  | 07538 921 174 |  |  | Windows & Doors
12 |  | 70756 |  | COMMENCEMENT PENDING |  | FLAT 9 | Whittle Croft | Birmingham |  | B35 6DN |  | Mrs E P Sperry |  | 07865443327 | Eileensperry@icloud.com |  | Windows & Doors
12 |  | 66109 |  | COMMENCEMENT PENDING |  | 5 | Worthydown Walk | Birmingham |  | B35 7NA |  | Miss JJ Froggatt |  | 07771 243 414 | jennifer2781@hotmail.co.uk |  | Windows & Doors
12 |  | 56874 |  | COMMENCEMENT PENDING |  | 7 | Worthydown Walk | Birmingham |  | B35 7NA |  | Mrs S Galbally |  | 07877 496 908 | tediss@hotmail.co.uk |  | Windows & Doors
12 |  | 56875 |  | COMMENCEMENT PENDING |  | 9 | Worthydown Walk | Birmingham |  | B35 7NA |  | Mrs B Jeffs | 07934 046 242 |  | belindajeffs73@gmail.com |  | Windows & Doors
12 |  | 63281 |  | COMMENCEMENT PENDING |  | 15 | Worthydown Walk | Birmingham |  | B35 7NA |  | Mrs KA Edmondson |  | 07412024048 |  |  | Windows & Doors
12 |  | 56878 |  | COMMENCEMENT PENDING |  | 19 | Worthydown Walk | Birmingham |  | B35 7NA |  | Miss J Walton |  |  |  |  | Windows & Doors
12 |  | 70147 |  | COMMENCEMENT PENDING |  | 21 | Worthydown Walk | Birmingham |  | B35 7NA |  | Mrs EO Ali | 07306891136 |  |  |  | Windows & Doors
12 |  | 67993 |  | COMMENCEMENT PENDING |  | 23 | Worthydown Walk | Birmingham |  | B35 7NA |  | Mrs E Lowry-Rawlins |  |  |  |  | Windows & Doors
12 |  | 58498 |  | COMMENCEMENT PENDING |  | 25 | Worthydown Walk | Birmingham |  | B35 7NA |  | Mrs T M Fisher | 0121 747 5472 | 07508 610 786 | mitch-beale@live.co.uk |  | Windows & Doors
12 |  | 68370 |  | COMMENCEMENT PENDING |  | 316 | Yatesbury Avenue | Birmingham |  | B35 6BX |  | Miss C Mitchell | 01217481399 | 07847822142 |  |  | Windows & Doors | M Turpin
12 |  | 64081 |  | COMMENCEMENT PENDING |  | 318 | Yatesbury Avenue | Birmingham |  | B35 6BX |  | Mrs L Elston | 0121 748 6045 |  |  |  | Windows & Doors | M Turpin
12 |  | 62844 |  | COMMENCEMENT PENDING |  | 320 | Yatesbury Avenue | Birmingham |  | B35 6BX |  | Mr N Simpson |  | 07557 090 731 |  |  | Windows & Doors | M Turpin
12 |  | 69671 |  | COMMENCEMENT PENDING |  | 322 | Yatesbury Avenue | Birmingham |  | B35 6BX |  | Mr D Berrow | 07305866512 | 07305 866512 |  |  | Windows & Doors | M Turpin
12 |  | 67410 |  | COMMENCEMENT PENDING |  | 324 | Yatesbury Avenue | Birmingham |  | B35 6BX |  | Mrs M Corbacho |  | 07776299574 |  |  | Windows & Doors | M Turpin
12 |  | 68391 |  | COMMENCEMENT PENDING |  | 342 | Yatesbury Avenue | Birmingham |  | B35 6BX |  | Miss J Adam |  |  |  |  | Windows & Doors | M Turpin
12 |  | 63966 |  | COMMENCEMENT PENDING |  | 346 | Yatesbury Avenue | Birmingham |  | B35 6BX |  | Miss S Crumpton |  | 07727407415 |  |  | Windows & Doors | M Turpin
12 |  | 69063 |  | COMMENCEMENT PENDING |  | 348 | Yatesbury Avenue | Birmingham |  | B35 6BX |  | Miss G Owens |  | 07795639483 |  |  | Windows & Doors | M Turpin
12 |  | 61949 |  | COMMENCEMENT PENDING |  | 350 | Yatesbury Avenue | Birmingham |  | B35 6BX |  | Miss L Payne |  |  | DiDi29xx@hotmail.com |  | Windows & Doors | M Turpin
12 |  | 60147 |  | COMMENCEMENT PENDING |  | 352 | Yatesbury Avenue | Birmingham |  | B35 6BX |  | Miss L Brettell |  | 07745412281 |  |  | Windows & Doors | M Turpin
12 |  | 64538 |  | COMMENCEMENT PENDING |  | 356 | Yatesbury Avenue | Birmingham |  | B35 6DA |  | Mrs SA Harris |  | 07502 588 442 | sharonharris13@hotmail.co.uk |  | Windows & Doors | M Turpin
12 |  | 67373 |  | COMMENCEMENT PENDING |  | 360 | Yatesbury Avenue | Birmingham |  | B35 6DA |  | Mr K Johnson |  | 07493673282 |  |  | Windows & Doors | M Turpin
12 |  | 69711 |  | COMMENCEMENT PENDING |  | 364 | Yatesbury Avenue | Birmingham |  | B35 6DA |  | Miss R Pell |  | 07917640186 | raepell69@icloud.com |  | Windows & Doors | M Turpin
12 |  | 68815 |  | COMMENCEMENT PENDING |  | 382 | Yatesbury Avenue | Birmingham |  | B35 6DG |  | Miss J Brown | 07494740587 | 07494740587 | mzjb@hotmail.co.uk |  | Windows & Doors | M Turpin
12 |  | 70723 |  | COMMENCEMENT PENDING |  | 192 | Yatesbury Avenue | Birmingham |  | B35 6DP |  | Miss K Poole | 07833173311 | 07833173311 | Kiera_poole@Yahoo.co.uk |  | Windows & Doors | M Turpin
12 |  | 56896 |  | COMMENCEMENT PENDING |  | 196 | Yatesbury Avenue | Birmingham |  | B35 6DP |  | Mrs E Warren |  | 07817 126486 |  |  | Windows & Doors | M Turpin
12 |  | 69384 |  | COMMENCEMENT PENDING |  | 206 | Yatesbury Avenue | Birmingham |  | B35 6DP |  | Mr J Smith |  | 07521 719307 |  |  | Windows & Doors | M Turpin
12 |  | 58043 |  | COMMENCEMENT PENDING |  | 208 | Yatesbury Avenue | Birmingham |  | B35 6DP |  | Miss R Cooksey |  | 07541 648167 |  |  | Windows & Doors | M Turpin
12 |  | 70461 |  | COMMENCEMENT PENDING |  | FLAT 156 | Yatesbury Avenue | Birmingham |  | B35 6DP |  | Mrs W Clarke |  | 07498882635 | Wendy.clarke@nhs.net |  | Windows & Doors | M Turpin
12 |  | 67138 |  | COMMENCEMENT PENDING |  | FLAT 160 | Yatesbury Avenue | Birmingham |  | B35 6DP |  | Mr K Grogan | 01215744810 |  |  |  | Windows & Doors | M Turpin
12 |  | 68625 |  | COMMENCEMENT PENDING |  | FLAT 164 | Yatesbury Avenue | Birmingham |  | B35 6DP |  | Mr P Houlihan | 07465 876 927 | 07465 876 927 |  |  | Windows & Doors | M Turpin
12 |  | 66019 |  | COMMENCEMENT PENDING |  | FLAT 168 | Yatesbury Avenue | Birmingham |  | B35 6DP |  | Mrs VE Hodnitt |  | 07951 241 724 |  |  | Windows & Doors | M Turpin
12 |  | 70566 |  | COMMENCEMENT PENDING |  | FLAT 176 | Yatesbury Avenue | Birmingham |  | B35 6DP |  | Mr P R Matthews |  | 07482720899 |  |  | Windows & Doors | M Turpin
12 |  | 56897 |  | COMMENCEMENT PENDING |  | FLAT 198 | Yatesbury Avenue | Birmingham |  | B35 6DP |  | Mrs Y Clarke |  | 07881 920 275 |  |  | Windows & Doors | M Turpin
12 |  | 64352 |  | COMMENCEMENT PENDING |  | FLAT 200 | Yatesbury Avenue | Birmingham |  | B35 6DP |  | Mr J Johnson |  | 07745989600 |  |  | Windows & Doors | M Turpin
12 |  | 69931 |  | COMMENCEMENT PENDING |  | FLAT 202 | Yatesbury Avenue | Birmingham |  | B35 6DP |  | Miss C Mead |  | 07591027079 | charlottemead-xo@outlook.com |  | Windows & Doors | M Turpin
12 |  | 67460 |  | COMMENCEMENT PENDING |  | FLAT 204 | Yatesbury Avenue | Birmingham |  | B35 6DP |  | Mr W Rickus | 01217767124 | 07917827641 | lukerick@live.co.uk |  | Windows & Doors | M Turpin
12 |  | 70747 |  | COMMENCEMENT PENDING |  | 272 | Yatesbury Avenue | Birmingham |  | B35 6DU |  | Miss Emma James |  |  | emma21james@yahoo.co.uk |  | Windows & Doors | M Turpin
12 |  | 68490 |  | COMMENCEMENT PENDING |  | 278 | Yatesbury Avenue | Birmingham |  | B35 6DU |  | Miss LM Davis |  | 07782328851 |  |  | Windows & Doors | M Turpin
12 |  | 66227 |  | COMMENCEMENT PENDING |  | FLAT 286 | Yatesbury Avenue | Birmingham |  | B35 6DU |  | Mr C Smith |  | 07385803683 |  |  | Windows & Doors | M Turpin
12 |  | 68211 |  | COMMENCEMENT PENDING |  | FLAT 288 | Yatesbury Avenue | Birmingham |  | B35 6DU |  | Mr M Welch | 07954007127 |  |  |  | Windows & Doors | M Turpin
12 |  | 58414 |  | COMMENCEMENT PENDING |  | FLAT 290 | Yatesbury Avenue | Birmingham |  | B35 6DU |  | Mr R Williams |  | 0759 3565545 |  |  | Windows & Doors | M Turpin
12 |  | 69970 |  | COMMENCEMENT PENDING |  | FLAT 292 | Yatesbury Avenue | Birmingham |  | B35 6DU |  | Miss S Maxwell |  |  | stacymaxx@gmail.com |  | Windows & Doors | M Turpin
12 |  | 69565 |  | COMMENCEMENT PENDING |  | FLAT 306 | Yatesbury Avenue | Birmingham |  | B35 6DU |  | Miss E Walsh | 07553032940 |  |  |  | Windows & Doors | M Turpin
12 |  | 56914 |  | COMMENCEMENT PENDING |  | FLAT 308 | Yatesbury Avenue | Birmingham |  | B35 6DU |  | Mr MA Brewster | 0121 747 9040 |  |  |  | Windows & Doors | M Turpin
12 |  | 70492 |  | COMMENCEMENT PENDING |  | FLAT 310 | Yatesbury Avenue | Birmingham |  | B35 6DU |  | Mrs M King |  | 07512859722 | shell8.ms@gmail.com |  | Windows & Doors | M Turpin
12 |  | 64668 |  | COMMENCEMENT PENDING |  | FLAT 312 | Yatesbury Avenue | Birmingham |  | B35 6DU |  | Mr M Murphy | 07964 538297 | 07964 538297 |  |  | Windows & Doors | M Turpin
12 |  | 69558 |  | COMMENCEMENT PENDING |  | FLAT 154 | Yatesbury Avenue | Birmingham |  | B35 6DW |  | Miss S Bryan |  | 07470734222 |  |  | Windows & Doors | M Turpin
12 |  | 68668 |  | COMMENCEMENT PENDING |  | FLAT 158 | Yatesbury Avenue | Birmingham |  | B35 6DW |  | Ms S Connor | 01217476152 | 0798 351 2781 |  |  | Windows & Doors | M Turpin
12 |  | 62807 |  | COMMENCEMENT PENDING |  | FLAT 162 | Yatesbury Avenue | Birmingham |  | B35 6DW |  | Mrs B Haughton | 0121 747 5709 | 07894 011 312 |  |  | Windows & Doors | M Turpin
12 |  | 67014 |  | COMMENCEMENT PENDING |  | FLAT 166 | Yatesbury Avenue | Birmingham |  | B35 6DW |  | Mrs P Madden |  | 07530709360 |  |  | Windows & Doors | M Turpin
12 |  | 67104 |  | COMMENCEMENT PENDING |  | FLAT 170 | Yatesbury Avenue | Birmingham |  | B35 6DW |  | Mrs S Hart | 01213133496 | 07564295682 |  |  | Windows & Doors | M Turpin
12 |  | 69662 |  | COMMENCEMENT PENDING |  | FLAT 172 | Yatesbury Avenue | Birmingham |  | B35 6DW |  | Mr C Hines |  | 07305642271 | coolman690@hotmail.com |  | Windows & Doors | M Turpin
12 |  | 67643 |  | COMMENCEMENT PENDING |  | FLAT 174 | Yatesbury Avenue | Birmingham |  | B35 6DW |  | Mr RJ Dyer |  | 07752 176 817 |  |  | Windows & Doors | M Turpin
12 |  | 64806 |  | COMMENCEMENT PENDING |  | 404 | Yatesbury Avenue | Birmingham |  | B35 6LA |  | Miss AO Hartley |  | 07912 552 856 |  |  | Windows & Doors | M Turpin
12 |  | 69849 |  | COMMENCEMENT PENDING |  | 412 | Yatesbury Avenue | Birmingham |  | B35 6LB |  | Miss N Rhone |  | 07472000006 | blackqueenie85@yahoo.co.uk |  | Windows & Doors | M Turpin
12 |  | 66903 |  | COMMENCEMENT PENDING |  | 414 | Yatesbury Avenue | Birmingham |  | B35 6LB |  | Miss C Dunleavy | 07958 578 729 |  | Chan_dun04@hotmail.com |  | Windows & Doors | M Turpin
12 |  | 56932 |  | COMMENCEMENT PENDING |  | FLAT 1 Block 509 | Yatesbury Avenue | Castle Vale |  | B35 6PU |  | Miss C T Cummins | 0772 0944060 | 0772 0944060 | carol1957@tgmail.com |  | Windows & Doors | M Turpin
12 |  | 69293 |  | COMMENCEMENT PENDING |  | FLAT 1 Block 511 | Yatesbury Avenue | Castle Vale |  | B35 6PU |  | Mrs S Taddese-Abdi | 07586194812 | 07586194812 | zewdu.r@yahoo.com |  | Windows & Doors | M Turpin
12 |  | 63355 |  | COMMENCEMENT PENDING |  | FLAT 2 Block 509 | Yatesbury Avenue | Castle Vale |  | B35 6PU |  | Mr P Sheard |  | 07769194832 |  |  | Windows & Doors | M Turpin
12 |  | 67728 |  | COMMENCEMENT PENDING |  | FLAT 2 Block 511 | Yatesbury Avenue | Castle Vale |  | B35 6PU |  | Mrs AR Barnes | 0121 748 6748 | 07587472533 |  |  | Windows & Doors | M Turpin
12 |  | 60750 |  | COMMENCEMENT PENDING |  | FLAT 3 Block 509 | Yatesbury Avenue | Castle Vale |  | B35 6PU |  | Mr W Mullis |  | 07981334060 |  |  | Windows & Doors | M Turpin
12 |  | 68955 |  | COMMENCEMENT PENDING |  | FLAT 3 Block 511 | Yatesbury Avenue | Castle Vale |  | B35 6PU |  | Miss R Baldwin |  | 07895349555 |  |  | Windows & Doors | M Turpin
12 |  | 67681 |  | COMMENCEMENT PENDING |  | FLAT 4 Block 511 | Yatesbury Avenue | Castle Vale |  | B35 6PU |  | Ms P Rutter | 07465 671 572 |  | pamelajoy123@yahoo.co.uk |  | Windows & Doors | M Turpin
12 |  | 56936 |  | COMMENCEMENT PENDING |  | FLAT 5 Block 509 | Yatesbury Avenue | Castle Vale |  | B35 6PU |  | Mr B Bonehill |  | 07754916465 |  |  | Windows & Doors | M Turpin
12 |  | 69330 |  | COMMENCEMENT PENDING |  | FLAT 5 Block 511 | Yatesbury Avenue | Castle Vale |  | B35 6PU |  | Miss J Cunniffe |  | 07376422476 | jenny_cunniffe@outlook.com |  | Windows & Doors | M Turpin
12 |  | 60291 |  | COMMENCEMENT PENDING |  | FLAT 6 Block 509 | Yatesbury Avenue | Castle Vale |  | B35 6PU |  | Mr V McCracken | 07947279190 |  |  |  | Windows & Doors | M Turpin
12 |  | 68696 |  | COMMENCEMENT PENDING |  | FLAT 6 Block 511 | Yatesbury Avenue | Castle Vale |  | B35 6PU |  | Miss E R McCracken | 07756206846 |  |  |  | Windows & Doors | M Turpin
12 |  | 67721 |  | COMMENCEMENT PENDING |  | 323 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Ms M Wall |  | 07789648008 |  |  | Windows & Doors | M Turpin
12 |  | 60132 |  | COMMENCEMENT PENDING |  | 325 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Mrs G Jefferies |  | 07958183065 |  |  | Windows & Doors | M Turpin
12 |  | 60148 |  | COMMENCEMENT PENDING |  | 353 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Miss J Sutherland |  | 07780 590067 |  |  | Windows & Doors | M Turpin
12 |  | 60149 |  | COMMENCEMENT PENDING |  | 355 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Miss A Hinds | 07542693109 | 07799 213 935 |  |  | Windows & Doors | M Turpin
12 |  | 68416 |  | COMMENCEMENT PENDING |  | 357 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Miss K L Day |  |  |  |  | Windows & Doors | M Turpin
12 |  | 65922 |  | COMMENCEMENT PENDING |  | 359 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Mrs L Robinson | 01212946600 | 07851604370 |  |  | Windows & Doors | M Turpin
12 |  | 60152 |  | COMMENCEMENT PENDING |  | 361 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Mr H Poyner |  | 07399190183 |  |  | Windows & Doors | M Turpin
12 |  | 60162 |  | COMMENCEMENT PENDING |  | 383 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Mrs J Smith |  | 07867 336 558 |  |  | Windows & Doors | M Turpin
12 |  | 60163 |  | COMMENCEMENT PENDING |  | 385 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Mrs P Jones |  | 07944 093 168 |  |  | Windows & Doors | M Turpin
12 |  | 67802 |  | COMMENCEMENT PENDING |  | 387 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Miss L Sandford | 07761 741 397 |  | louzana72@hotmail.com |  | Windows & Doors | M Turpin
12 |  | 65699 |  | COMMENCEMENT PENDING |  | 389 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Miss D D Asbury | 0121 218 0352 | 07950 351052 | danielleasbury@aol.com |  | Windows & Doors | M Turpin
12 |  | 60166 |  | COMMENCEMENT PENDING |  | 391 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Mrs P Smyth |  |  |  |  | Windows & Doors | M Turpin
12 |  | 63306 |  | COMMENCEMENT PENDING |  | 393 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Mr M Coley |  | 07907333631 |  |  | Windows & Doors | M Turpin
12 |  | 66850 |  | COMMENCEMENT PENDING |  | 395 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Mrs M Ashton | 07538 012811 | 07538 012 811 | margaret.ashton@hotmail.com |  | Windows & Doors | M Turpin
12 |  | 61669 |  | COMMENCEMENT PENDING |  | FLAT 347 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Mr C Ferrie | 01217301070 |  |  |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm
12 |  | 60157 |  | COMMENCEMENT PENDING |  | FLAT 371 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Mr B Shingler |  | 07473 115 805 |  |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm |  | 1 | 13/06 SMS text sent for 26/06. 26/6/2024; NO ACCESS, CARDED. | [28 empty] | Access via 1 Cranwell & 363 Yatesbury
12 |  | 60159 |  | COMMENCEMENT PENDING |  | FLAT 375 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Mrs J Evans |  | 07572601432 |  |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm |  | 1 | 13/06 SMS text sent for 26/06. 19/06 SMS called N/A lttr sent. 26/6/2024; NO ACCESS, CARDED. | [28 empty] | Access via 2 Cranwell & 381 Yatesbury
12 |  | 60169 |  | COMMENCEMENT PENDING |  | FLAT 397 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Mr R Shakespeare |  |  |  |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm | [31 empty] | Access via 395 Yatesbury & 138 Cosford
12 |  | 60170 |  | COMMENCEMENT PENDING |  | FLAT 399 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Mr W McMullan | 681 0549 |  |  |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm | [31 empty] | Access via 395 Yatesbury & 138 Cosford
12 |  | 60171 |  | COMMENCEMENT PENDING |  | FLAT 401 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Mr S Sawyer |  |  |  |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm | [31 empty] | Access via 395 Yatesbury & 138 Cosford
12 |  | 60172 |  | COMMENCEMENT PENDING |  | FLAT 403 | Yatesbury Avenue | Birmingham |  | B35 6QP |  | Mr I Hall | 07729 029 722 |  |  |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm | [31 empty] | Access via 395 Yatesbury & 138 Cosford
12 |  | 70676 |  | COMMENCEMENT PENDING |  | 457 | Yatesbury Avenue | Birmingham |  | B35 6QR |  | Mr D Plant | 01217492480 | 07999 924436 | English-pie67@hotmail.com |  | Windows & Doors | M Turpin
12 |  | 64167 |  | COMMENCEMENT PENDING |  | 459 | Yatesbury Avenue | Birmingham |  | B35 6QR |  | Mrs R O'Regan | 0121 776 7757 |  |  |  | Windows & Doors | M Turpin
12 |  | 63832 |  | COMMENCEMENT PENDING |  | 461 | Yatesbury Avenue | Birmingham |  | B35 6QR |  | Miss J M Strong |  | 07949495111 | joy.strong0121@outlook.com |  | Windows & Doors | M Turpin
12 |  | 60175 |  | COMMENCEMENT PENDING |  | 463 | Yatesbury Avenue | Birmingham |  | B35 6QR |  | Miss C Falconer |  |  |  |  | Windows & Doors | M Turpin
12 |  | 60176 |  | COMMENCEMENT PENDING |  | 465 | Yatesbury Avenue | Birmingham |  | B35 6QR |  | Miss P Kiely |  | 07903747247 |  |  | Windows & Doors | M Turpin
12 |  | 60177 |  | COMMENCEMENT PENDING |  | 467 | Yatesbury Avenue | Birmingham |  | B35 6QR |  | Mrs J Baggott | 0121 749 1942 | 07877 031 673 |  |  | Windows & Doors | M Turpin
12 |  | 68362 |  | COMMENCEMENT PENDING |  | 469 | Yatesbury Avenue | Birmingham |  | B35 6QR |  | Miss S Hall | 07387386918 | 07387386918 | steflle@hotmail.com |  | Windows & Doors | M Turpin
12 |  | 60179 |  | COMMENCEMENT PENDING |  | 471 | Yatesbury Avenue | Birmingham |  | B35 6QR |  | Mr B Eagle | 01217302073 | 07703849244 |  |  | Windows & Doors | M Turpin
12 |  | 60180 |  | COMMENCEMENT PENDING |  | 473 | Yatesbury Avenue | Birmingham |  | B35 6QR |  | Mrs K Luzyn |  | 07880 884 629 |  |  | Windows & Doors | M Turpin
12 |  | 60181 |  | COMMENCEMENT PENDING |  | 475 | Yatesbury Avenue | Birmingham |  | B35 6QR |  | Miss C Campbell |  |  |  |  | Windows & Doors | M Turpin
12 |  | 63721 |  | COMMENCEMENT PENDING |  | 477 | Yatesbury Avenue | Birmingham |  | B35 6QR |  | Miss S Williams | 07309637236 | 07309637236 |  |  | Windows & Doors | M Turpin
12 |  | 60183 |  | COMMENCEMENT PENDING |  | 479 | Yatesbury Avenue | Birmingham |  | B35 6QR |  | Miss B Creamer |  |  | creamerb7@aol.com |  | Windows & Doors | M Turpin
12 |  | 60184 |  | COMMENCEMENT PENDING |  | 481 | Yatesbury Avenue | Birmingham |  | B35 6QR |  | Miss M Canning | 01217497756 |  |  |  | Windows & Doors | M Turpin
12 |  | 60185 |  | COMMENCEMENT PENDING |  | 483 | Yatesbury Avenue | Birmingham |  | B35 6QR |  | Miss M Flanagan | 07790942118 |  |  |  | Windows & Doors | M Turpin
12 |  | 64612 |  | COMMENCEMENT PENDING |  | 485 | Yatesbury Avenue | Birmingham |  | B35 6QR |  | Mr N Crofts |  | 07471 503 437 |  |  | Windows & Doors | M Turpin
12 |  | 64973 |  | COMMENCEMENT PENDING |  | 487 | Yatesbury Avenue | Birmingham |  | B35 6QR |  | Miss C Wollaston |  | 07883075242 | cathrine.wollaston@sky.com |  | Windows & Doors | M Turpin
12 |  | 61674 |  | COMMENCEMENT PENDING |  | 489 | Yatesbury Avenue | Birmingham |  | B35 6QR |  | Mr S Leach |  |  |  |  | Windows & Doors | M Turpin
12 |  | 60189 |  | COMMENCEMENT PENDING |  | 491 | Yatesbury Avenue | Birmingham |  | B35 6QR |  | Mrs E Hewings |  |  |  |  | Windows & Doors | M Turpin
12 |  | 66780 |  | COMMENCEMENT PENDING |  | FLAT 493 | Yatesbury Avenue | Birmingham |  | B35 6QR |  | Mr L McCann | 07826 177106 |  |  |  | Windows & Doors | M Turpin | [33 empty] | Access via 491 Yatesbury & 82 Mere Avenue
12 |  | 64756 |  | COMMENCEMENT PENDING |  | FLAT 495 | Yatesbury Avenue | Birmingham |  | B35 6QR |  | Miss C Edmunds | 07725026790 |  |  |  | Windows & Doors | M Turpin | [33 empty] | Access via 491 Yatesbury & 82 Mere Avenue
12 |  | 69980 |  | COMMENCEMENT PENDING |  | FLAT 497 | Yatesbury Avenue | Birmingham |  | B35 6QR |  | Mr O Higgins |  | 07539217094 |  |  | Windows & Doors | M Turpin | [33 empty] | Access via 491 Yatesbury & 82 Mere Avenue
12 |  | 66816 |  | COMMENCEMENT PENDING |  | FLAT 499 | Yatesbury Avenue | Birmingham |  | B35 6QR |  | Mr SR Ashton |  | 07510220205 | ashtonsteven89@gmail.com |  | Windows & Doors | M Turpin | [33 empty] | Access via 491 Yatesbury & 82 Mere Avenue
19 |  | 68006 |  | COMMENCEMENT PENDING |  | 6 | Heyford Way | Birmingham |  | B35 6JH |  | Mr C O'Sullivan |  | 07505 338867 |  |  | Windows & Doors | P Beahan |  |  |  |  | TS-02/04/24 Text sent for 09/04/24. TS-02/04/24 Tenant text back no, text them asking which days are better. TS-15/04/24 Text sent offering 25/04/24. TS-18/04/24 Called left vm, text & ltr sent. TS-22/04/24 Tenant text no for survey 25/04/24. TS-26/04/24 Text sent for 09/05/24. TS-01/05/24 Called left vm, txt & ltr sent. 14/06 SMS text sent for 27/06. CONFIRMED for 27/06. 01/07 SMS surveyor reported not surveyed on 27/06 due to the condition of the property, await information on this being cleared before re-booking a survey. 16/07 SMS TLO advised property will be available to survey after 29/07/2024
19 |  | 67521 |  | ON HOLD | SEE COMMENTS | FLAT 32 | Kemble Drive | Birmingham |  | B35 6QS |  | Mr T Fulford |  |  |  |  | Windows & Doors | P Beahan |  | 8am to 12 noon |  |  | TS-04/04/24 Letter sent for 18/04/24 as no contact number. TS-17/04/24 Tenant called in to advise that they are moving out in 3 months time and do not want the upheavel of dealing with having the windows changed, emailed client to ask how they want us to proceed with the property. | [28 empty] | Access Via 28 Kemble & 2 Mere Avenue
20 |  | 62237 |  | NO ACCESS SURVEY |  | 58 | Watton Green | Birmingham |  | B35 7JP |  | Miss G Jones | 07942713340 |  |  |  | Windows & Doors | M Turpin |  |  |  | 3 | TS-25/04/24 Text sent for 07/05/24. TS-01/05/24 Called no answser or vm ltr and text sent.No Access on 07/05.29/05 SMS text sent for 10/06. 31/05 SMS called N/A. 03/06 SMS called N/A Lttr sent. 12/06 SMS surveyor reported that no access on 10/06 as turned surveyor away. Emailed Dominie to assist and emailed client to advise.(*Emailed Dominie & client to assist as this date would be 3rd attempt.) 13/06 SMS lttr sent. 24.06.24 SF Received top sheet from Martin, NO ACCESS again which is now the 3rd attempt.
20 |  | 70685 |  | NWR |  | 26 | Abingdon Way | Birmingham |  | B35 6QF |  | Miss A Lewis |  | 07877989612 | abigail.elsie.lewis1998@outlook.com |  | Windows & Doors | P Beahan | 2024-05-30 | 11am to 3pm |  |  | 16/05 SMS text sent for 30/05. 17/05 SMS tenant advised works where already done in December 2023, emailed client to advise and logged as NWR.
20 |  | 69667 |  | NWR |  | 7 | Concorde Drive | Birmingham |  | B35 7EE |  | Miss C Hopkins |  | 07896959369 | cazh86@live.co.uk |  | Windows & Doors | M Turpin | 2024-06-18 | 8am to 2pm |  |  | 04/06 SMS text sent for 18/06. CONFIRMED for 18/06. 20.06.24 SF Received top sheet from Martin, he's advised the property have all new windows & doors already, NWR as per surveyor
20 |  | 68714 |  | NO ACCESS SURVEY | SEE COMMENTS | 20 | Javelin Avenue | Birmingham |  | B35 7LW |  | Miss CL Johnson | 07925824781 |  | cazpuddinghead@gmail.com |  | Windows & Doors | M Turpin |  | 8am to 2pm |  | 3 | TS-12/04/24 Text sent for 23/04/24. TS-15/04/24 Survey CONFIRMED for 23/04/24. TS-23/04/24 Tenant called she can't make today rebooked her for 29/04/24 CONFIRMED. TS-29/04/24 Tenant called in she has a family emergency and can't make today text MT to advise not to attend.14/06 SMS text sent for 27/06. 19/6; AC rang and CONFIRMED for 27/06 - she has requested Dominie doesn't attend her property. 27.06.24 SF Martin called, tenant not home NO ACCESS this is the 3rd NO ACCESS. 03/07 SF sent client & Dominie email advising now 'no access survey'
20 |  | 61431 |  | REFUSAL |  | 28 | Lysander Way | Birmingham |  | B35 7JY |  | Mrs M Waring |  |  |  |  | Windows & Doors | M Turpin | 2024-05-01 | 8am to 2pm |  |  | TS-24/04/24 Ltr sent to the tenant for 01/05/24 as no contact number for tenant. TS-29/04/24 DM did a site visit to get confirmation but tenant is refusing to have her windows and doors replaced.
20 |  | 63681 |  | NWR |  | FLAT 46 | Mere Avenue | Birmingham |  | B35 6QT |  | Miss S Melaney |  | 07493430156 |  |  | Windows & Doors | P Beahan | 2024-04-24 | 8am to 12 noon |  |  | TS-15/04/24 Text sent for 24/04/24. TS-15/04/24 Survey CONFIRMED for 24/04/24. TS-26/04/24 Marked on the diary sheet that the windows were replaced in 2022. TS-08/05/24 Photos received and sent to the client. | [28 empty] | Access via 42 Mere Avenue & 52 Mere Avenue
20 |  | 70576 |  | CANCELLED |  | 5 | Neville Walk | Birmingham |  | B35 7JH |  | Mr M Sharp | 0121 747 3310 | 07799732700 |  |  | Windows & Doors | [34 empty] | *Email from client on 24/05 to advise to remove from the programme.
20 |  | 68312 |  | NO ACCESS SURVEY |  | FLAT 8 | Northolt Drive | Birmingham |  | B35 6QX |  | Mr M Atterbury |  | 07538 213 549 |  |  | Windows & Doors | S Burgess | 2024-06-25 | 8am to 12 noon |  | 3 | TS-04/04/24 Text sent for 16/04/24. TS-08/04/24 Called number nis - ltr sent for 16/04/24. TS-17/04/24 No access for 16/04/24 carded @ 13.15pm - sent to client. 23.05.2423.05.24 SF Sent text for 07.07. 29/05 SMS called no. NIS lttr sent. 10/06 SMS No access for 07/06/24 carded @ 9.30pm - sent to client. 11/06 SMS text sent for 18/06. 13/06 SMS no. NIS lttr sent. 19/06 SMS 3rd no access on 18/06 at 9.03am emailed client.19/06 SMS Dominie arranged direct with tenant to attend on 25/06. 25.06.24 SF Tenant called to advise he missed the survey today AGAIN NO ACCESS X 4th time as arranged by Dominie, emailed Dominie & client to advise what happens next, do we re-book or not. | [28 empty] | Access via 10 Northolt & 471 Yatesbury Avenue
20 |  | 65790 |  | NO ACCESS SURVEY |  | 74 | Watton Green | Birmingham |  | B35 7JP |  | Miss MC Dale | Contact P O'Brian 07931981160 |  |  |  | Windows & Doors | M Turpin | 2024-07-01 | 8am to 2pm |  | 3 | TS-25/04/24 Text sent for 07/05/24. TS-26/04/24 Survey CONFIRMED for 07/05/24.No Access on 07/05. 14/05 SMS text sent for 10/06. CONFIRMED for 10/06. 12/06 SMS surveyor reported that no access on 10/06 as turned surveyor away. Emailed Dominie to assist and emailed client to advise. 14/06 SMS Dominie gave us new contact for this tenant as P O'Brian 07931981160. 1/7; TENANT TURNED AWAY OUR SURVEYOR AGAIN SAYING "NOT TODAY". 3/7; AC emailed Leonie to advise.
Note on F2989: Andrea Cashmore: Front bay does not meet regs

## Installs Booked
Number | Street | Area | Postcode | Tenant Name | Tenant Contact Number | Tenant Contact Number | Tenant Email Address | CASE | TILT TURN | FULLY REVERSE | VERT SLIDER | FIRE | CAVITY CLOSER | SINGLE | DOUBLE | BI-FOLD | IN-LINE SLIDER | FRONT SOLID GRP | FRONT GLAZED GRP | REAR SOLID GRP | REAR GLAZED GRP | SOLID FIRE | GLAZED FIRE | BASIC SHED | INT TOP LIGHT | SEPARATE TOP LIGHT | SIDE LIGHT | comment | Call off number | Delivery Date | scheduled fitting date | Install Time | Installation team | Fitters Pack sent
ERIC - MONDAY 8th JULY
14 | Javelin Avenue | Birmingham | B35 7LW | Miss A Dean | 07930 656 107 |  | mandyjdean@hotmail.co.uk | 16 | [10 empty] | 1 |  | 2 | [6 empty] | 1st day of 3 day fit. CONFIRMED | PG02(W) | 2024-07-04 |  |  |  | 13/06 SMS fitters packs
ADRIAN - MONDAY 8th JULY
80 | Javelin Avenue | Birmingham | B35 7LW | Miss A Grant | 07947 201 836 |  | Ashagrant@hotmail.co.uk | 18 | [10 empty] | 1 |  | 3 | [6 empty] | 1st day of 3 day fit. CONFIRMED | PG02(W) | 2024-07-04 |  |  |  | 13/06 SMS fitters packs
ERIC - TUESDAY 9th JULY
14 | Javelin Avenue | Birmingham | B35 7LW | Miss A Dean | 07930 656 107 |  | mandyjdean@hotmail.co.uk | 16 | [10 empty] | 1 |  | 2 | [6 empty] | 2nd day of 3 day fit. CONFIRMED | PG02(W) | 2024-07-04 |  |  |  | 13/06 SMS fitters packs
ADRIAN - TUESDAY 9th JULY
80 | Javelin Avenue | Birmingham | B35 7LW | Miss A Grant | 07947 201 836 |  | Ashagrant@hotmail.co.uk | 18 | [10 empty] | 1 |  | 3 | [6 empty] | 2nd day of 3 day fit. CONFIRMED | PG02(W) | 2024-07-04 |  |  |  | 13/06 SMS fitters packs
ERIC - WEDNESDAY 10th JULY
14 | Javelin Avenue | Birmingham | B35 7LW | Miss A Dean | 07930 656 107 |  | mandyjdean@hotmail.co.uk | 16 | [10 empty] | 1 |  | 2 | [6 empty] | 3rd day of 3 day fit. CONFIRMED | PG02(W) | 2024-07-04 |  |  |  | 13/06 SMS fitters packs
ADRIAN - WEDNESDAY 10th JULY
80 | Javelin Avenue | Birmingham | B35 7LW | Miss A Grant | 07947 201 836 |  | Ashagrant@hotmail.co.uk | 18 | [10 empty] | 1 |  | 3 | [6 empty] | 3rd day of 3 day fit. CONFIRMED | PG02(W) | 2024-07-04 |  |  |  | 13/06 SMS fitters packs
JIM - WEDNESDAY 10th JULY
18 | Heyford Way | Birmingham | B35 6JH | Mr S B Brown | 01217494098 | 07956 658 295 |  | 10 | [6 empty] | 1 |  |  |  | 1 | [7 empty] | 1 | 1st day of 1.5 day fit. CONFIRMED | PG03(W) | 2024-07-08 |  |  |  | Fitters Packs SF 03/07
ERIC - THURSDAY 11th JULY
19 | Heyford Way | Birmingham | B35 6HY | Mr A Hughes | 07984 536 982 |  |  | 8 | [6 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 1 | 1st day of 1.5 day fit. CONFIRMED | PG03(W) | 2024-07-08 |  |  |  | Fitters Packs SF 03/07
ADRIAN - THURSDAY 11th JULY
25 | Heyford Way | Birmingham | B35 6HY | Miss D Newbold | 07854 247 764 |  |  | 8 | [6 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 1 | CONFIRMED - 1st day of 1.5 day fit - SCAFFOLD REQUIRED - Erect 08.07.24 | PG03(W) | 2024-07-08 | 2024-07-11 | 8am - 3pm | Adrian | Fitters Packs SF 03/07
JIM - THURSDAY 11th JULY
18 | Heyford Way | Birmingham | B35 6JH | Mr S B Brown | 01217494098 | 07956 658 295 |  | 10 | [6 empty] | 1 |  |  |  | 1 | [7 empty] | 1 | 2nd day of 1.5 day fit. CONFIRMED | PG03(W) | 2024-07-08 |  |  |  | Fitters Packs SF 03/07
ERIC - FRIDAY 12th JULY
19 | Heyford Way | Birmingham | B35 6HY | Mr A Hughes | 07984 536 982 |  |  | 8 | [6 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 1 | 2nd day of 1.5 day fit. CONFIRMED | PG03(W) | 2024-07-08 |  |  |  | Fitters Packs SF 03/07
ADRIAN - FRIDAY 12th JULY
25 | Heyford Way | Birmingham | B35 6HY | Miss D Newbold | 07854 247 764 |  |  | 8 | [6 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 1 | CONFIRMED - 1st day of 1.5 day fit - SCAFFOLD REQUIRED - Erect 08.07.24 | PG03(W) | 2024-07-08 | 2024-07-12 | 8am - 11am | Adrian | Fitters Packs SF 03/07
89 | Heyford Way | Birmingham | B35 6JB | Mr R J Hughes | 07704 255 990 |  |  | 8 | [8 empty] | 1 |  | 1 |  | 1 | [5 empty] | 1 | 1st day of 1.5 day fit. CONFIRMED | PG03(W) | 2024-07-08 | 2024-07-12 | 12pm - 3pm | Adrian | Fitters Packs SF 03/07
JIM - FRIDAY 12th JULY
40 | Heyford Way | Birmingham | B35 6JB | Miss K Clarke | 0121 748 3964 | 07947 832 739 |  | 8 | [6 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 1 | 2nd day of 1.5 day fit. CONFIRMED | PG05(W) | 2024-07-11 |  |  |  | Fitters Packs SF 03/07
50 | Heyford Way | Birmingham | B35 6HU | Mr J E Bramwell | 0121 748 1936 | 07848 932 573 | johnbramwell45@yahoo.co.uk | 8 | [6 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 1 | 1st day of 1.5 day fit. 02/07 SMS text sent for 12th & 15th July. 03/07 SMS called left voicemail. 04/07 SMS called N/A Lttr sent | PG03(W) | 2024-07-08 |  |  |  | Fitters Packs SF 03/07
Neil Court - FRIDAY 12th JULY
80 | Javelin Avenue | Birmingham | B35 7LW | Miss A Grant | 07947 201 836 | [22 empty] | 1 x Re-make unit 481 x 226 req deliv 11/07 |  | 2024-07-11
ERIC - MONDAY 15th JULY
78 | Heyford Way | Birmingham | B35 6HU | Mrs A Youssef | 07760 550 633 NIS | 07366459329 |  | 10 | [10 empty] | 1 |  | 1 | [6 empty] | 1st day of 1.5 day fit. 02/07 SMS text sent for 15th & 16th July. 03/07 SMS called no NIS Lttr sent. 08/07 SMS tenant CONFIRMED with TLO on 08/07 | PG03(W) | 2024-07-08 |  |  |  | Fitters Packs SF 03/07
ADRIAN - MONDAY 15th JULY
89 | Heyford Way | Birmingham | B35 6JB | Mr R J Hughes | 07704 255 990 |  |  | 8 | [8 empty] | 1 |  | 1 |  | 1 | [5 empty] | 1 | 2nd day of 1.5 day fit. CONFIRMED | PG03(W) | 2024-07-08 |  |  |  | Fitters Packs SF 03/07
9 | Heyford Way | Birmingham | B35 6HY | Mr T Woodward | 0121 749 2825 | 07572983481 |  | 11 | [10 empty] | 1 |  | 1 | [5 empty] | 1 | 1st day of 1.5 day fit. CONFIRMED | PG03(W) | 2024-07-08 |  |  |  | Fitters Packs SF 03/07
JIM - MONDAY 15th JULY
50 | Heyford Way | Birmingham | B35 6HU | Mr J E Bramwell | 0121 748 1936 | 07848 932 573 | johnbramwell45@yahoo.co.uk | 8 | [6 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 1 | 2nd day of 1.5 day fit. 02/07 SMS text sent for 12th & 15th July. 03/07 SMS called left voicemail. 04/07 SMS called N/A Lttr sent | PG03(W) | 2024-07-08 |  |  |  | Fitters Packs SF 03/07
ERIC - TUESDAY 16th JULY
78 | Heyford Way | Birmingham | B35 6HU | Mrs A Youssef | 07760 550 633 NIS | 07366459329 |  | 10 | [10 empty] | 1 |  | 1 | [6 empty] | 2nd day of 1.5 day fit. 02/07 SMS text sent for 15th & 16th July. 03/07 SMS called no NIS Lttr sent. 08/07 SMS tenant CONFIRMED with TLO on 08/07 | PG03(W) | 2024-07-08 |  |  |  | Fitters Packs SF 03/07
47 | Heyford Way | Birmingham | B35 6HZ | Mrs D M Phillips |  | 07511 960 048 |  | 9 | [10 empty] | 1 |  | 1 | [5 empty] | 1 | 1st day of 1.5 day fit. 11/07 left voicemail for amended date 16 & 17th July. CONFIRMED | PG05(W) | 2024-07-11 |  |  |  | Fitters Packs SF 03/07
ADRIAN - TUESDAY 16th JULY
9 | Heyford Way | Birmingham | B35 6HY | Mr T Woodward | 0121 749 2825 | 07572983481 |  | 11 | [10 empty] | 1 |  | 1 | [5 empty] | 1 | 2nd day of 1.5 day fit. CONFIRMED | PG03(W) | 2024-07-08 |  |  |  | Fitters Packs SF 03/07
74 | Heyford Way | Birmingham | B35 6HU | Miss A O'toole | 07787804787 |  | ange-71@hotmail.co.uk | 10 | [10 empty] | 1 |  | 1 | [6 empty] | 1st day of 1.5 day fit. CONFIRMED | PG04(W) | 2024-07-09 |  |  |  | Fitters Packs SF 03/07
JIM - TUESDAY 16th JULY
FLAT 10 | Northolt Drive | Birmingham | B35 6QX | Mr H Cadby | 07950 391 607 |  |  | 6 | [19 empty] | CONFIRMED for 16/07 | PG04(W) | 2024-07-09 |  |  |  | Fitters Packs SF 03/07
17 | Northolt Drive | Birmingham | B35 6QX | Mrs A O'regan | 07877 826 615 |  |  | 12 | [10 empty] | 1 |  | 2 | [5 empty] | 1 | 1st day of 1.5 day fit. CONFIRMED | PG06(W) | 2024-07-15
ERIC - WEDNESDAY 17th JULY
47 | Heyford Way | Birmingham | B35 6HZ | Mrs D M Phillips |  | 07511 960 048 |  | 8 | [6 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 1 | 2nd day of 1.5 day fit. 11/07 left voicemail for amended date 16 & 17th July. CONFIRMED | PG05(W) | 2024-07-11 |  |  |  | Fitters Packs SF 03/07
ADRIAN - WEDNESDAY 17th JULY
45 | Heyford Way | Birmingham | B35 6HY | Mrs E Hales | 0121747 9889 | 07473 520346 - Daughter | jackiekilday@yahoo.co.uk | 8 | [6 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 1 | 11/07 SMS left voicemail for 17/07 | PG05(W) | 2024-07-11 |  |  |  | Fitters Packs SF 03/07
JIM - WEDNESDAY 17th JULY
17 | Northolt Drive | Birmingham | B35 6QX | Mrs A O'regan | 07877 826 615 |  |  | 12 | [10 empty] | 1 |  | 2 | [5 empty] | 1 | 2nd day of 1.5 day fit. CONFIRMED | PG06(W) | 2024-07-15
ERIC - THURSDAY 18th JULY
39 | Heyford Way | Birmingham | B35 6HU | Mrs J Kilday | 0121 730 1217 | 07775 423 054 | jackiekilday@yahoo.co.uk | 10 | [10 empty] | 1 | [7 empty] | 1 | 2nd day of 1.5 day fit. 11/07 left voicemail to advise needs to be a two day fit to include 18/07 | PG05(W) | 2024-07-11 |  |  |  | Fitters Packs SF 03/07
ADRIAN - THURSDAY 18th JULY
93 | Heyford Way | Birmingham | B35 6HZ | Mrs D M Phillips | 07359 032 693 |  |  | 8 | [10 empty] | 1 |  | 1 | [5 empty] | 1 | 10/07 SMS text sent for 18/07. CONFIRMED | PG05(W) | 2024-07-11 |  |  |  | Fitters Packs SF 03/07
JIM - THURSDAY 18th JULY
19 | Northolt Drive | Birmingham | B35 6QX | Miss H O'Coy | 07462 777 770 |  | hailz_ocoy@yahoo.com | 12 | [10 empty] | 1 |  | 1 | [6 empty] | 2nd day of 1.5 day fit. 08/07 SMS text sent for 17 & 18. 11/07 SMS called N/A lttr sent. CONFIRMED | PG06(W) | 2024-07-15
ERIC - FRIDAY 19th JULY
39 | Heyford Way | Birmingham | B35 6HU | Mrs J Kilday | 0121 730 1217 | 07775 423 054 | jackiekilday@yahoo.co.uk | 10 | [10 empty] | 1 | [7 empty] | 1 | 2nd day of 1.5 day fit. 11/07 left voicemail to advise needs to be a two day fit to include 18/07 | PG05(W) | 2024-07-11 |  |  |  | Fitters Packs SF 03/07
JIM - FRIDAY 19th JULY
21 | Northolt Drive | Birmingham | B35 6QX | Miss E McLean |  | 07764 707 718 | elliemaymclean@icloud.com | 10 | [19 empty] | 1st day of 1.5 day fit. NO SOLVENT TO BE USED. 11/07 text sent for 19th & 23rd. 15/07 SMS left voicemail. | PG08(W) | 2024-07-18
ADRIAN - FRIDAY 19th JULY
101 | Heyford Way | Birmingham | B35 6JB | Miss N Campbell | 0121 748 3964 | 07306 617 934 |  | 8 | [6 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 1 | 1st day of 1.5 day fit. 10/07 SMS text sent for 19 & 22 July. CONFIRMED | PG05(W) | 2024-07-11 |  |  |  | Fitters Packs SF 03/07
ADRIAN - Monday 22nd JULY
14 | Northolt Drive | Birmingham | B35 6QX | Mrs H Evans | 07472 266 832 |  | hayley_chamberlain@hotmail.co.uk | 5 | [10 empty] | 1 |  | 1 | [5 empty] | 1 | (Scaff cancelled as not req) Install 22/07. CONFIRMED | PG04(W) | 2024-07-09 |  |  |  | Fitters Packs SF 03/07
16 | Northolt Drive | Birmingham | B35 6QX | Mr J Leek | 07384 277 336 | 07548541014 | jonathanleek66@live.com | 6 | [10 empty] | 1 | [8 empty] | (Access req no. 14) 10/07 SMS text sent for 22/07. CONFIRMED | PG06(W) | 2024-07-15
JIM - Monday 22nd JULY
25 | Northolt Drive | Birmingham | B35 6QX | Mrs B Wardell |  | 07384 626 802 |  | 6 | [10 empty] | 1 |  | 1 | [6 empty] | 12/07 SMS text sent for 22/07. CONFIRMED | PG07(W) | 2024-07-16
ERIC -Monday 22nd JULY ON ANNUAL LEAVE
ADRIAN - Tuesday 23rd JULY
80 | Javelin Avenue | Birmingham | B35 7LW | Miss A Grant | 07947 201 836 | [22 empty] | SF 1 x Remake unit, Win No2 401 x 1020, delivery 15.07 & Cill. DOWNSTAIRS BAY. 16/07 SMS left voicemail. CONFIRMED |  | 2024-07-15
14 | Javelin Avenue | Birmingham | B35 7LW | Miss A Dean | 07930 656 107 |  | mandyjdean@hotmail.co.uk | 1 | [19 empty] | 1 x Bed remake glazed frame reordered for delivery 18/7, surveyor error. Plus 1 X remake unit 441 x 936. |  | 2024-07-18
JIM - Tuesday 23rd JULY
FLAT 7 | Northolt Drive | Birmingham | B35 6QX | Mrs Adobor | 07947 625 350 |  | evelyn_mens@yahoo.com | 5 | [12 empty] | 1 | [5 empty] | 1 | SCAFFOLD Ordered Mon 22/07 COPY DOM IN. Access via 9 Northolt & 2 Mere Avenue. (Flat 5 & 7 are under same Scaffold quote so need to be done together) 12/07 SMS text tenant for Scaff on 22/07 & install 23/07. CONFIRMED | PG07(W) | 2024-07-16
ERIC -Tueday 23rd JULY ON ANNUAL LEAVE
ADRIAN - Wednesday 24th JULY
18 | Northolt Drive | Birmingham | B35 6QX | Mr C Lee | 07572 168 119 |  | cameronlee03@live.co.uk | 9 | [5 empty] | 2 |  |  |  |  | 1 | [8 empty] | Scaffold on 23/07 COPY DOM IN. F/bed pitch roof - 1st floor flat - access via Flat 20 (flat 20 still at sent 4 pricing stage) for 1st Floor windows.(18 & 22 need doing together due to Scaffolding)12/07 SMS text for 24/07. CONFIRMED | PG06(W) | 2024-07-15
JIM - Wednesday 24th JULY
FLAT 5 | Northolt Drive | Birmingham | B35 6QX | Miss A Holder | 07404 868 654 | 07424 790 036 | mandiejh1973@gmail.com | 5 | [12 empty] | 1 | [5 empty] | 1 | SCAFFOLD Ordered Mon 22/07 COPY DOM IN required under flat 7. Acess via 9 Northolt & 2 Mere Avenue (Flat 5 & 7 are under same Scaffold quote so need to be done together) 12/07 SMS text tenant for Scaff on 22/07 & install 24/07. 15/07 SMS left voicemail. 16.07.24 SF CONFIRMED | PG07(W) | 2024-07-16
ERIC - Wednesday 24th JULY
9 | Northolt Drive | Birmingham | B35 6QX | Mrs A Fletcher | 0121 7487 110 | 07511 467 413 |  | 6 | [10 empty] | 1 | [8 empty] | Re-scheduled from Monday 15/07 to sent text for 24/07. CONFIRMED | PG04(W) | 2024-07-09 |  |  |  | Fitters Packs SF 03/07
ADRIAN - Thursday 25th JULY
22 | Northolt Drive | Birmingham | B35 6QX | Miss S Sterling | 07507 642 265 |  | sabrinasterling83@gmail.com | 9 | [5 empty] | 2 |  |  |  |  | 1 | [8 empty] | Scaffold on 23/07 COPY DOM IN. Ded/cupboard pitch roof. Access via flat 24 to 1st floor (18 & 22 need doing together due to Scaffolding) 12/07 SMS text for 25/07. CONFIRMED | PG06(W) | 2024-07-15
JIM - Thursday 25th JULY
40 | Heyford Way | Birmingham | B35 6JB | Miss K Clarke | 0121 748 3964 | 07947 832 739 |  | 8 | [6 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 1 | 1st day of 1.5 day fit. CONFIRMED for 25/07 & 26/07 | PG05(W) | 2024-07-11 |  |  |  | Fitters Packs SF 03/07
ERIC - Thursday 25th JULY
11 | Northolt Drive | Birmingham | B35 6QX | Miss T Scrivens | 07307 000 453 NIS |  |  | 10 | [10 empty] | 1 | [8 empty] | 1st day of 1.5 day fit. 12/07 SMS text sent for 25 & 26 July. 15/07 SMS called no NIS Lttr sent | PG04(W) | 2024-07-09 |  |  |  | Fitters Packs SF 03/07
ADRIAN - Friday 26th JULY - ON ANNUAL LEAVE UNITL 02/08
JIM - Friday 26th JULY
40 | Heyford Way | Birmingham | B35 6JB | Miss K Clarke | 0121 748 3964 | 07947 832 739 |  | 8 | [6 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 1 | 2nd day of 1.5 day fit. 12/07 SMS text sent for 25 & 26 July. 15/07 SMS left voicemail. CONFIRMED for 25/07 & 26/07 | PG05(W) | 2024-07-11 |  |  |  | Fitters Packs SF 03/07
28 | Northolt Drive | Birmingham | B35 6QX | Miss C Butlin |  | 07508 400 061 | clairapeterButlin17@gmail.com | 5 | [10 empty] | 1 | [8 empty] | 17/07 SMS text for 26/07 | PG07(W) | 2024-07-16
ERIC - Friday 26th JULY
11 | Northolt Drive | Birmingham | B35 6QX | Miss T Scrivens | 07307 000 453 NIS |  |  | 10 | [10 empty] | 1 | [8 empty] | 2nd day of 1.5 day fit. 12/07 SMS text sent for 25 & 26 July. 15/07 SMS called no NIS Lttr sent | PG04(W) | 2024-07-09 |  |  |  | Fitters Packs SF 03/07
24 | Northolt Drive | Birmingham | B35 6QX | Mr D Holmes | 01213111804 | 07534 737 626 |  | 4 | [12 empty] | 1 | [6 empty] | 17/07 SMS text for 26/07 | PG06(W) | 2024-07-15
JIM - Monday 29th JULY
12 | Northolt Drive | Birmingham | B35 6QX | Miss J Flanagan | 07972 262 8256 | 07972 262850 | flanners07@hotmail.co.uk | 10 | [10 empty] | 1 |  | 1 | [6 empty] | 1st day of 1.5 fit. 17/07 SMS text for 29/07 & 30/07 | PG04(W) | 2024-07-09 |  |  |  | Fitters Packs SF 03/07
ERIC - Monday 29th JULY
15 | Northolt Drive | Birmingham | B35 6QX | Mrs S Cattell | 07498 590 107 |  |  | 10 | [10 empty] | 1 |  | 1 | [6 empty] | 1st day of 1.5 fit. 17/07 SMS text for 29/07 & 30/07. CONFIRMED | PG06(W) | 2024-07-15
JIM - Tuesday 30th JULY
12 | Northolt Drive | Birmingham | B35 6QX | Miss J Flanagan | 07972 262 8256 | 07972 262850 | flanners07@hotmail.co.uk | 10 | [10 empty] | 1 |  | 1 | [6 empty] | 2nd day of 1.5 fit. 17/07 SMS text for 29/07 & 30/07 | PG04(W) | 2024-07-09 |  |  |  | Fitters Packs SF 03/07
FLAT 1 | Northolt Drive | Birmingham | B35 6QX | Mr M Brookes |  | 07984 225 726 |  | 5 | [5 empty] | 2 | [13 empty] | Acess via 9 Northolt & 2 Mere Avenue. NO SOLVENT CLEANER ALLOWED. SCAFFOLD quote BSL 12/07-3 req 22/07. 17/07 SMS text sent for 30/07 | PG08(W) | 2024-07-18
ERIC - Tuesday 30th JULY
15 | Northolt Drive | Birmingham | B35 6QX | Mrs S Cattell | 07498 590 107 |  |  | 10 | [10 empty] | 1 |  | 1 | [6 empty] | 2nd day of 1.5 fit. 17/07 SMS text for 29/07 & 30/07. CONFIRMED | PG06(W) | 2024-07-15
FLAT 3 | Northolt Drive | Birmingham | B35 6QX | Mr P Mulholland |  | 07756 059 115 |  | 3 | [5 empty] | 1 | [13 empty] | SCAFFOLD - Bath/lounge combi pitch roof. Acess to rear through flat 469 Yatesbury Avenue. Acess via 9 Northolt & 2 Mere Avenue. Scaffold quote BSL 12/07-4 req 22/07. 17/07 SMS text sent for 30/07. CONFIRMED | PG08(W) | 2024-07-18
JIM - Wednesday 31st JULY
23 | Northolt Drive | Birmingham | B35 6QX | Miss C Ansell |  | 07542 011 929 | clara_bell@hotmail.co.uk | 10 | [10 empty] | 1 |  | 1 | [6 empty] | 1st day of 1.5 fit. 17/07 SMS text sent for 31/07 & 01/08 | PG07(W) | 2024-07-16
ERIC -Wednesday 31st JULY
JIM - Thursday 1st AUGUST
23 | Northolt Drive | Birmingham | B35 6QX | Miss C Ansell |  | 07542 011 929 | clara_bell@hotmail.co.uk | 10 | [10 empty] | 1 |  | 1 | [6 empty] | 2nd day of 1.5 fit. 17/07 SMS text sent for 31/07 & 01/08 | PG07(W) | 2024-07-16
FLAT 6 | Northolt Drive | Birmingham | B35 6QX | Mr T Gould | 07835 472 041 |  |  | 4 | [5 empty] | 2 | [12 empty] | 1 | SCAFFOLD REQ 29/07. Ref :- BSL 12/07-2 (same as no. Flat 4 & 6 as need to be done together)NO SOLVENT COPD - Access to rear through flat 10. Tenant has lung & stomach cancer is happy to proceed - FITTERS DO NOT ATTEND IF YOU HAVE ANY BUGS. Access via 10 Northolt & 471 Yatesbury Avenue. 17/07 SMS text sent for 01/08 | PG07(W) | 2024-07-16
ERIC - Thursday 1st AUGUST
FLAT 4 | Northolt Drive | Birmingham | B35 6QX | Miss O Shahbazi |  | 07463 894 102 | n.shahbazi82@yahoo.com | 4 | [5 empty] | 2 | [12 empty] | 1 | SCAFFOLD REQ 29/07. Ref :- BSL 12/07-2 (same as no. Flat 4 & 6 as need to be done together)1st floor - Acess to rear through 471 Yatesbury Avenue. Access via 10 Northolt & 471 Yatesbury Avenue. 17/07 SMS text sent for 01/08. CONFIRMED | PG07(W) | 2024-07-16
JIM - Friday 2nd AUGUST
FLAT 27 | Northolt Drive | Birmingham | B35 6QX | Miss Q Mapp |  | 07903 811 842 | queshia-teann.mapp@hotmail.co.uk | 5 | [5 empty] | 2 | [13 empty] | Acess via 18 Mere Avenue & 25 Northolt Drive. SCAFFOLD. Quote BSL 12/07-5. Scaff req 29/07. 17/07 SMS text sent for 02/08. CONFIRMED | PG08(W) | 2024-07-18
FLAT 34 | Northolt Drive | Birmingham | B35 6QX | Miss S Southcombe | 07773 354453 | 07368 455 874 | southylee@yahoo.co.uk | 4 | [5 empty] | 2 | [12 empty] | 1 | SCAFFOLD quote BSL 12/07-7 - Lounge balcony - Access via 32 Northolt Drive & 20 Mere Avenue. *Tenant will need RLO support during fitting. NO SOLVENT TO BE USED. Scaff req 29/07. 17/07 SMS text sent for 02/08 | PG08(W) | 2024-07-18
ERIC - Friday 2nd AUGUST
31 | Baginton Road | Birmingham | B35 6JS | Mrs M Cullen | 0121 747 7986 | 07971715764 |  | 5 | [12 empty] | 1 | [7 empty] | PG09(W) | 2024-08-01
JIM - MONDAY 5th AUGUST
35 | Baginton Road | Birmingham | B35 6JS | Miss L P Tye | 07985 376 516 |  |  | 6 | [10 empty] | 1 |  | 1 | [6 empty] | 17/07 SMS text sent for 02/08. CONFIRMED. 18/07 SMS tenant called to cancel 02/08, text sent to offer 05/08. CONFIRMED | PG09(W) | 2024-08-01
ERIC - MONDAY 5th AUGUST
37 | Baginton Road | Birmingham | B35 6JS | Mrs P Bermingham | 07757 383 294 | 0121 408 2804 |  | 5 | [10 empty] | 1 | [9 empty] | PG09(W) | 2024-08-01
ADRIAN - MONDAY 5th AUGUST
38 | Baginton Road | Birmingham | B35 6JE | Miss S Blackburn | 07958642315 | 07865 349 608 |  | 12 | [12 empty] | 1 | [6 empty] | 1 of 1.5 days. Son has ADHA & Autism - No Sovlent - SCAFFOLD F/bed pitch roof | PG09(W) | 2024-08-01
JIM - TUESDAY 6th AUGUST
66 | Javelin Avenue | Birmingham | B35 7LW | Mrs A Rogers | 07776 286 239 |  |  | 11 | [10 empty] | 1 |  | 1 | [5 empty] | 1 | 1 of 1.5 days.On holiday until after 5th August. 05/07 SMS re-make glass unit req deliv 11/07 | PG02(W) | 2024-07-11
ERIC - TUESDAY 6th AUGUST
2 | Baginton Road | Birmingham | B35 6HN | Mrs D Woolaston |  | 07940411081 |  | 10 | [10 empty] | 1 |  | 1 |  |  |  |  | 1 | 2 | 1 of 1.5 days | PG09(W) | 2024-08-01
ADRIAN - TUESDAY 6th AUGUST
38 | Baginton Road | Birmingham | B35 6JE | Miss S Blackburn | 07958642315 | 07865 349 608 |  | 12 | [12 empty] | 1 | [6 empty] | 2nd of 1.5 days. Son has ADHA & Autism - No Sovlent - SCAFFOLD F/bed pitch roof | PG09(W) | 2024-08-01
JIM - WEDNESDAY 7th AUGUST
66 | Javelin Avenue | Birmingham | B35 7LW | Mrs A Rogers | 07776 286 239 |  |  | 11 | [10 empty] | 1 |  | 1 | [5 empty] | 1 | 2nd of 1.5 days.On holiday until after 5th August. 05/07 SMS re-make glass unit req deliv 11/07 | PG02(W) | 2024-07-11
ERIC - WEDNESDAY 7th AUGUST
2 | Baginton Road | Birmingham | B35 6HN | Mrs D Woolaston |  | 07940411081 |  | 10 | [10 empty] | 1 |  | 1 |  |  |  |  | 1 | 2 | 2nd day of 1.5 | PG09(W) | 2024-08-01
ADRIAN - WEDNESDAY 7th AUGUST
JIM - THURSDAY 8th AUGUST
FLAT 29 | Northolt Drive | Birmingham | B35 6QX | Mr D Kelleher |  | 07543 339 344 | dkelleher26@gmail.com | 3 | [5 empty] | 1 | [12 empty] | 1 | COPD No Solvent - Acess via 18 Mere Avenue & 25 Northolt Drive. SCAFFOLD quote BSL 12/07-6. SCAFFOLD REQ 29/07. 17/07 SMS text sent for 01/08. Tenant declined 01/08 as away until 07/08 so text for 08/08. CONFIRMED | PG08(W) | 2024-07-18
ERIC - THURSDAY 8th AUGUST
ADRIAN - THURSDAY 8th AUGUST
JIM - FRIDAY 9th AUGUST
26 | Northolt Drive | Birmingham | B35 6QX | Miss M O'Loughlin | 07736 941 862 | 07710651416 | Megz_christina@hotmail.com | 6 | [19 empty] | Re-scheduled as prev no fitter, do not move from 09/08 | PG07(W) | 2024-07-16
ERIC - FRIDAY 9th AUGUST
ADRIAN - FRIDAY 9th AUGUST
Allocate Heyfords (1.5 days fit) to Eric & Adrian after 10th July
Allocate Jim to Northolt after 12th July (Will be changed to Graham as JIM will go on Riverside installs from the 23rd June)
ERIC ON LEAVE 22nd & 23RD JULY & from 22nd August - 18th September
ADRIAN ON LEAVE 26/07/2024 - 02/08/2024 & 11/08/2024 - 19/08/2024
JIM Mc DONALD ON LEAVE 15/8/24 till 30/8/24 all dates inclusive
DO NOT SCHEDULE - SCAFFOLDING AWAITING QUOTES OR QUERY
FLAT 38 | Northolt Drive | Birmingham | B35 6QX | Mr B Boyle |  | 07719 866 234 |  | 6 | [5 empty] | 1 | [13 empty] | Tenant has epilepsy. Access via 32 Northolt Drive & 20 Mere Avenue. Flat 38 & 40 need Scaff & install together, chased DA on 12/07 | PG08(W) | 2024-07-18
77 | Blenheim Way | Birmingham | B35 7JF | Void |  |  |  | 5 | [10 empty] | 1 |  | 1 | [6 empty] | Void Property contact Leonie Hammond for access. 12/07 SMS emailed Leionie to req access on 31/07, awaiting reply. 17/07 chased with client again. Client will advise when available. | PG01(W) | 2024-04-17 |  |  |  | DA collected
TO BE ALLOCATED
19 | Heyford Way | Birmingham | B35 6HY | Mr A Hughes | 07984 536 982 | [22 empty] | 1 x remake unit 552 X 606 |  | 2024-07-18
19 | Heyford Way | Birmingham | B35 6HY | Mr A Hughes | 07984 536 982 | [22 empty] | 1 x remake unit 481 x 241 & 256 x 661 |  | 2024-07-23
25 | Heyford Way | Birmingham | B35 6HY | Miss D Newbold | 07854 247 764 | [22 empty] | 2 remake units ; 276 x 656 cotswold and 568 x 811. |  | 2024-07-18
50 | Heyford Way | Birmingham | B35 6HU | Mr J E Bramwell | 0121 748 1936 | 07848 932 573 | johnbramwell45@yahoo.co.uk | [20 empty] | 1 x remake unit 441 x 886 |  | 2024-07-18
50 | Heyford Way | Birmingham | B35 6HU | Mr J E Bramwell | 0121 748 1936 | 07848 932 573 | johnbramwell45@yahoo.co.uk | [20 empty] | 15/07 SMS 1 x re-make unit 654 x 1803 |  | 2024-07-23
89 | Heyford Way | Birmingham | B35 6JB | Mr R J Hughes | 07704 255 990 | [22 empty] | 15/07 SMS 1 x rev dims for Lounge flag frame and glass 480 x 1185, survey error req deliv 23/07 |  | 2024-07-23
78 | Heyford Way | Birmingham | B35 6HU | Mrs A Youssef | 07760 550 633 NIS | 07366459329 | [21 empty] | 15/07 SMS 4 x glass re-makes 518 x 961 & 516 x 961 & 441 x 961 & 516 x 816 req deliv 23/07 |  | 2024-07-23
45 | Heyford Way | Birmingham | B35 6HY | Mrs E Hales | 0121747 9889 | 07473 520346 - Daughter | jackiekilday@yahoo.co.uk | [20 empty] | 15/07 SMS re-make glass unit 320 x 1,141 req deliv 23/07 |  | 2024-07-23
40 | Heyford Way | Birmingham | B35 6JB | Miss K Clarke | 0121 748 3964 | 07947 832 739 | [21 empty] | 15/07 SMS re-make glass unit 552 x 606 req deliv 23/07 |  | 2024-07-23
18 | Heyford Way | Birmingham | B35 6JH | Mr S B Brown | 01217494098 | 07956 658 295 | [21 empty] | 15/07 SMS re-make glass units 546 x 1783 & 295 x 741 req deliv 23/07 |  | 2024-07-23
17 | Northolt Drive | Birmingham | B35 6QX | Mrs A O'regan | 07877 826 615 | [22 empty] | 16/07 SMS re-make 461 x 871 req deliv 23/07/24 |  | 2024-07-23
9 | Heyford Way | Birmingham | B35 6HY | Mr T Woodward | 0121 749 2825 | 07572983481 | [21 empty] | 16/07 SMS re-make 441 x 886 req deliv 23/07 |  | 2024-07-23
FLAT 10 | Northolt Drive | Birmingham | B35 6QX | Mr H Cadby | 07950 391 607 | [22 empty] | 16/07 SF full bathroom remake frame & glass |  | 2024-07-30
47 | Heyford Way | Birmingham | B35 6HZ | Mrs D M Phillips |  | 07511 960 048 | [21 empty] | 18/07 SMS re-make 441 x 886 req deliv 30/07 |  | 2024-07-30
10 | Baginton Road | Birmingham | B35 6HN | Mrs S Mobbs | 01217491274 | 07521 031 740 | moobssally@yahoo.co.uk | 11 | [10 empty] | 1 |  | 1 | [5 empty] | 1 | 1 of 1.5 days.TLO - 10 Bagington, tenant is lady who has multiple health issues as well as brittle bones, the property has a lot of ‘stuff’ in two of the bedrooms which will make this hard for fitters. After speaking to Darren, I am happy to support this tenant, move the stuff for her, and stay present whilst fitting is taking place., I will make housing officer aware but if we could update to tracker to ensure I am present for fitting that would be great. (see attached image 3 and 4). No Solvent - F/bed x 2 pitched roof. Blinds fitted to 2 x kitchen windows (Schedule after 10th August...tenant on hols & copy TLO in) | PG09(W) | 2024-08-01
19 | Northolt Drive | Birmingham | B35 6QX | Miss H O'Coy | 07462 777 770 |  | hailz_ocoy@yahoo.com | 12 | [10 empty] | 1 |  | 1 | [6 empty] | 1.5 day fit. | PG06(W) | 2024-07-15
40 | Baginton Road | Birmingham | B35 6JE | Mr N S Mustafa | 01217497673 | 07305 545 492 |  | 10 | [10 empty] | 1 | [7 empty] | 1 | SCAFFOLD F/bed x 2 pitch roof. | PG09(W) | 2024-08-01
2 | Baginton Road | Birmingham | B35 6HN | Mrs D Woolaston |  | 07940411081 |  | 10 | [10 empty] | 1 |  | 1 |  |  |  |  | 1 | 2 |  | PG09(W) | 2024-08-01
130 | Watton Green | Birmingham | B35 7JT | Miss B Bonner | 07818650367 | 0121 574 2835 |  | 11 | [10 empty] | 1 |  | 1 | [7 empty] | PG10(W) | 2024-08-02
140 | Watton Green | Birmingham | B35 7JT | Mrs L Round | 07368 589 897 | 0121 572-0644 | lainey-01@hotmail.co.uk | 11 | [10 empty] | 1 |  | 1 | [7 empty] | PG10(W) | 2024-08-02
142 | Watton Green | Birmingham | B35 7JT | Miss G Powell |  | 07496 569 312 | spiderladyuk07@hotmail.com OR gaynapowell@outlook.com | 11 | [10 empty] | 1 |  | 1 | [7 empty] | PG10(W) | 2024-08-02
60 | Watton Green | Birmingham | B35 7JP | Mr & Mrs David Nelson | 0121 682 5256 | 07961 096 673 | Davienelson68@gmail.com | 10 | [10 empty] | 1 |  | 1 | [7 empty] | PG10(W) | 2024-08-02
82 | Heyford Way | Birmingham | B35 6HU | Miss N Clarke | 0121 747 9892 | 07530 588 432 |  | 11 | [10 empty] | 1 |  | 1 | [6 empty] | *5 missing windows*
107 | Hawker Drive | Birmingham | B35 7EA | Miss D Johns |  | 077 292 55 769 | dawnjohns1963@yahoo.com | 13 | [6 empty] | 1 |  |  |  | 1 | [8 empty] | *TLO to attend on fitting date | PG11(W) | 2024-08-05

## Surveys Booked
Pioneer Group - Tuesday 9th April - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
57A | Heyford Way | Birmingham | B35 6HZ | Miss S Trevis | 0121 747 1622 | 07966545174 |  | Windows & Doors | P Beahan | 2024-04-09 | 8am to 12pm | CONFIRMED for 09/04/24
57B | Heyford Way | Birmingham | B35 6HZ | Miss R E Anderson | 0121 747 3136 | 07711956370 | rosebeth54@gmail.com | Windows & Doors | P Beahan | 2024-04-09 | 8am to 12pm | CONFIRMED for 09/04/24
57C | Heyford Way | Birmingham | B35 6HZ | Mr C Kinsella |  | 7359238603 |  | Windows & Doors | P Beahan | 2024-04-09 | 8am to 12pm | TS-02/04/24 Txt sent. TS-03/04/24 Called number NIS sent ltr.
57D | Heyford Way | Birmingham | B35 6HZ | Mrs V M Hughes |  |  |  | Windows & Doors | P Beahan | 2024-04-09 | 8am to 12pm | TS-02/04/24 Ltr sent for 09/04/24.
57E | Heyford Way | Birmingham | B35 6HZ | Miss L Scott | 01212182712 | 079046 85 105 |  | Windows & Doors | P Beahan | 2024-04-09 | 8am to 12pm | TS-02/04/24 Txt sent. TS-03/04/24 Called left vm, txt & ltr sent.
57F | Heyford Way | Birmingham | B35 6HZ | Miss S Cooke | 0121 406 5559 |  |  | Windows & Doors | P Beahan | 2024-04-09 | 11am to 3pm | CONFIRMED for 09/04/24 - call tenant 20 mins before arrival.
72 | Heyford Way | Birmingham | B35 6HU | Mrs S Goulding | 01217485932 | 07951645495 |  | Windows & Doors | P Beahan | 2024-04-09 | 11am to 3pm | CONFIRMED for 09/04/24
74 | Heyford Way | Birmingham | B35 6HU | Miss A O'toole | 07787804787 |  | ange-71@hotmail.co.uk | Windows & Doors | P Beahan | 2024-04-09 | 11am to 3pm | CONFIRMED for 09/04/24
Pioneer Group - Tuesday 9th April - Steve Burgess
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
1 | Bicester Square | Birmingham | B35 6HR | Ms G Farbrother | 07723 067036 |  |  | Windows & Doors | S.Burgess | 2024-04-09 | 8am to 12pm | CONFIRMED for 09/04/24
3 | Bicester Square | Birmingham | B35 6HR | Miss K Burt | 07454317261 | 07454 317 261 | kayburt1965@gmail.com | Windows & Doors | S.Burgess | 2024-04-09 | 8am to 12pm | CONFIRMED for 09/04/24
5 | Bicester Square | Birmingham | B35 6HR | Mrs S Collins | 07428113447 | 07428175079 | p.collins015@sky.com | Windows & Doors | S.Burgess | 2024-04-09 | 8am to 12pm | CONFIRMED for 09/04/24
26 | Bicester Square | Birmingham | B35 6HR | Mrs J Hughes |  |  |  | Windows & Doors | S.Burgess | 2024-04-09 | 8am to 12pm | TS-02/04/24 Ltr sent for 09/04/24.
31 | Baginton Road | Birmingham | B35 6JS | Mrs M Cullen | 0121 747 7986 | 07971715764 |  | Windows & Doors | S.Burgess | 2024-04-09 | 8am to 12pm | CONFIRMED for 09/04/24
33 | Baginton Road | Birmingham | B35 6JS | Mr I Turner | 01217483216 |  |  | Windows & Doors | S.Burgess | 2024-04-09 | 8am to 12pm | TS-02/04/24 Called no answer or vm letter sent. TS-03/04/24 Called no answer/vm.
35 | Baginton Road | Birmingham | B35 6JS | Miss L P Tye | 07985376516 |  |  | Windows & Doors | S.Burgess | 2024-04-09 | 11am to 3pm | CONFIRMED for 09/04/24
37 | Baginton Road | Birmingham | B35 6JS | Mrs P Bermingham | 07757383294 | 0121 408 2804 |  | Windows & Doors | S.Burgess | 2024-04-09 | 11am to 3pm | CONFIRMED for 09/04/24
2 | Baginton Road | Birmingham | B35 6HN | Mrs D Woolaston | 07940411081 |  |  | Windows & Doors | S.Burgess | 2024-04-09 | 11am to 3pm | CONFIRMED for 09/04/24
Pioneer Group - Wednesday 10th April - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
76 | Heyford Way | Birmingham | B35 6HU | Mrs P Brown | 079254 14 091 |  |  | Windows & Doors | P Beahan | 2024-04-10 | 8am to 12pm | TS-02/04/24 Txt sent. TS-03/04/24 Called number NIS ltr sent.
78 | Heyford Way | Birmingham | B35 6HU | Mrs A Youssef | 07366459329 | 07760 550 633 |  | Windows & Doors | P Beahan | 2024-04-10 | 8am to 12pm | CONFIRMED FOR 10/04/24
82 | Heyford Way | Birmingham | B35 6HU | Miss N Clarke | 0121 747 9892 | 07530 588 432 |  | Windows & Doors | P Beahan | 2024-04-10 | 8am to 12pm | CONFIRMED for 10/04/24
8 | Heyford Way | Birmingham | B35 6JH | Mrs CEJ Cluley | 07596 913229 |  | catbro09@hotmail.com | Windows & Doors | P Beahan | 2024-04-10 | 11am to 3pm | CONFIRMED for 10/04/24 - please call 30 mins before arrival
9 | Heyford Way | Birmingham | B35 6HY | Mr T Woodward | 0121 749 2825 | 07572983481 |  | Windows & Doors | P Beahan | 2024-04-10 | 11am to 3pm | CONFIRMED for 10/04/24 - Please do not attend until after 1pm.
18 | Heyford Way | Birmingham | B35 6JH | Mr S B Brown | 01217494098 | 07956 658 295 |  | Windows & Doors | P Beahan | 2024-04-10 | 11am to 3pm | CONFIRMED for 10/04/24
Pioneer Group - Wednesday 10th April - Steve Burgess
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
10 | Baginton Road | Birmingham | B35 6HN | Mrs S Mobbs | 01217491274 | 07521031740 | moobssally@yahoo.co.uk | Windows & Doors | S.Burgess | 2024-04-10 | 8am to 12pm | CONFIRMED for 10/04/24.
38 | Baginton Road | Birmingham | B35 6JE | Miss S Blackburn | 7865349608 | 07958642315 |  | Windows & Doors | S.Burgess | 2024-04-10 | 8am to 12pm | TS-02/04/24 Txt sent. TS-03/04/24 Called left vm, text & ltr sent
40 | Baginton Road | Birmingham | B35 6JE | Mr N S Mustafa | 01217497673 | 07446412695 |  | Windows & Doors | S.Burgess | 2024-04-10 | 8am to 12pm | CONFIRMED for 10/04/24
20 | Bicester Square | Birmingham | B35 6HR | Mr J Powell | 0121 747 1197 |  |  | Windows & Doors | S.Burgess | 2024-04-10 | 8am to 12pm | CONFIRMED for 10/04/24.
24 | Bicester Square | Birmingham | B35 6HR | Miss P A Mooney | 07761898550 |  | pamelamooney@live.co.uk | Windows & Doors | S.Burgess | 2024-04-10 | 8am to 12pm | CONFIRMED for 10/04/24.
FLAT 2 Block 14 | Bicester Square | Castle Vale | B35 6HR | Mrs N W Griffiths | 07751 745 796 | 07742842219 |  | Windows & Doors | S.Burgess | 2024-04-10 | 11am to 3pm | CONFIRMED for 10/04/24 after 12pm (nurses leave by 12pm).
FLAT 3 Block 14 | Bicester Square | Birmingham | B35 6HR | Mr D Hobbs | 07368395454 |  |  | Windows & Doors | S.Burgess | 2024-04-10 | 11am to 3pm | TS-02/04/24 Txt sent. TS-03/04/24 Called left vm, text & ltr sent
Pioneer Group - Thursday 11th April - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
19 | Heyford Way | Birmingham | B35 6HY | Mr A Hughes | 07984536982 | 0121 749 1312 |  | Windows & Doors | P Beahan | 2024-04-11 | 8am to 12pm | CONFIRMED for 11/04/24
25 | Heyford Way | Birmingham | B35 6HY | Miss D Newbold | 07854247764 |  |  | Windows & Doors | P Beahan | 2024-04-11 | 8am to 12pm | CONFIRMED for 11/04/24
32 | Heyford Way | Birmingham | B35 6HU | Miss L Wood | 07903 305463 |  | lisa_1970@iphone.com | Windows & Doors | P Beahan | 2024-04-11 | 8am to 12pm | TS-02/04/24 Txt sent. TS-04/04/24 Called left vm, txt & ltr sent.
33 | Heyford Way | Birmingham | B35 6HY | Miss D Banner | 07714469572 | 07714469572 | dannioliver@me.com | Windows & Doors | P Beahan | 2024-04-11 | 8am to 12pm | CONFIRMED for 11/04/24
37 | Heyford Way | Birmingham | B35 6HY | Miss S McIntosh | 07523 980992 | 0121 480 1351 |  | Windows & Doors | P Beahan | 2024-04-11 | 11am to 3pm | CONFIRMED for 11/04/24
39 | Heyford Way | Birmingham | B35 6HY | Mrs J Kilday | 0121 730 1217 | 07775423054 | jackiekilday@yahoo.co.uk | Windows & Doors | P Beahan | 2024-04-11 | 11am to 3pm | CONFIRMED for 11/04/24
40 | Heyford Way | Birmingham | B35 6HU | Miss K Clarke | 07947832739 |  |  | Windows & Doors | P Beahan | 2024-04-11 | 11am to 3pm | CONFIRMED for 11/04/24
Pioneer Group - Friday 12th April - Steve Burgess
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
FLAT 4 Block 14 | Bicester Square | Birmingham | B35 6HR | Mr D Hilton | 07745835497 |  |  | Windows & Doors | S.Burgess | 2024-04-12 | 8am to 12pm | CONFIRMED for 12/04/24.
FLAT 5 Block 14 | Bicester Square | Birmingham | B35 6HR | VOID |  |  |  | Windows & Doors | S.Burgess | 2024-04-12 | 8am to 12pm | TS-04/04/23 Ltr sent.
FLAT 6 Block 14 | Bicester Square | Birmingham | B35 6HR | Mr L Dilloway | 07592758857 | 07779765081 | luke.dilloway@yahoo.co.uk | Windows & Doors | S.Burgess | 2024-04-12 | 8am to 12pm | CONFIRMED for 12/04/24.
FLAT 1 Block 16 | Bicester Square | Birmingham | B35 6HR | Miss S Smith | 07305 123 009 | 07535573006 | shereenago@me.com | Windows & Doors | S.Burgess | 2024-04-12 | 8am to 12pm | CONFIRMED for 12/04/24.
FLAT 2 Block 16 | Bicester Square | Birmingham | B35 6HR | Ms S Price | 07928 725 629 | 07928725629 | sueprice1948@hotmail.co.uk | Windows & Doors | S.Burgess | 2024-04-12 | 11am to 3pm | CONFIRMED for 12/04/24.
FLAT 3 Block 16 | Bicester Square | Birmingham | B35 6HR | Mr A Chinn | 07384 342527 |  |  | Windows & Doors | S.Burgess | 2024-04-12 | 11am to 3pm | CONFIRMED for 12/04/24.
FLAT 6 Block 16 | Bicester Square | Birmingham | B35 6HR | Miss KG Walker | 07557783791 | 07900574474 |  | Windows & Doors | S.Burgess | 2024-04-12 | 11am to 3pm | TS-02/04/24 Txt sent. TS-04/04/24 Called left vm, txt & ltr sent.
Pioneer Group - Monday 15th April - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
47 | Heyford Way | Birmingham | B35 6HZ | Mrs D M Phillips | 07511 960 048 |  |  | Windows & Doors | P Beahan | 2024-04-15 | 8am to 12pm | CONFIRMED for 15/04/24
50 | Heyford Way | Birmingham | B35 6HU | Mr J E Bramwell | 01217481936 | 07848932573 |  | Windows & Doors | P Beahan | 2024-04-15 | 8am to 12pm | CONFIRMED for 15/04/24
89 | Heyford Way | Birmingham | B35 6JB | Mr R J Hughes |  |  |  | Windows & Doors | P Beahan | 2024-04-15 | 8am to 12pm | TS-04/04/24 Letter sent to the tenant as no contact number for 15/04/24.
45 | Heyford Way | Birmingham | B35 6HZ | Mrs E Hales | 0121747 9889 |  |  | Windows & Doors | P Beahan | 2024-04-15 | 8am to 12pm | CONFIRMED for 15/04/24 after 11am.
93 | Heyford Way | Birmingham | B35 6JB | Miss J Leach | 01217482328 | 07359032693 |  | Windows & Doors | P Beahan | 2024-04-15 | 11am to 3pm | CONFIRMED for 15/04/24
101 | Heyford Way | Birmingham | B35 6JB | Miss N Campbell | 0121 748 3964 | 7306617934 |  | Windows & Doors | P Beahan | 2024-04-15 | 11am to 3pm | TS-08/0/24 Called no ans or vm, ltr sent.
16 | Heyford Way | Birmingham | B35 6JH | Miss C Ryley | 07517 709 503 |  |  | Windows & Doors | P Beahan | 2024-04-15 | 11am to 3pm | CONFIRMED for 15/04/24
48 | Heyford Way | Birmingham | B35 6HU | Mrs P Watkins | 0121 244 5837 | 0121 244 5837 |  | Windows & Doors | P Beahan | 2024-04-15 | 11am to 3pm | CONFIRMED for 15/04/24 After 12pm
Pioneer Group - Tuesday 16th April - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
FLAT 1 Block 64 | Heyford Way | Birmingham | B35 6HU | Mr J I Mitchell | 07828777910 |  | jim.mitchell38@live.com | Windows & Doors | P Beahan | 2024-04-16 | 8am to 12pm | CONFIRMED for 16/04/24
FLAT 2 Block 64 | Heyford Way | Birmingham | B35 6HU | Mr C Hosef | 07495270872 |  |  | Windows & Doors | P Beahan | 2024-04-16 | 8am to 12pm | CONFIRMED for 16/04/24
FLAT 5 Block 64 | Heyford Way | Birmingham | B35 6HU | Miss S Benjamin | 07548670282 |  |  | Windows & Doors | P Beahan | 2024-04-16 | 8am to 12pm | CONFIRMED for 16/04/24
FLAT 6 Block 64 | Heyford Way | Birmingham | B35 6HU | Mr Spragg | 0740 740 3601 |  | tonymagoo202@gmail.com | Windows & Doors | P Beahan | 2024-04-16 | 8am to 12pm | CONFIRMED for 16/04/24
FLAT 2 | Kemble Drive | Birmingham | B35 6QS | Mr B Riley | 01217484548 |  |  | Windows & Doors | P Beahan | 2024-04-16 | 11am to 3pm | CONFIRMED for 16/04/24
FLAT 4 | Kemble Drive | Birmingham | B35 6QS | Mr J G Carter | 07305295274 |  | jordancarter@hotmail.co.uk | Windows & Doors | P Beahan | 2024-04-16 | 11am to 3pm | CONFIRMED for 16/04/24 - after 1.30pm
FLAT 6 | Kemble Drive | Birmingham | B35 6QS | Miss S Davies | 07845 628 491 | 07845628491 |  | Windows & Doors | P Beahan | 2024-04-16 | 11am to 3pm | CONFIRMED for 16/04/24
Pioneer Group - Tuesday 16th April - Steve Burgess
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
FLAT 1 | Northolt Drive | Birmingham | B35 6QX | Mr M Brookes | 07984 225 726 |  |  | Windows & Doors | S.Burgess | 2024-04-16 | 8am to 12pm | TS-04/04/24 Text sent. TS-08/04/04 Called left vm, txt & ltr sent.
FLAT 3 | Northolt Drive | Birmingham | B35 6QX | Mr P Mulholland |  | 07756059115 |  | Windows & Doors | S.Burgess | 2024-04-16 | 8am to 12pm | CONFIRMED for 16/04/24
FLAT 4 | Northolt Drive | Birmingham | B35 6QX | Miss O Shahbazi |  | 07463 894102 | n.shahbazi82@yahoo.com | Windows & Doors | S.Burgess | 2024-04-16 | 8am to 12pm | CONFIRMED for 16/04/24
FLAT 5 | Northolt Drive | Birmingham | B35 6QX | Miss A Holder | 07404868654 | 07424790036 | mandiejh1973@gmail.com | Windows & Doors | S.Burgess | 2024-04-16 | 8am to 12pm | CONFIRMED for 16/04/24
FLAT 6 | Northolt Drive | Birmingham | B35 6QX | Mr T Gould | 07835 472 041 |  |  | Windows & Doors | S.Burgess | 2024-04-16 | 11am to 3pm | CONFIRMED for 16/04/24
FLAT 7 | Northolt Drive | Birmingham | B35 6QX | Miss E Mensah | 07947625350 |  | evelyn_mens@yahoo.com | Windows & Doors | S.Burgess | 2024-04-16 | 11am to 3pm | CONFIRMED for 16/04/24
FLAT 8 | Northolt Drive | Birmingham | B35 6QX | Mr M Atterbury |  | 07737671775 |  | Windows & Doors | S.Burgess | 2024-04-16 | 11am to 3pm | TS-04/04/24 Text sent. TS-08/04/24 Number NIS letter sent.
Pioneer Group - Wednesday 17th April - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
24 | Kemble Drive | Birmingham | B35 6QS | Miss J Pratt | 7932362321 |  |  | Windows & Doors | P Beahan | 2024-04-17 | First Call | CONFIRMED for 17/04/24 as first call
FLAT 8 | Kemble Drive | Birmingham | B35 6QS | Mr M Shutt | 07496 139 339 |  | shuttmartin@gmail.com | Windows & Doors | P Beahan | 2024-04-17 | 8am to 12pm | CONFIRMED for 17/04/24
10 | Kemble Drive | Birmingham | B35 6QS | Mrs M Powell | 07568358706 |  |  | Windows & Doors | P Beahan | 2024-04-17 | 8am to 12pm | CONFIRMED for 17/04/24
12 | Kemble Drive | Birmingham | B35 6QS | Mrs J Mullan | 07541 626 032 | 07788598163 |  | Windows & Doors | P Beahan | 2024-04-17 | 8am to 12pm | TS-04/04/24 Text sent. TS-08/04/24 Called tenant both numbers are NIS ltr sent.
14 | Kemble Drive | Birmingham | B35 6QS | Miss T Gray | 07380795623 |  |  | Windows & Doors | P Beahan | 2024-04-17 | 8am to 12pm | TS-04/04/24 Text sent. TS-08/04/24 Called tenant left vm, txt & ltr sent. Tenant can't make today.
16 | Kemble Drive | Birmingham | B35 6QS | Miss G Hogan | 07443 531 782 |  | jilly_nn@hotmail.co.uk | Windows & Doors | P Beahan | 2024-04-17 | 8am to 12pm | CONFIRMED for 17/04/24
18 | Kemble Drive | Birmingham | B35 6QS | Miss D Bree | 07900 288 081 |  |  | Windows & Doors | P Beahan | 2024-04-17 | 11am to 3pm | CONFIRMED for 17/04/24
20 | Kemble Drive | Birmingham | B35 6QS | Mr Z Amar | 7450214240 |  |  | Windows & Doors | P Beahan | 2024-04-17 | 11am to 3pm | CONFIRMED for 17/04/24
Pioneer Group - Wednesday 17th April - Steve Burgess
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
9 | Northolt Drive | Birmingham | B35 6QX | Mrs A Fletcher | 01217487110 | 075114 67413 |  | Windows & Doors | S.Burgess | 2024-04-17 | 8am to 12pm | CONFIRMED for 17/04/24
FLAT 10 | Northolt Drive | Birmingham | B35 6QX | Mr H Cadby |  | 07950391607 |  | Windows & Doors | S.Burgess | 2024-04-17 | 8am to 12pm | CONFIRMED for 17/04/24
11 | Northolt Drive | Birmingham | B35 6QX | Miss T Scrivens |  | 07307000453 |  | Windows & Doors | S.Burgess | 2024-04-17 | 8am to 12pm | CONFIRMED for 17/04/24
12 | Northolt Drive | Birmingham | B35 6QX | Miss J Flanagan |  | 07972 262850 | flanners07@hotmail.co.uk | Windows & Doors | S.Burgess | 2024-04-17 | 8am to 12pm | CONFIRMED for 17/04/24
14 | Northolt Drive | Birmingham | B35 6QX | Mrs H Evans |  | 07472266832 | hayley_chamberlain@hotmail.co.uk | Windows & Doors | S.Burgess | 2024-04-17 | 8am to 12pm | CONFIRMED for 17/04/24
15 | Northolt Drive | Birmingham | B35 6QX | Mrs S Cattell |  | 07498590107 |  | Windows & Doors | S.Burgess | 2024-04-17 | 11am to 3pm | CONFIRMED for 17/04/24
16 | Northolt Drive | Birmingham | B35 6QX | Mr J Leek | 07985883226 | 07548541014 | jonathanleek66@live.com | Windows & Doors | S.Burgess | 2024-04-17 | 11am to 3pm | TS-04/04/24 Text sent. TS-09/04/24 Called left vm, txt & ltr sent
17 | Northolt Drive | Birmingham | B35 6QX | Mrs A O'regan |  | 07877 826 615 |  | Windows & Doors | S.Burgess | 2024-04-17 | 11am to 3pm | CONFIRMED for 17/04/24
Pioneer Group - Thursday 18th April - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
26 | Kemble Drive | Birmingham | B35 6QS | Miss L Rhodes | 01217481778 | 07787140054 |  | Windows & Doors | P Beahan | 2024-04-18 | 8am to 12pm | CONFIRMED for 18/04/24
FLAT 30 | Kemble Drive | Birmingham | B35 6QS | Mr L Stokes | 07554843963 | 07359680237 |  | Windows & Doors | P Beahan | 2024-04-18 | 8am to 12pm | TS-04/04/24 Text sent. TS-09/04/24 Both numbers NIS - ltr sent.
FLAT 34 | Kemble Drive | Birmingham | B35 6QS | Mrs J Insley | 0121 493 6254 | 07765 161272 |  | Windows & Doors | P Beahan | 2024-04-18 | 8am to 12pm | TS-04/04/24 Text sent. TS-09/04/24 Called mob nis - landline temporary unavailable - ltr sent.
2 | Mere Avenue | Birmingham | B35 6QT | Mrs S Morgan |  | 07864538362 | gerty76.sm@gmail.com | Windows & Doors | P Beahan | 2024-04-18 | 11am to 3pm | CONFIRMED for 18/04/24
4 | Mere Avenue | Birmingham | B35 6QT | Mrs T Blunn | 748 5442 | 7470198312 |  | Windows & Doors | P Beahan | 2024-04-18 | 11am to 3pm | TS-04/04/24 Letter sent as no contact number.
31 | Heyford Way | Birmingham | B35 6HY | Miss N Hickin | 07810 473871 | 07762 385 162 |  | Windows & Doors | P Beahan | 2024-04-18 | 11am to 3pm | CONFIRMED for 18/04/24
FLAT 4 Block 64 | Heyford Way | Birmingham | B35 6HU | Miss S McCann | 07949552355 | 07470672942 |  | Windows & Doors | P Beahan | 2024-04-18 | 11am to 3pm | CONFIRMED for 18/04/24
Pioneer Group - Thursday 18th April - Steve Burgess
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
18 | Northolt Drive | Birmingham | B35 6QX | Mr C Lee |  | 07572168119 | cameronlee03@live.co.uk | Windows & Doors | S.Burgess | 2024-04-18 | 8am to 12pm | CONFIRMED for 18/04/24
19 | Northolt Drive | Birmingham | B35 6QX | Miss H O'Coy |  | 07462777770 | hailz_ocoy@yahoo.com | Windows & Doors | S.Burgess | 2024-04-18 | 8am to 12pm | CONFIRMED for 18/04/24
22 | Northolt Drive | Birmingham | B35 6QX | Miss S Sterling |  | 07507642265 | sabrinasterling83@gmail.com | Windows & Doors | S.Burgess | 2024-04-18 | 8am to 12pm | CONFIRMED for 18/04/24
24 | Northolt Drive | Birmingham | B35 6QX | Mr D Holmes | 01213111804 | 07961916755 | teddys@talktalk.net | Windows & Doors | S.Burgess | 2024-04-18 | 11am to 3pm | CONFIRMED for 18/04/24
25 | Northolt Drive | Birmingham | B35 6QX | Mrs B Wardell |  | 07384626802 |  | Windows & Doors | S.Burgess | 2024-04-18 | 11am to 3pm | CONFIRMED for 18/04/24
Pioneer Group - Monday 22nd April - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
6 | Mere Avenue | Birmingham | B35 6QT | Mrs D Tuckey |  | 07818743552 | donnatuckey1@icloud.com | Windows & Doors | P Beahan | 2024-04-22 | 8am to 12pm | CONFIRMED for 22/04/24.
8 | Mere Avenue | Birmingham | B35 6QT | Ms F F Benjamin | 07400919538 | 07922304111 | farrah7benjamin@yahoo.co.uk | Windows & Doors | P Beahan | 2024-04-22 | 8am to 12pm | CONFIRMED for 22/04/24.
10 | Mere Avenue | Birmingham | B35 6QT | Miss S Norton | 07895812824 |  |  | Windows & Doors | P Beahan | 2024-04-22 | 8am to 12pm | CONFIRMED for 22/04/24.
12 | Mere Avenue | Birmingham | B35 6QT | Miss KA Buchanan |  | 07460516629 | katieamandab95@gmail.com | Windows & Doors | P Beahan | 2024-04-22 | 8am to 12pm | CONFIRMED for 22/04/24.
14 | Mere Avenue | Birmingham | B35 6QT | Ms L Cole | 07902951923 | 07902951923 |  | Windows & Doors | P Beahan | 2024-04-22 | 8am to 12pm | CONFIRMED for 22/04/24.
16 | Mere Avenue | Birmingham | B35 6QT | Miss S Salmon | 07342977113 | 07473697233 | shantelsalmon22@gmail.com | Windows & Doors | P Beahan | 2024-04-22 | 11am to 3pm | CONFIRMED for 22/04/24.
Pioneer Group - Monday 22nd April - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
10 | Javelin Avenue | Birmingham | B35 7LW | Miss K Houliston | 07986992099 | 07986992099 | kaz22@live.co.uk | Windows & Doors | M Turpin | 2024-04-22 | 8am to 2pm | CONFIRMED for 22/04/24
5 | Javelin Avenue | Birmingham | B35 7LH | Miss S Lacey | 07756335015 |  |  | Windows & Doors | M Turpin | 2024-04-22 | 8am to 2pm | CONFIRMED for 22/04/24
6 | Javelin Avenue | Birmingham | B35 7LW | Miss C Fowler | 01217481882 |  | KATIE-FLOWER@HOTMAIL.CO.UK | Windows & Doors | M Turpin | 2024-04-22 | 8am to 2pm | TS-12/04/24 Called and left vm. TS-17/04/24 Called left vm & ltr sent.
7 | Javelin Avenue | Birmingham | B35 7LH | Miss S Myers | 07958391696 |  |  | Windows & Doors | M Turpin | 2024-04-22 | 8am to 2pm | CONFIRMED for 22/04/24
8 | Javelin Avenue | Birmingham | B35 7LW | Mr G Boocock |  | 07513144613 | julierosina@yahoo.co.uk | Windows & Doors | M Turpin | 2024-04-22 | 8am to 2pm | CONFIRMED for 22/04/24
9 | Javelin Avenue | Birmingham | B35 7LH | Mrs SE Johnson |  | 07545825999 | samanthahollis66@gmail.com | Windows & Doors | M Turpin | 2024-04-22 | 8am to 2pm | CONFIRMED for 22/04/24
11 | Javelin Avenue | Birmingham | B35 7LH | Miss KL Macken |  | 7538863242 | katemacken@hotmail.co.uk | Windows & Doors | M Turpin | 2024-04-22 | 8am to 2pm | CONFIRMED for 22/04/24
12 | Javelin Avenue | Birmingham | B35 7LW | Mr D McGahey | 01217301245 | 07960255278 |  | Windows & Doors | M Turpin | 2024-04-22 | 8am to 2pm | CONFIRMED for 22/04/24
14 | Javelin Avenue | Birmingham | B35 7LW | Miss A Dean |  | 07930 656107 |  | Windows & Doors | M Turpin | 2024-04-22 | 8am to 2pm | CONFIRMED for 22/04/24
15 | Javelin Avenue | Birmingham | B35 7LH | Miss M Harris |  | 07851914080 |  | Windows & Doors | M Turpin | 2024-04-22 | 8am to 2pm | CONFIRMED for 22/04/24
Pioneer Group - Tuesday 23rd April - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
28 | Mere Avenue | Birmingham | B35 6QT | Mrs LM Jones |  | 07557 558 772 | l.jones844@btinternet.com | Windows & Doors | P Beahan | 2024-04-23 | 8am to 12pm | CONFIRMED for 23/04/24 - As first call
24 | Mere Avenue | Birmingham | B35 6QT | Mrs D Somers | 01214088137 | 07415308670 | donnas1402@icloud.com | Windows & Doors | P Beahan | 2024-04-23 | 8am to 12pm | CONFIRMED for 23/04/24
26 | Mere Avenue | Birmingham | B35 6QT | Miss S Ansell | 0121 746 7508 | 07745 744 858 |  | Windows & Doors | P Beahan | 2024-04-23 | 8am to 12pm | CONFIRMED for 23/04/24
34 | Mere Avenue | Birmingham | B35 6QT | Miss V Brierley |  | 07742701034 | vickyplj@aol.com | Windows & Doors | P Beahan | 2024-04-23 | 11am to 3pm | CONFIRMED for 23/04/24
36 | Mere Avenue | Birmingham | B35 6QT | Mr A Gardner | 0121 747 4129 |  | apg6691@gmail.com | Windows & Doors | P Beahan | 2024-04-23 | 11am to 3pm | TS-12/04/24 Called left vm. TS-18/04/24 Called left vm & ltr sent.
32 | Mere Avenue | Birmingham | B35 6QT | Mrs H Lally | 01215375815 | 07850 323 036 | hayley_lally08@hotmail.co.uk | Windows & Doors | P Beahan | 2024-04-23 | LAST CALL After 2.30pm | CONFIRMED for 23/04/23 After 2.30pm
Pioneer Group - Tuesday 23rd April - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
19 | Javelin Avenue | Birmingham | B35 7LH | Ms T Griffiths |  | 07897591718 | theresa_griffiths@hotmail.co.uk | Windows & Doors | M Turpin | 2024-04-23 | 8am to 2pm | CONFIRMED for 23/04/24 as first call (tenant called 22/04/24 to ask emailed MT).
16 | Javelin Avenue | Birmingham | B35 7LW | Miss C Yearwood |  | 07481 700 725 |  | Windows & Doors | M Turpin | 2024-04-23 | 8am to 2pm | CONFIRMED for 23/04/24
17 | Javelin Avenue | Birmingham | B35 7LH | Mrs N Farrukh | 01217493816 |  |  | Windows & Doors | M Turpin | 2024-04-23 | 8am to 2pm | TS-17/04/24 Called tenant couldn't get through call minder - ltr sent.
20 | Javelin Avenue | Birmingham | B35 7LW | Miss CL Johnson | 07925824781 |  | cazpuddinghead@gmail.com | Windows & Doors | M Turpin | 2024-04-23 | 8am to 2pm | CONFIRMED for 23/04/24 Moved to 29/04/24
21 | Javelin Avenue | Birmingham | B35 7LH | Mrs E Hussain | 0121 216 0012 |  |  | Windows & Doors | M Turpin | 2024-04-23 | 8am to 2pm | TS-17/04/24 Called left vm & Ltr sent.
26 | Javelin Avenue | Birmingham | B35 7LW | Mr A Lo |  | 07908 828 649 | saabalo@hotmail.it | Windows & Doors | M Turpin | 2024-04-23 | 8am to 2pm | CONFIRMED for 23/04/24
30 | Javelin Avenue | Birmingham | B35 7LW | Mr L Flatley |  | 07388692700 | lukeflatley7@gmail.com | Windows & Doors | M Turpin | 2024-04-23 | 8am to 2pm | TS-12/04/24 Text sent. TS-17/04/24 Called number did not connect ltr sent.
32 | Javelin Avenue | Birmingham | B35 7LW | Mr W Hands |  | 07359004198 | waynehands@hotmail.co.uk | Windows & Doors | M Turpin | 2024-04-23 | 8am to 2pm | CONFIRMED for 23/04/24
76 | Javelin Avenue | Birmingham | B35 7LW | Mr J Walton | 01217474833 | 07858 620 855 |  | Windows & Doors | M Turpin | 2024-04-23 | 8am to 2pm | CONFIRMED for 23/04/24
80 | Javelin Avenue | Birmingham | B35 7LW | Miss A Grant | 07947201836 |  | Ashagrant@hotmail.co.uk | Windows & Doors | M Turpin | 2024-04-23 | 8am to 2pm | CONFIRMED for 23/04/24
Pioneer Group - Tuesday 23rd April - Steve Burgess
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
2 | Baginton Road | Birmingham | B35 6HN | Mrs D Woolaston | 07940411081 |  |  | Windows & Doors | S.Burgess | 2024-04-23 | 8am to 12pm | CONFIRMED for 23/04/24 - after 10am
33 | Baginton Road | Birmingham | B35 6JS | Mr I Turner | 01217483216 |  |  | Windows & Doors | S.Burgess | 2024-04-23 | 8am to 12pm | CONFIRMED for 23/04/24
26 | Northolt Drive | Birmingham | B35 6QX | Miss M O'Loughlin |  | 07710651416 | Megz_christina@hotmail.com | Windows & Doors | S.Burgess | 2024-04-23 | 8am to 12pm | CONFIRMED for 23/04/24
28 | Northolt Drive | Birmingham | B35 6QX | Miss C Butlin |  | 07508400061 | clairapeterButlin17@gmail.com | Windows & Doors | S.Burgess | 2024-04-23 | 8am to 12pm | CONFIRMED for 23/04/24
FLAT 29 | Northolt Drive | Birmingham | B35 6QX | Mr D Kelleher |  | 07543339344 | dkelleher26@gmail.com | Windows & Doors | S.Burgess | 2024-04-23 | 11am to 3pm | CONFIRMED for 23/04/24
FLAT 33 | Northolt Drive | Birmingham | B35 6QX | Miss S McClune |  | 07392784074 | shakhmcc1@gmail.com | Windows & Doors | S.Burgess | 2024-04-23 | 11am to 3pm | TS-12/04/24 Text sent. TS18/04/24 Called and left vm, txt & ltr sent.
Pioneer Group - Wednesday 24th April - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
38 | Mere Avenue | Birmingham | B35 6QT | Miss R Kirby |  | 07707937480 | roxanne1971@tiscili.co.uk | Windows & Doors | P Beahan | 2024-04-24 | 8am to 12pm | TS-15/04/24 Text sent. TS-18/04/24 Called left vm & text sent.
40 | Mere Avenue | Birmingham | B35 6QT | Miss E Davis | 07930385076 |  |  | Windows & Doors | P Beahan | 2024-04-24 | 8am to 12pm | TS-15/04/24 Text sent. TS-18/04/24 Called left vm & text sent.
42 | Mere Avenue | Birmingham | B35 6QT | Mrs D Ismaili |  | 07476824765 | dianemorgan1973@hotmail.com | Windows & Doors | P Beahan | 2024-04-24 | 8am to 12pm | CONFIRMED for 24/04/24
FLAT 46 | Mere Avenue | Birmingham | B35 6QT | Miss S Melaney |  | 07493430156 |  | Windows & Doors | P Beahan | 2024-04-24 | 8am to 12pm | CONFIRMED for 24/04/24
FLAT 50 | Mere Avenue | Birmingham | B35 6QT | Mr J Flynn |  | 07908536618 |  | Windows & Doors | P Beahan | 2024-04-24 | 11am to 3pm | CONFIRMED for 24/04/24 - cancelled tenant now has a hospital appointment.
52 | Mere Avenue | Birmingham | B35 6QT | Mr D Thomas | 07935698548 | 07849947852 |  | Windows & Doors | P Beahan | 2024-04-24 | 11am to 3pm | CONFIRMED for 24/04/24
Pioneer Group - Wednesday 24th April - Steve Burgess
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
23 | Northolt Drive | Birmingham | B35 6QX | Miss C Ansell |  | 07542 011 929 | clara_bell@hotmail.co.uk | Windows & Doors | S.Burgess | 2024-04-24 | 8am to 12pm | CONFIRMED for 24/04/24
FLAT 34 | Northolt Drive | Birmingham | B35 6QX | Miss S Southcombe | 07773 354453 |  | southylee@yahoo.co.uk | Windows & Doors | S.Burgess | 2024-04-24 | 8am to 12pm | TS-15/04/24 Text sent. TS-18/04/24 Called no answer text & ltr sent.
FLAT 36 | Northolt Drive | Birmingham | B35 6QX | Miss K Taylor |  | 07857 917 151 |  | Windows & Doors | S.Burgess | 2024-04-24 | 8am to 12pm | TS-15/04/24 Text sent. TS-18/04/24 Called left vm, text & ltr sent.
FLAT 38 | Northolt Drive | Birmingham | B35 6QX | Mr B Boyle | 07719866234 |  |  | Windows & Doors | S.Burgess | 2024-04-24 | 8am to 12pm | CONFIRMED for 24/04/24
3 | Biggin Close | Birmingham | B35 6BU | Mr M Waheed | 07480515723 | 07480515723 |  | Windows & Doors | S.Burgess | 2024-04-24 | 11am to 3pm | CONFIRMED for 24/04/24
4 | Biggin Close | Birmingham | B35 6BU | Mr J Hagans | 07790624520 | 07790 624 520 |  | Windows & Doors | S.Burgess | 2024-04-24 | 11am to 3pm | CONFIRMED for 24/04/24
Pioneer Group - Wednesday 24th April - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
35 | Javelin Avenue | Birmingham | B35 7LH | Miss K Shabir | 07885 646725 | 07885646725 |  | Windows & Doors | M Turpin | 2024-04-24 | 8am to 2pm | CONFIRMED for 24/04/24
36 | Javelin Avenue | Birmingham | B35 7LW | Mrs K M Disha |  | 07402 672742 | sweetniss56@hotmail.co.uk | Windows & Doors | M Turpin | 2024-04-24 | 8am to 2pm | TS-15/04/24 Text sent. TS-14/04/24 Called the line could not accept this call, text and ltr sent.
37 | Javelin Avenue | Birmingham | B35 7LH | Miss C Harvey | 07842513779 | 07842513779 | carleyD2000@gmail.com | Windows & Doors | M Turpin | 2024-04-24 | 8am to 2pm | CONFIRMED for 24/04/24
38 | Javelin Avenue | Birmingham | B35 7LW | Miss N C Palgrave | 07379 847080 |  |  | Windows & Doors | M Turpin | 2024-04-24 | 8am to 2pm | CONFIRMED for 24/04/24
39 | Javelin Avenue | Birmingham | B35 7LH | Mrs J McNally-Ward | 07957 207224 |  |  | Windows & Doors | M Turpin | 2024-04-24 | 8am to 2pm | CONFIRMED for 24/04/24
40 | Javelin Avenue | Birmingham | B35 7LW | Miss H Gough |  | 07951906468 |  | Windows & Doors | M Turpin | 2024-04-24 | 8am to 2pm | CONFIRMED for 24/04/24
41 | Javelin Avenue | Birmingham | B35 7LH | Miss K Rafferty | 07454 980143 |  | NO1Prittyk@live.co.uk | Windows & Doors | M Turpin | 2024-04-24 | 8am to 2pm | CONFIRMED for 24/04/24
42 | Javelin Avenue | Birmingham | B35 7LW | Mr E Frisenfelds | 01217494666 |  |  | Windows & Doors | M Turpin | 2024-04-24 | 8am to 2pm | CONFIRMED for 24/04/24
48 | Javelin Avenue | Birmingham | B35 7LW | Ms S Jones |  | 07389811707 | sarahjanejones1575@gmail.com | Windows & Doors | M Turpin | 2024-04-24 | 8am to 2pm | TS-15/04/24 Text sent. TS-17/04/24 Called phone is switched off - ltr and text sent.
Pioneer Group - Thursday 25th April - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
14 | Kemble Drive | Birmingham | B35 6QS | Miss T Gray |  | 7380795623 | terhagray@live.co.uk | Windows & Doors | P Beahan | 2024-04-25 | 8am to 12pm | CONFIRMED for 25/04/24
37 | Heyford Way | Birmingham | B35 6HY | Miss S McIntosh |  | 07523 980992 |  | Windows & Doors | P Beahan | 2024-04-25 | 8am to 12pm | CONFIRMED for 25/04/24
6 | Heyford Way | Birmingham | B35 6JH | Mr C O'Sullivan |  | 07505 338867 |  | Windows & Doors | P Beahan | 2024-04-25 | 8am to 12pm | TS-15/04/24 Text sent. TS-18/04/24 Called left vm & text & ltr sent. TS-22/04/24 Tenant text back no.
57C | Heyford Way | Birmingham | B35 6HZ | Mr C Kinsella | 07359 238 603 |  |  | Windows & Doors | P Beahan | 2024-04-25 | 8am to 12pm | CONFIRMED for 25/04/24
57E | Heyford Way | Birmingham | B35 6HZ | Miss L Scott | 01212182712 | 079046 85 105 |  | Windows & Doors | P Beahan | 2024-04-25 | 11am to 3pm | TS-15/04/24 Text sent. TS-18/04/24 Called left vm & text & ltr sent.
72 | Heyford Way | Birmingham | B35 6HU | Mrs S Goulding | 01217485932 | 07951645495 |  | Windows & Doors | P Beahan | 2024-04-25 | 11am to 3pm | CONFIRMED for 25/04/24
Pioneer Group - Thursday 25th April - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
44 | Javelin Avenue | Birmingham | B35 7LW | Mr B B Jones | 07928257661 | 077723448749 | brianjoshjones@AOL.com | Windows & Doors | M Turpin | 2024-04-25 | 8am to 2pm | CONFIRMED for 25/04/24
18 | Javelin Avenue | Birmingham | B35 7LW | Miss H Daly |  | 07732333535 | hayleydaly1@icloud.com | Windows & Doors | M Turpin | 2024-04-25 | 8am to 2pm | CONFIRMED for 25/04/24
28 | Javelin Avenue | Birmingham | B35 7LW | Miss B K Kirwan | 07772 526 747 |  | bianca-88@hotmail.co.uk | Windows & Doors | M Turpin | 2024-04-25 | 8am to 2pm | CONFIRMED for 25/04/24
50 | Javelin Avenue | Birmingham | B35 7LW | Miss N Douglas | 07444 876856 | 07444 876856 | natalie91x@live.co.uk | Windows & Doors | M Turpin | 2024-04-25 | 8am to 2pm | CONFIRMED for 25/04/24
54 | Javelin Avenue | Birmingham | B35 7LW | Miss A Lunn |  | 07939650369 | abbie.lunn@gmail.com | Windows & Doors | M Turpin | 2024-04-25 | 8am to 2pm | CONFIRMED for 25/04/24
56 | Javelin Avenue | Birmingham | B35 7LW | Mrs JM Ward | 07908497768 | 07854 494 361 |  | Windows & Doors | M Turpin | 2024-04-25 | 8am to 2pm | CONFIRMED for 25/04/24
58 | Javelin Avenue | Birmingham | B35 7LW | Mrs M Baldwin | 079208 73 703 |  |  | Windows & Doors | M Turpin | 2024-04-25 | 8am to 2pm | CONFIRMED for 25/04/24 - Please call 30 mins before arrival
60 | Javelin Avenue | Birmingham | B35 7LW | Miss D Marshall | 07746 999 097 |  |  | Windows & Doors | M Turpin | 2024-04-25 | 8am to 2pm | CONFIRMED for 25/04/24
66 | Javelin Avenue | Birmingham | B35 7LW | Mrs A Rogers | 07776 286239 |  | zeb_A_Dee@hotmail.com | Windows & Doors | M Turpin | 2024-04-25 | 8am to 2pm | CONFIRMED for 25/04/24
68 | Javelin Avenue | Birmingham | B35 7LW | Mr G Evans | 07576 879 727 |  | mailmege@gmail.com | Windows & Doors | M Turpin | 2024-04-25 | 8am to 2pm | TS-15/04/24 Text sent. TS-17/04/24 Number is nis letter sent.
70 | Javelin Avenue | Birmingham | B35 7LW | Mr J Duffy | 07761130917 | 07761130917 |  | Windows & Doors | M Turpin | 2024-04-25 | 8am to 2pm | TS-15/04/24 Text sent. TS-17/04/24 Called no answer or vm letter sent.
72 | Javelin Avenue | Birmingham | B35 7LW | Miss C Hill | 07385238097 |  | c07hill@aol.com | Windows & Doors | M Turpin | 2024-04-25 | 8am to 2pm | CONFIRMED for 25/04/24
74 | Javelin Avenue | Birmingham | B35 7LW | Miss S Sheekey |  | 07521 632 438 | stacysheekey@hotmail.co.uk | Windows & Doors | M Turpin | 2024-04-25 | 8am to 2pm | CONFIRMED for 25/04/24
Pioneer Group - Friday 26th April - Steve Burgess
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
7 | Biggin Close | Birmingham | B35 6BU | Mrs D Johnson |  | 07955013317 | debbie.johnson65@me.com | Windows & Doors | S.Burgess | 2024-04-26 | 8am to 12pm | CONFIRMED for 26/04/24
8 | Biggin Close | Birmingham | B35 6BU | Mr A Spriggs | 01217497374 | 07889183319 | roy29949@live.co.uk | Windows & Doors | S.Burgess | 2024-04-26 | 8am to 12pm | TS-15/04/24 Text sent. TS-18/04/24 Called both number mob nis no answer on landline letter sent.
9 | Biggin Close | Birmingham | B35 6BU | Miss A-M Wilson-Clarke |  |  | annmarie_clrk@yahoo.co.uk | Windows & Doors | S.Burgess | 2024-04-26 | 8am to 12pm | TS-18/04/24 Ltr sent as no contact details
10 | Biggin Close | Birmingham | B35 6BU | Miss E Hemming | 07368257842 |  | elaine.hemming1955@googlemail.com | Windows & Doors | S.Burgess | 2024-04-26 | 11am to 3pm | CONFIRMED for 26/04/24
17 | Biggin Close | Birmingham | B35 6BU | Miss K Wesley | 07517469381 |  | katie_cienna@hotmail.co.uk | Windows & Doors | S.Burgess | 2024-04-26 | 11am to 3pm | CONFIRMED for 26/04/24
6 | Biggin Close | Birmingham | B35 6BU | Miss S Spicer | 01217484193 | 07970847644 | spicersusan@hotmail.com | Windows & Doors | S.Burgess | 2024-04-26 | 11am to 3pm | CONFIRMED for 26/04/24
Pioneer Group - Monday 29th April - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
34 | Javelin Avenue | Birmingham | B35 7LW | Miss T Gordon |  | 07583 234 987 | TionnaGordon@hotmail.com | Windows & Doors | M Turpin | 2024-04-29 | 8am to 2pm | CONFIRMED for 29/04/24
20 | Javelin Avenue | Birmingham | B35 7LW | Miss CL Johnson | 07925824781 |  | cazpuddinghead@gmail.com | Windows & Doors | M Turpin | 2024-04-29 | 8am to 2pm | CONFIRMED for 29/04/24 - after 9.10, tenant has a school run 11.45am to 12pm TS-29/04/24 Tenant called she has a family emergency
52 | Javelin Avenue | Birmingham | B35 7LW | Mr R Hill |  | 07786 824 141 |  | Windows & Doors | M Turpin | 2024-04-29 | 8am to 2pm | CONFIRMED for 29/04/24
46 | Javelin Avenue | Birmingham | B35 7LW | Miss S Small |  | 07875151911 | samanthasmall86@yahoo.co.uk | Windows & Doors | M Turpin | 2024-04-29 | 8am to 2pm | CONFIRMED for 29/04/24
84 | Javelin Avenue | Birmingham | B35 7LW | Mrs L Hughes |  | 07821 493552 |  | Windows & Doors | M Turpin | 2024-04-29 | 8am to 2pm | CONFIRMED for 29/04/24
86 | Javelin Avenue | Birmingham | B35 7LW | Mr Y L Yankam | 07448 885452 |  | yankam92@yahoo.co.uk | Windows & Doors | M Turpin | 2024-04-29 | 8am to 2pm | TS-19/04/24 Text sent for 29/04/24. TS-23/04/24 Left vm, text & ltr sent. Can't do
120 | Javelin Avenue | Birmingham | B35 7LW | Miss C Collier | 0121 294 7041 | 07368168552 |  | Windows & Doors | M Turpin | 2024-04-29 | 8am to 2pm | CONFIRMED for 29/04/24
124 | Javelin Avenue | Birmingham | B35 7LW | Miss S Francis | 01215378153 | 7943653831 |  | Windows & Doors | M Turpin | 2024-04-29 | 8am to 2pm | TS-19/04/24 Text sent for 29/04/24. TS-23/04/24 Called number calls are not being connect at this moment - sent text & ltr. | DM carded 26.04
126 | Javelin Avenue | Birmingham | B35 7LW | Mr R Teager | 7494816011 |  |  | Windows & Doors | M Turpin | 2024-04-29 | 8am to 2pm | CONFIRMED for 29/04/24
14 | Lysander Way | Birmingham | B35 7JY | Miss J Walton | 0121 749 5995 |  |  | Windows & Doors | M Turpin | 2024-04-29 | 8am to 2pm | CONFIRMED for 29/04/24
15 | Lysander Way | Birmingham | B35 7JY | Mr M Duffy | 01217485808 |  | m.duffy100@icloud.com | Windows & Doors | M Turpin | 2024-04-29 | 8am to 2pm | CONFIRMED for 29/04/24
Pioneer Group - Tuesday 30th April - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
3 | Lysander Way | Birmingham | B35 7JY | Ms C Brown |  | 07486047902 | 00clare@gmail.com | Windows & Doors | M Turpin | 2024-04-30 | 8am to 2pm | CONFIRMED for 30/04/24 - TS-30/04/24 Tenant text in they are no longer available.
4 | Lysander Way | Birmingham | B35 7JY | Miss T Wadrup |  | 07423 694 345 |  | Windows & Doors | M Turpin | 2024-04-30 | 8am to 2pm | CONFIRMED for 30/04/24
6 | Lysander Way | Birmingham | B35 7JY | Miss E J Dove |  | 07915 260 427 |  | Windows & Doors | M Turpin | 2024-04-30 | 8am to 2pm | CONFIRMED for 30/04/24
7 | Lysander Way | Birmingham | B35 7JY | Mr S Makadji | 07984 943066 |  | smak1010@yahoo.co.uk | Windows & Doors | M Turpin | 2024-04-30 | 8am to 2pm | CONFIRMED for 30/04/24
8 | Lysander Way | Birmingham | B35 7JY | Miss S Humphrey | 07841 560208 |  |  | Windows & Doors | M Turpin | 2024-04-30 | 8am to 2pm | CONFIRMED for 30/04/24
9 | Lysander Way | Birmingham | B35 7JY | Mrs LA Parrott | 07870996161 | 07870996161 | lesleyannp@aol.com | Windows & Doors | M Turpin | 2024-04-30 | 8am to 2pm | CONFIRMED for 30/04/24 but needs to be between 11am to 12pm alongside Dominie - tenant has anixety.
16 | Lysander Way | Birmingham | B35 7JY | Mrs M Temple |  | 07503259162 |  | Windows & Doors | M Turpin | 2024-04-30 | 8am to 2pm | CONFIRMED for 30/04/24 between 11am - 1pm - tenant contacted DM
10 | Lysander Way | Birmingham | B35 7JY | Miss S R Thompson | 07450700720 | 07450700720 | sharon441@btinternet.com | Windows & Doors | M Turpin | 2024-04-30 | 8am to 2pm | CONFIRMED for 30/04/24
11 | Lysander Way | Birmingham | B35 7JY | Mrs C Birch |  | 07713918250 |  | Windows & Doors | M Turpin | 2024-04-30 | 8am to 2pm | CONFIRMED for 30/04/24
12 | Lysander Way | Birmingham | B35 7JY | Mrs B Amer | 07908977875 | 07908 977 875 |  | Windows & Doors | M Turpin | 2024-04-30 | 8am to 2pm | CONFIRMED for 30/04/24
21 | Lysander Way | Birmingham | B35 7JY | Mr V Eames | 0121 749 1796 | 07917 021951 |  | Windows & Doors | M Turpin | 2024-04-30 | 8am to 2pm | CONFIRMED for 30/04/24
Pioneer Group - Wednesday 1st May - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
22 | Lysander Way | Birmingham | B35 7JY | Mrs P Carpenter |  | 07365990184 |  | Windows & Doors | M Turpin | 2024-05-01 | 8am to 2pm | CONFIRMED for 01/05/24
23 | Lysander Way | Birmingham | B35 7JY | Mr N Doughty |  | 07555766851 | earl.salter@nhs.net | Windows & Doors | M Turpin | 2024-05-01 | 8am to 2pm | CONFIRMED for 01/05/24
24 | Lysander Way | Birmingham | B35 7JY | Mrs L Crisp | 01902352249 |  |  | Windows & Doors | M Turpin | 2024-05-01 | 8am to 2pm | CONFIRMED for 01/05/24
25 | Lysander Way | Birmingham | B35 7JY | Miss M Bhogal | 01217492763 | 7534514316 |  | Windows & Doors | M Turpin | 2024-05-01 | 8am to 2pm | TS-19/04/24 Text sent for 01/05/24. TS-24/04/24 Called left vm, text & ltr sent.
26 | Lysander Way | Birmingham | B35 7JY | Mrs A Hennessy |  | 07413172444 |  | Windows & Doors | M Turpin | 2024-05-01 | 8am to 2pm | CONFIRMED for 01/05/24
27 | Lysander Way | Birmingham | B35 7JY | VOID |  |  |  | Windows & Doors | M Turpin | 2024-05-01 | 8am to 2pm | Emailed client for the key safe code or tenant's details. Ltr sent
28 | Lysander Way | Birmingham | B35 7JY | Mrs M Waring |  |  |  | Windows & Doors | M Turpin | 2024-05-01 | 8am to 2pm | Ltr sent to the property as no contact number for tenant. REFUSED DM will advise client
29 | Lysander Way | Birmingham | B35 7JY | Mr M Younis | 07378866549 | 07378866549 | muhammadyoung.my@gmail.com | Windows & Doors | M Turpin | 2024-05-01 | 8am to 2pm | CONFIRMED for 01/05/24
30 | Lysander Way | Birmingham | B35 7JY | Mr R Palfrey |  | 07572126140 | richpalfrey@gmail.com | Windows & Doors | M Turpin | 2024-05-01 | 8am to 2pm | CONFIRMED for 01/05/24
8 | Watton Green | Birmingham | B35 7JS | Miss NL Cabena | 07460785785 |  | ninalcabena@gmail.com | Windows & Doors | M Turpin | 2024-05-01 | 8am to 2pm | CONFIRMED for 01/05/24
10 | Watton Green | Birmingham | B35 7JS | Miss L Da-Costa |  | 07709094089 | 3rdileading@gmail.com | Windows & Doors | M Turpin | 2024-05-01 | 8am to 2pm | CONFIRMED for 01/05/24
12 | Watton Green | Birmingham | B35 7JS | Miss M M Rose-Lewis |  | 07456 459 459 | maureenlewis.mmrl@gmail.com | Windows & Doors | M Turpin | 2024-05-01 | 8am to 2pm | CONFIRMED for 01/05/24
Pioneer Group - Thursday 2nd May - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
88 | Javelin Avenue | Birmingham | B35 7LW | Miss V Keen |  | 07731948831 | keenvicky@yahoo.co.uk | Windows & Doors | M Turpin | 2024-05-02 | 8am to 2pm | CONFIRMED for 02/05/24
18 | Watton Green | Birmingham | B35 7JS | Mr RP King | 07383235133 | 07383235133 |  | Windows & Doors | M Turpin | 2024-05-02 | 8am to 2pm | CONFIRMED for 02/05/24 - as early as possible
14 | Watton Green | Birmingham | B35 7JS | Miss K Bennett | 7960089498 | 07522094660 |  | Windows & Doors | M Turpin | 2024-05-02 | 8am to 2pm | CONFIRMED for 02/05/24
24 | Watton Green | Birmingham | B35 7JS | Mr AJ Delemere |  | 07896765025 |  | Windows & Doors | M Turpin | 2024-05-02 | 8am to 2pm | CONFIRMED for 02/05/24
28 | Watton Green | Birmingham | B35 7JS | Miss L Johnson |  | 07941 637 777 |  | Windows & Doors | M Turpin | 2024-05-02 | 8am to 2pm | CONFIRMED for 02/05/24
21 | Watton Green | Birmingham | B35 7JS | Miss KL Batchelor | 07493 984 344 |  | keelybatch@gmail.com | Windows & Doors | M Turpin | 2024-05-02 | 8am to 2pm | CONFIRMED for 02/05/24 11am - 1pm only
25 | Watton Green | Birmingham | B35 7JS | Mrs B A Cooke |  | 7837951264 |  | Windows & Doors | M Turpin | 2024-05-02 | 8am to 2pm | CONFIRMED for 02/05/24
27 | Watton Green | Birmingham | B35 7JS | Miss DA Hope | 01215373224 | 07969 774 937 | sweetlipzxx@live.co.uk | Windows & Doors | M Turpin | 2024-05-02 | 8am to 2pm | CONFIRMED for 02/05/24 after 9am due to school run
20 | Watton Green | Birmingham | B35 7JS | Miss S Khan | 7414146089 | 07704907888 |  | Windows & Doors | M Turpin | 2024-05-02 | 8am to 2pm | CONFIRMED for 02/05/24 as late as possible
Pioneer Group - Tuesday 7th May - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
FLAT 50 | Mere Avenue | Birmingham | B35 6QT | Mr J Flynn |  | 07908536618 |  | Windows & Doors | P Beahan | 2024-05-07 | 8am to 12pm | CONFIRMED for 07/05/24
FLAT 36 | Kemble Drive | Birmingham | B35 6QS | Miss W Stokes | 07445 945 554 |  |  | Windows & Doors | P Beahan | 2024-05-07 | 8am to 12pm | CONFIRMED for 07/05/24 - for 12pm approx
FLAT 64 | Mere Avenue | Birmingham | B35 6QT | Mr A Kimberley | 0121 749 7045 | 07867361210 | tonykimberley83@hotmail.com | Windows & Doors | P Beahan | 2024-05-07 | 8am to 12pm | TS-01/05/24 Text sent offering 07/05/24 - Tenant text in to cancel.
58 | Mere Avenue | Birmingham | B35 6QT | Ms E Bradnock | 07973 782 339 |  |  | Windows & Doors | P Beahan | 2024-05-07 | 11am to 3pm | CONFIRMED for 07/05/24
FLAT 60 | Mere Avenue | Birmingham | B35 6QT | Mr P J McCallion | 07751 066 503 |  | patrickmccallion8@gmail.com | Windows & Doors | P Beahan | 2024-05-07 | 11am to 3pm | TS-25/04/24 Text sent for 07/05/24. TS-01/05/24 Called left vm, txt & ltr sent.
FLAT 62 | Mere Avenue | Birmingham | B35 6QT | Miss C Timberlake | 07543445769 | 07543445769 | charleyanne5@aol.com | Windows & Doors | P Beahan | 2024-05-07 | 11am to 3pm | CONFIRMED for 070/05/24 - she has a nursery run at 12.50pm and is out for 30 mins
Pioneer Group - Tuesday 7th May - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
44 | Watton Green | Birmingham | B35 7JP | Mrs K Guest | 7708386172 | 07340357377 |  | Windows & Doors | M Turpin | 2024-05-07 | 8am to 2pm | CONFIRMED for 07/05/24 - FIRST CALL
33 | Watton Green | Birmingham | B35 7JS | Miss L Craddock |  | 07548278817 | l_craddock1988@outlook.com | Windows & Doors | M Turpin | 2024-05-07 | 8am to 2pm | CONFIRMED for 07/05/24 - Tenant called in family emergency
35 | Watton Green | Birmingham | B35 7JS | Miss V Davies | 07753 325107 | 07753325107 | victoria.davies@sainsbury.co.uk | Windows & Doors | M Turpin | 2024-05-07 | 8am to 2pm | CONFIRMED for 07/05/24
42 | Watton Green | Birmingham | B35 7JP | Miss C Hatton | 7909153474 | 07526178752 |  | Windows & Doors | M Turpin | 2024-05-07 | 8am to 2pm | CONFIRMED for 07/05/24
50 | Watton Green | Birmingham | B35 7JP | Miss T Arlow | 07453 414 148 |  |  | Windows & Doors | M Turpin | 2024-05-07 | 8am to 2pm | CONFIRMED for 07/05/24
54 | Watton Green | Birmingham | B35 7JP | Miss M-A Kells |  | 07391 853363 - nis |  | Windows & Doors | M Turpin | 2024-05-07 | 8am to 2pm | TS-25/04/24 Text sent for 07/05/24. TS-01/05/24 Number nis letter sent. Tenant cancelled
58 | Watton Green | Birmingham | B35 7JP | Miss G Jones |  | 07942713340 |  | Windows & Doors | M Turpin | 2024-05-07 | 8am to 2pm | TS-25/04/24 Text sent for 07/05/24. TS-01/05/24 Called no answer or vm ltr and text sent.
60 | Watton Green | Birmingham | B35 7JP | Mrs M Nelson |  |  |  | Windows & Doors | M Turpin | 2024-05-07 | 8am to 2pm | TS-29/04/24 Ltr sent.
68 | Watton Green | Birmingham | B35 7JP | Mrs R Mohamed |  | 07405 163499 |  | Windows & Doors | M Turpin | 2024-05-07 | 8am to 2pm | CONFIRMED for 07/05/24
74 | Watton Green | Birmingham | B35 7JP | Miss MC Dale |  | 07931981160 |  | Windows & Doors | M Turpin | 2024-05-07 | 8am to 2pm | CONFIRMED for 07/05/24
80 | Watton Green | Birmingham | B35 7JR | Mrs J Bradley |  | 07488358594 |  | Windows & Doors | M Turpin | 2024-05-07 | 8am to 2pm | CONFIRMED for 07/05/24 - after 2.30pm
Pioneer Group - Wednesday 8th May - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
28 | Kemble Drive | Birmingham | B35 6QS | Mrs S Faisal | 07498882503 |  |  | Windows & Doors | P Beahan | 2024-05-08 | 8am to 12pm | CONFIRMED for 08/05/24
56 | Mere Avenue | Birmingham | B35 6QT | Miss N Hall | 07825 036783 |  | natalie.l.hall@outlook.com | Windows & Doors | P Beahan | 2024-05-07 | 8am to 12pm | CONFIRMED for 08/05/24
FLAT 66 | Mere Avenue | Birmingham | B35 6QT | Miss S Snelson |  | 07467587073 | sarahlouisesnelson@hotmail.com | Windows & Doors | P Beahan | 2024-05-08 | 8am to 12pm | CONFIRMED for 08/05/24
FLAT 68 | Mere Avenue | Birmingham | B35 6QT | Mr S Gardiner | 07305 947 116 | 07873894184 - nis | mya1997@live.co.uk | Windows & Doors | P Beahan | 2024-05-08 | 11am to 3pm | CONFIRMED for 08/05/24
FLAT 70 | Mere Avenue | Birmingham | B35 6QT | Mr K Higgs |  | 07856 089 210 |  | Windows & Doors | P Beahan | 2024-05-08 | 11am to 3pm | CONFIRMED for 08/05/24
FLAT 72 | Mere Avenue | Birmingham | B35 6QT | Mr R Hylton |  | 07784740360 |  | Windows & Doors | P Beahan | 2024-05-08 | 11am to 3pm | CONFIRMED for 08/05/24
Pioneer Group - Thursday 9th May - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
FLAT 74 | Mere Avenue | Birmingham | B35 6QT | Mr M Finney |  | 07723311622 | imicki@icloud.com | Windows & Doors | P Beahan | 2024-05-09 | 8am to 12pm | CONFIRMED for 09/05/24
76 | Mere Avenue | Birmingham | B35 6QT | Mr G Rainsford | 07783084484 | 07783084484 | rainsfordg@googlemail.com | Windows & Doors | P Beahan | 2024-05-09 | 8am to 12pm | CONFIRMED for 09/05/24
78 | Mere Avenue | Birmingham | B35 6QT | Miss K Webb |  | 07508420333 | Kaywebb911@gmail.com | Windows & Doors | P Beahan | 2024-05-09 | 8am to 12pm | CONFIRMED for 09/05/24
80 | Mere Avenue | Birmingham | B35 6QT | Miss K Prince | 07985401739 |  | KimPrince1971@Hotmail.co.uk | Windows & Doors | P Beahan | 2024-05-09 | 11am to 3pm | CONFIRMED for 09/05/24
82 | Mere Avenue | Birmingham | B35 6QT | Miss M Jones | 07572404036 |  | jmatilda707@gmail.com | Windows & Doors | P Beahan | 2024-05-09 | 11am to 3pm | TS-26/04/24 Text sent for 09/05/24. TS-01/05/24 Called left vm, txt & ltr sent.
6 | Heyford Way | Birmingham | B35 6JH | Mr C O'Sullivan |  | 07505 338867 |  | Windows & Doors | P Beahan | 2024-05-09 | 11am to 3pm | TS-26/04/24 Text sent for 09/05/24. TS-01/05/24 Called left vm, txt & ltr sent.
Pioneer Group - Friday 10th May - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
8 | Abingdon Way | Birmingham | B35 6QF | Miss S Chambers | 07780469695 | 07780469586 |  | Windows & Doors | P Beahan | 2024-05-10 | 8am to 12pm | CONFIRMED FOR 10/05/24
FLAT 3 | Abingdon Way | Birmingham | B35 6QF | Miss M Hanson |  | 07497303467 |  | Windows & Doors | P Beahan | 2024-05-10 | 8am to 12pm | TS-26/04/24 Text sent for 10/05/24. TS-01/05/24 Called no answer or vm, text & ltr sent.
4 | Abingdon Way | Birmingham | B35 6QF | Miss J La Touche | 7931353477 |  |  | Windows & Doors | P Beahan | 2024-05-10 | 8am to 12pm | CONFIRMED FOR 10/05/24
FLAT 5 | Abingdon Way | Birmingham | B35 6QF | Miss L Bennett | 07449479838 | 07449479838 |  | Windows & Doors | P Beahan | 2024-05-10 | 11am to 3pm | CONFIRMED FOR 10/05/24
6 | Abingdon Way | Birmingham | B35 6QF | Miss S Ashford | 0121 749 1629 | 7774761517 | brumgirlsharon@outlook.com | Windows & Doors | P Beahan | 2024-05-10 | 11am to 3pm | CONFIRMED FOR 10/05/24
FLAT 7 | Abingdon Way | Birmingham | B35 6QF | Miss K Smart | 07940202851 |  | k.smart1969@gmail.com | Windows & Doors | P Beahan | 2024-05-10 | 11am to 3pm | CONFIRMED FOR 10/05/24
Pioneer Group - Monday 13th May - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
10 | Mere Avenue | Birmingham | B35 6QT | Miss S Norton | 07895812824 |  |  | Windows & Doors | P Beahan | 2024-05-13 | 8am to 12pm | CONFIRMED for 13/05/2024
18 | Mere Avenue | Birmingham | B35 6QT | Mr M Fitzgerald |  | 7919324496 NIS | michael.fitzgerald3@sky.com | Windows & Doors | P Beahan | 2024-05-13 | 8am to 12pm | TS-03/05/24 Text sent for 13/05/24. TS-07/05/24 Ltr sent for 13/05/24. 08/05 SMS called no. NIS. CANCELLED
20 | Mere Avenue | Birmingham | B35 6QT | Miss S Dhatt | 7734248580 |  | Simrendhatt@outlook.com | Windows & Doors | P Beahan | 2024-05-13 | 8am to 12pm | TS-03/05/24 Text sent for 13/05/24. TS-07/05/24 Ltr sent for 13/05/24. 08/05 SMS left voicemail.
22 | Mere Avenue | Birmingham | B35 6QT | Mrs F Dainty |  | 07947 56 59 58 | Francescaleigh2010@hotmail.co.uk | Windows & Doors | P Beahan | 2024-05-13 | 11am to 3pm | TS-03/05/24 Text sent for 13/05/24. TS-07/05/24 Ltr sent for 13/05/24. 08/05 SMS called tenant ended call. TENANT CANCELLED
FLAT 44 | Mere Avenue | Birmingham | B35 6QT | Miss T Rapier |  | 07341404533 NIS | teeseliax@gmail.com | Windows & Doors | P Beahan | 2024-05-13 | 11am to 3pm | TS-03/05/24 Text sent for 13/05/24. TS-07/05/24 Ltr sent for 13/05/24. 08/05 SMS called no. NIS
FLAT 48 | Mere Avenue | Birmingham | B35 6QT | Mr T Hillier |  | 07456 500 282 NIS | k1kel366@gmail.com | Windows & Doors | P Beahan | 2024-05-13 | 11am to 3pm | TS-03/05/24 Text sent for 13/05/24. TS-07/05/24 Ltr sent for 13/05/24. 08/05 SMS called no. NIS
Pioneer Group - Monday 13th May - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
107 | Hawker Drive | Birmingham | B35 7EA | Miss D Johns |  | 07729 255 769 | dawnjohns1963@yahoo.com | Windows & Doors | M Turpin | 2024-05-13 | 8am to 2pm | CONFIRMED for 13/05/24
27 | Brabazon Grove | Birmingham | B35 6DT | Miss A Witts | 07588 060 297 NIS |  |  | Windows & Doors | M Turpin | 2024-05-13 | 8am to 2pm | TS-03/05/24 Text sent for 13/05/24. TS-07/05/24 Ltr sent for 13/05/24. 08/05 SMS called no. NIS
34 | Brabazon Grove | Birmingham | B35 6DT | Mrs D Rivers | 01212411506 | 07969 870822 | dawnrivers169@yahoo.com | Windows & Doors | M Turpin | 2024-05-13 | 8am to 2pm | TS-03/05/24 Text sent for 13/05/24. TS-07/05/24 Ltr sent for 13/05/24. 08/05 SMS Called engaged
36 | Brabazon Grove | Birmingham | B35 6DT | Miss T Butler | 07956475367 | 07956475367 |  | Windows & Doors | M Turpin | 2024-05-13 | 8am to 2pm | TS-03/05/24 Text sent for 13/05/24. TS-07/05/24 Ltr sent for 13/05/24. 08/05 SMS left voicemail
37 | Brabazon Grove | Birmingham | B35 6DT | Mr J Meenan | 0121 730 1037 | 07846 480 995 | johnmeenan@hotmail.co.uk | Windows & Doors | M Turpin | 2024-05-13 | 8am to 2pm | CONFIRMED for 13/05/24
38 | Brabazon Grove | Birmingham | B35 6DT | Mrs M Sergeant |  | 07913 666 673 |  | Windows & Doors | M Turpin | 2024-05-13 | 8am to 2pm | TS-03/05/24 Text sent for 13/05/24. TS-07/05/24 Ltr sent for 13/05/24. 08/05 SMS left voicemail
42 | Brabazon Grove | Birmingham | B35 6DT | Mrs D Carr |  | 07376 809845 |  | Windows & Doors | M Turpin | 2024-05-13 | 8am to 2pm | TS-03/05/24 Text sent for 13/05/24. TS-07/05/24 Ltr sent for 13/05/24. 08/05 SMS called N/A
44 | Brabazon Grove | Birmingham | B35 6DT | Mr C Williams |  | 07894726478 |  | Windows & Doors | M Turpin | 2024-05-13 | 8am to 2pm | CONFIRMED for 13/05/24
31 | Brabazon Grove | Birmingham | B35 6DT | Mr K Massey |  | 07534247544 |  | Windows & Doors | M Turpin | 2024-05-13 | 12pm to 2pm | TS-03/05/24 Text sent for 13/05/24. TS-07/05/24 Ltr sent for 13/05/24. 08/05 SMS tenant CONFIRMED after 12 pls
Pioneer Group - Tuesday 14th May - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
4 | Mere Avenue | Birmingham | B35 6QT | Mrs T Blunn | 7470198312 | 7470198312 |  | Windows & Doors | P Beahan | 2024-05-14 | 8am to 12pm - First Call | CONFIRMED for 14/05/24 as FIRST CALL
FLAT 30 | Kemble Drive | Birmingham | B35 6QS | Mr L Stokes | 07554843963 NIS | 07359680237 NIS |  | Windows & Doors | P Beahan | 2024-05-14 | 8am to 12pm | TS-03/05/24 Text sent for 14/05/24. TS-07/05/24 Ltr sent for 14/05/24. 08/05 SMS called neither mobile number is in service.
FLAT 1 | Abingdon Way | Birmingham | B35 6QF | Mr T Hunt | 0121 730 2073 | 07455090417 | tghunt.1968@yahoo.co.uk | Windows & Doors | P Beahan | 2024-05-14 | 11am to 3pm | CONFIRMED for 14/05
2 | Abingdon Way | Birmingham | B35 6QF | Miss A Goode | 07715 470 787 |  | amanda.goode87@hotmail.co.uk | Windows & Doors | P Beahan | 2024-05-14 | 11am to 3pm | (Text sent offering 10/05/24. TS-26/04/24 Tenant text back no) 08/05 SMS left voicemail offering 14/05
76 | Heyford Way | Birmingham | B35 6HU | Mrs P Brown | 079254 14 091 NIS |  |  | Windows & Doors | P Beahan | 2024-05-14 | 8am to 12pm | NO access for 10/04/24. TS-03/05/24 Text sent for 14/05/24. TS-07/05/24 Ltr sent for 14/05/24. 08/05 SMS no. NIS
57E | Heyford Way | Birmingham | B35 6HZ | Miss L Scott | 01212182712 | 079046 85 105 |  | Windows & Doors | P Beahan | 2024-05-14 | 11am to 3pm | 2 x prev no access. TS-03/05/24 Text sent for 14/05/24. TS-07/05/24 Ltr sent for 14/05/24. 08/05 SMS left voicemail for 14/05
57D | Heyford Way | Birmingham | B35 6HZ | Keysafe 2404 | Keysafe 2404 |  |  | Windows & Doors | P Beahan | 2024-05-14 | 11am to 3pm | KEYSAFE 2404
Pioneer Group - Tuesday 14th May - Steve Burgess
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
FLAT 1 Block 14 | Bicester Square | Birmingham | B35 6HR | Miss C Mullen | 7415508478 |  |  | Windows & Doors | S.Burgess | 2024-05-14 | 8am to 12pm - First Call | CONFIRMED for 15/05/24 as FIRST CALL
FLAT 31 | Northolt Drive | Birmingham | B35 6QX | Mr M Phillips |  | 07598 421 064 |  | Windows & Doors | S.Burgess | 2024-05-14 | 8am to 12pm | TS-03/05/24 Text sent for 14/05/24. TS-07/05/24 Ltr sent for 14/05/24. 08/05 SMS left voicemail for 14/05
32 | Northolt Drive | Birmingham | B35 6QX | Miss L Jones |  | 07826723534 | laneyjones@live.co.uk | Windows & Doors | S.Burgess | 2024-05-14 | 8am to 12pm | CONFIRMED for 15/05/24
FLAT 40 | Northolt Drive | Birmingham | B35 6QX | Mr D Johnson | 07950667035 |  |  | Windows & Doors | S.Burgess | 2024-05-14 | 11am to 3pm | TS-03/05/24 Text sent for 14/05/24. TS-07/05/24 Ltr sent for 14/05/24. 08/05 SMS called N/A
1 | Biggin Close | Birmingham | B35 6BU | Miss J Nash |  | 07854 351518 |  | Windows & Doors | S.Burgess | 2024-05-14 | 11am to 3pm | CONFIRMED for 15/05/24
12 | Biggin Close | Birmingham | B35 6BU | Mr J Larkin |  |  |  | Windows & Doors | S.Burgess | 2024-05-14 | 11am to 3pm | TS-03/05/24 Text sent for 14/05/24. TS-07/05/24 Ltr sent for 14/05/24.
Pioneer Group - Tuesday 14th May - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
50 | Javelin Avenue | Birmingham | B35 7LW | Miss N Douglas | 07444 876856 | 07444 876856 | natalie91x@live.co.uk | Windows & Doors | M Turpin | 2024-05-15 | 8am to 2pm | CONFIRMED for 14/05/24
FLAT 56 | Brabazon Grove | Birmingham | B35 6DT | Mr D Wallace |  | 07719750799 |  | Windows & Doors | M Turpin | 2024-05-14 | 8am to 2pm | TS-03/05/24 Text sent for 14/05/24. TS-07/05/24 Ltr sent for 14/05/24. 08/05 SMS called N/A
FLAT 58 | Brabazon Grove | Birmingham | B35 6DT | Miss L Harding | 07491880111 |  | harding63@hotmail.com | Windows & Doors | M Turpin | 2024-05-14 | 8am to 2pm | CONFIRMED for 14/05/24
FLAT 60 | Brabazon Grove | Birmingham | B35 6DT | Mr N Flynn |  | 07947975847 |  | Windows & Doors | M Turpin | 2024-05-14 | 8am to 2pm | CONFIRMED for 14/05/24
61 | Brabazon Grove | Birmingham | B35 6DT | Miss R Russell |  | 07908 063 136 | remirussell@icloud.com> | Windows & Doors | M Turpin | 2024-05-14 | 8am to 2pm | CONFIRMED for 14/05/24
FLAT 62 | Brabazon Grove | Birmingham | B35 6DT | Mr ML Powers | 0121 748 7923 | 7446687757 | mickpowers64@gmail.com | Windows & Doors | M Turpin | 2024-05-14 | 8am to 2pm | CONFIRMED for 14/05/24
FLAT 64 | Brabazon Grove | Birmingham | B35 6DT | Ms B A Hinsley | 07891806772 |  |  | Windows & Doors | M Turpin | 2024-05-14 | 8am to 2pm | CONFIRMED for 14/05/24
68 | Brabazon Grove | Birmingham | B35 6DT | Miss T Pointon |  |  | tracy-1979@hotmail.co.uk | Windows & Doors | M Turpin | 2024-05-14 | 8am to 2pm | TS-07/05/24 Ltr sent for 14/05/24. 13/05 tenant cancelled
72 | Brabazon Grove | Birmingham | B35 6DT | Miss H Fanning |  |  |  | Windows & Doors | M Turpin | 2024-05-14 | 8am to 2pm | TS-07/05/24 Ltr sent for 14/05/24.
74 | Brabazon Grove | Birmingham | B35 6DT | Mr M Coleing | 0121 749 6902 |  |  | Windows & Doors | M Turpin | 2024-05-14 | 8am to 2pm | CONFIRMED for 14/05/24
Pioneer Group - Wednesday 15th May - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
26 | Brabazon Grove | Birmingham | B35 6DT | Miss R Haycock |  | 07455 966 933 | rhaycock1980@gmail.com | Windows & Doors | M Turpin | 2024-05-15 | 9.30am to 2pm | 15/05 CONFIRMED after 9.30am
76 | Brabazon Grove | Birmingham | B35 6DT | Mrs D Hughes | 0121 748 6129 |  |  | Windows & Doors | M Turpin | 2024-05-15 | 8am to 2pm | TS-07/05/24 Ltr sent for 15/05/24. 08/05 SMS called but got a silent line.
1 | Donibristle Croft | Birmingham | B35 6BL | Mrs L Hughes | 01217486954 | 07359072372 |  | Windows & Doors | M Turpin | 2024-05-15 | 8am to 2pm | CONFIRMED for 15/05/24
21 | Donibristle Croft | Birmingham | B35 6BL | Mrs T A Robinson | 01217487692 NIS |  | robrobinson@live.co.uk | Windows & Doors | M Turpin | 2024-05-15 | 8am to 2pm | TS-07/05/24 Ltr sent for 15/05/24. 08/05 SMS called but no. NIS
23 | Donibristle Croft | Birmingham | B35 6BL | Mrs T Hayes |  | 07508118298 | Tammyarnold1977@hotmail.co.uk | Windows & Doors | M Turpin | 2024-05-15 | 8am to 2pm | CONFIRMED for 15/05/24
29 | Donibristle Croft | Birmingham | B35 6BL | Mrs A Bevan |  | 07816780788 |  | Windows & Doors | M Turpin | 2024-05-15 | 8am to 2pm | CONFIRMED for 15/05/24
31 | Donibristle Croft | Birmingham | B35 6BL | Mrs N S Khdir | 07305545492 |  |  | Windows & Doors | M Turpin | 2024-05-15 | 8am to 2pm | CONFIRMED for 15/05/24
33 | Donibristle Croft | Birmingham | B35 6BL | Miss C Styche | 07856104283 |  | clairestyche@gmail.com | Windows & Doors | M Turpin | 2024-05-15 | 8am to 2pm | TS-03/05/24 Text sent for 15/05/24. TS-07/05/24 Ltr sent for 15/05/24. 08/05 SMS left voicemail for 15/05
35 | Donibristle Croft | Birmingham | B35 6BL | Miss L Adams |  | 07462244999 | georgia.6@live.co.uk | Windows & Doors | M Turpin | 2024-05-15 | 8am to 2pm | CONFIRMED for 15/05/24
18 | Donibristle Croft | Birmingham | B35 6BL | Mrs S Nicholls | 01217475303 | 07307626475 |  | Windows & Doors | M Turpin | 2024-05-15 | 8am to 2pm | CONFIRMED for 15/05/24
20 | Donibristle Croft | Birmingham | B35 6BL | Mrs F Chantler | 01217767481 |  |  | Windows & Doors | M Turpin | 2024-05-15 | 8am to 2pm | TS-07/05/24 Ltr sent for 15/05/24.
Pioneer Group - Thursday 16th May - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
22 | Donibristle Croft | Birmingham | B35 6BL | Mrs C Brotherson | 01212930867 | 07710 599 502 |  | Windows & Doors | M Turpin | 2024-05-16 | 8am to 2pm | CONFIRMED for 16/05/24
24 | Donibristle Croft | Birmingham | B35 6BL | Mrs G A Thomas | 0121 218 2260 | 07775 709 656 | glynisandderek@gmail.com | Windows & Doors | M Turpin | 2024-05-16 | After 10am only | CONFIRMED for 16/05/24 after 10am only as has carer in morning. 15/05 SMS tenant called to cancel
26 | Donibristle Croft | Birmingham | B35 6BL | Miss S Taylor |  | 07852810599 |  | Windows & Doors | M Turpin | 2024-05-16 | 8am to 2pm | CONFIRMED for 16/05/24
28 | Donibristle Croft | Birmingham | B35 6BL | Mr V Hepburn |  | 07939 567 290 |  | Windows & Doors | M Turpin | 2024-05-16 | 8am to 2pm | CONFIRMED for 16/05/24
5 | Donibristle Croft | Birmingham | B35 6BL | Mrs L C Rogers | 07445263092 |  | lroje@aol.com | Windows & Doors | M Turpin | 2024-05-16 | 8am to 2pm | CONFIRMED for 16/05/24
6 | Donibristle Croft | Birmingham | B35 6BL | Mr K A Omitoyin | 01217494442 | 07877496683 |  | Windows & Doors | M Turpin | 2024-05-16 | 8am to 2pm | TS-03/05/24 Text sent for 16/05/24. TS-07/05/24 Ltr sent for 16/05/24. 08/05 SMS called N/A
8 | Donibristle Croft | Birmingham | B35 6BL | Ms A Mensah | 07557792040 |  |  | Windows & Doors | M Turpin | 2024-05-16 | 9am to 2pm | CONFIRMED for 16/05/24 after 9am
12 | Donibristle Croft | Birmingham | B35 6BL | Mrs F Chowdhury | 07944918697 |  | chowdhuryfarhana88@hotmail.co.uk | Windows & Doors | M Turpin | 2024-05-16 | 8am to 2pm | CONFIRMED for 16/05/24
19 | Donibristle Croft | Birmingham | B35 6BL | Miss E Chick |  |  |  | Windows & Doors | M Turpin | 2024-05-16 | 8am to 2pm | TS-07/05/24 Ltr sent for 16/05/24.
FLAT 54 | Brabazon Grove | Birmingham | B35 6DT | Miss S Moore |  | 07887963343 | suemoore35@yahoo.co.uk | Windows & Doors | M Turpin | 2024-05-16 | 8am to 2pm | CONFIRMED for 16/05/24
Pioneer Group - THURSDAY 23rd MAY - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
80 | Heyford Way | Birmingham | B35 6HU | Miss S A Henry | 07955 990134 | 07931 261590 |  | Windows & Doors | P Beahan | 2024-05-23 | 8am to 12pm | 13/05 SMS text sent for 23/05. 15/05 SMS called N/A. 16/05 SMS lttr sent
10 | Abingdon Way | Birmingham | B35 6QF | Miss P Caraher |  | 07823771871 | Paula.Caraher@sky.com | Windows & Doors | P Beahan | 2024-05-23 | 8am to 12pm | 13/05 SMS text sent for 23/05. 15/05 SMS left voicemail. 16/05 SMS lttr sent
12 | Abingdon Way | Birmingham | B35 6QF | Miss S Palmer |  | 07309493666 | sylviapalmer67@gmail.com | Windows & Doors | P Beahan | 2024-05-23 | 11am to 3pm | CONFIRMED for 23/05
14 | Abingdon Way | Birmingham | B35 6QF | Miss D Smith | 07388043944 |  |  | Windows & Doors | P Beahan | 2024-05-23 | 11am to 3pm | 13/05 SMS text sent for 23/05. 16/05 SMS lttr sent
FLAT 9 | Abingdon Way | Birmingham | B35 6QF | Miss L Barnfield | 07415122085 |  | lindsaybar@icloud.com | Windows & Doors | P Beahan | 2024-05-23 | 12pm to 3pm | CONFIRMED after 12 only, also needs a phone call before attending pls
FLAT 11 | Abingdon Way | Birmingham | B35 6QF | Miss Natalie Redmond | 07818 754 543 |  |  | Windows & Doors | P Beahan | 2024-05-23 | 12pm to 3pm | CONFIRMED for 23/05
Pioneer Group - THURSDAY 23rd MAY - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
33 | Watton Green | Birmingham | B35 7JS | Miss L Craddock |  | 07548278817 | l_craddock1988@outlook.com | Windows & Doors | M Turpin | 2024-05-23 | 8am to 2pm | CONFIRMED for 23/05. 22/05 SMS tenant called to cancel
54 | Watton Green | Birmingham | B35 7JP | Miss M-A Kells |  | 07391 853363 NIS |  | Windows & Doors | M Turpin | 2024-05-23 | 8am to 2pm | 13/05 SMS text sent for 23/05. 15/05 SMS no. NIS. 16/05 SMS lttr sent
76 | Watton Green | Birmingham | B35 7JR | Lauren Heinz | 7850489726 |  |  | Windows & Doors | M Turpin | 2024-05-23 | 8am to 2pm | CONFIRMED for 23/05
16 | Watton Green | Birmingham | B35 7JS | Miss L Millington |  | 07903 735737 | kate.is.cool@live.com | Windows & Doors | M Turpin | 2024-05-23 | 8am to 2pm | 13/05 SMS text sent for 23/05. 15/05 SMS called N/A. 16/05 SMS lttr sent
26 | Watton Green | Birmingham | B35 7JS | Miss S Thomas | 7557154887 |  | thomas86@hotmail.co.uk | Windows & Doors | M Turpin | 2024-05-23 | 8am to 2pm | 13/05 SMS text sent for 23/05. 15/05 SMS left voicemail. 16/05 SMS lttr sent
86 | Watton Green | Birmingham | B35 7JR | Miss L E Oldham |  |  | lyssa_oldham@yahoo.co.uk | Windows & Doors | M Turpin | 2024-05-23 | 8am to 2pm | 13/05 SMS lttr sent for 23/05
88 | Watton Green | Birmingham | B35 7JR | Mr P Nicholas | 01217494548 | 07868521372 |  | Windows & Doors | M Turpin | 2024-05-23 | 8am to 2pm | CONFIRMED for 23/05
90 | Watton Green | Birmingham | B35 7JR | Mr M Mooney |  |  |  | Windows & Doors | M Turpin | 2024-05-23 | 8am to 2pm | 13/05 SMS lttr sent for 23/05
92 | Watton Green | Birmingham | B35 7JR | Mr A Russon | 7474341776 | 07891567847 |  | Windows & Doors | M Turpin | 2024-05-23 | 8am to 2pm | CONFIRMED for 23/05
97 | Watton Green | Birmingham | B35 7GA | Miss J Atterbury | 07970331259 |  |  | Windows & Doors | M Turpin | 2024-05-23 | 8am to 2pm | CONFIRMED for 23/05
Pioneer Group - FRIDAY 24th MAY - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
FLAT 15 | Abingdon Way | Birmingham | B35 6QF | Mr N Sheldon | 01217476769 |  |  | Windows & Doors | P Beahan | 2024-05-24 | 8am to 12pm | 13/05 SMS Lttr sent for 24/05. 17/05 SMS req Dominie do home visit b4 this surv date due to items obstructing internal windows
16 | Abingdon Way | Birmingham | B35 6QF | Mr K Murphy | 0121 439 3727 |  |  | Windows & Doors | P Beahan | 2024-05-24 | 8am to 12pm | 13/05 SMS Lttr sent for 24/05
17 | Abingdon Way | Birmingham | B35 6QF | Miss M Meadley | 07798934679 |  |  | Windows & Doors | P Beahan | 2024-05-24 | 8am to 12pm | CONFIRMED for 24/05
18 | Abingdon Way | Birmingham | B35 6QF | Miss S Henry | 7375076318 |  | shakerah25@gmail.com | Windows & Doors | P Beahan | 2024-05-24 | 11am to 3pm | 13/05 SMS text sent for 24/05. 15/05 SMS left voicemail. 16/05 SMS lttr sent
19 | Abingdon Way | Birmingham | B35 6QF | Miss A Jackson | 7713605361 |  | jacksonalison00@gmail.com | Windows & Doors | P Beahan | 2024-05-24 | 11am to 3pm | CONFIRMED for 24/05
20 | Abingdon Way | Birmingham | B35 6QF | Mr M Edwards | 7904591717 |  | eddybcfc@googlemail.com | Windows & Doors | P Beahan | 2024-05-24 | 11am to 3pm | CONFIRMED for 24/05
Pioneer Group - FRIDAY 24th MAY - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
70 | Brabazon Grove | Birmingham | B35 6DT | Mrs K Marshall | 01217493482 | 07943 129723 | kayleighmarshall24@outlook.com | Windows & Doors | M Turpin | 2024-05-24 | 8am to 2pm | 13/05 SMS text sent for 24/05. CONFIRMED for 24/05 - 24.05.24 SF CANCELLED via phone
22 | Watton Green | Birmingham | B35 7JS | Miss C Coope | 07983 203 104 |  |  | Windows & Doors | M Turpin | 2024-05-24 | 8am to 2pm | CONFIRMED for 24/05 - 24.05.24 SF CANCELLED via phone, she has no more time off until July, but will get her Mom to be in the property and will email us her door choice at the time
130 | Watton Green | Birmingham | B35 7JS | Miss B Bonner | 07818650367 NIS | 0121 574 2835 |  | Windows & Doors | M Turpin | 2024-05-24 | 8am to 2pm | 13/05 SMS text sent for 24/05. 15/05 SMS mob no NIS landlane N/A. 16/05 SMS lttr sent - 24.05.24 SF CANCELLED via phone, LM, no answer, sent text
132 | Watton Green | Birmingham | B35 7JT | Mrs MT Butcher | 01217485045 | 07912698243 | theresa.butcher@hotmail.co.uk | Windows & Doors | M Turpin | 2024-05-24 | 8am to 2pm | CONFIRMED for 24/05 text - 24.05.24 SF CANCELLED via phone, tenant not happy, she booked time off work
134 | Watton Green | Birmingham | B35 7JT | Mrs A Maglie | 7379130013 |  |  | Windows & Doors | M Turpin | 2024-05-24 | 8am to 10am | CONFIRMED for 24/05 Between 8 - 10am pls - 24.05.24 SF CANCELLED via phone, LM and sent a text
138 | Watton Green | Birmingham | B35 7JT | Miss Z L Harding | 07860618302 NIS |  |  | Windows & Doors | M Turpin | 2024-05-24 | 8am to 2pm | 13/05 SMS text sent for 24/05. 15/05 SMS mob no NIS . 16/05 SMS lttr sent - 24.05.24 SF CANCELLED via text message as number NIS
140 | Watton Green | Birmingham | B35 7JT | Mrs L Round | 07368 589 897 | 0121 572 0644 |  | Windows & Doors | M Turpin | 2024-05-24 | 8am to 2pm | CONFIRMED for 24/05 - 24.05.24 SF CANCELLED via phone, LM and sent text
142 | Watton Green | Birmingham | B35 7JT | Miss G Powell | 07496 569312 |  | spiderladyuk07@hotmail.com | Windows & Doors | M Turpin | 2024-05-24 | 8am to 2pm | 13/05 SMS text sent for 24/05. 15/05 SMS called N/A. 16/05 SMS letter sent - 24.05.24 SF CANCELLED via phone, LM and sent text
1 | Merlin Close | Birmingham | B35 7JW | Miss D Lewis | 07897 482 067 |  | dianelewis80@outlook.com | Windows & Doors | M Turpin | 2024-05-24 | 8am to 2pm | 13/05 SMS text sent for 24/05. 16/05 SMS lttr sent - 24.05.24 SF CANCELLED via phone, LM and sent text
68 | Brabazon Grove | Birmingham | B35 6DT | Miss T Pointon |  |  | tracy-1979@hotmail.co.uk | Windows & Doors | M Turpin | 2024-05-24 | 8am to 2pm | CONFIRMED for 24/05. 23/05 SMS tenant emailed to cancel
Pioneer Group - THURSDAY 30th MAY - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
21 | Abingdon Way | Birmingham | B35 6QF | Miss R Groves |  | 7951756553 | rg012h5048@blueyonder.co.uk | Windows & Doors | P Beahan | 2024-05-30 | 8am to 12pm | CONFIRMED for 30/05
22 | Abingdon Way | Birmingham | B35 6QF | Miss C Spencer |  | 07856 568 902 NIS |  | Windows & Doors | P Beahan | 2024-05-30 | 8am to 12pm | 16/05 SMS text sent for 30/05. 17/05 SMS no. NIS lttr sent
23 | Abingdon Way | Birmingham | B35 6QF | Miss G Croton | 7392426449 | 0121 439 3893 |  | Windows & Doors | P Beahan | 2024-05-30 | 8am to 12pm | 16/05 SMS text sent for 30/05. 17/05 SMS called N/A lttr sent
24 | Abingdon Way | Birmingham | B35 6QF | Miss N Asghar |  | 07597117573 |  | Windows & Doors | P Beahan | 2024-05-30 | 11am to 3pm | CONFIRMED for 30/05
25 | Abingdon Way | Birmingham | B35 6QF | Miss A Taylor | 07534095490 |  |  | Windows & Doors | P Beahan | 2024-05-30 | 11am to 3pm | 16/05 SMS text sent for 30/05. 17/05 SMS called N/A lttr sent
FLAT 26 | Bovingdon Road | Birmingham | B35 6QD | Mr P Owen | 07575386715 |  |  | Windows & Doors | P Beahan | 2024-05-30 | 11am to 3pm | CONFIRMED for 30/05
Pioneer Group - FRIDAY 31st MAY - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
27 | Abingdon Way | Birmingham | B35 6QF | Miss D Ward |  | 7535633828 | demi.p.ward96@hotmail.co.uk | Windows & Doors | P Beahan | 2024-05-31 | 8am to 12pm | CONFIRMED for 31/05
29 | Abingdon Way | Birmingham | B35 6QF | Mrs C Reeves | 7731361252 |  | clare.reeves.72@BTinternet.com | Windows & Doors | P Beahan | 2024-05-31 | 8am to 12pm | CONFIRMED for 31/05
30 | Abingdon Way | Birmingham | B35 6QF | Mrs D Douglas | 01217303001 | 07517 041 862 |  | Windows & Doors | P Beahan | 2024-05-31 | 8am to 12pm | 16/05 SMS text sent for 31/05. 17/05 SMS called N/A lttr sent
31 | Abingdon Way | Birmingham | B35 6QF | Mr G Blackburn | 01214393727 | 7847214967 |  | Windows & Doors | P Beahan | 2024-05-31 | 11am to 3pm | CONFIRMED for 31/05
32 | Abingdon Way | Birmingham | B35 6QF | Miss S C McNally | 01217474558 | 7983580836 | sandie123@19680talktalk.net | Windows & Doors | P Beahan | 2024-05-31 | 11am to 3pm | CONFIRMED for 31/05
33 | Abingdon Way | Birmingham | B35 6QF | Miss C Lewin | 07930748765 |  |  | Windows & Doors | P Beahan | 2024-05-31 | 11am to 3pm | (Access via 31 Abingdon Way) CONFIRMED for 31/05
Pioneer Group - WEDNESDAY 5th JUNE - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
34 | Abingdon Way | Birmingham | B35 6QF | Miss V Lindsey | 01217478826 | 07738 706165 |  | Windows & Doors | P Beahan | 2024-06-05 | 8am to 12pm | CONFIRMED for 05/06
37 | Abingdon Way | Birmingham | B35 6QF | Miss T Hannaby | 7301564265 |  | toni_hannaby@hotmail.com | Windows & Doors | P Beahan | 2024-06-05 | 8am to 12pm | CONFIRMED for 05/06
41 | Abingdon Way | Birmingham | B35 6QF | Mrs M Hulme | 07519 506 990 |  |  | Windows & Doors | P Beahan | 2024-06-05 | 8am to 12pm | CONFIRMED for 05/06
45 | Abingdon Way | Birmingham | B35 6QF | Mr DK White | 7703345794 |  |  | Windows & Doors | P Beahan | 2024-06-05 | 11am to 3pm | CONFIRMED for 05/06
FLAT 28 | Bovingdon Road | Birmingham | B35 6QD | Miss K Moxam | 7815443584 |  |  | Windows & Doors | P Beahan | 2024-06-05 | 11am to 3pm | 20/05 SMS text sent for 05/06. 29/05 SMS left voicemail. 30/05 SMS called N/A lttr sent. 03/06 SMS tenent cancelled, re-scheduled for 27/06
FLAT 30 | Bovingdon Road | Birmingham | B35 6QD | Mr R Oldland | 7909951048 NIS |  | robinoldland@gmail.com | Windows & Doors | P Beahan | 2024-06-05 | 11am to 3pm | 20/05 SMS text sent for 05/06. 29/05 SMS no. NIS Lttr sent
Pioneer Group - WEDNESDAY 5th JUNE - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
3 | Merlin Close | Birmingham | B35 7JW | Miss H Cother | 07588 615469 |  |  | Windows & Doors | M Turpin | 2024-06-05 | 8am to 2pm | CONFIRMED for 05/06
5 | Merlin Close | Birmingham | B35 7JW | Miss J Wardle | 7506220380 |  | jenniferwardle@icloud.com | Windows & Doors | M Turpin | 2024-06-05 | 8am to 2pm | CONFIRMED for 05/06 need to call tenant before attending to confirm time
7 | Merlin Close | Birmingham | B35 7JW | Mr D Milson | 0121 749 6885 |  | D.Milson@TalkTalk.NET | Windows & Doors | M Turpin | 2024-06-05 | 8am to 2pm | 20/05 SMS sent email for 05/06 / 23.05.24 SF Sent another email / 23.05.24 SF Email came back undelivered, sent letter
8 | Merlin Close | Birmingham | B35 7JW | Mrs V Brobbey-Sarpong | 07713 246696 |  | 1 | Windows & Doors | M Turpin | 2024-06-05 | 8am to 2pm | CONFIRMED for 05/06
9 | Merlin Close | Birmingham | B35 7JW | Mr R Wilkes | 7717106818 |  |  | Windows & Doors | M Turpin | 2024-06-05 | 8am to 2pm | CONFIRMED for 05/06
10 | Merlin Close | Birmingham | B35 7JW | Miss E C Wilson | 07988 62 85 88 |  |  | Windows & Doors | M Turpin | 2024-06-05 | 8am to 2pm | CONFIRMED for 05/06
11 | Merlin Close | Birmingham | B35 7JW | Miss A Taylor | 7930525324 |  | alison_taylor2007@hotmail.co.uk | Windows & Doors | M Turpin | 2024-06-05 | 8am to 2pm | CONFIRMED for 05/06
12 | Merlin Close | Birmingham | B35 7JW | Miss J Rudd | 07444 639584 |  |  | Windows & Doors | M Turpin | 2024-06-05 | 8am to 2pm | CONFIRMED for 05/06
136 | Watton Green | Birmingham | B35 7JT | Miss R Brown | 01214398486 | 7884087109 | rachelb1987@live.co.uk | Windows & Doors | M Turpin | 2024-06-05 | 9am to 2pm | CONFIRMED for 05/06 between 9am and 2pm please
33 | Watton Green | Birmingham | B35 7JS | Miss L Craddock |  | 7548278817 |  | Windows & Doors | M Turpin | 2024-06-05 | 9am to 2pm | CONFIRMED for 05/06 between 9am and 2pm please. 04/06 SMS tenant cancelled.
Pioneer Group - THURSDAY 6th JUNE - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
47 | Abingdon Way | Birmingham | B35 6QF | Miss S Ashe | 7746236858 |  |  | Windows & Doors | P Beahan | 2024-06-06 | 8am to 12pm | CONFIRMED for 06.06
49 | Abingdon Way | Birmingham | B35 6QF | Miss S Phillips | 7397891865 |  | sophiedadon14@gmail.com | Windows & Doors | P Beahan | 2024-06-06 | 8am to 12pm | CONFIRMED for 06.06
2 | Bovingdon Road | Birmingham | B35 6QD | Mrs J A Rutter | 0121 748 3402 | 07903 402 107 | janiutter2@sky.com | Windows & Doors | P Beahan | 2024-06-06 | 8am to 12pm | CONFIRMED for 06/06
4 | Bovingdon Road | Birmingham | B35 6QD | Miss K Shaheen | 7748442175 |  | kiran2400@icloud.com | Windows & Doors | P Beahan | 2024-06-06 | 11am to 3pm | CONFIRMED for 06/06
6 | Bovingdon Road | Birmingham | B35 6QD | Mr M Holliday | 7794786720 |  | malcolmholliday@hotmail.co.uk | Windows & Doors | P Beahan | 2024-06-06 | 11am to 3pm | CONFIRMED for 06/06
8 | Bovingdon Road | Birmingham | B35 6QD | Miss C Anderson-Wood | 7766743505 |  | booanderson2016@gmail.com | Windows & Doors | P Beahan | 2024-06-06 | 11am to 3pm | CONFIRMED for 06/06
Pioneer Group - THURSDAY 6th JUNE - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
10 | School Close | Birmingham | B35 7NU | Mrs K Smith | 7368456033 |  |  | Windows & Doors | M Turpin | 2024-06-06 | 8am to 2pm | CONFIRMED for 06/06
12 | School Close | Birmingham | B35 7NU | Mr & Mrs P Sinclair | 07949 806 674 |  | sinclair580@btinternet.com | Windows & Doors | M Turpin | 2024-06-06 | 8am to 2pm | CONFIRMED for 06.06
14 | School Close | Birmingham | B35 7NU | Miss J Harris | 0121 537 4644 | 07517 434 464 |  | Windows & Doors | M Turpin | 2024-06-06 | 8am to 2pm | CONFIRMED for 06/06
6 | School Close | Birmingham | B35 7NU | Mrs D Price | 7463427409 |  |  | Windows & Doors | M Turpin | 2024-06-06 | 8am to 2pm | CONFIRMED for 06/06
8 | School Close | Birmingham | B35 7NU | Mr H Malone | 7949843403 |  |  | Windows & Doors | M Turpin | 2024-06-06 | 8am to 2pm | 20/05 SMS sent email for 06/06 / 23.05.24 SF Sent another text. 29/05 SMS spoke to tenant & lttr sent.
88 | Javelin Avenue | Birmingham | B35 7LW | Miss V Keen | 7731948831 |  | keenvicky@yahoo.co.uk | Windows & Doors | M Turpin | 2024-06-06 | 8am to 2pm | *Dominie is overseing new date of 06/06 due to prev issue*. CONFIRMED for 06/06
35 | St Athan Croft | Birmingham | B35 7LR | Mr SD Brady | 7572011095 |  |  | Windows & Doors | M Turpin | 2024-06-06 | 8am to 2pm | 20/05 SMS sent email for 06/06 / 23.05.24 SF Sent another text. 29/05 SMS called N/A Lttr sent. 06/06 SMS tewnant called to cancel.
2 | St Athan Croft | Birmingham | B35 7LS | Mr J C Thompson |  |  | joethompson-88@hotmail.com | Windows & Doors | M Turpin | 2024-06-06 | 8am to 2pm | 23/05 SMS Lttr sent for 06/06
8 | Cosford Crescent | Birmingham | B35 6QE | Mrs S C Brice | 7368490634 |  | suzannewestbury@hotmail.com | Windows & Doors | M Turpin | 2024-06-06 | 8am to 2pm | 20/05 SMS sent email for 06/06 / 23.05.24 SF Sent another text & email. 29/05 SMS called N/A lttr sent.
FLAT 12 | Cosford Crescent | Birmingham | B35 6QE | Miss T Heathcote | 7938590661 |  | tracy.hat@blueyonder.co.uk | Windows & Doors | M Turpin | 2024-06-06 | 8am to 2pm | (Access via 8 Cosford & 2 Abingdon)CONFIRMED for 06/06
[8 empty] | Windows & Doors | M Turpin | 2024-06-06 | 8am to 2pm
Pioneer Group - FRIDAY 7th JUNE - S Burgess
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
FLAT 36 | Northolt Drive | Birmingham | B35 6QX | Miss K Taylor | 07857 917 151 |  |  | Windows & Doors | S Burgess | 2024-06-07 | 8am to 12pm | 23.05.24 SF Sent text for 07.06. 29/05 SMS left voicemail. 30/05 SMS called N/A lttr sent
FLAT 1 | Northolt Drive | Birmingham | B35 6QX | Mr M Brookes | 07984 225 726 |  |  | Windows & Doors | S Burgess | 2024-06-07 | 8am to 12pm | 23.05.24 SF Sent text for 07.06. 29/05 SMS called N/A. 30/05 SMS called N/A lttr sent
FLAT 8 | Northolt Drive | Birmingham | B35 6QX | Mr M Atterbury | 7737671775 NIS |  |  | Windows & Doors | S Burgess | 2024-06-07 | 8am to 12pm | 23.05.24 SF Sent text for 07.06. 29/05 SMS called no. NIS lttr sent.
21 | Northolt Drive | Birmingham | B35 6QX | Miss E McLean | 7764707718 |  | elliemaymclean@icloud.com | Windows & Doors | S Burgess | 2024-06-07 | 11am to 3pm | 23.05.24 SF Sent text for 07.06. 29/05 SMS called N/A. 30/05 SMS called N/A lttr sent. 04/06 SMS Dominie visited address and they confirmed for 07/06
FLAT 27 | Northolt Drive | Birmingham | B35 6QX | Miss Q Mapp | 07903 811 842 |  | queshia-teann.mapp@hotmail.co.uk | Windows & Doors | S Burgess | 2024-06-07 | 11am to 3pm | CONFIRMED via return text for 07.06
[8 empty] | Windows & Doors | S Burgess | 2024-06-07 | 11am to 3pm
Pioneer Group - MONDAY 10th JUNE - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
50 | Watton Green | Birmingham | B35 7JP | Miss T Arlow | 07453 414 148 |  |  | Windows & Doors | M Turpin | 2024-06-10 | 8am to 2pm | 29/05 SMS text sent for 10/06. 31/05 SMS left voicemail. 03/06 SMS called N/A Lttr sent
58 | Watton Green | Birmingham | B35 7JP | Miss G Jones | 7942713340 |  |  | Windows & Doors | M Turpin | 2024-06-10 | 8am to 2pm | 29/05 SMS text sent for 10/06. 31/05 SMS called N/A. 03/06 SMS called N/A Lttr sent
74 | Watton Green | Birmingham | B35 7JP | Miss MC Dale | 7931981160 |  |  | Windows & Doors | M Turpin | 2024-06-10 | 8am to 2pm | CONFIRMED for 10/06
327 | Yatesbury Avenue | Birmingham | B35 6QP | Mrs A Clarke | 7838705905 |  | annie-clarke@hotmail.co.uk | Windows & Doors | M Turpin | 2024-06-10 | 8am to 2pm | CONFIRMED for 10/06
FLAT 329 | Yatesbury Avenue | Birmingham | B35 6QP | Miss S L Reid | 0121 730 2729 | 7977348224 |  | Windows & Doors | M Turpin | 2024-06-10 | 8am to 2pm | (Access via 327 Yatesbury & 1 Cosford Crescent) CONFIRMED for 10/06
FLAT 331 | Yatesbury Avenue | Birmingham | B35 6QP | Mr W Hall | 7399591051 |  |  | Windows & Doors | M Turpin | 2024-06-10 | 8am to 2pm | (Access via 327 Yatesbury & 1 Cosford Crescent) 29/05 SMS text sent for 10/06. 31/05 SMS called N/A. 03/06 SMS called N/A Lttr sent
FLAT 333 | Yatesbury Avenue | Birmingham | B35 6QP | Miss K Welburn | 7460716756 |  | kayleighwelburn@hotmail.co.uk | Windows & Doors | M Turpin | 2024-06-10 | 8am to 2pm | (Access via 327 Yatesbury & 1 Cosford Crescent) CONFIRMED for 10/06
FLAT 335 | Yatesbury Avenue | Birmingham | B35 6QP | Mr RJ Sharpe | 7572975677 |  |  | Windows & Doors | M Turpin | 2024-06-10 | 8am to 2pm | (Access via 327 Yatesbury & 1 Cosford Crescent) 29/05 SMS text sent for 10/06. 31/05 SMS called N/A. 03/06 SMS called N/A Lttr sent
2 | Cosford Crescent | Birmingham | B35 6QE | Ms S Bills | 01215725293 |  |  | Windows & Doors | M Turpin | 2024-06-10 | 8am to 2pm | 31/05 SMS called N/A. 03/06 SMS called N/A Lttr sent
24 | Donibristle Croft | Birmingham | B35 6BL | Mrs G A Thomas | 0121 218 2260 | 07775 709 656 |  | Windows & Doors | M Turpin | 2024-06-10 | 10am to 2pm | CONFIRMED for 10/06 after 10am
Pioneer Group - TUESDAY 11th JUNE - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
349 | Yatesbury Avenue | Birmingham | B35 6QP | Mr P Mattey |  |  |  | Windows & Doors | M Turpin | 2024-06-11 | 8am to 2pm | 29/05 SMS lttr sent for 11/06
FLAT 337 | Yatesbury Avenue | Birmingham | B35 6QP | Mr G Kinsella | 07944 697 120 | 07984479727 |  | Windows & Doors | M Turpin | 2024-06-11 | 8am to 2pm | (Access via 349 Yatesbury & 2 Cosford Crescent) 29/05 SMS text sent for 11/06. 31/05 SMS left voicemail. 03/06 SMS called N/A Lttr sent
FLAT 339 | Yatesbury Avenue | Birmingham | B35 6QP | Mr A Rainbird | 07899 568 735 |  |  | Windows & Doors | M Turpin | 2024-06-11 | 8am to 2pm | (Access via 349 Yatesbury & 2 Cosford Crescent) CONFIRMED for 11/06
FLAT 341 | Yatesbury Avenue | Birmingham | B35 6QP | Mr G Walton | 7443730616 |  | gareth.walton1988@icloud.com | Windows & Doors | M Turpin | 2024-06-11 | 8am to 2pm | (Access via 349 Yatesbury & 2 Cosford Crescent) CONFIRMED for 11/06
FLAT 343 | Yatesbury Avenue | Birmingham | B35 6QP | Miss P Fisher | 7711581016 |  | paulinefisher21@hotmail.com | Windows & Doors | M Turpin | 2024-06-11 | 8am to 2pm | (Access via 349 Yatesbury & 2 Cosford Crescent) CONFIRMED for 11/06
FLAT 345 | Yatesbury Avenue | Birmingham | B35 6QP | Mr HA Zare | 7474530394 |  | hosseinali1980zare@gmail.com | Windows & Doors | M Turpin | 2024-06-11 | 8am to 2pm | (Access via 349 Yatesbury & 2 Cosford Crescent) CONFIRMED for 11/06
FLAT 14 | Cosford Crescent | Birmingham | B35 6QE | Mr G P Casey | 7903577086 |  | glencasey33@yahoo.co.uk | Windows & Doors | M Turpin | 2024-06-11 | 8am to 2pm | (Access via 8 Cosford & 2 Abingdon) CONFIRMED for 11/06
FLAT 16 | Cosford Crescent | Birmingham | B35 6QE | Miss J Mulholland | 7526535273 |  |  | Windows & Doors | M Turpin | 2024-06-11 | 8am to 2pm | (Access via 8 Cosford & 2 Abingdon) CONFIRMED for 11/06
FLAT 18 | Cosford Crescent | Birmingham | B35 6QE | Mr P McCormick | 01216490938 |  |  | Windows & Doors | M Turpin | 2024-06-11 | 8am to 2pm | (Access via 8 Cosford & 2 Abingdon) 31/05 SMS called for 11/06 N/A. 03/06 SMS called N/A Lttr sent
Pioneer Group - WEDNESDAY 12th JUNE - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
10 | Bovingdon Road | Birmingham | B35 6QD | Ms J Oliver | 7985476899 |  |  | Windows & Doors | P Beahan | 2024-06-12 | 8am to 12pm | CONFIRMED for 12/06
12 | Bovingdon Road | Birmingham | B35 6QD | Miss D Webb | 01217484992 | 07961 964 356 | donnawebb123@hotmail.com | Windows & Doors | P Beahan | 2024-06-12 | 8am to 12pm | CONFIRMED for 12/06
14 | Bovingdon Road | Birmingham | B35 6QD | Miss T Grinham | 7368828517 |  |  | Windows & Doors | P Beahan | 2024-06-12 | 8am to 12pm | CONFIRMED for 12/06
16 | Bovingdon Road | Birmingham | B35 6QD | Miss J-J Mckean | 7547322202 NIS |  | pwrincessjay@outlook.com | Windows & Doors | P Beahan | 2024-06-12 | 11am to 3pm | 29/05 SMS text sent for 12/06. 31/05 SMS called & no. NIS lttr sent.
18 | Bovingdon Road | Birmingham | B35 6QD | Miss C Chambers | 07779 003 594 |  | corrine.chambers@btinternet.com | Windows & Doors | P Beahan | 2024-06-12 | 11am to 3pm | CONFIRMED for 12/06
34 | Bovingdon Road | Birmingham | B35 6QD | Miss KA Day | 7472329129 |  |  | Windows & Doors | P Beahan | 2024-06-12 | 11am to 3pm | CONFIRMED for 12/06
Pioneer Group - WEDNESDAY 12th JUNE - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
22 | Watton Green | Birmingham | B35 7JS | Miss C Coope | 07983 203 104 |  |  |  | M Turpin | 2024-06-12 | 8am to 2pm | 10/06 SMS text sent for 12/06. 11/06 SMS called N/A
138 | Watton Green | Birmingham | B35 7JT | Miss Z L Harding | 07487 409 019 |  |  |  | M Turpin | 2024-06-12 | 8am to 2pm | CONFIRMED for 12/06
3 | Montrose Drive | Birmingham | B35 6DH | Miss K Eyles |  | 07949994313 | katieleigheyles@outlook.com |  | M Turpin | 2024-06-12 | 8am to 2pm | CONFIRMED for 12/06
5 | Montrose Drive | Birmingham | B35 6DH | Miss R Pilawski |  | 07860824519 | xox_bex_xox@hotmail.com |  | M Turpin | 2024-06-12 | 8am to 2pm | CONFIRMED for 12/06
7 | Montrose Drive | Birmingham | B35 6DH | Ms G Kavanagh | 07496163811 | 07432844536 | gemmakavanagh11@gmail.com |  | M Turpin | 2024-06-12 | 8am to 2pm | 10/06 SMS text sent for 12/06
8 | Montrose Drive | Birmingham | B35 6DH | Mr D Loveridge | 07761915204 | 07761915204 |  |  | M Turpin | 2024-06-12 | 8am to 2pm | 10/06 SMS text sent for 12/06. Dominie Carded
9 | Montrose Drive | Birmingham | B35 6DH | Miss R Garrington |  | 07397 384 556 |  |  | M Turpin | 2024-06-12 | 8am to 2pm | 10/06 SMS text sent for 12/06. Dominie Carded
11 | Montrose Drive | Birmingham | B35 6DH | Ms R Carter | 07481614010 | 07481614010 |  |  | M Turpin | 2024-06-12 | 8am to 2pm | 10/06 SMS text sent for 12/06
12 | Montrose Drive | Birmingham | B35 6DH | Mr S Walker |  | 07783756626 | swalker12@talktalk.net |  | M Turpin | 2024-06-12 | 8am to 2pm | CONFIRMED for 12/06
15 | Montrose Drive | Birmingham | B35 6DH | Mr D R Branson |  |  |  |  | M Turpin | 2024-06-12 | 8am to 2pm | CONFIRMED for 12/06
Pioneer Group - THURSDAY 13th JUNE - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
FLAT 20 | Bovingdon Road | Birmingham | B35 6QD | Mrs Z Ahmadi | 7305904298 |  | zoheeh_ahmadi@yahoo.com | Windows & Doors | P Beahan | 2024-06-13 | 8am to 12pm | CONFIRMED for 13/06
FLAT 22 | Bovingdon Road | Birmingham | B35 6QD | Mrs D P Loughran | 0121 748 2470 | 7454351543 | dawnloughran@aol.com | Windows & Doors | P Beahan | 2024-06-13 | 8am to 12pm | CONFIRMED for 13/06
FLAT 24 | Bovingdon Road | Birmingham | B35 6QD | Mr S Abhar | 7462086448 |  | sarooshabhar1@gmail.com | Windows & Doors | P Beahan | 2024-06-13 | 8am to 12pm | 29/05 SMS text sent for 13/06. 31/05 SMS left voicemail. 03/06 SMS called N/A Lttr sent
36 | Bovingdon Road | Birmingham | B35 6QD | Mrs W Ward | 748 1443 | 7531370562 | ww249@aol.com | Windows & Doors | P Beahan | 2024-06-13 | 11am to 3pm | CONFIRMED for 13/06
38 | Bovingdon Road | Birmingham | B35 6QD | Miss E Butler | 7983689667 |  | emilybutler@msn.com | Windows & Doors | P Beahan | 2024-06-13 | 11am to 3pm | CONFIRMED for 13/06. 13/06 tenant called and changed for tomorrow
40 | Bovingdon Road | Birmingham | B35 6QD | Miss D Maylor | 0121 748 5352 | 07951 616 000 |  | Windows & Doors | P Beahan | 2024-06-13 | 11am to 3pm | CONFIRMED for 13/06
Pioneer Group - FRIDAY 14th JUNE - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
14 | Chigwell Close | Birmingham | B35 7HH | Ms L Mullen | 07496 570635 | 07496 570635 |  | Windows & Doors | P Beahan | 2024-06-14 | 8am to 12pm | (DO NOT MOVE UNLESS SPOKEN TO DA AND SANDRA) 03/06 SMS text sent for 14/06. CONFIRMED for 14/06
FLAT 66 | Mere Avenue | Birmingham | B35 6QT | Miss S Snelson | 07467587073 |  | sarahlouisesnelson@hotmail.com | Windows & Doors | P Beahan | 2024-06-14 | 8am to 12pm | CONFIRMED for 14/06
FLAT 68 | Mere Avenue | Birmingham | B35 6QT | Mr S Gardiner | 07305 947 116 | 7873894184 NIS | mya1997@live.co.uk | Windows & Doors | P Beahan | 2024-06-14 | 8am to 12pm | CONFIRMED for 14/06
FLAT 60 | Mere Avenue | Birmingham | B35 6QT | Mr P J McCallion | 07751 066 503 |  | patrickmccallion8@gmail.com | Windows & Doors | P Beahan | 2024-06-14 | 11am to 3pm | 03/06 SMS text sent for 14/06. 04/06 SMS called left voicemail. 05/06 SMS called N/A Lttr sent
18 | Mere Avenue | Birmingham | B35 6QT | Mr M Fitzgerald |  | 7919324496 NIS | michael.fitzgerald3@sky.com | Windows & Doors | P Beahan | 2024-06-14 | 11am to 3pm | CONFIRMED for 14/06
38 | Bovingdon Road | Birmingham | B35 6QD | Miss E Butler | 7983689667 |  | emilybutler@msn.com | Windows & Doors | P Beahan | 2024-06-14 | 11am to 3pm | CONFIRMED for 14/06
Pioneer Group - MONDAY 17th JUNE - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
22 | Watton Green | Birmingham | B35 7JS | Miss C Coope | 07983 203 104 |  |  | Windows & Doors | M Turpin | 2024-06-17 | 7.30AM | 13/06 SMS text sent for 17/06 at 7.30am req by surveyor?
21 | Donibristle Croft | Birmingham | B35 6BL | Mrs T A Robinson | 01217487692 NIS |  | robrobinson@live.co.uk | Windows & Doors | M Turpin | 2024-06-17 | 8am to 2pm | 06/06 SMS called no. NIS lttr sent.
1 | Coltishall Close | Birmingham | B35 7EF | Miss C Tomkins |  | 07496 782816 | twiggy143@hotmail.com | Windows & Doors | M Turpin | 2024-06-17 | 8am to 2pm | CONFIRMED for 17/06
3 | Coltishall Close | Birmingham | B35 7EF | Miss S Ward | 07961649549 |  | sarswardy@gmail.com | Windows & Doors | M Turpin | 2024-06-17 | 8am to 2pm | CONFIRMED for 17/06
5 | Coltishall Close | Birmingham | B35 7EF | Miss S Wiggett |  | 07590912308 | samwiggett@outlook.com | Windows & Doors | M Turpin | 2024-06-17 | 8am to 2pm | CONFIRMED for 17/06
9 | Coltishall Close | Birmingham | B35 7EF | Miss N Horton |  | 07876 31 78 98 | nicolahorton1968@gmail.com | Windows & Doors | M Turpin | 2024-06-17 | 8am to 2pm | CONFIRMED for 17/06 (No. 11 has the key)
10 | Coltishall Close | Birmingham | B35 7EF | Mr S Marles | 0121 574 5664 | 7870635271 |  | Windows & Doors | M Turpin | 2024-06-17 | 8am to 2pm | 03/06 SMS text sent for 17/06. 06/06 SMS called N/A. 11/06 SMS called N/A Lttr sent. 14/06 SMS tenant caled to cancel.
11 | Coltishall Close | Birmingham | B35 7EF | Mrs P Clohessy |  |  | pam64@live.co.uk | Windows & Doors | M Turpin | 2024-06-17 | 8am to 2pm | 06/06 SMS lttr sent for 17/06
12 | Coltishall Close | Birmingham | B35 7EF | Mrs N Cheal |  | 7933940511 | n.cheal@hotmail.co.uk | Windows & Doors | M Turpin | 2024-06-17 | 8am to 2pm | CONFIRMED for 17/06
14 | Coltishall Close | Birmingham | B35 7EF | Miss L McBride |  | 7588323233 | laura_mcbride@live.co.uk | Windows & Doors | M Turpin | 2024-06-17 | 8am to 2pm | CONFIRMED for 17/06
15 | Coltishall Close | Birmingham | B35 7EF | Miss JP Johnson | 07472 605 384 |  |  | Windows & Doors | M Turpin | 2024-06-17 | 8am to 2pm | CONFIRMED for 17/06
8 | School Close | Birmingham | B35 7NU | Mr H Malone |  | 7949843403 |  | Windows & Doors | M Turpin | 2024-06-17 | 8am to 2pm | *PLEASE CONTACT DOMINIE WITH AN ARRIVAL TIME AS SHE WILL ATTEND ALSO* CONFIRMED for 17/06
Pioneer Group - TUESDAY 18th JUNE - S Burgess
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
FLAT 8 | Northolt Drive | Birmingham | B35 6QX | Mr M Atterbury |  | 07737671775 NIS |  | Windows & Doors | S Burgess | 2024-06-18 | 8am to 12pm | 11/06 SMS text sent for 18/06. 13/06 SMS no. NIS. Awaiting reply from Dominie before sending a letter
FLAT 36 | Northolt Drive | Birmingham | B35 6QX | Miss K Taylor |  | 07857 917 151 |  | Windows & Doors | S Burgess | 2024-06-18 | 8am to 12pm | 11/06 SMS text sent for 18/06. Awaiting reply from Dominie before sending a letter
FLAT 3 Block 16 | Bicester Square | Castle Vale | B35 6HR | Mr A Chinn |  | 07384 342527 |  | Windows & Doors | S Burgess | 2024-06-18 | 8am to 12pm | CONFIRMED for 18/06
FLAT 6 Block 16 | Bicester Square | Castle Vale | B35 6HR | Miss KG Walker | 7387314944 | 07557783791 |  | Windows & Doors | S Burgess | 2024-06-18 | 11am to 3pm | 04/06 SMS text sent for 18/06. 11/06 SMS called N/A. 13/06 SMS called N/A Lttr sent
FLAT 31 | Northolt Drive | Birmingham | B35 6QX | Mr M Phillips |  | 07598 421 064 |  | Windows & Doors | S Burgess | 2024-06-18 | 11am to 3pm | 04/06 SMS text sent for 18/06. 11/06 SMS left voicemail. 13/06 SMS called N/A Lttr sent
20 | Northolt Drive | Birmingham | B35 6QX | Miss T Benjamin |  | 07464732550 | tlb2001@hotmail.co.uk | Windows & Doors | S Burgess | 2024-06-18 | 1pm to 3pm | only available after 1pm. CONFIRMED for 18/06
Pioneer Group - TUESDAY 18th JUNE - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
3 | Concorde Drive | Birmingham | B35 7EE | Miss L Fox |  | 07904003519 |  | Windows & Doors | M Turpin | 2024-06-18 | 8am to 2pm | 04/06 SMS text sent for 18/06. 11/06 SMS called N/A. 13/06 SMS called N/A Lttr sent
7 | Concorde Drive | Birmingham | B35 7EE | Miss C Hopkins |  | 07896959369 | cazh86@live.co.uk | Windows & Doors | M Turpin | 2024-06-18 | 8am to 2pm | CONFIRMED for 01/07
9 | Concorde Drive | Birmingham | B35 7EE | Miss Z Newell |  | 07948 505 771 | ZenaNewall73@gmail.com | Windows & Doors | M Turpin | 2024-06-18 | 8am to 2pm | CONFIRMED for 01/07
11 | Concorde Drive | Birmingham | B35 7EE | Miss S Strachan |  | 07811487664 | sharonbrown1970@hotmail.co.uk | Windows & Doors | M Turpin | 2024-06-18 | 8am to 2pm | CONFIRMED for 18/06
17 | Concorde Drive | Birmingham | B35 7EE | Mrs V Green | 07724 272856 |  |  | Windows & Doors | M Turpin | 2024-06-18 | 8am to 2pm | CONFIRMED for 18/06
19 | Concorde Drive | Birmingham | B35 7EE | Mrs M Bowcott |  | 07904 122836 |  | Windows & Doors | M Turpin | 2024-06-18 | 8am to 2pm | CONFIRMED for 18/06
21 | Concorde Drive | Birmingham | B35 7EE | Miss J Weston |  | 07429922484 |  | Windows & Doors | M Turpin | 2024-06-18 | 8am to 2pm | 04/06 SMS text sent for 18/06. 11/06 SMS called N/A. 13/06 SMS called N/A lttr sent
23 | Concorde Drive | Birmingham | B35 7EE | Miss S Lewis | 0121 779 2571 | 07887745870 |  | Windows & Doors | M Turpin | 2024-06-18 | 8am to 2pm | CONFIRMED for 18/06
27 | Concorde Drive | Birmingham | B35 7EE | Mrs K Gillett | 07800773113 |  |  | Windows & Doors | M Turpin | 2024-06-18 | 8am to 2pm | CONFIRMED for 18/06
11 | Montrose Drive | Birmingham | B35 6DH | Ms R Carter | 07481614010 |  |  | Windows & Doors | M Turpin | 2024-06-18 | 8am to 2pm | 11/06 SMS text sent for 18/06. 13/06 SMS called N/A lttr sent 17/06 SMS tenant called to cancel
57E | Heyford Way | Birmingham | B35 6HZ | Miss L Scott | 7518481615 (Neice) | 079046 85 105 |  | Windows & Doors | M Turpin | 2024-06-18 | 8am to 2pm | 14/06 SMS Dominie arranged directly with tenant neice for 18/06, text sent also.
Pioneer Group - WEDNESDAY 19th JUNE - S Burgess
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
1 | Bond Drive | Birmingham | B35 7QQ | Mrs V Kerr |  | 07751977656 |  | Windows & Doors | S Burgess | 2024-06-19 | 8am to 12pm | CONFIRMED for 19/06
2 | Bond Drive | Birmingham | B35 7QQ | Miss K-M Goodwin |  | 07361881089 NIS | katiegoodwin1991@outlook.com | Windows & Doors | S Burgess | 2024-06-19 | 8am to 12pm | 05/06 SMS text sent for 19/06. 11/06 SMS called no. NIS lttr sent
3 | Bond Drive | Birmingham | B35 7QQ | Miss S P Mann | 01217491004 | 07526979351 NIS |  | Windows & Doors | S Burgess | 2024-06-19 | 8am to 12pm | 05/06 SMS text sent for 19/06. 11/06 SMS called no. NIS lttr sent
5 | Bond Drive | Birmingham | B35 7QQ | Mrs W Walsh |  | 07496 536972 | wendywalsh.cv@btinternet.com | Windows & Doors | S Burgess | 2024-06-19 | 11am to 3pm | 05/06 SMS text sent for 19/06. 11/06 SMS called N/A. 13/06 SMS called N/A lttr sent. 18/06 SMS tenant called to cancel, re-scheduled
6 | Bond Drive | Birmingham | B35 7QQ | Miss L Collingwood |  | 7541830345 | laura.collingwood93@hotmail.com | Windows & Doors | S Burgess | 2024-06-19 | 11am to 3pm | CONFIRMED for 19/06
7 | Bond Drive | Birmingham | B35 7QQ | Mr R H Nezad-Asl |  | 7383558099 | Majid.asll@yahoo.com | Windows & Doors | S Burgess | 2024-06-19 | 11am to 3pm | CONFIRMED for 19/06
Pioneer Group - WEDNESDAY 19th JUNE - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
5 | Concorde Drive | Birmingham | B35 7EE | Miss A S Rutter | 0121 408 0283 | 07534950731 | amandarutter01@outlook.com | Windows & Doors | M Turpin | 2024-06-19 | 8am to 2pm | CONFIRMED for 19/06. 18/06 SMS tenant called to cancel.
7 | Coltishall Close | Birmingham | B35 7EF | Miss M J Chantler |  | 07507013678 | mchantler@live.co.uk | Windows & Doors | M Turpin | 2024-06-19 | 8am to 2pm | Dominie arranged 19/06 direct with MT and Tenant.
31 | Concorde Drive | Birmingham | B35 7EE | Mrs R V Shakespeare |  | 07972147963 |  | Windows & Doors | M Turpin | 2024-06-19 | 8am to 2pm | CONFIRMED for 19/06
FLAT 1 Block 33 | Concorde Drive | Birmingham | B35 7EE | Miss SL Murphy |  | 07759039463 | mia-roseclarke11@outlook.com | Windows & Doors | M Turpin | 2024-06-19 | 8am to 2pm | 05/06 SMS text sent for 19/06. 11/06 SMS left voicemail. 13/06 SMS called N/A lttr sent
FLAT 2 Block 33 | Concorde Drive | Birmingham | B35 7EE | Mrs P Burden | 07729029722 |  |  | Windows & Doors | M Turpin | 2024-06-19 | 8am to 2pm | CONFIRMED for 19/06
FLAT 3 Block 33 | Concorde Drive | Birmingham | B35 7EE | Miss S Minhas |  | 07856434055 | minhasshahida@gmail.com | Windows & Doors | M Turpin | 2024-06-19 | 8am to 2pm | 05/06 SMS text sent for 19/06. 11/06 SMS called N/A. 13/06 SMS called N/A lttr sent
FLAT 4 Block 33 | Concorde Drive | Birmingham | B35 7EE | Mrs S Mohammad | 07479559511 |  | shahen452@hotmail.com | Windows & Doors | M Turpin | 2024-06-19 | 8am to 2pm | CONFIRMED for 19/06
FLAT 5 Block 33 | Concorde Drive | Birmingham | B35 7EE | Miss D Styche |  | 07512756223 NIS | dolciestyche@icloud.com | Windows & Doors | M Turpin | 2024-06-19 | 8am to 2pm | 05/06 SMS text sent for 19/06. 11/06 SMS called no. NIS lttr sent
FLAT 6 Block 33 | Concorde Drive | Birmingham | B35 7EE | Miss L Pettitt |  | 07982 174 217 |  | Windows & Doors | M Turpin | 2024-06-19 | 12pm to 2pm | CONFIRMED for 19/06 after 12noon pls
4 | De Havilland Drive | Birmingham | B35 7FP | Miss M Morahan | 0121 439 7477 | 07913206896 |  | Windows & Doors | M Turpin | 2024-06-19 | 8am to 2pm | 05/06 SMS text sent for 19/06. 11/06 SMS called N/A Lttr sent.
10 | De Havilland Drive | Birmingham | B35 7FP | Mrs J Shakespeare-Hines |  | 07960 520 021 |  | Windows & Doors | M Turpin | 2024-06-19 | 12pm to 2pm | CONFIRMED for 19/06 after 12pm pls
33 | Watton Green | Birmingham | B35 7JS | Miss L Craddock |  | 07548278817 | l_craddock1988@outlook.com | Windows & Doors | M Turpin | 2024-06-19 | 8am to 2pm | CONFIRMED for 19/06
29 | Lysander Way | Birmingham | B35 7JY | Mr M Younis | 07378866549 | 07378866549 | muhammadyoung.my@gmail.com | Windows & Doors | M Turpin | 2024-06-19 | 8am to 2pm | CONFIRMED for 19/06
Pioneer Group - THURSDAY 20th JUNE - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
32 | Montrose Drive | Birmingham | B35 6DH | Miss W Jesson | 01214489328 | 07960771767 | wendyjesson@hotmail.co.uk | Windows & Doors | M Turpin | 2024-06-20 | FIRST CALL | Confirmed for 20/06, first call pls
17 | Montrose Drive | Birmingham | B35 6DH | Mr N Proffitt |  | 07874 328 741 NIS |  | Windows & Doors | M Turpin | 2024-06-20 | 8am to 2pm | 11/06 text sent for 20/06. 13/06 SMS called no. NIS lttr sent
19 | Montrose Drive | Birmingham | B35 6DH | Mr MA Smith | 07908293857 | 07908 293 857 |  | Windows & Doors | M Turpin | 2024-06-20 | 8am to 2pm | 11/06 text sent for 20/06. 13/06 SMS called N/A. 14/06 SMS called N/A Lttr sent.
24 | Montrose Drive | Birmingham | B35 6DH | Miss L Gordon | 776 7658 | 07920 793 854 |  | Windows & Doors | M Turpin | 2024-06-20 | 8am to 2pm | CONFIRMED for 20/06
28 | Montrose Drive | Birmingham | B35 6DH | Mr J Belliss |  | 01217471760 | jimbellis@talktalk.net | Windows & Doors | M Turpin | 2024-06-20 | 8am to 2pm | 13/06 SMS called N/A. 14/06 SMS called N/A Lttr sent.
30 | Montrose Drive | Birmingham | B35 6DH | Mrs J Belliss | 0121 748 1898 | 07515 426 279 |  | Windows & Doors | M Turpin | 2024-06-20 | 8am to 2pm | CONFIRMED for 20/06
FLAT 1 Block 1 | Montrose Drive | Birmingham | B35 6DH | Miss A McLaren | 01217478782 |  |  | Windows & Doors | M Turpin | 2024-06-20 | 8am to 2pm | 13/06 SMS called N/A. 14/06 SMS called N/A Lttr sent.
FLAT 2 Block 1 | Montrose Drive | Birmingham | B35 6DH | Mrs B Mosson |  |  |  | Windows & Doors | M Turpin | 2024-06-20 | 8am to 2pm | 13/06 lttr sent
FLAT 4 Block 1 | Montrose Drive | Birmingham | B35 6DH | Mrs A J Preston |  | 07845185767 |  | Windows & Doors | M Turpin | 2024-06-20 | 8am to 2pm | 11/06 text sent for 20/06. 13/06 SMS called N/A. 14/06 SMS called N/A Lttr sent. 19/06 SMS tenant text back on 19/06 to cancel
FLAT 5 Block 1 | Montrose Drive | Birmingham | B35 6DH | Mr K Palmer |  | 07399584441 | kanepalmer@gmail.com | Windows & Doors | M Turpin | 2024-06-20 | 8am to 2pm | CONFIRMED for 20/06
FLAT 6 Block 1 | Montrose Drive | Birmingham | B35 6DH | Mr N A Ryan | 07581365287 | 07470079469 | Nicho_Ryan@hotmail.com | Windows & Doors | M Turpin | 2024-06-20 | 8am to 2pm | 11/06 text sent for 20/06. 13/06 SMS called N/A, lttr sent
58 | Watton Green | Birmingham | B35 7JP | Miss G Jones |  | 07942713340 |  | Windows & Doors | M Turpin | 2024-06-20 | 8am to 2pm | (*Emailed Dominie & client to assist as this date would be 3rd attempt.) 13/06 SMS lttr sent. Dom visited, they have asked this to be cancelled - Martin informed
Pioneer Group - MONDAY 24th JUNE - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
FLAT 36 | Cosford Crescent | Birmingham | B35 6QE | Mr K Nzumba | 7826497918 |  |  | Windows & Doors | M Turpin | 2024-06-24 | BETWEEN 8am - 9am | (Access via 30 & 46 Cosford Crescent)CONFIRMED between 8am - 9am
FLAT 34 | Cosford Crescent | Birmingham | B35 6QE | Ms S Phelan | 7468602288 |  |  | Windows & Doors | M Turpin | 2024-06-24 | 8am to 2pm | (Access via 30 & 46 Cosford Crescent) CONFIRMED by return text
46 | Cosford Crescent | Birmingham | B35 6QE | Miss N Altaf | 7546085463 |  | nafizah9@gmail.com | Windows & Doors | M Turpin | 2024-06-24 | 8am to 2pm | (Access via 30 & 46 Cosford Crescent) - CONFIRMED by return text
FLAT 44 | Cosford Crescent | Birmingham | B35 6QE | Miss C Hassall | 7821914116 |  | charlie.hassall@yahoo.com | Windows & Doors | M Turpin | 2024-06-24 | BETWEEN 12pm - 1pm | (Access via 30 & 46 Cosford Crescent) - CONFIRMED between 12pm - 1pm call 30min prior to arrival
30 | Cosford Crescent | Birmingham | B35 6QE | Miss F Bah | 7429320418 |  | fatoubah@hotmail.co.uk | Windows & Doors | M Turpin | 2024-06-24 | 8am to 2pm | (Access via 30 & 46 Cosford Crescent) - 13.06.24 SF sent text / NIS sent letter
FLAT 32 | Cosford Crescent | Birmingham | B35 6QE | Mr MJ Thornton | 7831304890 |  | Neilthornton1@outlook.com | Windows & Doors | M Turpin | 2024-06-24 | 8am to 2pm | (Access via 30 & 46 Cosford Crescent) - 13.06.24 SF sent text / LM sent letter
FLAT 38 | Cosford Crescent | Birmingham | B35 6QE | Mr C A Layton | 7784729094 |  |  | Windows & Doors | M Turpin | 2024-06-24 | 8am to 2pm | (Access via 30 & 46 Cosford Crescent) - 13.06.24 SF sent text / NIS sent letter
FLAT 40 | Cosford Crescent | Birmingham | B35 6QE | Mr C L Jones | 0121 7481010 | 7894708299 | c.jones99965@yahoo.com | Windows & Doors | M Turpin | 2024-06-24 | 8am to 2pm | (Access via 30 & 46 Cosford Crescent) - 13.06.24 SF sent text / NA & NIS sent letter
64 | Cosford Crescent | Birmingham | B35 6QE | Mr J Daly | 01217767133 |  | JD2ippy@hotmail.com | Windows & Doors | M Turpin | 2024-06-24 | 8am to 2pm | 13.06.24 SF Sent text / LM sent letter
FLAT 66 | Cosford Crescent | Birmingham | B35 6QE | Mr H Troman |  |  | harry_troman@yahoo.co.uk | Windows & Doors | M Turpin | 2024-06-24 | 8am to 2pm | 13.06.24 SF No contact number, email address undelivered, sent letter
1 | Cosford Crescent | Birmingham | B35 6QE | Miss F C Morris | 7926757397 |  | morrisfiona020@gmail.com | Windows & Doors | M Turpin | 2024-06-24 | 8am to 2pm | 19.06.24 SF LM, sent text & letter / 21.06.24 SF Tenant text and said NO to the survey on this day
Pioneer Group - TUESDAY 25th JUNE - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
2 | Cranwell Way | Birmingham | B35 6QH | Mr RA Mitchell | 07518496711 |  |  | Windows & Doors | M Turpin | 2024-06-25 | First Call | Access via 2 Cranwell & 381 Yatesbury. CONFIRMED for 25/06 first call pls
21 | Cranwell Way | Birmingham | B35 6QH | Miss P Davidson | 07920420656 |  | paulinepritchard@hotmail.co.uk | Windows & Doors | M Turpin | 2024-06-25 | 8am to 2pm | CONFIRMED for 25/06
1 | Cranwell Way | Birmingham | B35 6QH | Mr T Barnfield | 07967191780 |  |  | Windows & Doors | M Turpin | 2024-06-25 | 8am to 2pm | CONFIRMED for 25/06 AFTER 10AM.
3 | Cranwell Way | Birmingham | B35 6QH | Miss Z Carr | 7856402181 |  |  | Windows & Doors | M Turpin | 2024-06-25 | 8am to 2pm | 14/06 SMS text sent for 25/06. 18/6; AC rang and LM.
4 | Cranwell Way | Birmingham | B35 6QH | Mrs CS Gould | 07927317403 INCORRECT NUMBER. |  | woodgould@hotmail.co.uk | Windows & Doors | M Turpin | 2024-06-25 | 8am to 2pm | 14/06 SMS text sent for 25/06. 18/6 AC emailed.
5 | Cranwell Way | Birmingham | B35 6QH | Mr TJ Quinn | 07311 282 274 |  | tj.quinn@hotmail.co.uk | Windows & Doors | M Turpin | 2024-06-25 | 8am to 2pm | CONFIRMED for 25/06
FLAT 68 | Cosford Crescent | Birmingham | B35 6QE | Miss J Nicholls | 01217487100 | 07931111161 | jeannicholls78@gmail.com | Windows & Doors | M Turpin | 2024-06-25 | 8am to 2pm | CONFIRMED for 25/06
FLAT 70 | Cosford Crescent | Birmingham | B35 6QE | Miss D C Jacques | 0121 572 3707 | 07889917444 | davinajacques@hotmail.com | Windows & Doors | M Turpin | 2024-06-25 | 8am to 2pm | CONFIRMED for 25/06
FLAT 74 | Cosford Crescent | Birmingham | B35 6QE | Miss T Forrester | 07900023270 |  | tamaya.forrester@yahoo.co.uk | Windows & Doors | M Turpin | 2024-06-25 | 8am to 2pm | CONFIRMED for 25/06
FLAT 76 | Cosford Crescent | Birmingham | B35 6QE | Miss D Broderick | 07961 738077 | 07947630130 | dbroderick@live.co.uk | Windows & Doors | M Turpin | 2024-06-25 | 8am to 2pm | CONFIRMED for 25/06
FLAT 78 | Cosford Crescent | Birmingham | B35 6QE | Mr D Gayle | 01212412287 | 07858 988830 | darrengayle@ymail.com INCORRECT EMAIL ADDRESS. | Windows & Doors | M Turpin | 2024-06-25 | 8am to 2pm | 14/06 SMS text sent for 25/06. 18/6; AC rang LM and emailed BUT EMAIL INCORRECT AND BOUNCED BACK - letter sent
FLAT 8 | Northolt Drive | Birmingham | B35 6QX | Mr M Atterbury | 07538 213 549 |  |  | Windows & Doors | M Turpin | 2024-06-25 | 8am to 2pm | Dominie arranged survey date direct with tenant, this is 4th visit. PLEASE VISIT 1st
Pioneer Group - WEDNESDAY 26th JUNE - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
FLAT 373 | Yatesbury Avenue | Birmingham | B35 6QP | Mr GA Tucker | 07593596645 NIS |  | garytucker@yahoo.co.uk | Windows & Doors | M Turpin | 2024-06-26 | 8am to 2pm | Access via 2 Cranwell & 381 Yatesbury. 13/06 SMS text sent for 26/06. 19/06 SMS called no. NIS lttr sent
FLAT 377 | Yatesbury Avenue | Birmingham | B35 6QP | Mr R Riddell | 0121 747 5544 NIS |  |  | Windows & Doors | M Turpin | 2024-06-26 | 8am to 2pm | Access via 2 Cranwell & 381 Yatesbury. 19/06 SMS called no. NIS lttr sent
FLAT 379 | Yatesbury Avenue | Birmingham | B35 6QP | Mr K Woolley | 01217493031 | 07479550144 | kevin_woolley@hotmail.com | Windows & Doors | M Turpin | 2024-06-26 | 8am to 2pm | Access via 2 Cranwell & 381 Yatesbury. CONFIRMED for 26/06
381 | Yatesbury Avenue | Birmingham | B35 6QP | Mr G Wilkes | 07444 577 903 |  |  | Windows & Doors | M Turpin | 2024-06-26 | 8am to 2pm | Access via 2 Cranwell & 381 Yatesbury. CONFIRMED for 26/06
363 | Yatesbury Avenue | Birmingham | B35 6QP | Mr DJ Worswick | 01215376063 | 0788 5985151 | derekworswick@hotmail.co.uk | Windows & Doors | M Turpin | 2024-06-26 | 8am to 2pm | Access via 1 Cranwell & 363 Yatesbury. CONFIRMED for 26/06
FLAT 365 | Yatesbury Avenue | Birmingham | B35 6QP | Mr J Donnelly | 07394020678 |  | jamesdonnelly955@gmail.com | Windows & Doors | M Turpin | 2024-06-26 | 8am to 2pm | Access via 1 Cranwell & 363 Yatesbury. CONFIRMED for 26/06
FLAT 367 | Yatesbury Avenue | Birmingham | B35 6QP | Mr J Smith | 0121748 6274 |  |  | Windows & Doors | M Turpin | 2024-06-26 | 8am to 2pm | Access via 1 Cranwell & 363 Yatesbury. 19/06 SMS called N/A Lttr sent
FLAT 369 | Yatesbury Avenue | Birmingham | B35 6QP | Miss A Ward | 7946173023 |  |  | Windows & Doors | M Turpin | 2024-06-26 | 8am to 2pm | Access via 1 Cranwell & 363 Yatesbury. 13/06 SMS text sent for 26/06. 19/06 SMS left voicemail
FLAT 371 | Yatesbury Avenue | Birmingham | B35 6QP | Mr B Shingler | 07473 115 805 |  |  | Windows & Doors | M Turpin | 2024-06-26 | 8am to 2pm | Access via 1 Cranwell & 363 Yatesbury. 13/06 SMS text sent for 26/06. 19/06 SMS called N/A Lttr sent
FLAT 375 | Yatesbury Avenue | Birmingham | B35 6QP | Mrs J Evans | 07572601432 |  |  | Windows & Doors | M Turpin | 2024-06-26 | 8am to 2pm | Access via 2 Cranwell & 381 Yatesbury. 13/06 SMS text sent for 26/06. 19/06 SMS called N/A lttr sent
3 | Lysander Way | Birmingham | B35 7JY | Ms C Brown | 07486047902 |  | 00clare@gmail.com | Windows & Doors | M Turpin | 2024-06-26 | 8am to 2pm | 13/06 SMS text sent for 26/06. 19/06 SMS called N/A Lttr sent
5 | Lysander Way | Birmingham | B35 7JY | Miss L Sera | 07555587067 | 07769341460 |  | Windows & Doors | M Turpin | 2024-06-26 | 8am to 2pm | 13/06 SMS text sent for 26/06. 19/06 SMS called N/A Lttr sent
Pioneer Group - THURSDAY 27th JUNE - S Burgess
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
30 | Northolt Drive | Birmingham | B35 6QX | Mrs N Parry | 7707478425 |  | nickki250@live.co.uk | Windows & Doors | S Burgess | 2024-06-27 | 8am to 12pm | CONFIRMED for 27/06
8 | Bond Drive | Birmingham | B35 7QQ | Miss J Walsh | 07943 517 988 |  | jacqueline.07@hotmail.co.uk | Windows & Doors | S Burgess | 2024-06-27 | 8am to 12pm | CONFIRMED for 27/06
10 | Bond Drive | Birmingham | B35 7QQ | Miss J Wilkins | 07792145097 |  | jessy_mariewilkins@hotmail.co.uk | Windows & Doors | S Burgess | 2024-06-27 | 8am to 12pm | CONFIRMED for 27/06
12 | Bond Drive | Birmingham | B35 7QQ | Mr S Tonks | 07950800156 |  |  | Windows & Doors | S Burgess | 2024-06-27 | 11am to 3pm | CONFIRMED for 27/06
14 | Bond Drive | Birmingham | B35 7QQ | Miss R Key | 07708338388 | 07708 338 388 | becki.26@hotmail.co.uk | Windows & Doors | S Burgess | 2024-06-27 | 11am to 3pm | CONFIRMED for 27/06
16 | Bond Drive | Birmingham | B35 7QQ | Mr D Raven | 01217481669 |  | draven159@aol.com | Windows & Doors | S Burgess | 2024-06-27 | 11am to 3pm | CONFIRMED for 27/06
Pioneer Group - THURSDAY 27th JUNE - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
57D | Heyford Way | Birmingham | B35 6HZ |  | KEYSAFE 2404 |  |  | Windows & Doors | P Beahan | 2024-06-27 | 8am to 12pm | KEYSAFE 2404
FLAT 28 | Bovingdon Road | Birmingham | B35 6QD | Miss K Moxam | 7815443584 |  |  | Windows & Doors | P Beahan | 2024-06-27 | 8am to 12pm | CONFIRMED for 27/06
2 | Chigwell Close | Birmingham | B35 7HH | Miss L Lloyd | 0121 749 4567 |  |  | Windows & Doors | P Beahan | 2024-06-27 | 8am to 12pm | 19/6; AC rang but canot leave message, sent letter.
4 | Chigwell Close | Birmingham | B35 7HH | Mr S Doyle | 07735495850 |  | stevendoyle1984@hotmail.co.uk | Windows & Doors | P Beahan | 2024-06-27 | 11am to 3pm | 14/06 SMS text sent for 27/06. 19/6; AC rang but cannot leave message, emailed and sent letter.
6 | Chigwell Close | Birmingham | B35 7HH | Ms L Cahill | 0798550451 | 07720301863 | leanne79lou@gmail.com | Windows & Doors | P Beahan | 2024-06-27 | 11am to 3pm | CONFIRMED for 27/06
6 | Heyford Way | Birmingham | B35 6JH | Mr C O'Sullivan | 07505 338867 |  |  | Windows & Doors | P Beahan | 2024-06-27 | 11am to 3pm | CONFIRMED for 27/06
Pioneer Group - THURSDAY 27th JUNE - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
11 | Javelin Avenue | Birmingham | B35 7LH | Miss KL Macken | 07538863242 |  | katemacken@hotmail.co.uk | Windows & Doors | M Turpin | 2024-06-27 | 8am to 2pm | 14/06 SMS text sent for 27/06. 19/6; AC rang LM, emailed and sent letter.
20 | Javelin Avenue | Birmingham | B35 7LW | Miss CL Johnson | 07925824781 |  | cazpuddinghead@gmail.com | Windows & Doors | M Turpin | 2024-06-27 | 8am to 2pm | CONFIRMED for 27/06 - has requested Dominie doesn’t attend
34 | Javelin Avenue | Birmingham | B35 7LW | Miss T Gordon |  | 07583 234 987 | TionnaGordon@hotmail.com | Windows & Doors | M Turpin | 2024-06-27 | 8am to 2pm | CONFIRMED for 27/06
48 | Javelin Avenue | Birmingham | B35 7LW | Ms S Jones |  | 07389811707 | sarahjanejones1575@gmail.com | Windows & Doors | M Turpin | 2024-06-27 | 8am to 2pm | 14/06 SMS text sent for 27/06. 19/6; AC rang but phone switched off. Emailed and sent letter.
122 | Javelin Avenue | Birmingham | B35 7LW | Mrs J S Belgrove Coldicott |  | 07961 277 945 | jacquibelgrove70@icould.com INCORRECT EMAIL. | Windows & Doors | M Turpin | 2024-06-27 | 8am to 2pm | 14/06 SMS text sent for 27/06. 19/6; AC rang LM, emailed and sent letter. Email bounced back incorrect.
2 | Drem Croft | Birmingham | B35 7HW | Ms J Sheridan | 07752 744 103 |  | juliesheridan712@gmail.com | Windows & Doors | M Turpin | 2024-06-27 | 8am to 2pm | CONFIRMED for 27/06
4 | Drem Croft | Birmingham | B35 7HW | Mrs H Symonds | 07754122094 |  |  | Windows & Doors | M Turpin | 2024-07-01 | 8am to 2pm | CONFIRMED for 27/06
6 | Drem Croft | Birmingham | B35 7HW | Mr D W Henry |  | 07986 013017 |  | Windows & Doors | M Turpin | 2024-06-27 | 8am to 2pm | CONFIRMED for 27/06
8 | Drem Croft | Birmingham | B35 7HW | Mrs A Bricknell | 2506476 | 07982301728 incorrect number | no@email.com | Windows & Doors | M Turpin | 2024-06-27 | 8am to 2pm | 14/06 SMS text sent for 27/06. 19/6; AC sent letter. COMPLETED, Martin advised 27.06.24 over phone
9 | Montrose Drive | Birmingham | B35 6DH | Miss R Garrington |  | 07397 384 556 |  | Windows & Doors | M Turpin | 2024-06-27 | 8am to 2pm | 19/06 SMS text sent for 27/06 and AC rang and left message and sent letter.
FLAT 10 | Cosford Crescent | Birmingham | B35 6QE | Miss JM Lydon | 01217302262 | 07732885362 | jacquelinelydon@gmail.com | Windows & Doors | M Turpin | 2024-06-27 | 8am to 2pm | 19/06 SMS text sent for 27/06. 24/06 SMS tenant text back to decline appointment
Pioneer Group - FRIDAY 28th JUNE - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
15 | Chigwell Close | Birmingham | B35 7HG | Ms G Metcalfe |  | 07487723099 | Georginahumphries@icloud.com | Windows & Doors | P Beahan | 2024-06-28 | 8am to 12pm | 19/06 SMS text sent for 28/06. 19/6; AC emailed. / NO ACCESS RE-BOOKED FOR 17.07.24 | NO ACCESS
8 | Chigwell Close | Birmingham | B35 7HH | Mr N Kendall |  | 07539 309 821 |  | Windows & Doors | P Beahan | 2024-06-28 | 8am to 12pm | 19/06 SMS text sent for 28/06
10 | Chigwell Close | Birmingham | B35 7HH | Miss A Delaney |  |  | angeldelaney96@outlook.com | Windows & Doors | P Beahan | 2024-06-28 | 8am to 12pm | 19/06 SMS lttr sent. 19/6; AC emailed too.
16 | Chigwell Close | Birmingham | B35 7HH | Mrs V Cattell |  | 07547468483 | vgaunt61@gmail.com | Windows & Doors | P Beahan | 2024-06-28 | 11am to 3pm | CONFIRMED for 28/06
FLAT 48 | Mere Avenue | Birmingham | B35 6QT | Mr T Hillier |  | 07456 500 282 |  | Windows & Doors | P Beahan | 2024-06-28 | 11am to 3pm | CONFIRMED for 28/06 after 11am (do not move this appointment)
FLAT 64 | Mere Avenue | Birmingham | B35 6QT | Mr A Kimberley | 0121 749 7045 | 7867361210 | tonykimberley83@hotmail.com | Windows & Doors | P Beahan | 2024-06-28 | 11am to 3pm | CONFIRMED for 28/06
Pioneer Group - MONDAY 1st JULY - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
12 | Drem Croft | Birmingham | B35 7HW | Mrs A Hatton |  |  | LENHATTON@TALKTALK.NET INCORRECT EMAIL. | Windows & Doors | M Turpin | 2024-07-01 | 8am to 2pm | 19/06 SMS lttr sent. 19/6 AC emailed. EMAIL BOUNCED BACK INCORRECT.
14 | Drem Croft | Birmingham | B35 7HW | Mrs L Smith | 7730792476 |  |  | Windows & Doors | M Turpin | 2024-07-01 | 8am to 2pm | CONFIRMED for 01/07
16 | Drem Croft | Birmingham | B35 7HW | Mrs P Hughes |  |  |  | Windows & Doors | M Turpin | 2024-07-01 | 8am to 2pm | 19/06 SMS lttr sent
3 | Trident Boulevard | Birmingham | B35 7LZ | Miss M Lambert | 07369 280 512 |  |  | Windows & Doors | M Turpin | 2024-07-01 | 8am to 2pm | CONFIRMED for 01/07.
5 | Trident Boulevard | Birmingham | B35 7LZ | Mrs J Donovan | 07766513778 |  | joannedonovan00@outlook.com | Windows & Doors | M Turpin | 2024-07-01 | 8am to 2pm | CONFIRMED for 01/07.
6 | Trident Boulevard | Birmingham | B35 7LZ | Miss D Chapman | 07951623530 |  |  | Windows & Doors | M Turpin | 2024-07-01 | 8am to 2pm | CONFIRMED for 01/07
8 | Trident Boulevard | Birmingham | B35 7LZ | Mr D Yelland | 07956045548 |  | deanyelland@hotmail.com | Windows & Doors | M Turpin | 2024-07-01 | 8am to 2pm | CONFIRMED for 01/07.
10 | Trident Boulevard | Birmingham | B35 7LZ | Mrs G Poole | 07535 608 915 |  |  | Windows & Doors | M Turpin | 2024-07-01 | 8am to 2pm | 19/06 SMS text sent for 01/07. 21/6; AC letter sent.
12 | Trident Boulevard | Birmingham | B35 7LZ | Mr D Sztuk | 07498595415 |  | sztukdawid@gmail.com | Windows & Doors | M Turpin | 2024-07-01 | 10am to 2pm | CONFIRMED for 01/07 after 10am
74 | Watton Green | Birmingham | B35 7JP | Miss MC Dale | Contact P O'Brian 07931981160 | 07931981160 |  | Windows & Doors | M Turpin | 2024-07-01 | 8am to 2pm | 19/06 AC lttr sent
FLAT 72 | Cosford Crescent | Birmingham | B35 6QE | Mr MB Hatton | 07469170364 |  |  | Windows & Doors | M Turpin | 2024-07-01 | 8am to 2pm | NEEDS TWO WEEKS NOTICE - 21.06.24 SF called Mr Hatton, said to call back on Monday 24.06.24 and see if he has a got someone to house it on this day
Pioneer Group - TUESDAY 2nd JULY - S Burgess
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
18 | Bond Drive | Birmingham | B35 7QQ | Miss N Price | 0121 748 8664 | 07706 568103 |  | Windows & Doors | S Burgess | 2024-07-02 | 8am to 12pm | confirmed for 2/7
5 | Avro Way | Birmingham | B35 7NW | Mrs B Turner | 07972277089 |  |  | Windows & Doors | S Burgess | 2024-07-02 | 8am to 12pm | confirmed for 2/7
6 | Avro Way | Birmingham | B35 7NW | Mrs W Hickin | 01217302863 | 7771952042 |  | Windows & Doors | S Burgess | 2024-07-02 | 11am to 3pm | confirmed for 2/7
7 | Avro Way | Birmingham | B35 7NW | Mr RWJ Lynch | 07581 300 286 |  | rlynchmufc@aol.com | Windows & Doors | S Burgess | 2024-07-02 | 11am to 3pm | confirmed for 2/7
8 | Avro Way | Birmingham | B35 7NW | Mrs L Payne | 07724 237324 |  |  | Windows & Doors | S Burgess | 2024-07-02 | 11am to 3pm | confirmed for 2/7
16 | Sopwith Croft | Birmingham | B35 7QH | Mr D Kingston | 07523 375509 |  |  | Windows & Doors | S Burgess | 2024-07-02 | 11am to 3pm | CONFIRMED for 2/7. 02/07 SMS surveyor advised not have time to attend this address today, called and advised the tenant.
Pioneer Group - TUESDAY 2nd JULY - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
22 | Trident Boulevard | Birmingham | B35 7LZ | Miss J Mytton |  | 07801 887 912 | jaynemytton@talktalk.net | Windows & Doors | M Turpin | 2024-07-02 | 8am to 9pm | CONFIRMED for 2/7 FIRST CALL
14 | Trident Boulevard | Birmingham | B35 7LZ | Mr R Beech |  |  |  | Windows & Doors | M Turpin | 2024-07-02 | 8am to 2pm | 19/6; AC sent letter.
15 | Trident Boulevard | Birmingham | B35 7LZ | Miss S Lynch | 7800777467 |  | shazlynch1971@hotmail.com | Windows & Doors | M Turpin | 2024-07-02 | 8am to 2pm | CONFIRMED for 2/7
16 | Trident Boulevard | Birmingham | B35 7LZ | Miss L Hanson | 01217493832 |  |  | Windows & Doors | M Turpin | 2024-07-02 | 8am to 2pm | 19/6; AC sent letter.
18 | Trident Boulevard | Birmingham | B35 7LZ | Mrs T High |  |  |  | Windows & Doors | M Turpin | 2024-07-02 | 8am to 2pm | 19/6; AC sent letter.
19 | Trident Boulevard | Birmingham | B35 7LZ | Miss AW Isaac | 07956530229 |  |  | Windows & Doors | M Turpin | 2024-07-02 | 8am to 2pm | 19/6; AC text for 2/7. 21/6; AC rang LM AND SENT LETTER
20 | Trident Boulevard | Birmingham | B35 7LZ | Miss M G Bourne | 07725346049 | 07897582846 | moniquebourne321@gmail.com | Windows & Doors | M Turpin | 2024-07-02 | 8am to 2pm | 19/6; AC text for 2/7 and emailed. 21/6; AC rang LM AND SENT LETTER.
21 | Trident Boulevard | Birmingham | B35 7LZ | Mr K Mohammed |  | 07411 980335 | alekozaifamily@yahoo.com | Windows & Doors | M Turpin | 2024-07-02 | 8am to 2pm | 19/6; AC text for 2/7 and emailed. 21/6; AC rang LM AND SENT LETTER
23 | Trident Boulevard | Birmingham | B35 7LZ | VOID (NEED KEY SAFE) | Keysafe 2405 |  |  | Windows & Doors | M Turpin | 2024-07-02 | 8am to 2pm | VOID
24 | Trident Boulevard | Birmingham | B35 7LZ | Miss K Collin |  | 07443 461 580 | kellycollin625@yahoo.co.uk | Windows & Doors | M Turpin | 2024-07-02 | after 8.30am to 2pm | CONFIRMED for 2/7
50 | Watton Green | Birmingham | B35 7JP | Miss T Arlow | 07453 414 148 |  |  | Windows & Doors | M Turpin | 2024-07-02 | 8am to 2pm | CONFIRMED for 2/7
Pioneer Group - WEDNESDAY 3rd JULY - S Burgess
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
FLAT 6 Block 16 | Bicester Square | Birmingham | B35 6HR | Miss KG Walker | 7387314944 | 07557783791 |  | Windows & Doors | S Burgess | 2024-07-03 | BEFORE 11.30am | CONFIRMED FOR 3/7.
14 | Avro Way | Birmingham | B35 7NW | Mr L Caulfield |  |  |  | Windows & Doors | S Burgess | 2024-07-03 | 8am to 12pm | 19/6; AC sent letter.
16 | Avro Way | Birmingham | B35 7NW | Mr J Brennan | 0121 748 2482 |  |  | Windows & Doors | S Burgess | 2024-07-03 | 8am to 12pm | 19/6; AC rang NA, sent letter.
18 | Avro Way | Birmingham | B35 7NW | Mrs M Mackenzie | 01217485666 | 07955 882689 |  | Windows & Doors | S Burgess | 2024-07-03 | 8am to 12pm | CONFIRMED FOR 3/7.
20 | Avro Way | Birmingham | B35 7NW | Mrs S Pearson |  | 07957991918 incorrect number |  | Windows & Doors | S Burgess | 2024-07-03 | 11am to 3pm | 19/6; AC text for 3/7. 21/6; RANG BUT WRONG NUMBER, SENT LETTER.
17 | Avro Way | Birmingham | B35 7NW | Mr M Fone | 07488 2777 74 |  |  | Windows & Doors | S Burgess | 2024-07-03 | 11am to 3pm | CONFIRMED FOR 3/7. epileptic, asthmatic, arthritis and blood cancer
Pioneer Group - THURSDAY 4th JULY - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
DO NOT BOOK ANY SURVEYS FOR THIS DAY DA REQ ON 18/06 TO BE KEPT CLEAR SO PB CAN CATCH UP
Pioneer Group - FRIDAY 5th JULY - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
10 | Chigwell Close | Birmingham | B35 7HH | Miss A Delaney |  |  | angeldelaney96@outlook.com | Windows & Doors | P Beahan | 2024-07-05 | 8am to 12pm | CONFIRMED FOR 5/7
20 | Chigwell Close | Birmingham | B35 7HH | Mrs S Webb | 0121 649 3211 |  |  | Windows & Doors | P Beahan | 2024-07-05 | 8am to 12pm | 19/6; AC sent letter. 21/6; AC rang NA.
27 | Chigwell Close | Birmingham | B35 7HG | Miss K Finney | 07812996853 |  |  | Windows & Doors | P Beahan | 2024-07-05 | 8am to 12pm | CONFIRMED FOR 5/7
55 | Chigwell Close | Birmingham | B35 7HG | Mr M Hughes | 07368627234 |  |  | Windows & Doors | P Beahan | 2024-07-05 | 8am to 12pm | CONFIRMED FOR 5/7
61 | Chigwell Close | Birmingham | B35 7HG | Mrs D Machin | 07860 112 206 |  |  | Windows & Doors | P Beahan | 2024-07-05 | 11am to 3pm | CONFIRMED FOR 5/7
63 | Chigwell Close | Birmingham | B35 7HG | Mrs D V Heath |  |  |  | Windows & Doors | P Beahan | 2024-07-05 | 11am to 3pm | 19/6; AC sent letter.
6 | Hawker Drive | Birmingham | B35 7EG | Mrs T Hobbis | 07823471922 |  |  | Windows & Doors | P Beahan | 2024-07-05 | 11am to 3pm | CONFIRMED FOR 5/7
Pioneer Group - TUESDAY 9th JULY - S Burgess
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
3 | Pioneer Way | Birmingham | B35 7LA | Mrs E Sturdy | 07985 494 722 | 07985 494 722 |  | Windows & Doors | S Burgess | 2024-07-09 | 8am to 12pm | CONFIRMED for 09/07
FLAT 4 | Pioneer Way | Birmingham | B35 7LA | Mrs S Weller | 07859 419 990 |  |  | Windows & Doors | S Burgess | 2024-07-09 | 8am to 12pm | 24/06 SMS text sent for 09/07. 25/06 SMS left voicemail. 26/6; AC sent letter.
5 | Pioneer Way | Birmingham | B35 7LA | Ms H F Day | 07375 064068 |  | feathers0201@live.co.uk | Windows & Doors | S Burgess | 2024-07-09 | 8am to 12pm | CONFIRMED for 09/07
FLAT 6 | Pioneer Way | Birmingham | B35 7LA | Mr J Barrett | 0121 748 7212 |  |  | Windows & Doors | S Burgess | 2024-07-09 | 11am to 3pm | CONFIRMED for 09/07
7 | Pioneer Way | Birmingham | B35 7LA | Miss L Swann | 07902696139 |  | leanneswann@hotmail.co.uk | Windows & Doors | S Burgess | 2024-07-09 | 11am to 3pm | 24/06 SMS text sent for 09/07. 25/06 SMS called N/A. 26/6; AC sent letter.
5 | Bond Drive | Birmingham | B35 7QQ | Mrs W Walsh | 07496 536972 |  | wendywalsh.cv@btinternet.com | Windows & Doors | S Burgess | 2024-07-09 | 11am to 3pm | CONFIRMED for 09/07. 04/07 SMS tenant Cancelled
Pioneer Group - TUESDAY 9th JULY - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
25 | Trident Boulevard | Birmingham | B35 7LZ | Mr M M Jones | 07917 809 148 |  |  | Windows & Doors | M Turpin | 2024-07-09 | 8am to 2pm | CONFIRMED for 09/07
27 | Trident Boulevard | Birmingham | B35 7LZ | Miss M O'Coy | 07947 378488 |  | Mazwaz2010@yahoo.com | Windows & Doors | M Turpin | 2024-07-09 | 8am to 2pm | CONFIRMED for 09/07
28 | Trident Boulevard | Birmingham | B35 7LZ | Mrs K Parsons | 07856412925 NIS | 07411372543 |  | Windows & Doors | M Turpin | 2024-07-09 | 8am to 2pm | 24/06 SMS text sent for 09/07. 25/06 SMS called NIS. 26/6; AC sent letter.
29 | Trident Boulevard | Birmingham | B35 7LZ | Mr D Jones |  |  |  | Windows & Doors | M Turpin | 2024-07-09 | 8am to 2pm | 24/06 SMS lttr sent for 09/07
FLAT 127B | Farnborough Road | Birmingham | B35 7LQ | Miss S Rutter | 07411 016352 |  | sarahrutter1@live.co.uk | Windows & Doors | M Turpin | 2024-07-09 | 8am to 2pm | CONFIRMED for 09/07
FLAT 127C | Farnborough Road | Birmingham | B35 7LQ | Mr DM Hughes | 07376064601 | 07932903425 |  | Windows & Doors | M Turpin | 2024-07-09 | 8am to 2pm | 24/06 SMS text sent for 09/07. 25/06 SMS called N/A. 26/6; AC sent letter.
FLAT 127D | Farnborough Road | Birmingham | B35 7LQ | Mrs C Singleton | 07425 262 715 |  |  | Windows & Doors | M Turpin | 2024-07-09 | 8am to 2pm | CONFIRMED for 09/07
12 | Merlin Close | Birmingham | B35 7JW | Miss J Rudd | 07444 639584 |  |  | Windows & Doors | M Turpin | 2024-07-09 | 8am to 2pm | CONFIRMED for 09/07
8 | De Havilland Drive | Birmingham | B35 7FP | Mr S Plant | 01217492697 | 07815 443 140 |  | Windows & Doors | M Turpin | 2024-07-09 | 8am to 2pm | CONFIRMED for 09/07
10 | Drem Croft | Birmingham | B35 7HW | Mr T Finn | 7552168904 |  |  | Windows & Doors | M Turpin | 2024-07-09 | 8am to 2pm | CONFIRMED for 09/07
5 | Concorde Drive | Birmingham | B35 7EE | Miss A S Rutter | 0121 408 0283 | 07534950731 |  | Windows & Doors | M Turpin | 2024-07-09 | 8am to 2pm | 01/07 SMS text sent for 09/07
Pioneer Group - WEDNESDAY 10th JULY - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
1 | Hawker Drive | Birmingham | B35 7DX | Miss K Hinett | 0790 197 5798 | 0121 749 5278 |  | Windows & Doors | P Beahan | 2024-07-10 | 8am to 12pm | 24/06 SMS text sent for 10/07. 25/06 SMS called and tenant cut off call. 26/6; AC sent letter.
FLAT 2A | Hawker Drive | Birmingham | B35 7EG | Mr C Moran | 07867922078 |  | conormoran93@putlook.com | Windows & Doors | P Beahan | 2024-07-10 | 9am to 12pm | CONFIRMED for 10/07 after 10am
FLAT 2B | Hawker Drive | Birmingham | B35 7EG | Mrs J Wheeler | 01217470368 | 07828 664416 | joanbw@yahoo.com | Windows & Doors | P Beahan | 2024-07-10 | 8am to 12pm | 24/06 SMS text sent for 10/07. 25/06 SMS called N/A. 26/6; AC sent letter.
4A | Hawker Drive | Birmingham | B35 7EG | Miss C Davis | 07794540365 |  | claire_davis3@hotmail.co.uk | Windows & Doors | P Beahan | 2024-07-10 | 11am to 3pm | CONFIRMED for 10/07
18 | Bovingdon Road | Birmingham | B35 6QD | Miss C Chambers | 07779 003 594 |  | corrine.chambers@btinternet.com | Windows & Doors | P Beahan | 2024-07-10 | 11am to 3pm | CONFIRMED for 10/07
57 | Chigwell Close | Birmingham | B35 7HG | Miss D Taylor |  | 07508 198 215 |  | Windows & Doors | P Beahan | 2024-07-10 | 11am to 3pm | CONFIRMED for 10/07
Pioneer Group - WEDNESDAY 10th JULY - S Burgess
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
FLAT 8 | Pioneer Way | Birmingham | B35 7LA | Miss B Tregillies | 07759302013 |  | biancatregillies1993@gmail.com | Windows & Doors | S Burgess | 2024-07-10 | 8am to 12pm | 24/06 SMS text sent for 10/07. 25/06 SMS called N/A. 26/6; AC sent letter.
FLAT 10 | Pioneer Way | Birmingham | B35 7LA | Mr S Walker | 07737940069 |  |  | Windows & Doors | S Burgess | 2024-07-10 | 8am to 12pm | 24/06 SMS text sent for 10/07. 25/06 SMS called N/A. 26/6; AC sent letter.
12 | Pioneer Way | Birmingham | B35 7LA | Mrs J M Whitehouse | 01214082382 NIS |  |  | Windows & Doors | S Burgess | 2024-07-10 | 8am to 12pm | 24/06 SMS called no NIS, lttr sent
14 | Pioneer Way | Birmingham | B35 7LA | Miss K Caines | 07429788939 |  |  | Windows & Doors | S Burgess | 2024-07-10 | 11am to 3pm | CONFIRMED for 10/07
16 | Pioneer Way | Birmingham | B35 7LA | Miss C Griffiths | 07940 330004 |  |  | Windows & Doors | S Burgess | 2024-07-10 | 11am to 3pm | 24/06 SMS text sent for 10/07. 25/06 SMS called N/A. 26/6; AC sent letter. 09/07 tenant cancelled
18 | Pioneer Way | Birmingham | B35 7LA | Miss C Proudfoot | 07923 963 048 |  | caronheath098@icloud.com | Windows & Doors | S Burgess | 2024-07-10 | 11am to 3pm | CONFIRMED for 10/07
Pioneer Group - WEDNESDAY 10th JULY - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
FLAT 129F | Farnborough Road | Birmingham | B35 7LQ | Mr D Lewis |  | 07877843613 |  | Windows & Doors | M Turpin | 2024-07-10 | First Call | CONFIRMED for 10/07 first Call pls
FLAT 127A | Farnborough Road | Birmingham | B35 7LQ | Miss S Horton | 07920013224 |  | symonehorton@yahoo.co.uk | Windows & Doors | M Turpin | 2024-07-10 | 8am to 2pm | 28/06 AC rang and LM also text sent for 10/07 and email.
FLAT 129A | Farnborough Road | Birmingham | B35 7LQ | Miss S Perry | 07947665556 |  | suzetteperry101@gmail.com | Windows & Doors | M Turpin | 2024-07-10 | 8am to 2pm | 24/06 SMS text sent for 10/07. 25/06 SMS called N/A. 26/6; AC sent letter.
FLAT 129B | Farnborough Road | Birmingham | B35 7LQ | Miss G Hewston | 01952217000 NIS |  |  | Windows & Doors | M Turpin | 2024-07-10 | 8am to 2pm | 24/06 SMS called no. NIS lttr sent
FLAT 129C | Farnborough Road | Birmingham | B35 7LQ | Miss D Brown | 07990486128 |  | dinneka901@outlook.com | Windows & Doors | M Turpin | 2024-07-10 | 8am to 2pm | 24/06 SMS text sent for 10/07. 25/06 SMS called N/A. 26/6; AC sent letter.
FLAT 129D | Farnborough Road | Birmingham | B35 7LQ | Miss C Morris | 01217767045 NIS |  | cat_and_corey23@outlook.com | Windows & Doors | M Turpin | 2024-07-10 | 8am to 2pm | 24/06 SMS called no. NIS, lttr sent. 05/07 SMS tenant cancelled.
FLAT 129E | Farnborough Road | Birmingham | B35 7LQ | Mr R Edwards | 01217491989 | 07376092266 |  | Windows & Doors | M Turpin | 2024-07-10 | 8am to 2pm | 24/06 SMS text sent for 10/07. 25/06 SMS called N/A. 26/6; AC sent letter.
FLAT 131A | Farnborough Road | Birmingham | B35 7LQ | Mrs A C Cattell | 07751976640 |  | AnitaCattell@icloud.com | Windows & Doors | M Turpin | 2024-07-10 | 8am to 2pm | CONFIRMED for 10/07
FLAT 131B | Farnborough Road | Birmingham | B35 7LQ | Ms M Kerr | 07861385674 |  | antonia-adams@hotmail.co.uk | Windows & Doors | M Turpin | 2024-07-10 | 8am to 2pm | CONFIRMED for 10/07
FLAT 131C | Farnborough Road | Birmingham | B35 7LQ | Mr D Capper | 07944 611 428 |  |  | Windows & Doors | M Turpin | 2024-07-10 | 8am to 2pm | 24/06 SMS text sent for 10/07. 26/6; AC sent letter.
FLAT 337 | Yatesbury Avenue | Birmingham | B35 6QP | Mr G Kinsella | 07984479727 |  |  | Windows & Doors | M Turpin | 2024-07-10 | 8am to 2pm | 20/06 SMS Dominie CONFIRMED this date 10/07 directly with the tenant.24/06 SMS text sent for 10/07. CONFIRMED
Pioneer Group - THURSDAY 11th JULY - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
22 | Mere Avenue | Birmingham | B35 6QT | Mrs F Dainty | 07947 56 59 58 |  | Francescaleigh2010@hotmail.co.uk | Windows & Doors | P Beahan | 2024-07-11 | 8am to 12pm | CONFIRMED for 11/07
FLAT 60 | Mere Avenue | Birmingham | B35 6QT | Mr P J McCallion | 7751066503 |  | patrickmccallion8@gmail.com | Windows & Doors | P Beahan | 2024-07-11 | 8am to 12pm | CONFIRMED for 11/07 - 11.07.24 SF Tenant called to cancel, re-book
FLAT 68 | Mere Avenue | Birmingham | B35 6QT | Mr S Gardiner | 07305 947 116 | 07873894184 | mya1997@live.co.uk | Windows & Doors | P Beahan | 2024-07-11 | 8am to 12pm | CONFIRMED for 11/07
14 | Bovingdon Road | Birmingham | B35 6QD | Miss T Grinham | 07368828517 |  |  | Windows & Doors | P Beahan | 2024-07-11 | 11am to 3pm | CONFIRMED for 11/07
16 | Bovingdon Road | Birmingham | B35 6QD | Miss J-J Mckean | 7512032487 |  | pwrincessjay@outlook.com | Windows & Doors | P Beahan | 2024-07-11 | 11am to 3pm | CONFIRMED for 11/07
FLAT 24 | Bovingdon Road | Birmingham | B35 6QD | Mr S Abhar | 07462086448 |  | sarooshabhar1@gmail.com | Windows & Doors | P Beahan | 2024-07-11 | 11am to 3pm | 24/06 SMS text sent for 11/07. 25/06 SMS called N/A. 26/6; AC sent letter.
Pioneer Group - THURSDAY 11th JULY - S Burgess
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
4 | Sopwith Croft | Birmingham | B35 7QH | Mr AG Butler | 07545 965196 |  |  | Windows & Doors | S Burgess | 2024-07-11 | 8am to 12pm | CONFIRMED for 11/07
6 | Sopwith Croft | Birmingham | B35 7QH | Miss C Turner | 07811587683 |  | chriscutler92@live.com | Windows & Doors | S Burgess | 2024-07-11 | 8am to 12pm | 24/06 SMS text sent for 11/07. 25/06 SMS called N/A. 26/6; AC sent letter.
8 | Sopwith Croft | Birmingham | B35 7QH | Mrs J O'Hare | 01217475102 | 07411 914 261 |  | Windows & Doors | S Burgess | 2024-07-11 | 8am to 12pm | 24/06 SMS text sent for 11/07. 25/06 SMS left voicemail. 26/6; AC sent letter.
10 | Sopwith Croft | Birmingham | B35 7QH | Mrs J Pearce | 01217767619 | 07861451530 | leaaubreyjack@aol.com | Windows & Doors | S Burgess | 2024-07-11 | 11am to 3pm | CONFIRMED for 11/07
14 | Sopwith Croft | Birmingham | B35 7QH | Mrs I Rigby | 07380 369 666 |  |  | Windows & Doors | S Burgess | 2024-07-11 | 11am to 3pm | CONFIRMED for 11/07
7 | Bond Drive | Birmingham | B35 7QQ | Mr R H Nezad-Asl | 07383558099 |  | Majid.asll@yahoo.com | Windows & Doors | S Burgess | 2024-07-11 | 11am to 3pm | CONFIRMED for 11/07
Pioneer Group - THURSDAY 11th JULY - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
FLAT 131D | Farnborough Road | Birmingham | B35 7LQ | Mr L Morley | 0121 747 0291 |  |  | Windows & Doors | M Turpin | 2024-07-11 | 8am to 2pm | CONFIRMED for 11/07 Lttr sent on tenants req
FLAT 131E | Farnborough Road | Birmingham | B35 7LQ | Miss K Mckenzie | 07380855627 NIS | 07359526982 | keishaadelle@icloud.com | Windows & Doors | M Turpin | 2024-07-11 | 8am to 2pm | 24/06 SMS text sent for 11/07. 26/6; AC sent letter.
FLAT 131F | Farnborough Road | Birmingham | B35 7LQ | Mr I Rolland |  |  |  | Windows & Doors | M Turpin | 2024-07-11 | 8am to 2pm | 24/06 SMS lttr sent
FLAT 131G | Farnborough Road | Birmingham | B35 7LQ | Miss G Grant | 07929020526 |  | maxgrant330@gmail.com | Windows & Doors | M Turpin | 2024-07-11 | 8am to 2pm | CONFIRMED for 11/07
FLAT 133A | Farnborough Road | Birmingham | B35 7LQ | Miss J Walsh | 07580985191 |  | jennywalsh77@yahoo.co.uk | Windows & Doors | M Turpin | 2024-07-11 | 8am to 2pm | 24/06 SMS text sent for 11/07. 25/06 SMS left voicemail. 26/6; AC sent letter.
FLAT 133B | Farnborough Road | Birmingham | B35 7LQ | Mrs C Kenny | 0121 448 4649 | 07946073502 |  | Windows & Doors | M Turpin | 2024-07-11 | 8am to 2pm | CONFIRMED for 11/07
FLAT 133D | Farnborough Road | Birmingham | B35 7LQ | Miss J Bassett | 07368 423 999 |  |  | Windows & Doors | M Turpin | 2024-07-11 | 8am to 2pm | 24/06 SMS text sent for 11/07. 25/06 SMS called N/A. 26/6; AC sent letter.
FLAT 127E | Farnborough Road | Birmingham | B35 7LQ | Miss G E Kiely | 0121 747 8606 | 074110 16352 |  | Windows & Doors | M Turpin | 2024-07-11 | After 9am | 24/06 SMS text sent for 11/07. 25/06 SMS called N/A. 26/6; AC sent letter.
FLAT 331 | Yatesbury Avenue | Birmingham | B35 6QP | Mr W Hall | 07399591051 |  |  | Windows & Doors | M Turpin | 2024-07-11 | 8am to 2pm | 24/06 SMS text sent for 11/07. 25/06 SMS called N/A. 26/6; AC sent letter.
FLAT 335 | Yatesbury Avenue | Birmingham | B35 6QP | Mr RJ Sharpe | 07572975677 |  |  | Windows & Doors | M Turpin | 2024-07-11 | 8am to 2pm | Tenant confirmed this date direct with Dominie for 11/07
7 | Coltishall Close | Birmingham | B35 7EF | Miss M J Chantler | 07507013678 |  | mchantler@live.co.uk | Windows & Doors | M Turpin | 2024-07-11 | 8am to 2pm | Dominie arranging/speaking to tenant over this one, ref to her as tenant would not stop shouting
FLAT 42 | Cosford Crescent | Birmingham | B35 6QE | Mr W Doyle | 7858206323 |  |  | Windows & Doors | M Turpin | 2024-07-11 | 8am to 2pm | (Access via 30 & 46 Cosford Crescent). 24/06 SMS text sent for 11/07. 25/06 SMS called N/A. 26/6; AC sent letter.
7 | Trident Boulevard | Birmingham | B35 7LZ | Mrs K L Baker | 07943729362 |  | Kelly.Sinclair1@btinternet.com INCORRECT EMAIL. | Windows & Doors | M Turpin | 2024-07-11 | 8am to 2pm | CONFIRMED for 11/07
Pioneer Group - TUESDAY 16TH JULY - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
FLAT 143A | Farnborough Road | Birmingham | B35 7LQ | Mrs S Williams | 7594515544 |  | sowilliams23@gmail.com | Windows & Doors | M Turpin | 2024-07-16 | 8am to 2pm | CONFIRMED for 16/07
FLAT 143B | Farnborough Road | Birmingham | B35 7LQ | Miss E Ashmore | 7958626988 | 7487792466 | elleashmore@yahoo.com | Windows & Doors | M Turpin | 2024-07-16 | 8am to 2pm | 04.07.24 SF Sent text message. 05/07 SMS left voicemail. 08/07 SMS called N/A lttr sent
FLAT 143C | Farnborough Road | Birmingham | B35 7LQ | Miss C Ricketts | 7811487664 |  | charnelle1@live.co.uk | Windows & Doors | M Turpin | 2024-07-16 | 8am to 2pm | CONFIRMED for 16/07
FLAT 143D | Farnborough Road | Birmingham | B35 7LQ | Miss S Mason |  |  |  | Windows & Doors | M Turpin | 2024-07-16 | 8am to 2pm | 04.07.24 SF Sent letter
FLAT 143E | Farnborough Road | Birmingham | B35 7LQ | Mr D McEwen | 7896744634 | 7802263271 |  | Windows & Doors | M Turpin | 2024-07-16 | 8am to 2pm | 04.07.24 SF Sent text message. 08/07 SMS called N/A lttr sent
FLAT 143F | Farnborough Road | Birmingham | B35 7LQ | Mr N Smith |  |  | nigel_smith2007@yahoo.co.uk | Windows & Doors | M Turpin | 2024-07-16 | 8am to 2pm | 04.07.24 SF Sent letter & email
FLAT 141A | Farnborough Road | Birmingham | B35 7LQ | Miss M J Ancill | 7488361831 |  |  | Windows & Doors | M Turpin | 2024-07-16 | 8am to 2pm | CONFIRMED for 16/07
FLAT 141B | Farnborough Road | Birmingham | B35 7LQ | Miss S Hinds | 7542648635 |  | princessrylee17@outlook.com | Windows & Doors | M Turpin | 2024-07-16 | 8am to 2pm | CONFIRMED for 16/07
FLAT 141D | Farnborough Road | Birmingham | B35 7LQ | Mr K Sullivan | 7795551880 |  |  | Windows & Doors | M Turpin | 2024-07-16 | 8am to 2pm | 04.07.24 SF Sent text message. 10/07 SMS called N/A, lttr sent
FLAT 141E | Farnborough Road | Birmingham | B35 7LQ | Mr A Wornast | 7907914379 NIS |  |  | Windows & Doors | M Turpin | 2024-07-16 | 8am to 2pm | 04.07.24 SF Sent text message. 10/07 SMS called NIS, lttr sent
FLAT 1 Block 33 | Concorde Drive | Birmingham | B35 7EE | Miss SL Murphy | 7759039463 |  |  | Windows & Doors | M Turpin | 2024-07-16 | 8am to 2pm | 04.07.24 SF Sent text message. 10/07 SMS left voicemail. 11/07 SMS called N/A lttr sent
FLAT 3 Block 33 | Concorde Drive | Birmingham | B35 7EE | Miss S Minhas | 7856434055 |  |  | Windows & Doors | M Turpin | 2024-07-16 | 8am to 2pm | 04.07.24 SF Sent text message. 10/07 SMS N/A lttr sent
8 | Montrose Drive | Birmingham | B35 6DH | Mr D Loveridge | 07761915204 | 07761915204 |  | Windows & Doors | M Turpin | 2024-07-16 | 8am to 2pm | TLO (Dom) arranging this date direct with the tenant.
Pioneer Group - WEDNESDAY 17TH JULY - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
FLAT 135C | Farnborough Road | Birmingham | B35 7LQ | Ms M Stawna | 7904642860 |  | magdalenastawna7@gmail.com | Windows & Doors | M Turpin | 2024-07-17 | FIRST CALL | CONFIRMED, First call pls
FLAT 141F | Farnborough Road | Birmingham | B35 7LQ | Ms A A Taylor | 01212940421 |  | aggyfox@hotmail.co.uk | Windows & Doors | M Turpin | 2024-07-17 | 8am to 2pm | CONFIRMED for 17.07.24
FLAT 133E | Farnborough Road | Birmingham | B35 7LQ | Mr D Phillips | 7902773605 |  |  | Windows & Doors | M Turpin | 2024-07-17 | 8am to 2pm | CONFIRMED for 17.07.24
FLAT 133F | Farnborough Road | Birmingham | B35 7LQ | Miss Z Garratty | 7834836241 |  |  | Windows & Doors | M Turpin | 2024-07-17 | 8am to 2pm | CONFIRMED for 17.07.24
FLAT 133G | Farnborough Road | Birmingham | B35 7LQ | Miss L Capper | 7704560976 |  |  | Windows & Doors | M Turpin | 2024-07-17 | 8am to 2pm | CONFIRMED for 17.07.24
FLAT 135A | Farnborough Road | Birmingham | B35 7LQ | Mr S Rahman | 7402352462 |  | sid8810@outlook.com | Windows & Doors | M Turpin | 2024-07-17 | 8am to 2pm | CONFIRMED for 17.07.24
FLAT 135B | Farnborough Road | Birmingham | B35 7LQ | Mrs C Fletcher | 7954896701 | 7389700395 |  | Windows & Doors | M Turpin | 2024-07-17 | 8am to 2pm | CONFIRMED for 17.07.24
FLAT 135D | Farnborough Road | Birmingham | B35 7LQ | Miss S Martin | 07888 296 587 NIS | 07517 015137 | Sandra_26@live.co.uk | Windows & Doors | M Turpin | 2024-07-17 | 8am to 2pm | 03.07.24 SF Sent text message. 04/07 SMS called No ending 587 is NIS. 10/07 SMS called N/A lttr sent
FLAT 135E | Farnborough Road | Birmingham | B35 7LQ | Miss D Kirby | 7519452670 |  | dparrish520@gmail.com | Windows & Doors | M Turpin | 2024-07-17 | 8am to 2pm | CONFIRMED for 17.07.24
FLAT 135F | Farnborough Road | Birmingham | B35 7LQ | Ms M Gome | 7950704659 |  | maggygome@yahoo.co.uk | Windows & Doors | M Turpin | 2024-07-17 | 9am to 2pm | CONFIRMED for 17.07.24 after 9am
FLAT 137A | Farnborough Road | Birmingham | B35 7LQ | Miss M Johnson | 07522 319 231 |  |  | Windows & Doors | M Turpin | 2024-07-17 | 8am to 2pm | 10/07 SMS text sent for 17/07. 11/07 SMS left voicemail & Lttr sent
FLAT 137B | Farnborough Road | Birmingham | B35 7LQ | Miss N Burley Hanson | 7494283968 |  | xnicolehansonx@hotmail.co.uk | Windows & Doors | M Turpin | 2024-07-17 | 8am to 2pm | 03.07.24 SF Sent text message. 10/07 SMS left voicemail. 11/07 SMS called N/A Lttr sent
FLAT 133C | Farnborough Road | Birmingham | B35 7LQ | Mr S Webb | 01212389607 | 07402935863 | swebb1965.sw@google.com | Windows & Doors | M Turpin | 2024-07-17 | 8am to 2pm | CONFIRMED for 17.07.24 - Please call 1 HOUR before arriving, he'll be home at 2pm
Pioneer Group - WEDNESDAY 17TH JULY - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
4 | Chigwell Close | Birmingham | B35 7HH | Mr S Doyle | 07735495850 |  | stevendoyle1984@hotmail.co.uk | Windows & Doors | P Beahan | 2024-07-17 | 8am to 12pm | CONFIRMED for 17.07.24 -
10 | Chigwell Close | Birmingham | B35 7HH | Miss A Delaney |  |  | angeldelaney96@outlook.com | Windows & Doors | P Beahan | 2024-07-17 | 8am to 12pm | CONFIRMED for 17.07.24
15 | Chigwell Close | Birmingham | B35 7HG | Ms G Metcalfe | 07854 614 241 |  | Georginahumphries@icloud.com | Windows & Doors | P Beahan | 2024-07-17 | 8am to 12pm | CONFIRMED for 17.07.24 - Re-arranged for this date, was NO ACCESS previous date
8 | Hawker Drive | Birmingham | B35 7EG | Mrs V Hassall | 7552733533 |  |  | Windows & Doors | P Beahan | 2024-07-17 | 11am to 3pm | CONFIRMED for 17.07.24
8A | Hawker Drive | Birmingham | B35 7EG | Miss D Meah |  |  | meahdonna58@gmail.com | Windows & Doors | P Beahan | 2024-07-17 | 11am to 3pm | 08/07 SMS lttr sent for 17/07
8B | Hawker Drive | Birmingham | B35 7EG | Miss C Wallace |  |  |  | Windows & Doors | P Beahan | 2024-07-17 | 11am to 3pm | 03.07.24 SF Sent letter
Pioneer Group - THURSDAY 18TH JULY - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
4B | Hawker Drive | Birmingham | B35 7EG | Miss K Hanson |  |  |  | Windows & Doors | P Beahan | 2024-07-18 | 8am to 12pm | 05/07 SMS lttr sent for 18/07
6A | Hawker Drive | Birmingham | B35 7EG | Mrs E Venard | 0121 749 1523 | 07486 522672 |  | Windows & Doors | P Beahan | 2024-07-18 | 8am to 12pm | 05/07 SMS text sent for 18/07. 08/07 SMS called N/A. 10/07 SMS called N/A Lttr sent.
10 | Hawker Drive | Birmingham | B35 7EG | Miss S Kelly | 01217482006 | 07564366180 |  | Windows & Doors | P Beahan | 2024-07-18 | 8am to 12pm | 05/07 SMS text sent for 18/07. 08/07 SMS left voicemail. 10/07 SMS called N/A Lttr sent.
10A | Hawker Drive | Birmingham | B35 7EG | Mrs K Moore | 07857 457916 |  |  | Windows & Doors | P Beahan | 2024-07-18 | 11am to 3pm | CONFIRMED for 18/07.
26 | Hawker Drive | Birmingham | B35 7EG | Mrs L Cutler | 7476400896 |  |  | Windows & Doors | P Beahan | 2024-07-18 | 11am to 3pm | 05/07 SMS lttr sent for 18/07. New contact no. given. 15/07 SMS tenant called to cancel.
35 | Hawker Drive | Birmingham | B35 7DY | Mrs G Brown-Robinson | 01216784443 NIS |  |  | Windows & Doors | P Beahan | 2024-07-18 | 11am to 3pm | 05/07 SMS called no. NIS lttr sent for 18/07
Pioneer Group - WEDNESDAY 24TH JULY - Steve Burgess
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
3 | Avro Way | Birmingham | B35 7NW | Mr M Riddell | 07980833904 |  |  | Windows & Doors | S Burgess | 2024-07-24 | 8am to 12pm | CONFIRMED for 24/07
4 | Avro Way | Birmingham | B35 7NW | Miss T Watson | 07748 332296 |  | tessakwatson@yahoo.co.uk | Windows & Doors | S Burgess | 2024-07-24 | 8am to 12pm | CONFIRMED for 24/07
FLAT 6 Block 16 | Bicester Square | Birmingham | B35 6HR | Miss KG Walker | 7387314944 | 07557783791 |  | Windows & Doors | S Burgess | 2024-07-24 | 8am to 12pm | 04/07 SMS emailed client & Dominie to arrange this 3rd access attenmpt directly with the tenant.
30 | Northolt Drive | Birmingham | B35 6QX | Mrs N Parry | 07707478425 |  |  | Windows & Doors | S Burgess | 2024-07-24 | 8am to 12pm | CONFIRMED for 24/07
5 | Bond Drive | Birmingham | B35 7QQ | Mrs W Walsh | 07496 536972 |  | wendywalsh.cv@btinternet.com | Windows & Doors | S Burgess | 2024-07-24 | 11am to 3pm | 05/07 SMS emailed tenant for 24/07. 10/07 SMS left voicemail. 11/07 SMS called N/A lttr sent
1 | Shawberry Avenue | Birmingham | B35 6QU | Miss L Ginn | 07305092651 |  | Lucymginn@hotmail.co.uk | Windows & Doors | S Burgess | 2024-07-24 | 11am to 3pm | CONFIRMED for 24/07
2 | Shawberry Avenue | Birmingham | B35 6QU | Miss S McGuire | 07517 408 879 |  |  | Windows & Doors | S Burgess | 2024-07-24 | 11am to 3pm | CONFIRMED for 24/07
Pioneer Group - WEDNESDAY 24TH JULY - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
38 | Hawker Drive | Birmingham | B35 7EG | Mrs S L Burke |  | 07470280658 |  | Windows & Doors | P Beahan | 2024-07-24 | 8am to 12pm | CONFIRMED for 24/07
39 | Hawker Drive | Birmingham | B35 7DY | Ms P C Moran | 01217477076 | 07455 201 844 NIS |  | Windows & Doors | P Beahan | 2024-07-24 | 8am to 12pm | 08/07 SMS text sent for 24/07. 10/07 called no. NIS. 11/07 SMS lttr sent
43 | Hawker Drive | Birmingham | B35 7DY | Mrs Y Taylor | 01217487193 |  |  | Windows & Doors | P Beahan | 2024-07-24 | 11am to 3pm | 08/07 SMS lttr sent for 24/07
45 | Hawker Drive | Birmingham | B35 7DY | Miss L Jones |  | 07312253894 NIS |  | Windows & Doors | P Beahan | 2024-07-24 | 11am to 3pm | 08/07 SMS text sent for 24/07. 11/07 SMS called no. NIS, lttr sent
60 | Hawker Drive | Birmingham | B35 7EG | Miss T Doherty | 0121 240 0267 | 07502225839 | Tammy.1987@hotmail.co.uk | Windows & Doors | P Beahan | 2024-07-24 | 11am to 3pm | CONFIRMED for 24/07
Pioneer Group - WEDNESDAY 24TH JULY - Martin Turpin - TO BE CANCELLED ONCE HAVE NEW AUGUST DATES AS MT ON LEAVE
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
FLAT 129D | Farnborough Road | Birmingham | B35 7LQ | Miss C Morris | 01217767045 NIS |  | cat_and_corey23@outlook.com | Windows & Doors | M Turpin | 2024-07-24 | 8am to 2pm | CONFIRMED for 24/07
FLAT 139A | Farnborough Road | Birmingham | B35 7LQ | Mr W Draper | 07901 702 357 |  |  | Windows & Doors | M Turpin | 2024-07-24 | 8am to 2pm | 08/07 SMS text sent for 24/07
FLAT 139B | Farnborough Road | Birmingham | B35 7LQ | Mr M Lawerence | 07543 036 936 | 07543746836 | chicogrimes@gmail.com | Windows & Doors | M Turpin | 2024-07-24 | 8am to 2pm | 08/07 SMS text sent for 24/07
FLAT 139C | Farnborough Road | Birmingham | B35 7LQ | Mr AJ Mcmahon | 07986980943 |  |  | Windows & Doors | M Turpin | 2024-07-24 | 8am to 2pm | 08/07 SMS text sent for 24/07
FLAT 139D | Farnborough Road | Birmingham | B35 7LQ | Mr S B Howell | 07707 806198 |  |  | Windows & Doors | M Turpin | 2024-07-24 | 8am to 2pm | CONFIRMED for 24/07
FLAT 139E | Farnborough Road | Birmingham | B35 7LQ | Mr J Sullivan | 07507382658 |  |  | Windows & Doors | M Turpin | 2024-07-24 | 8am to 2pm | 08/07 SMS text sent for 24/07
FLAT 139F | Farnborough Road | Birmingham | B35 7LQ | Mr V Smith | 07506312689 |  |  | Windows & Doors | M Turpin | 2024-07-24 | 8am to 2pm | 08/07 SMS text sent for 24/07
FLAT 145A | Farnborough Road | Birmingham | B35 7LQ | Mr A Shakespeare | 07428 715 334 |  |  | Windows & Doors | M Turpin | 2024-07-24 | 8am to 2pm | 08/07 SMS text sent for 24/07
FLAT 145B | Farnborough Road | Birmingham | B35 7LQ | Mr J Cassidy | 07800850130 |  |  | Windows & Doors | M Turpin | 2024-07-24 | 8am to 2pm | 08/07 SMS text sent for 24/07
FLAT 145C | Farnborough Road | Birmingham | B35 7LQ | Mrs M Corcoran | 0121 748 2849 |  |  | Windows & Doors | M Turpin | 2024-07-24 | 8am to 2pm | 08/07 SMS called line engaged
FLAT 145E | Farnborough Road | Birmingham | B35 7LQ | Mr PJ Guest | 07718 613 519 |  | Paul-Guest1985@Hotmail.co.uk | Windows & Doors | M Turpin | 2024-07-24 | 8am to 2pm | CONFIRMED for 24/07
FLAT 145F | Farnborough Road | Birmingham | B35 7LQ | Miss S L Whitehouse | 07762123269 |  | sharna161120@gmail.com | Windows & Doors | M Turpin | 2024-07-24 | 8am to 2pm | CONFIRMED for 24/07
FLAT 145G | Farnborough Road | Birmingham | B35 7LQ | Miss R Mcmahon | 07473126803 |  |  | Windows & Doors | M Turpin | 2024-07-24 | 8am to 2pm | 08/07 SMS text sent for 24/07
Pioneer Group - THURSDAY 25TH JULY - Steve Burgess
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
14 | Avro Way | Birmingham | B35 7NW | Mr L Caulfield |  |  |  | Windows & Doors | S Burgess | 2024-07-25 | 8am to 12pm | 08/07 SMS no contact details so lttr sent for 25/07
18 | Sopwith Croft | Birmingham | B35 7QH | Mr B Pike | 07760994271 | 07760994271 |  | Windows & Doors | S Burgess | 2024-07-25 | 8am to 12pm | CONFIRMED for 25/07
20 | Sopwith Croft | Birmingham | B35 7QH | Mr C Molloy |  | 07400705148 |  | Windows & Doors | S Burgess | 2024-07-25 | 8am to 12pm | CONFIRMED for 25/07
26 | Sopwith Croft | Birmingham | B35 7QH | Mr PD Littler | 07861770066 |  |  | Windows & Doors | S Burgess | 2024-07-25 | 11am to 3pm | 08/07 SMS text sent for 25/07. 15/7; AC letter sent.
3 | Shawberry Avenue | Birmingham | B35 6QU | Miss L Cross |  | 07301529422 | lucymarie2015@gmail.com | Windows & Doors | S Burgess | 2024-07-25 | 11am to 3pm | CONFIRMED for 25/07
4 | Shawberry Avenue | Birmingham | B35 6QU | Mrs B Brough | 07884 141 491 |  | sarahrutter1@live.co.uk | Windows & Doors | S Burgess | 2024-07-25 | 11am to 3pm | 08/07 SMS text sent for 25/07. 15/7; AC letter sent.
Pioneer Group - THURSDAY 25TH JULY - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
76 | Heyford Way | Birmingham | B35 6HU | Mrs P Brown | 079254 14 091 |  |  | Windows & Doors | P Beahan | 2024-07-25 | 8am to 12pm | 03/07 SMS as 3rd access atempt client emailed to arrange directly with tenant for access.
2 | Abingdon Way | Birmingham | B35 6QF | Miss A Goode | 07715 470 787 | 07715 470 787 |  | Windows & Doors | P Beahan | 2024-07-25 | 8am to 12pm | 08/07 SMS text sent for 25/07. 15/7; AC letter sent.
35 | Abingdon Way | Birmingham | B35 6QF | Mr L Willetts | 07496159464 | 07564057802 |  | Windows & Doors | P Beahan | 2024-07-25 | 8am to 12pm | CONFIRMED for 25/07
FLAT 60 | Mere Avenue | Birmingham | B35 6QT | Mr P J McCallion | 7751066503 |  | patrickmccallion8@gmail.com | Windows & Doors | P Beahan | 2024-07-25 | 8am to 12pm | CONFIRMED for 25/07 - Tenant will arrange for himself or a friend to be in the property
FLAT 68 | Mere Avenue | Birmingham | B35 6QT | Mr S Gardiner | 07305 947 116 | 07873894184 | mya1997@live.co.uk | Windows & Doors | P Beahan | 2024-07-25 | 11am to 3pm | FINAL ATTEMPT. 15/7; AC asked client and TLO to confirm this appointment.
Pioneer Group - THURSDAY 25TH JULY - Martin Turpin. TO BE CANCELLED ONCE HAVE NEW AUGUST DATES AS MT ON LEAVE
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
10 | Coltishall Close | Birmingham | B35 7EF | Mr S Marles | 0121 574 5664 | 07870635271 |  | Windows & Doors | M Turpin | 2024-07-25 | FIRST CALL | CONFIRMED for 25/07 - FIRST CALL
FLAT 147A | Farnborough Road | Birmingham | B35 7LQ | Miss S Al-Muhimin | 07860377737 |  | sammara.93@hotmail.co.uk | Windows & Doors | M Turpin | 2024-07-25 | 8am to 2pm | CONFIRMED for 25/07
FLAT 147B | Farnborough Road | Birmingham | B35 7LQ | Mr M Larkin | 01217477887 |  |  | Windows & Doors | M Turpin | 2024-07-25 | 8am to 2pm | 08/07 SMS lttr sent
FLAT 147C | Farnborough Road | Birmingham | B35 7LQ | Mr D Doe | 07712405839 |  |  | Windows & Doors | M Turpin | 2024-07-25 | 8am to 2pm | 08/07 SMS text sent for 25/07
FLAT 147D | Farnborough Road | Birmingham | B35 7LQ | Miss A Gray | 07944199293 |  | grayantoinette79@gmail.com | Windows & Doors | M Turpin | 2024-07-25 | 8am to 2pm | CONFIRMED for 25/07
FLAT 147E | Farnborough Road | Birmingham | B35 7LQ | Miss E Krause | 0121 574 1978 |  | epakrause@gmail.com | Windows & Doors | M Turpin | 2024-07-25 | 8am to 2pm | 08/07 SMS lttr sent
FLAT 147F | Farnborough Road | Birmingham | B35 7LQ | Miss J Morgan | 07738 388 182 |  |  | Windows & Doors | M Turpin | 2024-07-25 | 8am to 2pm | 08/07 SMS text sent for 25/07
FLAT 4 Block 214 | 1-6 Farnborough Road | Castle Vale | B35 7NH | Miss M Khalid | 07587324064 | 07401887702 | maneeba.khalid@hotmail.com | Windows & Doors | M Turpin | 2024-07-25 | 8am to 2pm | 08/07 SMS text sent for 25/07
FLAT 1 Flats 214 | 1-6 Farnborough Road | Castle Vale | B35 7NH | Miss C Wilson | 07581576078 |  | chelseawilson1997@yahoo.co.uk | Windows & Doors | M Turpin | 2024-07-25 | 8am to 2pm | CONFIRMED for 25/07
FLAT 3 Flats 214 | 1-6 Farnborough Road | Castle Vale | B35 7NH | Miss K Savage | 07950913901 |  | savagekeyleigh@gmail.com | Windows & Doors | M Turpin | 2024-07-25 | 8am to 2pm | 08/07 SMS text sent for 25/07
FLAT 5 Flats 214 | 1-6 Farnborough Road | Castle Vale | B35 7NH | Miss G Simmonds |  |  |  | Windows & Doors | M Turpin | 2024-07-25 | 8am to 2pm | 08/07 SMS lttr sent
FLAT 6 Flats 214 | 1-6 Farnborough Road | Castle Vale | B35 7NH | Mrs L Moss | 01217478044 |  |  | Windows & Doors | M Turpin | 2024-07-25 | 8am to 2pm | 08/07 SMS lttr sent
21 | Concorde Drive | Birmingham | B35 7EE | Miss J Weston | 07429922484 |  |  | Windows & Doors | M Turpin | 2024-07-25 | 8am to 2pm | 08/07 SMS text sent for 25/07
Pioneer Group - MONDAY 29TH JULY - Martin Turpin. TO BE CANCELLED ONCE HAVE NEW AUGUST DATES AS MT ON LEAVE
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
11 | Javelin Avenue | Birmingham | B35 7LH | Miss KL Macken | 07538863242 |  |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm | 3rd attempt, emailed client & Dom to arrange access directly with the tenant for 29/07. 15/07 SMS emailed TLO to advise needs cancelling
34 | Javelin Avenue | Birmingham | B35 7LW | Miss T Gordon | 07583 234 987 |  |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm | 3rd attempt, emailed client & Dom to arrange access directly with the tenant for 29/07. 15/07 SMS emailed TLO to advise needs cancelling
48 | Javelin Avenue | Birmingham | B35 7LW | Ms S Jones | 07389811707 |  |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm | 3rd attempt, emailed client & Dom to arrange access directly with the tenant for 29/07. 15/07 SMS emailed TLO to advise needs cancelling
9 | Montrose Drive | Birmingham | B35 6DH | Miss R Garrington | 07397 384 556 |  |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm | 3rd attempt, emailed client & Dom to arrange access directly with the tenant for 29/07. 15/07 SMS emailed TLO to advise needs cancelling
17 | Montrose Drive | Birmingham | B35 6DH | Mr N Proffitt | 07874 328 741 |  |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm
19 | Montrose Drive | Birmingham | B35 6DH | Mr MA Smith | 07908293857 |  |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm
FLAT 5 Block 1 | Montrose Drive | Birmingham | B35 6DH | Mr K Palmer | 07399584441 |  |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm
FLAT 347 | Yatesbury Avenue | Birmingham | B35 6QP | Mr C Ferrie | 01217301070 |  |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm
FLAT 371 | Yatesbury Avenue | Birmingham | B35 6QP | Mr B Shingler | 07473 115 805 |  |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm | Access via 1 Cranwell & 363 Yatesbury. 1 x no access previously.
FLAT 375 | Yatesbury Avenue | Birmingham | B35 6QP | Mrs J Evans | 07572601432 |  |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm | Access via 1 Cranwell & 363 Yatesbury. 1 x no access previously.
FLAT 397 | Yatesbury Avenue | Birmingham | B35 6QP | Mr R Shakespeare |  |  |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm
FLAT 399 | Yatesbury Avenue | Birmingham | B35 6QP | Mr W McMullan | 681 0549 |  |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm
FLAT 401 | Yatesbury Avenue | Birmingham | B35 6QP | Mr S Sawyer |  |  |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm
FLAT 403 | Yatesbury Avenue | Birmingham | B35 6QP | Mr I Hall | 07729 029 722 |  |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm
21 | Donibristle Croft | Birmingham | B35 6BL | Mrs T A Robinson | 01217487692 |  |  | Windows & Doors | M Turpin | 2024-07-29 | 8am to 2pm
Pioneer Group - TUESDAY 30TH JULY - Martin Turpin. TO BE CANCELLED ONCE HAVE NEW AUGUST DATES AS MT ON LEAVE
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
3 | Lysander Way | Birmingham | B35 7JY | Ms C Brown | 07486047902 |  | 00clare@gmail.com | Windows & Doors | M Turpin | 2024-07-30 | 8am to 2pm
29 | Lysander Way | Birmingham | B35 7JY | Mr M Younis | 07378866549 | 07378866549 | muhammadyoung.my@gmail.com | Windows & Doors | M Turpin | 2024-07-30 | 8am to 2pm
FLAT 127F | Farnborough Road | Birmingham | B35 7LQ | Miss A Evetts | 01217482950 | 07817842712 |  | Windows & Doors | M Turpin | 2024-07-30 | 8am to 2pm | 03.07.24 SF CONFIRMED
3 | Cranwell Way | Birmingham | B35 6QH | Miss Z Carr |  | 07856402181 |  | Windows & Doors | M Turpin | 2024-07-30 | 8am to 2pm
FLAT 10 | Cosford Crescent | Birmingham | B35 6QE | Miss JM Lydon | 01217302262 | 07732885362 |  | Windows & Doors | M Turpin | 2024-07-30 | 8am to 2pm | 11/07 SMS spoke to tenant on phone so 27/07 is CONFIRMED
FLAT 38 | Cosford Crescent | Birmingham | B35 6QE | Mr C A Layton | 07784729094 |  |  | Windows & Doors | M Turpin | 2024-07-30 | 8am to 2pm | 1 X NO ACCESS. 3/7; AC sent letter for survey 30/7.
FLAT 40 | Cosford Crescent | Birmingham | B35 6QE | Mr C L Jones | 0121 7481010 | 07894708299 | c.jones99965@yahoo.com | Windows & Doors | M Turpin | 2024-07-30 | 8am to 2pm | 1 X NO ACCESS. 3/7; AC sent letter for survey 30/7.
FLAT 72 | Cosford Crescent | Birmingham | B35 6QE | Mr MB Hatton |  | 07469170364 |  | Windows & Doors | M Turpin | 2024-07-30 | 8am to 2pm | 1 X NO ACCESS. 3/7; AC sent letter for survey 30/7.
FLAT 78 | Cosford Crescent | Birmingham | B35 6QE | Mr D Gayle | 01212412287 | 07858 988830 |  | Windows & Doors | M Turpin | 2024-07-30 | 8am to 2pm | 3/7; AC sent letter for survey 30/7.
1 | Cosford Crescent | Birmingham | B35 6QE | Miss F C Morris | 07926757397 |  | morrisfiona020@gmail.com | Windows & Doors | M Turpin | 2024-07-30 | 8am to 2pm
24 | Cosford Crescent | Birmingham | B35 6QE | Miss S N Smith |  | 07307377916 |  | Windows & Doors | M Turpin | 2024-07-30 | 8am to 2pm
28 | Cosford Crescent | Birmingham | B35 6QE | Miss S Meenan |  | 07753 676 037 | STACEY-MEENAN@HOTMAIL.CO.UK | Windows & Doors | M Turpin | 2024-07-30 | 8am to 2pm
58 | Cosford Crescent | Birmingham | B35 6QE | Mr M Lambert |  | 07368 848 378 | lamb262001@yahoo.com | Windows & Doors | M Turpin | 2024-07-30 | 8am to 2pm
30 | Trident Boulevard | Birmingham | B35 7LZ | Miss R Douglas | 07778035265 |  |  | Windows & Doors | M Turpin | 2024-07-30 | 8am to 2pm | 11/07 SMS spoke to tenant CONFIRMED
[8 empty] | Windows & Doors | M Turpin | 2024-07-30 | 8am to 2pm
Pioneer Group - WEDNESDAY 31ST JULY - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
49 | Hawker Drive | Birmingham | B35 7DY | Mrs M Franks | 07828956007 |  |  | Windows & Doors | P Beahan | 2024-07-31 | 8am to 12pm | 15/7; CONFIRMED.
53 | Hawker Drive | Birmingham | B35 7DY | Mrs G Wilkins | 01217486754 | 07941037147 |  | Windows & Doors | P Beahan | 2024-07-31 | 8am to 12pm | 15/7; AC survey text sent.
55 | Hawker Drive | Birmingham | B35 7DY | Mr T Greenfield | 0121 681 5011 | 07545381214 |  | Windows & Doors | P Beahan | 2024-07-31 | 8am to 12pm | 15/7; CONFIRMED.
63 | Hawker Drive | Birmingham | B35 7DY | Mr M Eaton | 01217491552 | 07717307605 |  | Windows & Doors | P Beahan | 2024-07-31 | 11am to 3pm | 17/7; CONFIRMED.
65 | Hawker Drive | Birmingham | B35 7DY | Mr K Griffiths |  |  |  | Windows & Doors | P Beahan | 2024-07-31 | 11am to 3pm | 15/7; AC sent letter.
1 | Hawker Drive | Birmingham | B35 7DX | Miss K Hinett | 0790 197 5798 | 0121 749 5278 |  | Windows & Doors | P Beahan | 2024-07-31 | 11am to 3pm | 15/7; AC survey text sent.
Pioneer Group - THURSDAY 1ST AUGUST - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
17 | Chigwell Close | Birmingham | B35 7HG | Ms P Vincent | 01217492601 | 07796805324 | pennyroger2@yahoo.co.uk | Windows & Doors | P Beahan | 2024-08-01 | 8am to 12pm | 15/7; CONFIRMED.
19 | Chigwell Close | Birmingham | B35 7HG | Mrs J Dunston | 07754 213858 |  | jdunston35@googlemail.com | Windows & Doors | P Beahan | 2024-08-01 | 8am to 12pm | 15/7; AC survey text sent.
21 | Chigwell Close | Birmingham | B35 7HG | Miss J Cooney |  | 07876191419 | janecooney@hotmail.co.uk | Windows & Doors | P Beahan | 2024-08-01 | 8am to 12pm | 15/7; AC survey text sent.
25 | Chigwell Close | Birmingham | B35 7HH | Miss K Haughton |  | 07312 421 916 |  | Windows & Doors | P Beahan | 2024-08-01 | 11am to 3pm | 15/7; AC survey text sent.
97 | Hawker Drive | Birmingham | B35 7EA | Miss J Campbell |  | 7543350787 |  | Windows & Doors | P Beahan | 2024-08-01 | 11am to 3pm | 15/7; AC survey text sent.
101 | Hawker Drive | Birmingham | B35 7EA | Miss J Marston |  | 07379359151 |  | Windows & Doors | P Beahan | 2024-08-01 | 11am to 3pm | 15/7; CONFIRMED.
Pioneer Group - AUGUST…..? - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
FLAT 4 Block 1 | Montrose Drive | Birmingham | B35 6DH | Mrs A J Preston | 07845185767 |  |  | Windows & Doors | M Turpin |  | 8am to 2pm
15 | Concorde Drive | Birmingham | B35 7EE | Ms J Mulligan |  | 07496108763 |  | Windows & Doors | M Turpin |  | 8am to 2pm
25 | Concorde Drive | Birmingham | B35 7EE | Miss J Cowan | 01217486221 | 07788230297 |  | Windows & Doors | M Turpin |  | 8am to 2pm
29 | Concorde Drive | Birmingham | B35 7EE | Miss DL Carter |  | 07342016962 |  | Windows & Doors | M Turpin |  | 8am to 2pm
15A | Coltishall Close | Birmingham | B35 7EF | Miss T A Edwards | 0121 408 9836 | 07305 595 250 | na_edwards@hotmail.com | Windows & Doors | M Turpin |  | 8am to 2pm
16 | Coltishall Close | Birmingham | B35 7EF | Mrs M Duffy |  | 07900 652 579 |  | Windows & Doors | M Turpin |  | 8am to 2pm
17 | Coltishall Close | Birmingham | B35 7EF | Mrs T Cottrell | 01217481461 | 07445676678 |  | Windows & Doors | M Turpin |  | 8am to 2pm
19 | Coltishall Close | Birmingham | B35 7EF | Miss H Condron |  |  | hollycondronhc@hotmail.co.uk | Windows & Doors | M Turpin |  | 8am to 2pm
FLAT 141C | Farnborough Road | Birmingham | B35 7LQ | Miss J Neave | 07583019842 |  | j.neave0987@googlemail.com | Windows & Doors | M Turpin |  | 8am to 2pm
56 | Cosford Crescent | Birmingham | B35 6QE | Miss A Crowley |  | 07592 464 037 |  | Windows & Doors | M Turpin |  | 8am to 2pm
60 | Cosford Crescent | Birmingham | B35 6QE | Miss L Sharpe |  | 07731618505 | lisaamu18@gmail.com | Windows & Doors | M Turpin |  | 8am to 2pm
62 | Cosford Crescent | Birmingham | B35 6QE | Mr C Liwolweki |  | 07802293624 | csliwo_0878@hotmail.com | Windows & Doors | M Turpin |  | 8am to 2pm
15 | Concorde Drive | Birmingham | B35 7EE | Ms J Mulligan |  | 07496108763 |  | Windows & Doors | M Turpin |  | 8am to 2pm
Pioneer Group - AUGUST….? - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
3 | Cosford Crescent | Birmingham | B35 6QE | Mrs B E Peach |  | 07518755167 | brenda.liss@hotmail.co.uk | Windows & Doors | M Turpin |  | 8am to 2pm
4 | Cosford Crescent | Birmingham | B35 6QE | Miss K Kehoe | 0121 218 3025 | 07562272502 |  | Windows & Doors | M Turpin |  | 8am to 2pm
5 | Cosford Crescent | Birmingham | B35 6QE | Miss A Roe | 07951676470 |  | angieroe01@gmail.com | Windows & Doors | M Turpin |  | 8am to 2pm
6 | Cosford Crescent | Birmingham | B35 6QE | Miss E Johnson |  | 07769596226 | jhns330@hotmail.co.uk | Windows & Doors | M Turpin |  | 8am to 2pm
7 | Cosford Crescent | Birmingham | B35 6QE | Miss A O'regan | 07495993808 |  |  | Windows & Doors | M Turpin |  | 8am to 2pm
9 | Cosford Crescent | Birmingham | B35 6QE | Mrs J Baker | 07983 746 872 |  | julieanne001@hotmail.com | Windows & Doors | M Turpin |  | 8am to 2pm
11 | Cosford Crescent | Birmingham | B35 6QE | Mr A Connolly | 07432316830 |  | starlord0032@icloud.com | Windows & Doors | M Turpin |  | 8am to 2pm
26 | Cosford Crescent | Birmingham | B35 6QE | Mrs M Doherty |  | 07713826954 | MAZDOHERTY@HOTMAIL.CO.UK | Windows & Doors | M Turpin |  | 8am to 2pm
48 | Cosford Crescent | Birmingham | B35 6QE | Miss J Caesar | 01217482042 | 07837320565 |  | Windows & Doors | M Turpin |  | 8am to 2pm
52 | Cosford Crescent | Birmingham | B35 6QE | Miss N Chambers |  | 07877481007 |  | Windows & Doors | M Turpin |  | 8am to 2pm
54 | Cosford Crescent | Birmingham | B35 6QE | Miss S Rollason |  | 07742309599 |  | Windows & Doors | M Turpin |  | 8am to 2pm
[8 empty] | Windows & Doors | M Turpin |  | 8am to 2pm
[8 empty] | Windows & Doors | M Turpin |  | 8am to 2pm
Pioneer Group - Date - Martin Turpin
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
[9 empty] | M Turpin |  | 8am to 2pm
[9 empty] | M Turpin |  | 8am to 2pm
[9 empty] | M Turpin |  | 8am to 2pm
[9 empty] | M Turpin |  | 8am to 2pm
[9 empty] | M Turpin |  | 8am to 2pm
[9 empty] | M Turpin |  | 8am to 2pm
[9 empty] | M Turpin |  | 8am to 2pm
[9 empty] | M Turpin |  | 8am to 2pm
[9 empty] | M Turpin |  | 8am to 2pm
[9 empty] | M Turpin |  | 8am to 2pm
[9 empty] | M Turpin |  | 8am to 2pm
[9 empty] | M Turpin |  | 8am to 2pm
[9 empty] | M Turpin |  | 8am to 2pm
Pioneer Group - Date - Paul Beahan
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
[9 empty] | P Beahan |  | 8am to 12pm
[9 empty] | P Beahan |  | 8am to 12pm
[9 empty] | P Beahan |  | 8am to 12pm
[9 empty] | P Beahan |  | 11am to 3pm
[9 empty] | P Beahan |  | 11am to 3pm
[9 empty] | P Beahan |  | 11am to 3pm
Pioneer Group - Date - Steve Burgess
House Number | Street | Town | Postcode | Tenant Name | Telephone Number (Primary) | Telephone Number (Secondary) | Email Address | Scope of Work | Surveyor | Survey Date | AM / PM Appointment | Comments | P= Accessed or X = Carded/No Access (include Time) | No. of Windows Surveyed | No. of Doors Surveyed
[9 empty] | S Burgess |  | 8am to 12pm
[9 empty] | S Burgess |  | 8am to 12pm
[9 empty] | S Burgess |  | 8am to 12pm
[9 empty] | S Burgess |  | 11am to 3pm
[9 empty] | S Burgess |  | 11am to 3pm
[9 empty] | S Burgess |  | 11am to 3pm
Martin Turpin on Annual leave 19th July - 4th August then 19th August until 31st August
05/07 - SMS Email from client requesting we now prioritise Shawberry Avenue for surveying - Allocated to Steve Burgess on tracker
Pioneer Group - FRIDAY ??? - Martin Turpin
78 | Javelin Avenue | Birmingham | B35 7LW | Miss C Belle |  | 07985555420 | carlabelle@ymail.com | Windows & Doors | M Turpin |  |  | FRIDAYS ONLY
Pioneer Group - WEDNESDAY ?? - S Burgess
Pioneer Group - Date - Paul Beahan
27 | Chigwell Close | Birmingham | B35 7HG | Miss K Finney | 07812996853 |  |  | Windows & Doors | P Beahan |  |  | SEPTEMBER

## Scaffold
Flats 1-6 Block 14 | Bicester Square | Ref :- BSL 01/05-2
Flats 1-6 Block 16 | Bicester Square | Ref :- BSL 01/05-3
2 | Bond Drive | Ref :- BSL 17/07-2
6 | Bond Drive | Ref :- BSL 17/07-4
8 | Bond Drive | Ref :- BSL 17/07-5
3 | Concorde Drive | Ref :- BSL 17/07-6
5 | Concorde Drive | Ref :- BSL 17/07-3
1 & 3 | Coltishall Close | Ref : BSL 28/06-1
5 | Coltishall Close | Ref: BSL28/06-2
7 | Coltishall Close | Awaiting Darren to req quote
9 & 11 | Coltishall Close | Ref: BSL 28/06-3
15 | Coltishall Close | Ref: BSL 28/06-4
8 | De Havilland
29 | Donbristle Croft | Ref: BSL 23/05-1
131D | Farnborough Road
129F | Farnborough Road
131G | Farnborough Road
25 | Heyford Way | Ref :- BSL 26/04-1 | POG118982-DA
Block 64 | Heyford Way | Awaiting Darren to req quote for whole of block 64
FLAT 2 - 8 | Kemble Drive | Ref :- BSL 17/07-1
Flat 1 | Northolt Drive | Ref :- BSL 12/07-3 | POG12064-DA
Flat 3 | Northolt Drive | Ref :- BSL 12/07-4 | POG120465-DA
Flat 4 | Northolt Drive | Ref :- BSL 12/07-2 (same as no. Flat 4 & 6 as need to be done together) | POG120500-DA
Flat 5 | Northolt Drive | Ref :- BSL 30/04-1 & quote for netting BSL 12/07-1 | POG120117-DA
Flat 6 | Northolt Drive | Ref :- BSL 12/07-2 (same as no. Flat 4 & 6 as need to be done together) | POG120500-DA
Flat 7 | Northolt Drive | Ref :- BSL 30/04-1 & quote for netting BSL 12/07-1 | POG120117-DA
14 | Northolt Drive | Ref :- BSL 18/06-1 | POG119748-DA | TLO advised not req so cancelled with BSL on 17/07
18 | Northolt Drive | Ref :- BSL 26/04-2 | POG120123-DA
22 | Northolt Drive | Ref :- BSL 26/04-2 | POG120123-DA
FLAT 27 | Northolt Drive | Ref :- BSL 12/07-5 | POG120499-DA
Flat 29 | Northolt Drive | Ref :- BSL 12/07-6 | POG120496-DA
Flat 34 | Northolt Drive | Ref :- BSL 12/07-7 | POG120494-DA
Flat 38 | Northolt Drive | Await quote as need 40 Northolt at same time as will be Scaff & Install together
Flat 40 | Northolt Drive | Await quote as need 40 Northolt at same time as will be Scaff & Install together
97 | Watton Green | Ref: BSL 28/06-5
10 | Watton Green | Ref :- BSL 18/07-1

## Address sort tool
|  | This formula tells Excel to start at the left end of the information in cell A2 and find the first space, which should fall immediately after the house number, then display the information to the left of the space. | This formula instructs Excel to find all the characters in the address except for the number of characters occupied by the house number, then remove the space from the beginning of that text and display the result.
uprn | address | House Number | Street
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE!

## List
Copy From Vision Lookup
Status | Access Equipment | Construction Type | Property Archetype | Disability | Time | Surveyor |  | Query Type | Delivery Point | Installation Team | Inspector | Route march
COMMENCEMENT PENDING | Independent Scaffold | EWI | House | Vision | 7:30am | A Lethridge | Yes | CLIENT ISSUE | Depot | Brian Gordon | Client | 1
ON HOLD | Tower Scaffold | No Fines | Flat | Violent | 8am to 10am | A Meldrum | No | SEE COMMENTS | Container | Alex Clark |  | 2
SURVEY BOOKED | MEWP | IWI | Bungalow | Mobility Issues | 8am to 12 noon | B Sinclair |  | DOOR CHOICE |  | Julian Abbey |  | 3
SCOPE SURVEY | Jammer System | Brick | Communal | Communicating | 9am to 1pm | I Roy |  | FIRE PRODUCTS; ON HOLD |  | Dave Bennett |  | 4
SURVEY RECEIVED |  | Brick & Render | Terrace | Hearing | 10am to 2pm | P Beahan |  | UPRN Missing |  | Neil Bucknall |  | 5
PM TO CLEANSE |  | Render |  | Life Limiting Illness | 11am to 3pm | S Burgess |  | Asbestos Report Required |  | Jim McDonald |  | 6
Survey In Vision, PM to cleanse |  | Peddle Dash |  | Mental Health | 12 noon to 4pm | Tony Lee |  | Lintel Required |  | Eric |  | 7
CLEANSED |  | Timber |  | Breathing Difficulties | 1pm To 5pm | Mick Clingan |  | Door Query, see comments |  | Adrian |  | 8
SENT FOR PRICING |  | Brick & Cladding |  |  | AM | M Turpin |  | Awaiting all paperwork |  |  |  | 9
PRICED |  |  |  |  | PM | D Ansell |  | Photos rec'd, await survey. |  |  |  | 10
AWAIT CLIENT APPROVAL |  |  |  |  | First Call |  |  | Survey Rec'd, awaiting photos |  |  |  | 11
CALLED OFF |  |  |  |  | 8am to 2pm |  |  | Survey with surveyor |  |  |  | 12
DELIVERED TO DEPOT/CONTAINER |  |  |  |  | 10am-3pm |  |  | Aluminium |  |  |  | 13
BOOKED TO FIT |  |  |  |  | 8am to 2pm |  |  | Asbestos to be removed |  |  |  | 14
PART FITTED |  |  |  |  | 9am to 3pm |  |  | Await survey to be cleansed |  |  |  | 15
FITTED |  |  |  |  | 8am to 2pm |  |  | SERVICE CALL BOOKED |  |  |  | 16
HANDED OVER | [7 empty] | CUSTOMER CARE ATTENDING |  |  |  | 17
CANCELLED | [7 empty] | Ready to be Called Off |  |  |  | 18
NWR | [7 empty] | Ready to be Called Off when approved |  |  |  | 19
NO ACCESS SURVEY | [7 empty] | READY TO SEND FOR PRICING |  |  |  | 20
NO ACCESS INSTALL | [7 empty] | POST 2000 |  |  |  | 21
REFUSAL | [7 empty] | Survey with surveyor |  |  |  | 22
HANDED BACK | [7 empty] | Electrician Required |  |  |  | 23
DUPLICATE | [7 empty] | Asbestos removal req'd? |  |  |  | 24
SUPPLY ONLY | [7 empty] | Nothing rec'd on hold with surveyor / DA |  |  |  | 25
RECALL REQUIRED | [11 empty] | 26
FAILED INSTALL | [11 empty] | 27
28
29
Access Call | [11 empty] | 30
1
2 | .
3
Supply Only
Handed Back

## Vision Lookup (hidden)
Surveyor | Vision ID | Installer | Vision ID
A Lethridge | 28 | (Stephen) Paul Sedgmore | 191
A Meldrum | 29 | Aaron Wheatstone | 234
B Sinclair | 30 | Adam Beasor | 9
C Hamerston | 31 | Adam Holden | 112
D Aitkin | 2 | Adam Lowe | 146
D Keogh | 13 | Adam Wilson | 245
I Roy | 32 | Adrian Guest | 101
K Holland | 9 | Adrian Todoran | 219
M Thorne | 33 | Alex OConner | 258
M Wakes | 34 | Alexsander Nowak | 172
P Beahan | 3 | Alun Evans | 68
P Hickson | 7 | Andrea Cashmore Test | 254
P Russell | 35 | Andrew Jenkinson | 126
R Jones | 12 | Andrew Llewellyn | 145
S Burgess | 5 | Andrew Martin | 152
S Hutchinson | 11 | Aneurin (John) Bevan | 15
S Simmons | 17 | Anthony Adamson | 2
T Swift | 36 | Anthony Cooper | 49
|  | Anthony Haughton | 106
|  | Anthony Hildige | 111
|  | Anthony Tighe | 218
|  | Ashley Buck | 30
|  | Ashley Davies | 58
|  | Ashley Holder | 113
|  | Barry Sinclair | 261
|  | Ben Clarke | 260
|  | Brian Gordon | 92
|  | Byron Babin | 7
|  | Carl Crossley | 52
|  | Carl Duthie | 65
|  | Carl Stubbs | 204
|  | Charles Brooks | 26
|  | Charlie Gordon | 93
|  | Chris (Mark) Williams | 243
|  | Chris Maher | 151
|  | Christian Smart | 194
|  | Christian Street | 201
|  | Christopher Thomas | 213
|  | Christopher Wigfield | 238
|  | Colin Griffiths | 97
|  | Colin Neville | 169
|  | Colin Roberts | 188
|  | Connor Vice | 228
|  | Connor Whitehouse | 237
|  | Conor Bullock | 32
|  | Constantin Dinu | 60
|  | Corey Gardner | 83
|  | Crae Jackson | 124
|  | Craig Atwill | 6
|  | Craig Geddes | 85
|  | Craig Kerry | 133
|  | Damian Noga | 170
|  | Damien Masham | 154
|  | Daniel Buck | 31
|  | Daniel Wells | 233
|  | Daniel Wild | 239
|  | Daniel Alcock | 3
|  | Daniel Llewellyn | 144
|  | Daniel Pastre | 176
|  | Danny Guest | 263
|  | Danny Hughes | 121
|  | Dariusz Sniegulski | 198
|  | Darren Atkins | 5
|  | Darren Bowen | 20
|  | Darren Wood | 247
|  | Darren Boulton | 18
|  | Darren Boyle | 23
|  | Darren John Hollins | 116
|  | Darren Martin | 153
|  | David Clarke | 43
|  | David Hawkins | 107
|  | David Bryant | 28
|  | David Deacon | 59
|  | David John Harrison | 104
|  | David Sloan | 193
|  | David Topliss | 222
|  | Dean Wild | 240
|  | Domonic Jordan | 130
|  | Elliot James Rogers | 189
|  | Eric Gamble | 82
|  | Francesco Iovine | 123
|  | Gareth Andrews | 4
|  | Gareth Stubbs | 202
|  | Gary Horton | 119
|  | Gary Cocker | 46
|  | Gary Lynch | 149
|  | Gary North | 171
|  | Gavin Chawner | 37
|  | Geraint Davies | 57
|  | Graham Luxford | 148
|  | Harry Sheen | 192
|  | Howard Smart | 195
|  | Ian Hutchinson | 122
|  | Ian Steemson-Brooks | 199
|  | Ian Tallents | 206
|  | Iestyn Evans | 69
|  | Iliyan Yurukov | 251
|  | Iulian Ciobotaru | 40
|  | Jack Bettoney | 14
|  | Jack Mason | 156
|  | Jack White | 236
|  | Jake Chambers | 36
|  | Jake Duthie | 64
|  | James Boulton | 19
|  | James Gibson | 88
|  | James Leigh Lewis | 142
|  | James Maddox | 150
|  | James Roberts | 187
|  | James Tarpey | 207
|  | James Williams | 244
|  | Jamie Plant | 179
|  | Jason Horton | 117
|  | Jason Chesterton | 39
|  | Jason Leppard | 141
|  | Jason Waskiewicz | 232
|  | Jason Whitaker | 235
|  | John Fenemore | 73
|  | John Grosvenor | 100
|  | John Taylor | 209
|  | Jonathan Thorne | 215
|  | Jordan Bird | 16
|  | Jordan Dowse | 63
|  | Joseph Murphy | 167
|  | Joshua Fullalove | 79
|  | Joshua Tyler | 226
|  | Kai Kilmartin | 134
|  | Kamil Kwiatkowski | 137
|  | Karol Kowalski | 135
|  | Keenan Thomas | 214
|  | Keiron Hatton | 105
|  | Keith Bennett | 12
|  | Kevin Clark | 41
|  | Kevin Collins | 47
|  | Kevin Linney | 143
|  | Kevin Bentley | 13
|  | Kevin Hammond | 102
|  | Kieron Smith | 196
|  | Kieron Wilkins | 241
|  | Kurtis Reacord | 183
|  | Kyle Fitzpatrick | 74
|  | Kyle Fulcher | 78
|  | Kyle Troke | 223
|  | Laurentiu Dobromir | 62
|  | Lee Brewin | 24
|  | Lee Jarvis | 125
|  | Lee Penny | 178
|  | Lee Richards | 185
|  | Lee Stovold | 200
|  | Leigh Ann Woodward | 249
|  | Leigh Davies | 56
|  | Leigh Gilbert | 90
|  | Leigh Goodrem | 91
|  | Leon Belmont | 10
|  | Liam Cassin | 34
|  | Lincoln Gamble | 81
|  | Lloyd Jones | 128
|  | Lukasz Walawender | 230
|  | Luke Buck | 29
|  | Luke Jones | 129
|  | Lyn Headon | 108
|  | Marcus Clarke | 45
|  | Marcus Farmer | 71
|  | Marcus Van Spall | 227
|  | Mark Cattell | 35
|  | Mark Kelly | 132
|  | Mark Leech | 139
|  | Mark Stubbs | 203
|  | Mark Taylor | 208
|  | Mark Thorne | 259
|  | Mark Welch Test | 253
|  | Martin Boyle | 22
|  | Martin Brookes | 25
|  | Martin Cheeseman | 38
|  | Matt Brown | 27
|  | Matthew Butler | 33
|  | Matthew Dadswell | 53
|  | Matthew Green | 95
|  | Matthew Hughes | 120
|  | Matthew Thewlis | 212
|  | Max Leppard | 140
|  | Michael Bone | 262
|  | Michael Cooper | 48
|  | Michael Reddick | 184
|  | Michal Michno | 159
|  | Nathan Griffiths | 96
|  | Neil Clarke | 42
|  | Neil Summerhayes | 205
|  | Nicholas Thorne | 216
|  | Nick Morris | 165
|  | Nigel Fox | 75
|  | Noel Moss | 166
|  | Paul Pendlebury | 177
|  | Paul Franklin | 76
|  | Paul Gibson | 89
|  | Paul Harrison | 103
|  | Paul Holder | 114
|  | Paul Jenkinson | 127
|  | Paul Leech | 138
|  | Paul Lowe | 147
|  | Paul Vidor | 229
|  | Pawel Winniczuk | 246
|  | Peter O Flanagan | 174
|  | Piotr Migut | 160
|  | Przemyslaw Poplawski | 181
|  | Reece Hollins | 115
|  | Reece Trueman | 224
|  | Richard (Kim) Bendall | 11
|  | Richard Anthony Booth | 17
|  | Richard Frost | 77
|  | Richard Groom | 99
|  | Richard Milburn | 161
|  | Rob McKenna | 157
|  | Rob Gaskins | 84
|  | Rob Geddes | 86
|  | Robert Warner | 231
|  | Robert Brokenshire | 255
|  | Robert Keen | 131
|  | Robert Orton | 175
|  | Rodney Heritage | 110
|  | Rupert Woods | 248
|  | Russell Woodward | 250
|  | Ryan Ackerman | 252
|  | Sam Davenport-Turley | 54
|  | Sam Chapel | 256
|  | Scott Miller | 163
|  | Scott Taylor | 264
|  | Scott Tibbins | 217
|  | Sean Nealon | 168
|  | Shaun Morgan | 164
|  | Shaun OConner | 257
|  | Simon Critchlow | 51
|  | Simon Heathcote | 109
|  | Simon Taylor | 211
|  | Simon Terence Smith | 197
|  | Simon Tonks | 221
|  | Spare | 210
|  | Stephen Davidson | 55
|  | Stephen Elms | 67
|  | Stephen Gee | 87
|  | Steve Farris | 72
|  | Steve Horton | 118
|  | Stuart Mason | 155
|  | Stuart McLaughlin | 158
|  | Stuart Millard | 162
|  | Stuart Reacord | 182
|  | Terry Barker | 8
|  | Terry Costello | 50
|  | Thomas Clarke | 44
|  | Thomas Evans | 70
|  | Tom Bowers | 21
|  | Tomasz Grabek | 94
|  | Tony Wilkins | 242
|  | Tony Tongue | 220
|  | Trandafir Dinu | 61
|  | Vernon Fullalove | 80
|  | Waldemar Plucner | 180
|  | Wayne Groom | 98
|  | Wayne Riley | 186
|  | Wesley Tyler | 225
|  | Wieslaw Kut | 136
|  | William (Buster) Eddies | 66
|  | William Rumble | 190
|  | Wojciech Nowak | 173
Kathan Stenton
Andy Raynor
Alex Windsor

## data collection
2017 | TOTAL PROPERTIES | TOTAL ELEMENTS |  |  | Start | Finish | Approx. WORKING Days | Targeted Properties Per Day
1388 | COMMENCEMENT PENDING |  |  | Project Constraints | 2024-06-13 | 2025-07-31 | 295 | 6.8068
2 | ON HOLD |  |  | Time Elapsed |  | 8.475% | 25
108 | SURVEY BOOKED | CASE | 2590
0 | SCOPE SURVEY | TILT TURN | 1 | Targeted | Targeted Handovers | Hand Overs Achieved
173 | SURVEY RECEIVED | FULLY REVERSE | 0 |  | 170.1695 | 0 | 0%
75 | PM TO CLEANSE | VERT SLIDER | 0
0 | Survey In Vision, PM to cleanse | FIRE | 0
0 | CLEANSED | CAVITY CLOSER | 0
123 | SENT FOR PRICING | SINGLE | 48 | If the spreadsheet drop down boxes or row colours are not working follow this process-
2 | PRICED | DOUBLE | 41 | 1) Make sure that the spreadsheet is not in "shared" mode. If you click on the "repair" button you will get an error message
81 | AWAIT CLIENT APPROVAL | BI-FOLD | 0 | 2) If it is "unshare" the spreadsheet (you may wish to complete the repair first thing in the morning or last thing in the evening)
12 | CALLED OFF | IN-LINE SLIDER | 7 | 3) Click on the "repair spreadsheet" button
4 | DELIVERED TO DEPOT/CONTAINER | FRONT SOLID GRP | 1
31 | BOOKED TO FIT | FRONT GLAZED GRP | 212 | 4) Save the spreadsheet and reactivate "shared" mode
2 | PART FITTED | REAR SOLID GRP | 3
0 | FITTED | REAR GLAZED GRP | 255
0 | HANDED OVER | SOLID FIRE | 0
1 | CANCELLED | GLAZED FIRE | 0
3 | NWR | BASIC SHED | 0
4 | NO ACCESS SURVEY | INT TOP LIGHT | 0
0 | NO ACCESS INSTALL | SEPARATE TOP LIGHT | 3
1 | REFUSAL | SIDE LIGHT | 76
0 | HANDED BACK | Communal Door | 0
0 | DUPLICATE
0 | SUPPLY ONLY
9 | RECALL REQUIRED
0 | FAILED INSTALL
2017 | TOTAL PROPERTIES | TOTAL ELEMENTS | 3237
2012
No Access Figures - Survey
| Properties with survey no access | 71
| No access stage 1 | 50
| No access stage 2 | 17
| No access stage 3 | 4
| Handed back | 0
No Access Figures - Installation
| Properties with Installation no access | 0
| No access stage 1 | 0
| No access stage 2 | 0
| No access stage 3 | 0
| Handed back | 0
client hold status
| 1 | client issue
Note on J4: Matthew Johnson: Cell formula refers to an empty cell

## Asbestos
Property Detail | [6 empty] | Sampling Detail |  | Number of samples required of what? - Please insert a number | [10 empty] | Sampling Detail |  | Asbestos Sampling Process | [8 empty] | Asbestos Removals Process
On Hold Query | Status | House number | Street | Town | County | Postcode | Location of presumed asbestos (what elements cannot be installed because of the asbestos, give locations i.e. front, rear, shed, windows, communal doors etc.) | Is the suspected asbestos located internally or externally | Soffits | Ceiling | Artex (textured coating) | Materials to the head | Materials to the jams | Mastic | Floor Titles | Packers | Panels | Fire Door Internals | Sash window cord | Photo(s) available | Passed for Review | Quotation requested from Contractor | Quotation received from Contractor | Works costed by Commercial | VO issued to Client | Signed VO received | PO issued to contractor | Scheduled sampling date | Sampling report received | Asbestos removals required | Quotation requested from Contractor | Quotation received from Contractor | Works costed by Commercial | VO issued to Client | Signed VO received | PO issued to contractor | Scheduled removal date | Asbestos removal RAMS received | Asbestos removal Date | Comments
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Asbestos
Note on W47: Emma Burrup: Carried over from 2016-2017 programme